## Slide 1: XXXX Environment Strategy for ERP Project

## Slide 2
Objective
Executive Summary
Deployment Strategy
Oracle Cloud Environment Details
Oracle EPM Environment Details
Oracle Middleware Environment Strategy
Oracle Environment Refresh Plan
Oracle Finance Cloud Patches
Oracle quarterly vs monthly patching
Refresh and Release Updates Considerations
What gets copied and what not during refresh
Responsibility Matrix
Boundary Applications Environment Strategy
Open Items

## Slide 3: Objective
The objective of this document is to explain the proposed environment strategy for Oracle Cloud transformation project for Cornerstone
The strategy details how many environments are required, when they are required and how they would be used during the project timeline
It outlines the refreshes planned to synchronize the data and configurations between different PODS at various stages of the project lifecycle
The document also provides guidance on managing quarterly updates by Oracle

## Slide 4: Executive Summary
In order to support the implementation, cutover and post go-live activities of Oracle Cloud application, following instance strategy is proposed :-
Cornerstone needs to have at least PROD + 4 Non-PROD Oracle Cloud instances(PODs) for the project
The best practice dictates a dedicated instance each for development, conversion and integration testing for implementation
The refreshes of instances will be carried out based on the project time lines and inline with Oracle patch/update releases
As the project unfolds and makes progress, the proposed refresh dates might change and would need to be kept abreast of changes in schedule and communicated with Oracle
Terminology | Usage
POD | Oracle refers to an instance/environment as a POD (Portable on Demand)
P2T Refresh | Production to Test Refresh. Refreshing Test (stage) instance from Production (Gold) instance
T2T Refresh | Test to Test Refresh. Refreshing Test (stage) instance from another test instance
Oracle Cloud ERP | Enterprise Resource Planning
SIT | System Integration Testing
UAT | User Acceptance Testing

## Slide 5: Deployment Strategy – wholistic POD strategy
We recommend the following instances, to deliver the project effectively.
Recommendation |  |  |  |  | 
ERP (SaaS) | Non-Prod | Non-Prod | Non-Prod | Non-Prod | Prod
 | Development Environment | FUT , Training | GOLD,SIT2, Mock Cutover | Conversion, SIT1, UAT | Production Environment
IMAGINE
DELIVER
RUN
5 Pods : 1 Dev, 1 Test *, 1 Gold, 1 Conv , 1 Prod
Support, Dev, Test, Training Post Go-Live
Go-Live
5 Pods are recommended
Pods sized based on their purpose
UAT Pod needs to be sized as Prod.
Number and purpose of environments
DEV + SPRINTS
1
DEV
PROD
5
PROD
3
SIT 2
Mock Cutover
TEST
SIT 1,
4
UAT
Prod Support
FUT + Mock Conversion (2&3) + Training Activities
2
GOLD Configs
Conversion
* Test Instance will be used only during the implementation phase and post go-live we will have 3+1 PODS(3 Non Prod and 1 Prod)

## Slide 6: Oracle Finance Cloud Environments (PODS)
Below table illustrates the 5 oracle finance cloud PODs (4 Non-Prod + 1 Prod) to be utilized to support design, build, conversions, integration and cutover dress rehearsal testing, break fixes and production.
Environment | Usage | Description
DEV1 | RICE Development Unit Testing | Used for developing custom RICE components. Perform the unit testing of the components and doing Proof of concepts.
DEV2 | Functional Unit Testing User Training | Used for Functional Unit Testing of Integrations and Reports. Used for User Training.
TEST1 | Mock Conversion SIT Cycle 1 User Acceptance Testing QA Post Go-Live | Used for executing mock conversions, SIT1, UAT. Used as QA Environment post Go live.
TEST2 | GOLD SIT Cycle 2 Mock Cutover | Used for executing SIT2 and mock cutover environment before the “Go-Live” cutover start.
PROD | Production Deployment | At the time of go live, this instance will be used as the live production environment and final resting spot for all information after “Go-Live”. All approved reports, security, interfaces, and conversion data will be migrated to the Production Environment during “Go-Live” Cutover.
At the time of UAT , we will need to expand environment strategy for Post Production, considering Future phases, production release planning

## Slide 7: Oracle EPM Environments (PODS)
Below table illustrates the 2 oracle EPM PODs (1 Non-Prod + 1 Prod) to be utilized to support design, build, test, break fixes and production.
Environment | Usage | Description
Test | Build Testing Training | Used for build, testing data loads and training purposes.
PROD | Data Validation End to End Testing UAT Production Deployment | Before go-live this instance will be used for Data Validation, Validation Reports, end to end testing, UAT. At the time of go live, this instance will be used as the live production environment and final resting spot for all information after “Go-Live”.

## Slide 8: Oracle-SFDC- Middleware Environment Strategy
MuleSoft is the identified platform for the middleware-based integrations.
Middleware platform will be repurposed between environments.
Table below illustrates how the mule environment will be connected to different ERP Pods.
Mule Env | Oracle ERP POD | SFDC Een | Description & Usage
Dev | DEV1 | NORTHSTAR_R1DEV | Separate set of application for Dev1 and Dev 2 but both hosted on Dev Box Connected to ERP Dev1 used for development purposes.
Dev | DEV2 | NORTHSTAR_R1QA (Developer Org) | Separate set of application for Dev1 and Dev 2 but both hosted on Dev Box Connected to ERP Dev2(TEST) used for FUT, mock conversion 2 and 3 and training purposes.
Sandbox | TEST | NORTHSTAR_SIT (Full Copy Org) | Connected to ERP TEST(CONV) used for conversions,SIT1 and UAT. Post Go-live ERP TEST will be the production support Instance.
UAT | DEV3 | NORTHSTAR_UAT (Full Copy Org) | Connected to ERP DEV3(GOLD) used for Gold configurations,SIT2 and mock cutover.
PROD | PROD | NORTHSTAR PROD (Production) | Connected to PROD ERP.

## Slide 9: Oracle Environment Refresh Plan
Oracle Financials cloud environments should be refreshed in parallel to keep the data in sync between the environments. E.g. : When development environment for Oracle Financials cloud is refreshed
Environment refresh plan is a living document that will be updated during the course project
For Cornerstone’s environment refresh plan please check the spreadsheet ‘XXXX ERP Project - Environment Strategy.xlsx’ sheet ‘Refresh Timeline - 4+1’
Boundary Systems Strategy will be updated accordingly on the basis of further discussions
XXXX ERP Project – Environment Strategy

## Slide 10: Oracle Finance Cloud Patches (Cohort C)
Based on the planned Go-live date, We will go live with finance cloud version 23A
Oracle will deploy the patch to Non-Prod environments on the first Friday of the month and to production on the third Friday of the month
At the commencement of the Project, the Project will start with Oracle’s most recent finance cloud release (22C)
The patching process is expected to continue through UAT. Prior to start of the UAT, the Project team (XXXX and Deloitte Consulting) will implement an upgrade /code freeze to enable a stable environment at go-live
Release of system updates will be on a quarterly basis post base deployment
23A and 23B Upgrades will happen during SIT1 and UAT respectively. Regression testing should be planned during that time
 | 2022 |  |  |  |  |  |  |  |  | 2023 |  |  | 2023 |  |  | 2023 |  | 
 | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  | 
Month | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP
Cohort A |  | 22B |  |  | 22C |  |  | 22D |  |  | 23A |  |  | 23B |  |  | 23C | 
Cohort C | 22A |  |  | 22B |  |  | 22C |  |  | 22D |  |  | 23A |  |  | 23B |  | 
Cohort | Patch Schedule
A | Feb-May-Aug-Nov
B | Mar-Jun-Sept-Dec
C | Jan-Apr-Jul-Oct
SIT1
SIT2
UAT

## Slide 11: Oracle Quarterly vs Monthly Patching
Quarterly Patching
Oracle applies the mandatory patches on first month of the quarter
Monthly Patching
Oracle will apply the mandatory patches on every month. These typically are critical bug fixes and do not have major releases for ERP.
These patches cannot be skipped or deferred
PODs are down and not available for use during the patching window. The normal patching window is 24-48 hours and patching starts at 10pm EST on Friday. For non-production, it is on 1st week of the month and for Production it is 3rd week of the month
Need to plan for POD downtime on monthly basis;
Don’t have to wait for 90 days to have new functionality of fixes as in the case of Quarterly patches

## Slide 12: Refresh and Release Updates Considerations
For environment refresh/release upgrade SR need to be raised using My Oracle Service portal (this is new from April 2017 onwards)
For T2T/P2T, both Source and Target PODs must be at same patch level and Release level
Blackout dates for T2T/P2T
To schedule a T2T/P2T, raise an SR at-least 21 days before (3 to 12 weeks range)
SR Cancellation request must be 7 days before the T2T/P2T
P2T refreshes can only happen in the 2nd, 4th and 5th weeks of the month
Release upgrade starts normally on Tuesday of the week
It is recommended to confirm the release upgrade date early by raising an SR to have better planning around the down time
For POD sizing requests, we need to provide "Environment Usage Evaluation Form“ at least 4 weeks prior to the next scheduled quarterly update. The evaluation form typically includes transaction volumes for given module scope
Send SR details to CSM to get the cloning/release upgrade schedule finalized/approved
Any issues/questions related to Oracle Cloud are addressed through the SRs (Service Requests) to Oracle Support Team (MOS Portal)

## Slide 13: What gets copied and what not during refresh
Below table illustrates what is copied and what is not during refresh between PODS:
Entity | Copied
All data in the Fusion schema (Transactional and Functional Setup) | ✓
Published Sandboxes | ✓
Custom Reports and Report Customizations | ✓
Compiled objects like fusion application binaries, HCM Cloud Services customers, compiled Fast Formula. | ×
Home page notifications like approval requests | ×
Data maintained in the Functional Setup Manager’s (FSM) Topology Manager | ×
Enterprise Scheduler Service (ESS) process parameters | ×

## Slide 14: Responsibility Matrix
Below are the various environment related activities that are ensued during the project implementation phase and the responsible parties.
Activity | XXXX | Deloitte
Planning the Oracle Cloud instance strategy | Secondary | Primary
Validating the instances after refresh | Secondary | Primary
Raise SRs on product bugs and enhancements | Secondary | Primary
Access provisioning, Security and controls | Secondary | Primary
Perform Impact analysis and regression testing required for Any oracle patches | Joint | Joint
Raising Oracle SR for instance refresh or other environment Admin configurations | Secondary | Primary*
Circulating the system outage email | Secondary | Primary*
Escalation management with Oracle | Secondary | Primary*
Provision, maintain and refresh (from PROD) test instances for boundary & legacy applications | Primary | Not Applicable
* For hyper care it will be a joint effort , post hyper care this activity will be transitioned to XXXX

## Slide 15: Boundary Applications Environment Strategy
To ensure integrations and data conversions for Oracle Cloud applications are carried out against the latest production data, legacy and boundary environments should be refreshed or provisioned as explained below:
Integrations
Each Internal application that would have integrations with Oracle Cloud, should be refreshed from production before each phase i.e., Development, SIT, and UAT cycles. The refresh should be completed before the start of the test cycle
During SIT and UAT, one dedicated environment separate from development should be provided
For external applications (Eg: Banks), a test server should be provided.
Conversions
For conversion, source applications should be refreshed before each phase i.e., Mock, SIT and UAT cycles
During SIT and UAT, source conversion data environments should not be altered until one week after the data load to Oracle is completed to ensure data reconciliation is accurate.

## Slide 16: Open Items
Id | Description | Follow up Comments | Owner | Due Date | Status
1 | Salesforce Environment mapping to be updated | Updated with SFDC Environment | CRM Team | 10/21/2022 | Closed
2 | Will any of the 4 non-prod env's be refreshed/cloned for a fresh testing cycle until Jun-22? | Yes, documented in Instance Plan | Deloitte team (Ravi/Arvind) |  | Closed
3 | What all env's be used for Boundary Application integrations like Workiva, Ambar Road etc? | Not All, as Conversion instance will not be connected to Boundry Systems, SITs instance will connect to boundary Application | Deloitte team (Ravi/Arvind) |  | Closed
4 | What's the instance strategy to map different boundary application to Oracle pods? (eg:- SFDC Test -> Mulesoft Test -> Oracle Cloud Test etc) | Dev get mapped to Dev of boundary systems, for testing cycle not all boundary systems will not that many systems, the approach to work with boundary systems to connect non prod cycles | Deloitte team (Ravi/Arvind) |  | Closed

## Slide 17: Open Items
Id | Description | Follow up Comments | Owner | Due Date | Status
5 | What's the contingency plan if any of the new features rolled-out by Oracle for any 23X release fails? | Oracle Provide 2 weeks to validate the functionality to work with oracle to close out if something is not working and push the patch in case issues does not get resolved. | Deloitte team (Ravi/Arvind) |  | Closed
6 | Will UAT be the final env which will have conversions data, integrations, incremental 23X patches, boundary systems that way we will have a consolidated testing? | Yes, UAT is the last environment before we move to prod, between UAT and PROD no new patches are introduced, while working with Oracle | Deloitte team (Ravi/Arvind) |  | Closed
7 | How do we make sure the correct custom security roles are used for all testing cycles? (eg:- Conversion process should have it's own dedicated role/user for all Mock conversions) | The roles are validated with business before setting up in the systems and users granted with those roles | Deloitte team (Ravi/Arvind) |  | Closed

## Slide 18: Open Items
Id | Description | Follow up Comments | Owner | Due Date | Status
8 | Should we be expecting monthly patches too? | This happens on ad-hoc basis by Oracle for critical bug-fixes. Oracle will publish downtime usually on weekends. These are not major releases and do not need regression test | Deloitte team (Ravi/Arvind) |  | Closed
9 | “All payroll customers are by default on Monthly patch schedule”? Is it for Oracle Cloud HRMS only or for all other modules? | ERP is not on monthly patch schedule. Updated Slides accordingly. | Deloitte team (Ravi/Arvind) |  | Closed
10 | As patching window starts on 10pm EST on Friday, can the team elaborate when we say “Need to plan for POD downtime on monthly basis; might impact the overall implementation timeline”? | Once we are live, we need to plan for the Integrations that usually run on weekends. We will need turn off the integrations to avoid failures. Removed the line on timeline impact. | Deloitte team (Ravi/Arvind) |  | Closed

## Slide 19: Open Items
Id | Description | Follow up Comments | Owner | Due Date | Status
11 | How do we determine if POD sizing is required? Can we get sample copy of "Environment Usage Evaluation Form”? | This form can be downloaded from Oracle Support, here : link The right POD Sizing will be based on the transaction counts, concurrent user logins. These are the inputs we need to send in the above form. | Deloitte team (Ravi/Arvind) |  | Closed
12 | FRS Reports: So, do we need to re-create the reports in new instance or is there way to migrate these between instances? | No, we need not recreate these reports and they can migrate using import , export options.(Ref Oracle Documentation : link) | Deloitte team (Ravi/Arvind) |  | Closed
13 | So, we need to copy FRS reports to the new refreshed instance every time? | In a refreshed instance it will get copied, but in a new instance we can use the import/export option. Removed this line from the deck. | Deloitte team (Ravi/Arvind) |  | Closed

## Slide 20: Open Items
Id | Description | Follow up Comments | Owner | Due Date | Status
14 | Data Maintained in FSM (Functional Setup Manager). May I know what kind of data we are referring here? | FSM enables migration of setups between instances using export and import options. We first export these files in an instance which is then downloaded into local machine and can be imported to other instance for migration. These exported files (.zip/.csv) will not get copied to the target instance during refreshes. Hence as best practice we download the files and use for import purposes in other instances. | Deloitte team (Ravi/Arvind) |  | Closed
15 | So, are we talking about any specific setups here? As long as the setups are in Production, my understanding is they would be copied to the new refreshed instance? | Yes the setups that are done will get copied from the source to the target. These exported files(.zip/csv) are the temporary files containing the setups which can be used for import - export purposes(when we are setting up a new instance all together). | Deloitte team (Ravi/Arvind) |  | Closed

## Slide 21: Open Items
Id | Description | Follow up Comments | Owner | Due Date | Status
16 | ESS: What is this used for? | Enterprise Schedule Service enables to schedule Jobs (Processes) in Oracle fusion to run at specified time, using the parameters specified during the schedule creation. These schedules can be created on Standard (out of box jobs) provided by Oracle e.g. ‘Create Accounting’ , or we can also create custom ess jobs e.g. an ess job to run a custom BI report. These schedules and related parameters for a given job will not get copied during refreshes | Deloitte team (Ravi/Arvind) |  | Closed

## Slide 22: Open Items
Id | Description | Follow up Comments | Owner | Due Date | Status
17 | When should we request for change in Cohort? Is it a month before the current upgrade cycle or a month before the new upgrade cycle that we want to move into? | for the cohort switch to happen from C to A, we will have to raise the SR with Oracle latest by 1-Jul 2023(1 month before the scheduled update in the new cohort), for the 23C upgrade to happen in Aug as per Cohort A. With that we will basically have 2 back to back upgrades: 23B Quarterly Update in Jul as per Cohort C 23C Quarterly Update in Aug as per Cohort A | Deloitte team (Ravi/Arvind) |  | Closed
18 | Should this be 23C as 23B will be updated in Apr as per Cohort C? If it's 23C, it would be just change of Cohort from C to A in Aug right and no need of another upgrade. Please confirm? | As per the Upgrades shared by Lisa from Oracle, 23B Quarterly Update will happen in Jul as per Cohort C 23C Quarterly Update in Aug as per Cohort A. Hence we will have back to back updates in Jul and Aug. Updated the Upgrade versions in slide 10 to reflect the correct versions shared by Oracle. | Deloitte team (Ravi/Arvind) |  | Closed

## Slide 23
Q&A