## UAT1 Draft (hidden)
Task / Activities | V4 Start Date | V4 End Date | V6 Start Date | V6 End Date
SIT2 testing defects/enhancements for MF AP |  | 2022-11-11
SIT2 testing defects/enhancements for MF AR |  | 2022-11-11
FY23 Event based changes - Business Rule Change (Includes Inventory) |  | 2022-11-11
Description Rules (Header / Lines) |  | 2022-11-11
Business Requirement - Open questions/ clarifications - 1 | 2022-11-14 | 2022-11-15
Business Requirement for Dept rules | 2022-11-16 | 2022-11-16
Configuration setup / FUT - MF AP, MF AR | 2022-11-17 | 2022-11-30 | 2022-11-17 | 2022-11-30
SIT2 testing defects/enhancements for MF Inventory |  | 2022-11-18 |  | 2022-11-18
Business Requirement - Open questions/ clarifications | 2022-11-28 | 2022-11-30 | 2022-11-28 | 2022-11-30
Configuration setup / FUT - MF Inventory & Concur | 2022-12-01 | 2022-12-09 | 2022-12-01 | 2022-12-09
FUT Approval - MF AP, MF AR | 2022-12-02 | 2022-12-02 | 2022-12-01 | 2022-12-02
BR100 released for Business Approval - MF AP, MF AR, 3rd Party & associated JAVA tool (except Concur) | 2022-12-05 | 2022-12-06 | 2022-12-05 | 2022-12-06
BR100 - Approval - MF AP, MF AR, 3rd Party & associated JAVA tool (except Concur) | 2022-12-07 | 2022-12-08 | 1900-01-06 | 2022-12-08
UAT1 Instance setup - MF AP, MF AR, 3rd Party Systems (including related Java Tools) except Concur | 2022-12-09 | 2022-12-16 | 2022-12-09 | 2022-12-16
FUT Approval - MF Inventory & Concur | 2022-12-12 | 2022-12-13
BR100 released for Business Approval - MF Inventory & Concur | 2022-12-14 | 2022-12-15
BR100 - Approval - MF Inventory & Concur | 2022-12-15 | 2022-12-16
Smoke testing - MF AP, MF AR, 3rd Party Systems (including related Java Tools) except Concur | 2022-12-17 | 2022-12-20
UAT1 Instance Setup - MF Inventory & Concur | 2022-12-19 | 2022-12-23
Formulas:
V4 Start Date = [V4 End Date]

## Dev20 Config (hidden)
JERS
[7 empty] | # | Steps | PIC | V6 ETA | Revised ETA | Status
Assignee | Source | Global COA | Poland | Norway | France | Spain | 1 | TO Registration in Dev20 | Rajesh | NA | 2022-12-05 | Completed
Ankur | ICI | Done | Done | Done | Done | Done | 2 | Export MF INV Setups from SIT2 | Rajesh |  | 2022-12-05 | Completed
Ankur | FTI | Done | Done | Done | Done | Done | 3 | Import MF INV Setups to Dev20 | Kathir |  | 2022-12-06 | Completed
Kathir | ISI | Done | Done | Done | Done | Done | 4 | FY23 Manual Config MF INV | Rajesh/Kathir/Ankur | 2022-12-09 | 2022-12-07 | Completed
Rajesh | FII | Done | Done | Done | Done | Done | 5 | Custom Profile Options | Sravya |  | 2022-12-06 | Completed
Rajesh | IBI | Done | Done | Done | Done | Done | 6 | FY23 MF INV FUT | Kathir |  | 2022-12-13 | Completed
Rajesh | CQI | Done | Done | Done | Done | Done | 7 | FUT Approval - MF INV FY23 | Nil | 2022-12-13 | 2022-12-14 | Completed
Sravya | AII | Done | Done | Done | Done | Done | 8 | BR100 Approval - MF INV FY23 | Nil | 2022-12-16 | 2022-12-14 | Completed
Sravya | IRI | Done | Done | Done | Done | Done | 9 | UAT 1 Config for MF INV | Kathir | 2022-12-19 | 2022-12-20
Rajesh | Conversion | Done | Done | Done | Done | Done | 10 | Subledger Options setup | Sravya | 2022-12-09
Rajesh | Java Tool | Done | Done | Done | Done | Done | 11 | Setup Validation
Kathir | SPC | Done | Done | Done | Done | Done | 12 | MF AP MF AR 29Nov COA files to be used for Values load | Completed
Kathir | DAI | Done | Done | Done | Done | Done
Rajesh | AII | Done | Done | Done | Done | Done
Time in HRS for 1 resource
| Tasks - Updates required | MF AP | MF AR | MF INV
| Mapping Set Update | 0 | 0 | 1
| Account Rules | 1 | 1 | 1
| JERS | 1 | 3 | 8
| Mapping Set Value Upload - FBDI | 2 | 2 | 3 |  |  |  | With FY23 | 1 | Export Dev20
| FBDI Prep Time | 2 | 2 | 4 |  |  |  |  | 2 | Compare with Dev21-Dev20 | Differences
| Total Hrs | 6 | 8 | 17 |  |  |  |  | 3 | Import Dev20 config in Dev21 | Success
[9 empty] | 4 | Export Dev20
| MF INV | Optional | Tasks | [5 empty] | 5 | Compare with Dev21-Dev20 | No differences
Thursday | Rajesh + Kathir | Neha | Mapping Set Value Upload - FBDI | [5 empty] | 6
Friday | Rajesh + Kathir + Ankur
| MF AR | [7 empty] | Source | Target
Thursday | Sravya + Nil | Manpreet | [5 empty] | Mainframe | Dev20/Test | Dev2 / UAT
Friday | Sravya + Prachi | [6 empty] | All Other | Dev21/SIT2 | Dev2 / UAT
BKI | Prachi
JTI | Prachi
SII | Sravya
LSI | Prachi
ARI | Prachi
SPR | Prachi
Conversion | Prachi
Friday | MF AP
CAI | Ankur
ADI | Ankur
API | Ankur
AQI | Rajesh
BKI | Nil
LSI | Nil
Conversion | Nil
JTI | Nil
Note on C19: Arun, Gheware Nilakanth: Not applicable
Note on D19: Arun, Gheware Nilakanth: Not applicable
Note on D27: Arun, Gheware Nilakanth: 3 Mapping set load is pending

## Session Agenda (hidden)
RPT008 | Subledger Period Close Exception Report by Ledger Set | Check with Rajesh for Re-Test
RPT006 | AHCS Error Report (Retrofit)
RPT009 | Subledger Account Analysis Report (Retrofit)
INT043 | AHCS to IAP Details

## SIT2 Config (hidden)
|  | Primary Ledger |  |  | Secondary ledger | [5 empty] | Completed
[5 empty] | Spain COA | France COA | Norway COA Poland COA |  |  |  | In Progress
Source | Subledger | 2022-09-12 | 2022-09-13 | 2022-09-14 | 2022-09-15 | 2022-09-16 |  | 2022-09-19 | 2022-09-20 | 2022-09-21 | Delayed
CAI | MF AP | Ankur |  | Ankur-France | Ankur-Norway | Manpreet-Spain | Ankur-Poland |  |  | Review
ADI | MF AP | Ankur |  | Ankur-France | Ankur-Norway | Manpreet-Spain | Ankur-Poland | Ankur-Spain |  | Review
API | MF AP | Ankur |  | Ankur-France | Ankur-Norway | Manpreet-Spain | Ankur-Poland | Ankur-Spain |  | Review
AQI | MF AP |  | Ankur | Ankur-France | Ankur-Norway | Manpreet-Spain | Ankur-Poland | Ankur-Spain |  | Review
BKIP | MF AP |  | Ankur | Ankur-France | Ankur-Norway | Manpreet-Spain | Ankur-Poland |  |  | Review
LSIP | MF AP |  | Ankur | Ankur-France | Ankur-Norway | Manpreet-Spain | Ankur-Poland |  |  | Review
CQI | MF Inventory | Kathir/Rajesh |  |  | Rajesh-All SL |  |  |  |  | Review
IRI | MF Inventory | Kathir/Rajesh |  |  | Kathir-All SL |  |  |  |  | Review
IBI | MF Inventory | Kathir/Rajesh | Rajesh |  | Rajesh-All SL |  |  |  |  | Review
DAI | MF Inventory |  | Rajesh |  |  | Rajesh-All SL |  |  |  | Review
SPEC | MF Inventory |  | Rajesh |  |  | Neha-All SL |  | Neha-Spain France, Poland done Norway - done |  | Review
ISI | MF Inventory |  | Kathir | Kathir |  | Kathir-All SL |  | Kathir-All SL Spain |  | Review
FII | MF Inventory |  |  | Nilkanth | Nilkanth-All SL |  |  |  |  | Review
FTI | MF Inventory |  |  | Nilkanth | Nilkanth-All SL |  |  |  |  | Review
ICI | MF Inventory |  |  | Kathir |  | Kathir-All SL |  |  |  | Review
AII | MF Inventory |  |  | Rajesh |  | Rajesh-All SL |  | Rajesh-All SL (ES done) |  | Review
BKIR | MF AR | Sravya |  |  | Sravya-Spain Prachi-France | Sravya-Norway Prachi-Poland |  |  |  | Review
CRI | MF AR | Sravya | Sravya |  | Sravya-Spain Prachi-France | Sravya-Norway Prachi-Poland |  | Sravya-Norway Prachi-Poland |  | Review
SII | MF AR | Sravya | Sravya | Sravya | Sravya-Spain Prachi-France | Sravya-Spain, Norway Prachi-France, Poland |  | Sravya-Spain, Norway Prachi-France, Poland |  | Review
LSIR | MF AR |  | Sravya |  | Sravya-Spain Prachi-France | Sravya-Norway Prachi-Poland |  |  |  | Review
ARI | MF AR |  | Sravya |  | Sravya-Spain Prachi-France | Sravya-Norway Prachi-Poland |  |  |  | Review
SPER | MF AR |  | Sravya |  | Sravya-Spain Prachi-France | Sravya-Norway Prachi-Poland |  |  |  | Review
Oracle LSI (Oracle Solution) | Oracle LSI (Oracle Solution) |  |  | Prachi PL& SL | [5 empty] | Review
Conversions | Conversions |  | Nilkanth | Nilkanth |  | Nilkanth-All SL |  |  |  | Review
Java Tool | Java Tool |  |  | Nilkanth |  | Nilkanth-All SL |  | Nilkanth-All SL |  | Review
SXEUS | SXEUS | Nilkanth |  |  | Not Applicable |  |  |  |  | Review
ECLPS | ECLPS | Nilkanth | [7 empty] | Review
TREASURY | TREASURY | Nilkanth | [7 empty] | Review
CloudPay | CloudPay |  | Nilkanth | [6 empty] | Review
PSFA | PSFA |  | Nilkanth | [6 empty] | Review
LEASES | LEASES |  | Nilkanth-PL&SL | [6 empty] | Review
Note on B29: Arun, Gheware Nilakanth: No SL applicable
Note on B30: Arun, Gheware Nilakanth: No SL applicable
Note on B31: Arun, Gheware Nilakanth: No SL applicable

## MF BSR list (hidden)
PS Account | Oracle Account | BSR Assigment
310010000 | 211001 | ABSR
310028008 | 211050 | UBSR
133010009 | 115152 | UBSR
310028000 | 211003 | UBSR
310028001 | 211045 | UBSR
310028005 | 211049 | UBSR
310010009 | 211036 | ABSR
312700000 | 212001 | ABSR
121100000 | 112101 | ABSR
121100001 | 112112 | ABSR
122900000 | 113008 | ABSR
139000011 | 115110 | ABSR
122500000 | 113006 | ABSR
132000000 | 115114 | ABSR
121100009 | 112157 | ABSR
351100009 | 213020 | ABSR
328361009 | 218635 | ABSR
101400001 | 111384 | ABSR
101499999 | 111385 | ABSR
379990009 | 218077 | ABSR
127000000 | 114001 | ABSR
133000001 | 115101 | ABSR
133040000 | 115102 | ABSR
133010001 | 115144 | ABSR
133010002 | 115145 | ABSR
133010003 | 115146 | ABSR
133010004 | 115147 | ABSR
133010005 | 115148 | ABSR
133010006 | 115149 | ABSR
133010007 | 115150 | ABSR
133010008 | 115151 | ABSR
133010010 | 115153 | ABSR
133010020 | 115111 | ABSR
133000023 | 115118 | ABSR
310028002 | 211046 | UBSR
310028004 | 211048 | UBSR

## BSR-Dev22 (hidden)
Subledger | Interface | JLRs (BR100) | JERS(BR100) | JLRs (Config) | JERS(Config) | SL(France) | SL(Spain) | SL(Poland) | SL(Norway) | SL(Austria) | SL(Germany) | SL(Saudia Arabia) | Notes (PL) |  | SRs |  |  | BSR Assignment Value
MF AP | API | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Splitting 3 JLR & Assign SR accordingly | [8 empty] | Trading Partner NBR
MF AP | AQI | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Splitting 2 JLR |  |  | Source | Object Name | ABSR | UBSR | NBSR | NULL
MF AP | LSI | N/A | Complete | N/A | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | No JLR split , Only SR assignment |  |  | CAI | MF AP | NA | NA | NA | X
MF AP | ADI | N/A | Complete | N/A | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | No JLR split , Only SR assignment |  |  | ADI | MF AP | X | X | X | NA
MF AP | CAI | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | No JLR split , Only SR assignment |  |  | API | MF AP | X | X | X | NA
MF AP | BKI | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete |  |  |  | AQI | MF AP | X | X | X | NA
MF AR | ARI | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete |  |  |  | BKIP | MF AP | X | X | X | NA
MF AR | BKI | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete |  |  |  | LSIP | MF AP | X | X | X | NA
MF AR | CRI | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete |  |  |  | BKIR | MF AR | X | X | X | NA
MF AR | SII | N/A | Complete | N/A | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete |  |  |  | CRI | MF AR | NA | NA | NA | X
MF AR | SPER | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete |  |  |  | SII | MF AR | NA | NA | NA | X
MF AR | LSI | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete |  |  |  | LSIR | MF AR | X | X | X | NA
MF INV | CQI | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | FUT Done |  |  | ARI | MF AR | X | X | X | NA
MF INV | IRI | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | FUT Done |  |  | SPER | MF AR | X | X | X | NA
MF INV | ISI | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | FUT Done |  |  | CQI | MF Inventory | X | X | X | X
MF INV | FII | N/A | Complete | N/A | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | FUT Done | No JLR split , Only SR assignment |  | IRI | MF Inventory | NA | NA | NA | X
MF INV | FTI | N/A | Complete | N/A | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | FUT Done | No JLR split , Only SR assignment (change from BSR to NBSR for all lines) |  | IBI | MF Inventory | X | X | X | X
MF INV | ICI | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | All ABSR, no need to test |  |  | DAI | MF Inventory | X | X | X | NA
MF INV | AII | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | All ABSR, no need to test |  |  | SPEC | MF Inventory | X | X | X | NA
MF INV | IBI | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | FUT Done |  |  | ISI | MF Inventory | NA | NA | NA | X
MF INV | DAI | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | FUT Done |  |  | FII | MF Inventory | NA | NA | NA | X
MF INV | SSI | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | FUT Done |  |  | FTI | MF Inventory | NA | NA | NA | X
[16 empty] | ICI | MF Inventory | NA | NA | NA | X | Always ABSR
[16 empty] | AII | MF Inventory | NA | NA | NA | X | Always ABSR
Note on U3: Arun, Gheware Nilakanth: All BSR applicable
Note on V3: Arun, Gheware Nilakanth: Only GL Location as BSR
Note on W3: Arun, Gheware Nilakanth: No Balnce SR
Note on X3: Arun, Gheware Nilakanth: No Legacy account COA to populate 'DNU' OIC to populate 'NULL'
Note on X4: Arun, Gheware Nilakanth: Based on Analysis and Oracle Account Value
Note on U5: Arun, Gheware Nilakanth: Based on Analysis and Oracle Account Value
Note on V5: Arun, Gheware Nilakanth: Based on Analysis and Oracle Account Value
Note on W5: Arun, Gheware Nilakanth: Based on Analysis and Oracle Account Value
Note on U6: Arun, Gheware Nilakanth: Based on Analysis and Oracle Account Value
Note on V6: Arun, Gheware Nilakanth: Based on Analysis and Oracle Account Value
Note on W6: Arun, Gheware Nilakanth: Based on Analysis and Oracle Account Value
Note on U7: Arun, Gheware Nilakanth: Based on Analysis and Oracle Account Value
Note on V7: Arun, Gheware Nilakanth: Based on Analysis and Oracle Account Value
Note on W7: Arun, Gheware Nilakanth: Based on Analysis and Oracle Account Value
Note on U8: Arun, Gheware Nilakanth: Based on Analysis and Oracle Account Value
Note on V8: Arun, Gheware Nilakanth: Based on Analysis and Oracle Account Value
Note on W8: Arun, Gheware Nilakanth: Based on Analysis and Oracle Account Value
Note on U9: Arun, Gheware Nilakanth: Based on Analysis and Oracle Account Value
Note on V9: Arun, Gheware Nilakanth: Based on Analysis and Oracle Account Value
Note on W9: Arun, Gheware Nilakanth: Based on Analysis and Oracle Account Value
Note on U10: Arun, Gheware Nilakanth: Based on Analysis and Oracle Account Value
Note on V10: Arun, Gheware Nilakanth: Based on Analysis and Oracle Account Value
Note on W10: Arun, Gheware Nilakanth: Based on Analysis and Oracle Account Value
Note on X11: Arun, Gheware Nilakanth: Based on Analysis and Oracle Account Value
Note on X12: Arun, Gheware Nilakanth: Based on Analysis and Oracle Account Value
Note on U13: Arun, Gheware Nilakanth: Based on Analysis and Oracle Account Value
Note on V13: Arun, Gheware Nilakanth: Based on Analysis and Oracle Account Value
Note on W13: Arun, Gheware Nilakanth: Based on Analysis and Oracle Account Value
Note on U14: Arun, Gheware Nilakanth: Based on Analysis and Oracle Account Value
Note on V14: Arun, Gheware Nilakanth: Based on Analysis and Oracle Account Value
Note on W14: Arun, Gheware Nilakanth: Based on Analysis and Oracle Account Value
Note on U15: Arun, Gheware Nilakanth: Based on Analysis and Oracle Account Value
Note on V15: Arun, Gheware Nilakanth: Based on Analysis and Oracle Account Value
Note on W15: Arun, Gheware Nilakanth: Based on Analysis and Oracle Account Value
Note on U16: Arun, Gheware Nilakanth: Based on Analysis and Oracle Account Value
Note on V16: Arun, Gheware Nilakanth: Based on Analysis and Oracle Account Value
Note on W16: Arun, Gheware Nilakanth: Based on Analysis and Oracle Account Value
Note on X16: Arun, Gheware Nilakanth: Based on Analysis and Oracle Account Value
Note on X17: Arun, Gheware Nilakanth: Based on Analysis and Oracle Account Value
Note on U18: Arun, Gheware Nilakanth: Based on Analysis and Oracle Account Value
Note on V18: Arun, Gheware Nilakanth: Based on Analysis and Oracle Account Value
Note on W18: Arun, Gheware Nilakanth: Based on Analysis and Oracle Account Value
Note on X18: Arun, Gheware Nilakanth: Based on Analysis and Oracle Account Value
Note on X21: Arun, Gheware Nilakanth: Based on Analysis and Oracle Account Value
Note on X22: Arun, Gheware Nilakanth: Based on Analysis and Oracle Account Value
Note on X23: Arun, Gheware Nilakanth: Based on Analysis and Oracle Account Value
Note on X24: Arun, Gheware Nilakanth: Based on Analysis and Oracle Account Value
Note on X25: Arun, Gheware Nilakanth: Based on Analysis and Oracle Account Value

## AHCS-SL (hidden)
|  | Kathir |  |  | Prachi |  | Ankur
| COA | Global COA | Global COA | Global COA | Spain COA | France COA | Norway COA | Poland COA
| SLAM | WSC ATGAAP | WSC DEGAAP | WSC SAGAAP | WSCESGAAP | WSCFRGAAP | WSCNOGAAP | WSCPLGAAP
Kathir | PSFA | No Additional Chages required for Secondary ledger |  |  | XXPSFA_WSCESGAAP_JERS | XXPSFA_WSCFRGAAP_JERS | XXPSFA_WSCNOGAAP_JERS | XXPSFA_WSCPLGAAP_JERS
Kathir | LEASES |  |  |  | XXLHI_WSCESGAAP_JERS | XXLHI_WSCFRGAAP_JERS | XXLHI_WSCNOGAAP_JERS | XXLHI_WSCPLGAAP_JERS
SXEUS
ECLPS
Kathir | TREASURY |  |  |  | XXAPS_WSCESGAAP_JERS | XXAPS_WSCFRGAAP_JERS | XXAPS_WSCNOGAAP_JERS | XXAPS_WSCPLGAAP_JERS
CloudPay
Ankur | MF AP |  |  |  | XXMFAP_WSCESGAAP_JERS | XXMFAP_WSCFRGAAP_JERS | XXMFAP_WSCNOGAAP_JERS | XXMFAP_WSCPLGAAP_JERS
Prachi | MF AR |  |  |  | XXMFAR_WSCESGAAP_JERS | XXMFAR_WSCFRGAAP_JERS | XXMFAR_WSCNOGAAP_JERS | XXMFAR_WSCPLGAAP_JERS
JERS
PIC | Sources | Description Rules | Mng Account Rules | SR | Manage Journal Line Rules
Kathir | PSFA |  | LE Copy rest all Constant |  | XXPSFAWSCESGAAPDebit Line | XXPSFAWSCFRGAAPDebit Line | XXPSFAWSCNOGAAPDebit Line | XXPSFAWSCPLGAAPDebit Line
Prachi | LEASES |  |  |  | XXLEASESWSCESGAAPDebit Line | XXLEASESWSCFRGAAPDebit Line | XXLEASESWSCNOGAAPDebit Line | XXLEASESWSCPLGAAPDebit Line
SXEUS
ECLPS
Nil | TREASURY |  |  |  | XXTREASURYWSCESGAAPDebit Line | XXTREASURYWSCFRGAAPDebit Line | XXTREASURYWSCNOGAAPDebit Line | XXTREASURYWSCPLGAAPDebit Line
CloudPay
Ankur | MFAP |  |  |  | XXMFAPWSCESGAAPDebit Line | XXMFAPWSCFRGAAPDebit Line | XXMFAPWSCNOGAAPDebit Line | XXMFAPWSCPLGAAPDebit Line
Ankur | MFAP |  |  |  | XXMFAPWSCESGAAPCredit Line | XXMFAPWSCFRGAAPCredit Line | XXMFAPWSCNOGAAPCredit Line | XXMFAPWSCPLGAAPCredit Line
Rajesh | MFAR |  |  |  | XXMFARWSCESGAAPDebit Line | XXMFARWSCFRGAAPDebit Line | XXMFARWSCNOGAAPDebit Line | XXMFARWSCPLGAAPDebit Line
Rajesh | MFAR |  |  |  | XXMFARWSCESGAAPCredit Line | XXMFARWSCFRGAAPCredit Line | XXMFARWSCNOGAAPCredit Line | XXMFARWSCPLGAAPCredit Line
| Legal Entity | 1 | Source |  |  | 1998382
| Operating Group | 1 | 0000 |  |  | 1998384
| Account | 1 | TBD
| Department | 1 | 0000
| Site | 1 | 00000
| Intercompany | 1 | 0000
| Project | 1 | 0000
| Future 1 | 1 | 0000
| Future 2 | 1 | 0000
Subledger Application | Name | Short Name | Description | Chart of Accounts | Rule Type | Segment | Priority | Value Type | Value | Condition | 1B Requirement Sheet Mapping
APS TREASURY | XXAPS TREASURY_AccountRuleSL_LE | XXAPS_TREASURYSL_ACCTRULE_LE | XXAPS TREASURY_AccountRuleSL_LE | Spain COA | Segment | Legal Entity | 1 | Source | GL Legal Entity
APS TREASURY | XXAPS TREASURY_AccountRuleSL_Op_Grp | XXAPS_TREASURYSL_ACCTRULE_OP_GRP | XXAPS TREASURY_AccountRuleSL_Op_Grp | Spain COA | Segment | Operating Group | 1 | Constant | 0000
APS TREASURY | XXAPS TREASURY_AccountRuleSL_Account | XXAPS_TREASURYSL_ACCTRULE_ACCT | XXAPS TREASURY_AccountRuleSL_Account | Spain COA | Segment | Account | 1 | Constant | 1000000
APS TREASURY | XXAPS TREASURY_AccountRuleSL_Dept | XXAPS_TREASURYSL_ACCTRULE_DEPT | XXAPS TREASURY_AccountRuleSL_Dept | Spain COA | Segment | Department | 1 | Constant | 0000
APS TREASURY | XXAPS TREASURY_AccountRuleSL_Site | XXAPS_TREASURYSL_ACCTRULE_SITE | XXAPS TREASURY_AccountRuleSL_Site | Spain COA | Segment | Site | 1 | Constant | 00000
APS TREASURY | XXAPS TREASURY_AccountRuleSL_IC | XXAPS_TREASURYSL_ACCTRULE_IC | XXAPS TREASURY_AccountRuleSL_IC | Spain COA | Segment | Intercompany | 1 | Constant | 0000
APS TREASURY | XXAPS TREASURY_AccountRuleSL_Project | XXAPS_TREASURYSL_ACCTRULE_PROJ | XXAPS TREASURY_AccountRuleSL_Project | Spain COA | Segment | Project | 1 | Constant | 0000
APS TREASURY | XXAPS TREASURY_AccountRuleSL_Future1 | XXAPS_TREASURYSL_ACCTRULE_FUT1 | XXAPS TREASURY_AccountRuleSL_Future1 | Spain COA | Segment | Future 1 | 1 | Constant | 0000
APS TREASURY | XXAPS TREASURY_AccountRuleSL_Future2 | XXAPS_TREASURYSL_ACCTRULE_FUT2 | XXAPS TREASURY_AccountRuleSL_Future2 | Spain COA | Segment | Future 2 | 1 | Constant | 0000
APS TREASURY | XXAPS TREASURYFR_AccountRuleSL_LE | XXAPS_TREASURYFRSL_ACCTRULE_LE | XXAPS TREASURYFR_AccountRuleSL_LE | France COA | Segment | Legal Entity | 1 | Source | GL Legal Entity
APS TREASURY | XXAPS TREASURYFR_AccountRuleSL_Op_Grp | XXAPS_TREASURYFRSL_ACCTRULE_OP_GRP | XXAPS TREASURYFR_AccountRuleSL_Op_Grp | France COA | Segment | Operating Group | 1 | Constant | 0000
APS TREASURY | XXAPS TREASURYFR_AccountRuleSL_Account | XXAPS_TREASURYFRSL_ACCTRULE_ACCT | XXAPS TREASURYFR_AccountRuleSL_Account | France COA | Segment | Account | 1 | Constant | 1011000
APS TREASURY | XXAPS TREASURYFR_AccountRuleSL_Dept | XXAPS_TREASURYFRSL_ACCTRULE_DEPT | XXAPS TREASURYFR_AccountRuleSL_Dept | France COA | Segment | Department | 1 | Constant | 0000
APS TREASURY | XXAPS TREASURYFR_AccountRuleSL_Site | XXAPS_TREASURYFRSL_ACCTRULE_SITE | XXAPS TREASURYFR_AccountRuleSL_Site | France COA | Segment | Site | 1 | Constant | 00000
APS TREASURY | XXAPS TREASURYFR_AccountRuleSL_IC | XXAPS_TREASURYFRSL_ACCTRULE_IC | XXAPS TREASURYFR_AccountRuleSL_IC | France COA | Segment | Intercompany | 1 | Constant | 0000
APS TREASURY | XXAPS TREASURYFR_AccountRuleSL_Project | XXAPS_TREASURYFRSL_ACCTRULE_PROJ | XXAPS TREASURYFR_AccountRuleSL_Project | France COA | Segment | Project | 1 | Constant | 0000
APS TREASURY | XXAPS TREASURYFR_AccountRuleSL_Future1 | XXAPS_TREASURYFRSL_ACCTRULE_FUT1 | XXAPS TREASURYFR_AccountRuleSL_Future1 | France COA | Segment | Future 1 | 1 | Constant | 0000
APS TREASURY | XXAPS TREASURYFR_AccountRuleSL_Future2 | XXAPS_TREASURYFRS_ACCTRULE_FU2 | XXAPS TREASURYFR_AccountRuleSL_Future2 | France COA | Segment | Future 2 | 1 | Constant | 0000
APS TREASURY | XXAPS TREASURYNR_AccountRuleSL_LE | XXAPS_TREASURYNRSL_ACCTRULE_LE | XXAPS TREASURYNR_AccountRuleSL_LE | Norway COA | Segment | Legal Entity | 1 | Source | GL Legal Entity
APS TREASURY | XXAPS TREASURYNR_AccountRuleSL_Op_Grp | XXAPS_TREASURYNRSL_ACCTRULE_OP_GRP | XXAPS TREASURYNR_AccountRuleSL_Op_Grp | Norway COA | Segment | Operating Group | 1 | Constant | 0000
APS TREASURY | XXAPS TREASURYNR_AccountRuleSL_Account | XXAPS_TREASURYNRSL_ACCTRULE_ACCT | XXAPS TREASURYNR_AccountRuleSL_Account | Norway COA | Segment | Account | 1 | Constant | 10
APS TREASURY | XXAPS TREASURYNR_AccountRuleSL_Dept | XXAPS_TREASURYNRSL_ACCTRULE_DEPT | XXAPS TREASURYNR_AccountRuleSL_Dept | Norway COA | Segment | Department | 1 | Constant | 0000
APS TREASURY | XXAPS TREASURYNR_AccountRuleSL_Site | XXAPS_TREASURYNRSL_ACCTRULE_SITE | XXAPS TREASURYNR_AccountRuleSL_Site | Norway COA | Segment | Site | 1 | Constant | 00000
APS TREASURY | XXAPS TREASURYNR_AccountRuleSL_IC | XXAPS_TREASURYNRSL_ACCTRULE_IC | XXAPS TREASURYNR_AccountRuleSL_IC | Norway COA | Segment | Intercompany | 1 | Constant | 0000
APS TREASURY | XXAPS TREASURYNR_AccountRuleSL_Project | XXAPS_TREASURYNRSL_ACCTRULE_PROJ | XXAPS TREASURYNR_AccountRuleSL_Project | Norway COA | Segment | Project | 1 | Constant | 0000
APS TREASURY | XXAPS TREASURYNR_AccountRuleSL_Future1 | XXAPS_TREASURYNRSL_ACCTRULE_FUT1 | XXAPS TREASURYNR_AccountRuleSL_Future1 | Norway COA | Segment | Future 1 | 1 | Constant | 0000
APS TREASURY | XXAPS TREASURYNR_AccountRuleSL_Future2 | XXAPS_TREASURYNRS_ACCTRULE_FU2 | XXAPS TREASURYNR_AccountRuleSL_Future2 | Norway COA | Segment | Future 2 | 1 | Constant | 0000
APS TREASURY | XXAPS TREASURYPL_AccountRuleSL_LE | XXAPS_TREASURYPLSL_ACCTRULE_LE | XXAPS TREASURYPL_AccountRuleSL_LE | Poland COA | Segment | Legal Entity | 1 | Source | GL Legal Entity
APS TREASURY | XXAPS TREASURYPL_AccountRuleSL_Op_Grp | XXAPS_TREASURYPLSL_ACCTRULE_OP_GRP | XXAPS TREASURYPL_AccountRuleSL_Op_Grp | Poland COA | Segment | Operating Group | 1 | Constant | 0000
APS TREASURY | XXAPS TREASURYPL_AccountRuleSL_Account | XXAPS_TREASURYPLSL_ACCTRULE_ACCT | XXAPS TREASURYPL_AccountRuleSL_Account | Poland COA | Segment | Account | 1 | Constant | 10
APS TREASURY | XXAPS TREASURYPL_AccountRuleSL_Dept | XXAPS_TREASURYPLSL_ACCTRULE_DEPT | XXAPS TREASURYPL_AccountRuleSL_Dept | Poland COA | Segment | Department | 1 | Constant | 0000
APS TREASURY | XXAPS TREASURYPL_AccountRuleSL_Site | XXAPS_TREASURYPLSL_ACCTRULE_SITE | XXAPS TREASURYPL_AccountRuleSL_Site | Poland COA | Segment | Site | 1 | Constant | 13414
APS TREASURY | XXAPS TREASURYPL_AccountRuleSL_IC | XXAPS_TREASURYPLSL_ACCTRULE_IC | XXAPS TREASURYPL_AccountRuleSL_IC | Poland COA | Segment | Intercompany | 1 | Constant | 0000
APS TREASURY | XXAPS TREASURYPL_AccountRuleSL_Project | XXAPS_TREASURYPLSL_ACCTRULE_PROJ | XXAPS TREASURYPL_AccountRuleSL_Project | Poland COA | Segment | Project | 1 | Constant | 0000
APS TREASURY | XXAPS TREASURYPL_AccountRuleSL_Future1 | XXAPS_TREASURYPLSL_ACCTRULE_FUT1 | XXAPS TREASURYPL_AccountRuleSL_Future1 | Poland COA | Segment | Future 1 | 1 | Constant | 0000
APS TREASURY | XXAPS TREASURYPL_AccountRuleSL_Future2 | XXAPS_TREASURYPLS_ACCTRULE_FU2 | XXAPS TREASURYPL_AccountRuleSL_Future2 | Poland COA | Segment | Future 2 | 1 | Constant | 0000
LEASES | XXLEASES AccountRule_LE_ESGAAP | XXLEASES_ACCOUNTRULE_LE_ESGAAP | XXLEASES AccountRule_LE_ESGAAP | Spain COA | Segment | Legal Entity | 1 | Source | GL Legal Entity
LEASES | XXLEASES AccountRule_Op_Grp_ESGAAP | XXLEASES_ACCOUNTRULE_OP_GRP_ESGAAP | XXLEASES AccountRule_Op_Grp_ESGAAP | Spain COA | Segment | Operating Group | 1 | Constant | 0000
LEASES | XXLEASES AccountRule_Account_ESGAAP | XXLEASES_ACCOUNTRULE_ACCOUNT_ESGAAP | XXLEASES AccountRule_Account_ESGAAP | Spain COA | Segment | Account | 1 | Constant | 1000000
LEASES | XXLEASES AccountRule_Dept_ESGAAP | XXLEASES_ACCOUNTRULE_DEPT_ESGAAP | XXLEASES AccountRule_Dept_ESGAAP | Spain COA | Segment | Department | 1 | Constant | 0000
LEASES | XXLEASES AccountRule_Site_ESGAAP | XXLEASES_ACCOUNTRULE_SITE_ESGAAP | XXLEASES AccountRule_Site_ESGAAP | Spain COA | Segment | Site | 1 | Constant | 00000
LEASES | XXLEASES AccountRule_IC_ESGAAP | XXLEASES_ACCOUNTRULE_IC_ESGAAP | XXLEASES AccountRule_IC_ESGAAP | Spain COA | Segment | Intercompany | 1 | Constant | 0000
LEASES | XXLEASES AccountRule_Project_ESGAAP | XXLEASES_ACCOUNTRULE_PROJECT_ESGAAP | XXLEASES AccountRule_Project_ESGAAP | Spain COA | Segment | Project | 1 | Constant | 0000
LEASES | XXLEASES AccountRule_Future1_ESGAAP | XXLEASES_ACCOUNTRULE_FUTURE1_ESGAAP | XXLEASES AccountRule_Future1_ESGAAP | Spain COA | Segment | Future 1 | 1 | Constant | 0000
LEASES | XXLEASES AccountRule_Future2_ESGAAP | XXLEASES_ACCOUNTRULE_FUTURE2_ESGAAP | XXLEASES AccountRule_Future2_ESGAAP | Spain COA | Segment | Future 2 | 1 | Constant | 0000
LEASES | XXLEASES AccountRule_LE_FRGAAP | XXLEASES_ACCOUNTRULE_LE_FRGAAP | XXLEASES AccountRule_LE_FRGAAP | France COA | Segment | Legal Entity | 1 | Source | GL Legal Entity
LEASES | XXLEASES AccountRule_Op_Grp_FRGAAP | XXLEASES_ACCOUNTRULE_OP_GRP_FRGAAP | XXLEASES AccountRule_Op_Grp_FRGAAP | France COA | Segment | Operating Group | 1 | Constant | 0000
LEASES | XXLEASES AccountRule_Account_FRGAAP | XXLEASES_ACCOUNTRULE_ACCOUNT_FRGAAP | XXLEASES AccountRule_Account_FRGAAP | France COA | Segment | Account | 1 | Constant | 1011000
LEASES | XXLEASES AccountRule_Dept_FRGAAP | XXLEASES_ACCOUNTRULE_DEPT_FRGAAP | XXLEASES AccountRule_Dept_FRGAAP | France COA | Segment | Department | 1 | Constant | 0000
LEASES | XXLEASES AccountRule_Site_FRGAAP | XXLEASES_ACCOUNTRULE_SITE_FRGAAP | XXLEASES AccountRule_Site_FRGAAP | France COA | Segment | Site | 1 | Constant | 00000
LEASES | XXLEASES AccountRule_IC_FRGAAP | XXLEASES_ACCOUNTRULE_IC_FRGAAP | XXLEASES AccountRule_IC_FRGAAP | France COA | Segment | Intercompany | 1 | Constant | 0000
LEASES | XXLEASES AccountRule_Project_FRGAAP | XXLEASES_ACCOUNTRULE_PROJECT_FRGAAP | XXLEASES AccountRule_Project_FRGAAP | France COA | Segment | Project | 1 | Constant | 0000
LEASES | XXLEASES AccountRule_Future1_FRGAAP | XXLEASES_ACCOUNTRULE_FUTURE1_FRGAAP | XXLEASES AccountRule_Future1_FRGAAP | France COA | Segment | Future 1 | 1 | Constant | 0000
LEASES | XXLEASES AccountRule_Future2_FRGAAP | XXLEASES_ACCOUNTRULE_FUTURE2_FRGAAP | XXLEASES AccountRule_Future2_FRGAAP | France COA | Segment | Future 2 | 1 | Constant | 0000
LEASES | XXLEASES AccountRule_LE_NOGAAP | XXLEASES_ACCOUNTRULE_LE_NOGAAP | XXLEASES AccountRule_LE_NOGAAP | Norway COA | Segment | Legal Entity | 1 | Source | GL Legal Entity
LEASES | XXLEASES AccountRule_Op_Grp_NOGAAP | XXLEASES_ACCOUNTRULE_OP_GRP_NOGAAP | XXLEASES AccountRule_Op_Grp_NOGAAP | Norway COA | Segment | Operating Group | 1 | Constant | 0000
LEASES | XXLEASES AccountRule_Account_NOGAAP | XXLEASES_ACCOUNTRULE_ACCOUNT_NOGAAP | XXLEASES AccountRule_Account_NOGAAP | Norway COA | Segment | Account | 1 | Constant | 10
LEASES | XXLEASES AccountRule_Dept_NOGAAP | XXLEASES_ACCOUNTRULE_DEPT_NOGAAP | XXLEASES AccountRule_Dept_NOGAAP | Norway COA | Segment | Department | 1 | Constant | 0000
LEASES | XXLEASES AccountRule_Site_NOGAAP | XXLEASES_ACCOUNTRULE_SITE_NOGAAP | XXLEASES AccountRule_Site_NOGAAP | Norway COA | Segment | Site | 1 | Constant | 00000
LEASES | XXLEASES AccountRule_IC_NOGAAP | XXLEASES_ACCOUNTRULE_IC_NOGAAP | XXLEASES AccountRule_IC_NOGAAP | Norway COA | Segment | Intercompany | 1 | Constant | 0000
LEASES | XXLEASES AccountRule_Project_NOGAAP | XXLEASES_ACCOUNTRULE_PROJECT_NOGAAP | XXLEASES AccountRule_Project_NOGAAP | Norway COA | Segment | Project | 1 | Constant | 0000
LEASES | XXLEASES AccountRule_Future1_NOGAAP | XXLEASES_ACCOUNTRULE_FUTURE1_NOGAAP | XXLEASES AccountRule_Future1_NOGAAP | Norway COA | Segment | Future 1 | 1 | Constant | 0000
LEASES | XXLEASES AccountRule_Future2_NOGAAP | XXLEASES_ACCOUNTRULE_FUTURE2_NOGAAP | XXLEASES AccountRule_Future2_NOGAAP | Norway COA | Segment | Future 2 | 1 | Constant | 0000
LEASES | XXLEASES AccountRule_LE_PLGAAP | XXLEASES_ACCOUNTRULE_LE_PLGAAP | XXLEASES AccountRule_LE_PLGAAP | Poland COA | Segment | Legal Entity | 1 | Source | GL Legal Entity
LEASES | XXLEASES AccountRule_Op_Grp_PLGAAP | XXLEASES_ACCOUNTRULE_OP_GRP_PLGAAP | XXLEASES AccountRule_Op_Grp_PLGAAP | Poland COA | Segment | Operating Group | 1 | Constant | 0000
LEASES | XXLEASES AccountRule_Account_PLGAAP | XXLEASES_ACCOUNTRULE_ACCOUNT_PLGAAP | XXLEASES AccountRule_Account_PLGAAP | Poland COA | Segment | Account | 1 | Constant | 10
LEASES | XXLEASES AccountRule_Dept_PLGAAP | XXLEASES_ACCOUNTRULE_DEPT_PLGAAP | XXLEASES AccountRule_Dept_PLGAAP | Poland COA | Segment | Department | 1 | Constant | 0000
LEASES | XXLEASES AccountRule_Site_PLGAAP | XXLEASES_ACCOUNTRULE_SITE_PLGAAP | XXLEASES AccountRule_Site_PLGAAP | Poland COA | Segment | Site | 1 | Constant | 13414
LEASES | XXLEASES AccountRule_IC_PLGAAP | XXLEASES_ACCOUNTRULE_IC_PLGAAP | XXLEASES AccountRule_IC_PLGAAP | Poland COA | Segment | Intercompany | 1 | Constant | 0000
LEASES | XXLEASES AccountRule_Project_PLGAAP | XXLEASES_ACCOUNTRULE_PROJECT_PLGAAP | XXLEASES AccountRule_Project_PLGAAP | Poland COA | Segment | Project | 1 | Constant | 0000
LEASES | XXLEASES AccountRule_Future1_PLGAAP | XXLEASES_ACCOUNTRULE_FUTURE1_PLGAAP | XXLEASES AccountRule_Future1_PLGAAP | Poland COA | Segment | Future 1 | 1 | Constant | 0000
LEASES | XXLEASES AccountRule_Future2_PLGAAP | XXLEASES_ACCOUNTRULE_FUTURE2_PLGAAP | XXLEASES AccountRule_Future2_PLGAAP | Poland COA | Segment | Future 2 | 1 | Constant | 0000

## SIT2 Enhancements (hidden)
Jira ID | Details | Impacted RICE ID | Source System | Issue Status | Target Fix | Priority | Primary Owner | Secondary Owner | FUT completion
CTPFS-7477 | AQI - Confirmation on Line Description where Amount type is FIC | Config Change | MF AP | Closed | 1B SIT2 | P1 | Ankur | Rajesh | Completed
CTPFS-6950 | Reconfirmation regarding creation of AQI - Freight Invoice Material Line in AHCS |  | MF AP | Closed | 1B SIT1 | P1 | Ankur | Rajesh | Completed
CTPFS-6934 | Line Description missing |  | MF AP | Closed | 1B SIT1 | P1 | Ankur | Rajesh | Completed
CTPFS-7555 | As per approved BR100, SPER does not have conditions for amount type ISH and ISL | Config Change | MF AR | In Progress | 1B SIT1 | P1 | Sravya | Prachi | Completed
CTPFS-7427 | RA event type is as "debit" on the INT043 report plus in Oracle and should be as "credit" based on what is in production. | Config Change | MF AR | Fixed | 1B SIT1 | P1 | Sravya | Prachi | Completed
CTPFS-7424 | OIC LSIR Error 301¦Line DR/CR amount mismatch |  | MF AR | Closed | 1B SIT1 | P1 | Sravya | Prachi | NA
CTPFS-7380 | COA values not present in SIT1 | Config Change | MF AR | Closed | 1B SIT1 | P1 | Sravya | Prachi | NA
CTPFS-7356 | 3 CASH (CRI) transactions of event type CRI_CASH_ALLOWANCES are not processed in AHCS | Config Change | MF AR | New User Story | 1B SIT2 | P1 | Sravya | Prachi | Completed
CTPFS-7097 | Sale: SII TRD PNRAF9 Credits: unable to find value in Mapping set for 00898 and 00013, 00326 Legacy BU | Config Change | MF AR | Closed | 1B SIT1 | P1 | Sravya | Prachi | NA
CTPFS-7058 | Late fee transaction failed accounting | Config Change | MF AR | In Progress | 1B SIT2 | P1 | Sravya | Prachi | Completed
CTPFS-7055 | Last Line skipped due to special character for MF AP - MF AR |  | MF AR | Closed | 1B SIT1 | P1 | Ankur | Rajesh | Completed
CTPFS-7013 | MF AR - LSIR - INT216 - 301¦Line DR/CR amount mismatch |  | MF AR | Closed | 1B SIT1 | P1 | Sravya | Prachi | NA
CTPFS-7342 | RPT009 needs Accounting sequencing added |  | RPT009 | New User Story | 1B SIT2 | P1 | Sravya | Ankur | Completed
CTPFS-7045 | SXE and Eclipse accounting doesn't match legacy transaction date |  | SXE | Closed | 1B SIT1 | P1 | Rajesh | Ankur | Completed
CTPFS-7018 | Eclipse : CTPFS-6668 (SXEUS) - step 4 |  | ECLIPSE | Closed | 1B SIT2 | P1 | Rajesh | Ankur | Completed
CTPFS-7429 | Enhancement - Criteria to split INT043 data by Subledger for performance and easy access |  | INT043 | New User Story | 1B SIT2 | P1 | Rajesh | Kathir | Completed
CTPFS-7343 | INT043 needs Accounting sequencing added |  | INT043 | New User Story | 1B SIT2 | P1 | Kathiravan | Rajesh | Completed
CTPFS-7323 | INT043 - AHCS Details to IAP missing Accounting Class Code |  | INT043 | New User Story | 1B SIT2 | P1 | Kathiravan | Rajesh | Completed
CTPFS-7446 | Balances not match according to the IAP production |  | INT044 | Closed | 1B SIT1 | P1 | Ankur | Rajesh | Completed
CTPFS-7359 | INT044 Needs to be changed to YTD | INT044 | INT044 | New User Story | 1B SIT2 | P1 | Prachi | Ankur | Completed
CTPFS-7412 | RPT006 - Performance | RPT006 | RPT006 | Open | 1B SIT2 | P1 | Ankur | Rajesh | Completed
CTPFS-7397 | MF AP TO changes - Vendor Payment type and PO type fields are removed | Config Change | MF AP | Open | 1B SIT2 | P1 | Ankur | Rajesh | Completed
CTPSF- 7397 | MF AP Legacy Data Missing - Legacy Transaction Type - Line Type |  | MF AP | Open | 1B SIT2 | P1 | Ankur | Rajesh | Completed
CSTONE-11506 | Conduct FUT - Oracle - MF AP BKI and LSI transactions to be balanced by LE |  | MF AP | Open | 1B SIT2 | P1 | Ankur | Rajesh | Completed
CSTONE-11954 | Conduct FUT - Enable Invoice date as balance enabled supporting reference for AP Subledger |  | MF AP | Open | 1B SIT2 | P1 | Ankur | Rajesh | Completed
| Enable Legacy GL Location as balanced enabled SR | Config Change | MF AP | Open | 1B SIT2 | P1 | Ankur | Rajesh | Completed
| Enable Legacy GL Location as balanced enabled SR | Config Change | MF AR | Open | 1B SIT2 | P1 | Sravya | Prachi | Completed
| Enable Legacy GL Location as balanced enabled SR | Config Change | MF INV | Open | 1B SIT2 | P1 | Kathiravan | Rajesh | Completed
| Remove Legacy COA 1-4 as balanced SR for 1B subledgers and move it to non-balanced SR | Config Change | MF AP | Open | 1B SIT2 | P1 | Ankur | Rajesh | Completed
| Remove Legacy COA 1-4 as balanced SR for 1B subledgers and move it to non-balanced SR | Config Change | MF AR | Open | 1B SIT2 | P1 | Sravya | Prachi | Completed
| Remove Legacy COA 1-4 as balanced SR for 1B subledgers and move it to non-balanced SR | Config Change | MF INV | Open | 1B SIT2 | P1 | Kathiravan | Rajesh | Completed
| RPT 006 Enhancement Changes 1. Three New columns would be added in RPT006 – • Total File Line Count – Total Number of Lines from Successfully processed OIC File • AHCS ( Final Accounted ) Amount – Accounted amount for file success records. • AHCS Unprocessed Amount - Accounted amount for file Unsuccess records ( Error, Invalid, Unprocessed etc.) 2. Change in Last Column ( P ) from Diff Amount (File Total Amount - GL Posted Amt) to Diff Amount (AHCS Posted Amount - GL Posted Amt) |  | RPT006 | Open | 1B SIT2 | P1 | Ankur | Rajesh | Completed
| INT044 Enhancements 1. YTD balances instead of PTD 2. Include Invoice date as balance enabled supporting reference for AP Subledger 3. Enable Legacy GL Location as balanced enabled SR for MF AP 4. Remove Legacy COA 1-4 as balanced SR for 1B subledgers and move it to non-balanced SR |  | INT044 | Open | 1B SIT2 | P1 | Prachi | Ankur | Completed
CTPSF - 5363 | Mainframe to split LSI file before sending to oracle (Split LSI extracted transactions by Legal Entity) |  | MF AP | Open | 1B SIT2 | P1 | Ankur | Rajesh | Completed
CTPSF- 6924 | Grouping Logic of Transactions by Ledger |  | MF AP | Open | 1B SIT2 | P1 | Ankur | Rajesh | Completed
| RPT208 Testing |  | RPT208 | Open | 1B SIT2 | P1 | Ankur | Rajesh | Completed
CTPFS-7430 | New Outbound integrate for AHCS Conversion Details |  | INT244 | New User Story | 1B SIT2 | P1 | Rajesh | Kathir | Completed
| Volumne (Merge, Split) testing |  | All | Open | 1B SIT2 | P2 | All | All | Completed
| MF AP Secondary Ledger Config |  | MF AP | Open | 1B SIT2 | P3 | Ankur | Rajesh | Completed
| MF AP Secondary Ledger FUT |  | MF AP | Open | 1B SIT2 | P3 | Ankur | Rajesh | Completed
CTPFS-5363 | Transaction Split testing | Decision | MF AR | In Progress | 1B SIT2 | P1 | Sravya | Prachi | Completed
| MF AR Secondary Ledger Config | INT216,217,240 | MF AR | Open | 1B SIT2 | P3 | Sravya | Prachi | Completed
| MF AR Secondary Ledger FUT | INT216,217,240 | MF AR | Open | 1B SIT2 | P3 | Sravya | Prachi | Completed
| MF INV Secondary Ledger Config | INT222, INT223 | MF INV | Open | 1B SIT2 | P3 | Kathiravan | Rajesh,Prachi | Completed
| MF INV Secondary Ledger FUT | INT222, INT223 | MF INV | Open | 1B SIT2 | P3 | Kathiravan | Rajesh,Prachi | Completed
| Leases Secondary Ledger Config |  | Leases | Closed | 1B SIT2 | P3 | Prachi | Sravya | Completed
| Leases Secondary Ledger FUT |  | Leases | Closed | 1B SIT2 | P3 | Prachi | Sravya | Completed
| Leases New Enhancement for Accounting Date (Sysdate -5) |  | Leases | Closed | 1B SIT2 | P1 | Prachi | Sravya | Completed
| Oracle LSI Secondary Ledger Config |  | Oracle LSI | Closed | 1B SIT2 | P3 | Prachi | Sravya | Completed
| Oracle LSI Secondary Ledger FUT |  | Oracle LSI | Closed | 1B SIT2 | P3 | Prachi | Sravya | Completed
| Concur Primary Ledger Config |  | Concur | Open | 1B SIT2 | P3 | Prachi | Sravya | Completed
| Concur Primary Ledger FUT |  | Concur | Open | 1B SIT2 | P3 | Prachi | Sravya | Completed
| Concur Secondary Ledger Config |  | Concur | Open | 1B SIT2 | P3 | Prachi | Sravya | Completed
| Concur Secondary Ledger FUT |  | Concur | Open | 1B SIT2 | P3 | Prachi | Sravya | Completed
| Line Sequence number for BKI will be populated from line sequence number from source | INT216,217,240 | MF AR |  | 1B SIT2 | P2 | Sravya | Prachi | Completed

## New Feature working (hidden)
Create Accouting Final Mode by ledegr | [7 empty] | Create Accouting Final Mode by ledegr | [8 empty] | MF AR |  | MF AP |  |  | Create Accouting Draft Mode by File | [6 empty] | EMEA Primary LS
MF AR |  | Request ID | Submission Time | Completion Time | T1 | T2 | Time Taken | MF AP |  | Request ID | Submission Time | Completion Time | T1 | T2 | Time Taken | Time (hh:mm) | Create Accounting (Final) Ledgers | Create Accounting (Draft) File | Create Accounting (Final) Ledgers | Create Accounting (Draft) File |  | Subledger | File | Total time | Count of File | Column Labels | Count of File | Column Labels | AE USGAAP USD | CALA Primary LS | REQUESTID | Region | APPLICATION | USERNAME | NAME | PROCESSSTART | PROCESSEND
AE USGAAP USD | AE USGAAP USD | 2083013 | 9/6/22 10:08 AM IST | 9/6/22 10:09 AM IST | 44810.4222 | 44810.4229 | 0:01 | AE USGAAP USD | EMEA | 2083260 | 9/6/22 10:50 AM IST | 9/6/22 10:52 AM IST | 44810.4514 | 44810.4528 | 0:02 | 0:00 | 100 | 7 | 99 | 4 |  | MF AR | MF_SPER_AL_20220609_081252 | 1.45 | Row Labels | MF AP | Row Labels | MF AR | AT USGAAP EUR | AR USGAAP USD | 2083278 | EMEA | FscmEss | rajesh.kumar | XLABABUP | 2022-06-09T05:22:14.844+00:00 | 2022-06-09T05:22:20.750+00:00 | 24:01
AR USGAAP USD | #N/A | 2083028 | 9/6/22 10:11 AM IST | 9/6/22 10:11 AM IST | 44810.4243 | 44810.4243 | 0:00 | AR USGAAP USD | CALA | 2083319 | 9/6/22 10:56 AM IST | 9/6/22 10:57 AM IST | 44810.4556 | 44810.4563 | 0:01 | 0:00 | 7 | 3 | 15 | 2 |  | MF AR | MF_ARIN_AL_20220609_081238 | 1.33 | 0.37 | 1 | 0.47 | 1 | BE USGAAP EUR | BB USGAAP USD | 2083385 | EMEA | FscmEss | rajesh.kumar | XLABABUP | 05:34:16.915+00:00 | 05:34:27.271+00:00 | 24:01
AT USGAAP EUR | AT USGAAP EUR | 2083036 | 9/6/22 10:13 AM IST | 9/6/22 10:13 AM IST | 44810.4257 | 44810.4257 | 0:00 | AT USGAAP EUR | EMEA | 2083335 | 9/6/22 10:59 AM IST | 9/6/22 11:01 AM IST | 44810.4576 | 44810.459 | 0:02 | 0:00 | 1 | 3 | 2 | 5 |  | MF AR | MF_SALE_AL_20220609_081611 | 2.83 | 0.73 | 1 | 0.87 | 1 | CH USGAAP CHF | BR USGAAP BRL | 2083428 | EMEA | FscmEss | rajesh.kumar | XLABABUP | 05:41:01.693+00:00 | 05:41:37.563+00:00 | 24:01
AU USGAAP AUD | #N/A | 2083059 | 9/6/22 10:18 AM IST | 9/6/22 10:19 AM IST | 44810.4292 | 44810.4299 | 0:01 | AU USGAAP AUD | NA | 2083369 | 9/6/22 11:02 AM IST | 9/6/22 11:04 AM IST | 44810.4597 | 44810.4611 | 0:02 | [6 empty] | MF AR | MF_CASH_AL_20220609_081323 | 0.87 | 1.23 | 1 | 1.13 | 1 | DE USGAAP EUR | BR USGAAP USD | 2083524 | EMEA | FscmEss | rajesh.kumar | XLABABUP | 05:53:48.253+00:00 | 05:53:57.472+00:00 | 24:01
BB USGAAP USD | #N/A | 2083076 | 9/6/22 10:21 AM IST | 9/6/22 10:22 AM IST | 44810.4313 | 44810.4319 | 0:01 | BB USGAAP USD | CALA | 2083391 | 9/6/22 11:05 AM IST | 9/6/22 11:06 AM IST | 44810.4618 | 44810.4625 | 0:01 | [6 empty] | MF AR | MF_SALE_AC_20220609_081608 | 1.13 | 1.37 | 1 | 1.33 | 1 | DK USGAAP DKK | CL USGAAP USD | 2083735 | EMEA | FscmEss | rajesh.kumar | XLABABUP | 06:05:37.403+00:00 | 06:05:42.309+00:00 | 24:01
BE USGAAP EUR | BE USGAAP EUR | 2083083 | 9/6/22 10:24 AM IST | 9/6/22 10:25 AM IST | 44810.4333 | 44810.434 | 0:01 | BE USGAAP EUR | EMEA | 2083409 | 9/6/22 11:08 AM IST | 9/6/22 11:10 AM IST | 44810.4639 | 44810.4653 | 0:02 | [6 empty] | MF AR | MF_SPER_AC_20220609_081245 | 1.35 | 1.5 | 1 | 1.35 | 1 | EG USGAAP EGP | CO USGAAP USD | 2083768 | EMEA | FscmEss | rajesh.kumar | XLABABUP | 06:08:50.269+00:00 | 06:09:07.364+00:00 | 24:01
BR USGAAP USD | #N/A | 2083107 | 9/6/22 10:27 AM IST | 9/6/22 10:28 AM IST | 44810.4354 | 44810.4361 | 0:01 | BR USGAAP BRL | CALA | 2083438 | 9/6/22 11:11 AM IST | 9/6/22 11:12 AM IST | 44810.466 | 44810.4667 | 0:01 | [6 empty] | MF AR | MF_CASH_AC_20220609_081313 | 2.35 | 1.57 | 1 | 1.45 | 1 | FI USGAAP EUR | CR USGAAP USD | 2083810 | EMEA | FscmEss | rajesh.kumar | XLABABUP | 06:11:21.082+00:00 | 06:11:25.085+00:00 | 24:01
CA USGAAP CAD | #N/A | 2083115 | 9/6/22 10:30 AM IST | 9/6/22 10:31 AM IST | 44810.4375 | 44810.4382 | 0:01 | BR USGAAP USD | CALA | 2083450 | 9/6/22 11:13 AM IST | 9/6/22 11:15 AM IST | 44810.4674 | 44810.4688 | 0:02 | Option 1 | Option 2 | Option 3 | Option 4 | EMEA |  | MF AR | MF_CASH_EU_20220609_081336 | 1.47 | 2.58 | 1 | 1.47 | 1 | FR USGAAP EUR | DO USGAAP USD | 2083858 | EMEA | FscmEss | rajesh.kumar | XLABABUP | 06:16:36.363+00:00 | 06:16:40.901+00:00 | 24:01
CH USGAAP CHF | CH USGAAP CHF | 2083164 | 9/6/22 10:37 AM IST | 9/6/22 10:37 AM IST | 44810.4424 | 44810.4424 | 0:00 | CA USGAAP CAD | NA | 2083477 | 9/6/22 11:16 AM IST | 9/6/22 11:20 AM IST | 44810.4694 | 44810.4722 | 0:04 | Count | Count | Count | Count | Option 1, 2 | Option 3 | MF AR | MF_SPER_EU_20220609_081258 | 0.47 | 3.37 | 1 | 1.52 | 1 | GB USGAAP USD | GT USGAAP USD | 2083870 | EMEA | FscmEss | rajesh.kumar | XLABABUP | 06:19:22.021+00:00 | 06:19:35.052+00:00 | 24:01
CL USGAAP USD | #N/A | 2083171 | 9/6/22 10:38 AM IST | 9/6/22 10:39 AM IST | 44810.4431 | 44810.4437 | 0:01 | CH USGAAP CHF | EMEA | 2083515 | 9/6/22 11:22 AM IST | 9/6/22 11:23 AM IST | 44810.4736 | 44810.4743 | 0:01 | 5 | 1 | 5 | 5 | Import Acounting | Import Accounting Transactions into Interface | MF AR | MF_ARIN_EU_20220609_081242 | 1.52 | 3.58 | 1 | 2.1 | 1 | GR USGAAP EUR | JM USGAAP USD | 2084519 | EMEA | FscmEss | NArun | XLABABUP | 07:56:44.884+00:00 | 07:56:54.791+00:00 | 24:01
CN USGAAP CNY | #N/A | 2083178 | 9/6/22 10:39 AM IST | 9/6/22 10:40 AM IST | 44810.4437 | 44810.4444 | 0:01 | CL USGAAP USD | CALA | 2083530 | 9/6/22 11:24 AM IST | 9/6/22 11:26 AM IST | 44810.475 | 44810.4764 | 0:02 | 75 | 0 | 0 | 0 | Create Accounting (Draft) | Create Accounting (Draft) | MF AR | MF_SALE_EU_20220609_081612 | 2.1 | 4.62 | 1 | 2.35 | 1 | HU USGAAP HUF | PA USGAAP USD | 2084542 | EMEA | FscmEss | NArun | XLABABUP | 07:57:58.469+00:00 | 07:59:45.988+00:00 | 24:02
CO USGAAP USD | #N/A | 2083186 | 9/6/22 10:40 AM IST | 9/6/22 10:41 AM IST | 44810.4444 | 44810.4451 | 0:01 | CN USGAAP CNY | NA | 2083561 | 9/6/22 11:27 AM IST | 9/6/22 11:28 AM IST | 44810.4771 | 44810.4778 | 0:01 | 15 | 15 | 15 | 75 | Create Accounting (Final) | Create Accounting (Final) | MF AP | MF_ADIN_EU_20220609_080623 | 1.23 | 4.63 | 1 | 2.83 | 1 | IT USGAAP EUR | PE USGAAP USD | 2084543 | EMEA | FscmEss | NArun | XLABABUP | 07:58:13.510+00:00 | 07:58:18.965+00:00 | 24:01
CR USGAAP USD | #N/A | 2083201 | 9/6/22 10:42 AM IST | 9/6/22 10:43 AM IST | 44810.4458 | 44810.4465 | 0:01 | CO USGAAP USD | CALA | 2083664 | 9/6/22 11:30 AM IST | 9/6/22 11:31 AM IST | 44810.4792 | 44810.4799 | 0:01 | 15 | 15 | 15 | 75 | Create Accounting: Subprocess | Post Subledger Journal Entries | MF AP | MF_APIN_EU_20220609_080642 | 0.73 | Grand Total | 11 | Grand Total | 11 | MA USGAAP MAD | PR USGAAP USD | 2084575 | EMEA | FscmEss | NArun | XLABABUP | 08:01:02.942+00:00 | 08:01:06.483+00:00 | 24:01
CZ USGAAP CZK | #N/A | 2083204 | 9/6/22 10:43 AM IST | 9/6/22 10:44 AM IST | 44810.4465 | 44810.4472 | 0:01 | CR USGAAP USD | CALA | 2083706 | 9/6/22 11:32 AM IST | 9/6/22 11:33 AM IST | 44810.4806 | 44810.4812 | 0:01 | 15 | 15 | 15 | 75 | Post Subledger Journal Entries | Create Accounting: Subprocess | MF AP | MF_CAIN_EU_20220609_080704 | 1.37 |  |  |  |  | NO USGAAP NOK | TT USGAAP USD | 2084672 | EMEA | FscmEss | NArun | XLABABUP | 08:08:48.572+00:00 | 08:08:53.349+00:00 | 24:01
DE USGAAP EUR | DE USGAAP EUR | 2083224 | 9/6/22 10:46 AM IST | 9/6/22 10:47 AM IST | 44810.4486 | 44810.4493 | 0:01 | CZ USGAAP CZK | EMEA | 2083720 | 9/6/22 11:34 AM IST | 9/6/22 11:35 AM IST | 44810.4819 | 44810.4826 | 0:01 | 15 | 15 | 15 | 75 | Post Subledger Journal Entries Subprocess | Import Journals Child | MF AP | MF_AQIN_EU_20220609_080653 | 1.57 |  |  |  |  | PT USGAAP EUR | UY USGAAP USD | 2084715 | EMEA | FscmEss | NArun | XLABABUP | 08:14:19.094+00:00 | 08:14:28.369+00:00 | 24:01
DK USGAAP DKK | DK USGAAP DKK | 2083228 | 9/6/22 10:46 AM IST | 9/6/22 10:47 AM IST | 44810.4486 | 44810.4493 | 0:01 | DE USGAAP EUR | EMEA | 2083754 | 9/6/22 11:36 AM IST | 9/6/22 11:38 AM IST | 44810.4833 | 44810.4847 | 0:02 | 15 | 15 | 15 | 75 | Import Journals Child | Post Subledger Journal Entries Subprocess | MF AP | MF_CAIN_AC_20220609_080655 | 0.37 |  |  |  |  | RU USGAAP USD | VE USGAAP USD | 2084735 | EMEA | FscmEss | NArun | XLABABUP | 08:15:15.802+00:00 | 08:15:20.298+00:00 | 24:01
EG USGAAP EGP | EG USGAAP EGP | 2083241 | 9/6/22 10:48 AM IST | 9/6/22 10:49 AM IST | 44810.45 | 44810.4507 | 0:01 | DK USGAAP DKK | EMEA | 2083784 | 9/6/22 11:39 AM IST | 9/6/22 11:41 AM IST | 44810.4854 | 44810.4868 | 0:02 | 15 | 15 | 15 | 75 | Post Journals for Single Ledger | Post Journals for Single Ledger | MF AP | MF_ADIN_AC_20220609_080547 | 4.63 |  |  |  |  | SA USGAAP SAR |  | 2083382 | NA | FscmEss | NArun | XLABABUP | 05:34:01.860+00:00 | 05:34:05.820+00:00 | 24:01
ES USGAAP EUR | #N/A | 2083247 | 9/6/22 10:49 AM IST | 9/6/22 10:50 AM IST | 44810.4507 | 44810.4514 | 0:01 | EC USGAAP USD | NA | 2083812 | 9/6/22 11:42 AM IST | 9/6/22 11:43 AM IST | 44810.4875 | 44810.4882 | 0:01 | 15 | 15 | 15 | 75 | Update Subledger Accounting Balances | Update Subledger Accounting Bala | MF AP | MF_CAIN_AL_20220609_080701 | 1.5 |  |  |  |  | SE USGAAP SEK |  | 2083502 | NA | FscmEss | rajesh.kumar | XLABABUP | 05:51:02.853+00:00 | 05:54:20.256+00:00 | 24:03
FI USGAAP EUR | FI USGAAP EUR | 2083272 | 9/6/22 10:51 AM IST | 9/6/22 10:52 AM IST | 44810.4521 | 44810.4528 | 0:01 | EG USGAAP EGP | EMEA | 2083842 | 9/6/22 11:45 AM IST | 9/6/22 11:46 AM IST | 44810.4896 | 44810.4903 | 0:01 | 185 | 106 | 110 | 530 |  |  | MF AP | MF_ADIN_AL_20220609_080556 | 3.58 |  |  |  |  | SK USGAAP EUR |  | 2083575 | NA | FscmEss | rajesh.kumar | XLABABUP | 05:58:33.638+00:00 | 05:58:39.115+00:00 | 24:01
FR USGAAP EUR | FR USGAAP EUR | 2083280 | 9/6/22 10:52 AM IST | 9/6/22 10:53 AM IST | 44810.4528 | 44810.4535 | 0:01 | ES USGAAP EUR | EMEA | 2083859 | 9/6/22 11:47 AM IST | 9/6/22 11:49 AM IST | 44810.491 | 44810.4924 | 0:02 | [6 empty] | MF AP | MF_AQIN_AL_20220609_080646 | 2.58 |  |  |  |  | TR USGAAP USD |  | 2083818 | NA | FscmEss | rajesh.kumar | XLABABUP | 06:13:21.451+00:00 | 06:13:25.346+00:00 | 24:01
GB USGAAP GBP | #N/A | 2083290 | 9/6/22 10:53 AM IST | 9/6/22 10:54 AM IST | 44810.4535 | 44810.4542 | 0:01 | FI USGAAP EUR | EMEA | 2084439 | 9/6/22 3:26 PM IST | 9/6/22 3:27 PM IST | 44810.6431 | 44810.6438 | 0:01 | [6 empty] | MF AP | MF_APIN_AC_20220609_080627 | 3.37 |  |  |  |  | IL USGAAP ILS |  | 2084540 | NA | FscmEss | NArun | XLABABUP | 07:57:44.875+00:00 | 07:57:49.838+00:00 | 24:01
GB USGAAP USD | GB USGAAP USD | 2083305 | 9/6/22 10:54 AM IST | 9/6/22 10:55 AM IST | 44810.4542 | 44810.4549 | 0:01 | FR USGAAP EUR | EMEA | 2084496 | 9/6/22 1:25 PM IST | 9/6/22 1:26 PM IST | 44810.559 | 44810.5597 | 0:01 | [6 empty] | MF AP | MF_APIN_AL_20220609_080636 | 4.62 | [6 empty] | 2084642 | NA | FscmEss | NArun | XLABABUP | 08:06:48.419+00:00 | 08:07:12.537+00:00 | 24:01
GT USGAAP USD | #N/A | 2083327 | 9/6/22 10:58 AM IST | 9/6/22 10:58 AM IST | 44810.4569 | 44810.4569 | 0:00 | GB USGAAP GBP | NA | 2084500 | 9/6/22 1:25 PM IST | 9/6/22 1:27 PM IST | 44810.559 | 44810.5604 | 0:02 | [15 empty] | 2084740 | NA | FscmEss | NArun | XLABABUP | 08:15:34.316+00:00 | 08:15:39.133+00:00 | 24:01
HK USGAAP HKD | #N/A | 2083361 | 9/6/22 11:01 AM IST | 9/6/22 11:02 AM IST | 44810.459 | 44810.4597 | 0:01 | GB USGAAP USD | EMEA | 2084517 | 9/6/22 1:26 PM IST | 9/6/22 1:27 PM IST | 44810.5597 | 44810.5604 | 0:01
ID USGAAP USD | #N/A | 2083368 | 9/6/22 11:02 AM IST | 9/6/22 11:03 AM IST | 44810.4597 | 44810.4604 | 0:01 | GR USGAAP EUR | EMEA | 2084527 | 9/6/22 1:27 PM IST | 9/6/22 1:28 PM IST | 44810.5604 | 44810.5611 | 0:01
IE USGAAP EUR | #N/A | 2083387 | 9/6/22 11:05 AM IST | 9/6/22 11:06 AM IST | 44810.4618 | 44810.4625 | 0:01 | GT USGAAP USD | CALA | 2084545 | 9/6/22 1:29 PM IST | 9/6/22 1:31 PM IST | 44810.5618 | 44810.5632 | 0:02
IN USGAAP INR | #N/A | 2083413 | 9/6/22 11:08 AM IST | 9/6/22 11:08 AM IST | 44810.4639 | 44810.4639 | 0:00 | HK USGAAP HKD | APAC | 2084580 | 9/6/22 1:31 PM IST | 9/6/22 1:32 PM IST | 44810.5632 | 44810.5639 | 0:01
IT USGAAP EUR | IT USGAAP EUR | 2083435 | 9/6/22 11:11 AM IST | 9/6/22 11:12 AM IST | 44810.466 | 44810.4667 | 0:01 | ID USGAAP USD | APAC | 2084594 | 9/6/22 1:32 PM IST | 9/6/22 1:33 PM IST | 44810.5639 | 44810.5646 | 0:01
JM USGAAP USD | #N/A | 2083463 | 9/6/22 11:14 AM IST | 9/6/22 11:16 AM IST | 44810.4681 | 44810.4694 | 0:02 | IE USGAAP EUR | NA | 2084616 | 9/6/22 1:34 PM IST | 9/6/22 1:36 PM IST | 44810.5653 | 44810.5667 | 0:02
JP USGAAP JPY | #N/A | 2083486 | 9/6/22 11:18 AM IST | 9/6/22 11:20 AM IST | 44810.4708 | 44810.4722 | 0:02 | IL USGAAP ILS | EMEA | 2084653 | 9/6/22 1:37 PM IST | 9/6/22 1:38 PM IST | 44810.5674 | 44810.5681 | 0:01
KR USGAAP KRW | #N/A | 2083511 | 9/6/22 11:21 AM IST | 9/6/22 11:21 AM IST | 44810.4729 | 44810.4729 | 0:00 | IN USGAAP INR | APAC | 2084689 | 9/6/22 1:42 PM IST | 9/6/22 1:44 PM IST | 44810.5708 | 44810.5722 | 0:02
MA USGAAP MAD | MA USGAAP MAD | 2083527 | 9/6/22 11:24 AM IST | 9/6/22 11:25 AM IST | 44810.475 | 44810.4757 | 0:01 | IT USGAAP EUR | EMEA | 2084693 | 9/6/22 1:43 PM IST | 9/6/22 1:44 PM IST | 44810.5715 | 44810.5722 | 0:01
MX USGAAP MXN | #N/A | 2083554 | 9/6/22 11:25 AM IST | 9/6/22 11:26 AM IST | 44810.4757 | 44810.4764 | 0:01 | JM USGAAP USD | CALA | 2084702 | 9/6/22 1:43 PM IST | 9/6/22 1:44 PM IST | 44810.5715 | 44810.5722 | 0:01
MY USGAAP MYR | #N/A | 2083568 | 9/6/22 11:27 AM IST | 9/6/22 11:28 AM IST | 44810.4771 | 44810.4778 | 0:01 | JP USGAAP JPY | APAC | 2084716 | 9/6/22 1:44 PM IST | 9/6/22 1:45 PM IST | 44810.5722 | 44810.5729 | 0:01
NL USGAAP EUR | #N/A | 2083580 | 9/6/22 11:29 AM IST | 9/6/22 11:30 AM IST | 44810.4785 | 44810.4792 | 0:01 | KR USGAAP KRW | APAC | 2084724 | 9/6/22 1:44 PM IST | 9/6/22 1:45 PM IST | 44810.5722 | 44810.5729 | 0:01
NO USGAAP NOK | NO USGAAP NOK | 2083691 | 9/6/22 11:31 AM IST | 9/6/22 11:32 AM IST | 44810.4799 | 44810.4806 | 0:01 | MA USGAAP MAD | EMEA | 2084731 | 9/6/22 1:45 PM IST | 9/6/22 1:46 PM IST | 44810.5729 | 44810.5736 | 0:01
NZ USGAAP NZD | #N/A | 2083701 | 9/6/22 11:32 AM IST | 9/6/22 11:32 AM IST | 44810.4806 | 44810.4806 | 0:00 | MX USGAAP MXN | NA | 2084739 | 9/6/22 1:45 PM IST | 9/6/22 1:47 PM IST | 44810.5729 | 44810.5743 | 0:02
PA USGAAP USD | #N/A | 2083721 | 9/6/22 11:34 AM IST | 9/6/22 11:35 AM IST | 44810.4819 | 44810.4826 | 0:01 | MY USGAAP MYR | APAC | 2084749 | 9/6/22 1:45 PM IST | 9/6/22 1:46 PM IST | 44810.5729 | 44810.5736 | 0:01
PE USGAAP USD | #N/A | 2083745 | 9/6/22 11:36 AM IST | 9/6/22 11:37 AM IST | 44810.4833 | 44810.484 | 0:01 | NL USGAAP EUR | EMEA | 2084910 | 9/6/22 2:03 PM IST | 9/6/22 2:04 PM IST | 44810.5854 | 44810.5861 | 0:01
PH USGAAP PHP | #N/A | 2083762 | 9/6/22 11:38 AM IST | 9/6/22 11:39 AM IST | 44810.4847 | 44810.4854 | 0:01 | NO USGAAP NOK | EMEA | 2084900 | 9/6/22 2:02 PM IST | 9/6/22 2:03 PM IST | 44810.5847 | 44810.5854 | 0:01
PL USGAAP PLN | #N/A | 2083769 | 9/6/22 11:38 AM IST | 9/6/22 11:38 AM IST | 44810.4847 | 44810.4847 | 0:00 | NZ USGAAP NZD | APAC | 2084894 | 9/6/22 2:01 PM IST | 9/6/22 2:02 PM IST | 44810.584 | 44810.5847 | 0:01
PR USGAAP USD | #N/A | 2083776 | 9/6/22 11:39 AM IST | 9/6/22 11:40 AM IST | 44810.4854 | 44810.4861 | 0:01 | PA USGAAP USD | CALA | 2084877 | 9/6/22 2:00 PM IST | 9/6/22 2:01 PM IST | 44810.5833 | 44810.584 | 0:01
PT USGAAP EUR | PT USGAAP EUR | 2083782 | 9/6/22 11:39 AM IST | 9/6/22 11:41 AM IST | 44810.4854 | 44810.4868 | 0:02 | PE USGAAP USD | CALA | 2084858 | 9/6/22 1:59 PM IST | 9/6/22 2:00 PM IST | 44810.5826 | 44810.5833 | 0:01
RU USGAAP USD | RU USGAAP USD | 2083819 | 9/6/22 11:43 AM IST | 9/6/22 11:45 AM IST | 44810.4882 | 44810.4896 | 0:02 | PH USGAAP PHP | APAC | 2084850 | 9/6/22 1:58 PM IST | 9/6/22 1:59 PM IST | 44810.5819 | 44810.5826 | 0:01
SA USGAAP SAR | SA USGAAP SAR | 2083825 | 9/6/22 11:44 AM IST | 9/6/22 11:45 AM IST | 44810.4889 | 44810.4896 | 0:01 | PL USGAAP PLN | EMEA | 2084844 | 9/6/22 1:57 PM IST | 9/6/22 1:58 PM IST | 44810.5813 | 44810.5819 | 0:01
SE USGAAP SEK | SE USGAAP SEK | 2083830 | 9/6/22 11:44 AM IST | 9/6/22 11:45 AM IST | 44810.4889 | 44810.4896 | 0:01 | PR USGAAP USD | CALA | 2084835 | 9/6/22 1:56 PM IST | 9/6/22 1:57 PM IST | 44810.5806 | 44810.5813 | 0:01
SG USGAAP SGD | #N/A | 2083871 | 9/6/22 11:49 AM IST | 9/6/22 11:50 AM IST | 44810.4924 | 44810.4931 | 0:01 | PT USGAAP EUR | EMEA | 2084823 | 9/6/22 1:55 PM IST | 9/6/22 1:56 PM IST | 44810.5799 | 44810.5806 | 0:01
SG USGAAP USD | #N/A | 2083875 | 9/6/22 11:49 AM IST | 9/6/22 11:51 AM IST | 44810.4924 | 44810.4938 | 0:02 | RU USGAAP USD | EMEA | 2084816 | 9/6/22 1:53 PM IST | 9/6/22 1:55 PM IST | 44810.5785 | 44810.5799 | 0:02
TH USGAAP THB | #N/A | 2083879 | 9/6/22 11:50 AM IST | 9/6/22 11:51 AM IST | 44810.4931 | 44810.4938 | 0:01 | SA USGAAP SAR | EMEA | 2084805 | 9/6/22 1:52 PM IST | 9/6/22 1:53 PM IST | 44810.5778 | 44810.5785 | 0:01
TR USGAAP USD | TR USGAAP USD | 2083886 | 9/6/22 11:50 AM IST | 9/6/22 11:51 AM IST | 44810.4931 | 44810.4938 | 0:01 | SE USGAAP SEK | EMEA | 2084791 | 9/6/22 1:50 PM IST | 9/6/22 1:51 PM IST | 44810.5764 | 44810.5771 | 0:01
TT USGAAP USD | #N/A | 2083893 | 9/6/22 11:50 AM IST | 9/6/22 11:52 AM IST | 44810.4931 | 44810.4944 | 0:02 | SG USGAAP SGD | NA | 2084781 | 9/6/22 1:49 PM IST | 9/6/22 1:50 PM IST | 44810.5757 | 44810.5764 | 0:01
TW USGAAP TWD | #N/A | 2083907 | 9/6/22 11:51 AM IST | 9/6/22 11:52 AM IST | 44810.4938 | 44810.4944 | 0:01 | SG USGAAP USD | APAC | 2084774 | 9/6/22 1:48 PM IST | 9/6/22 1:49 PM IST | 44810.575 | 44810.5757 | 0:01
US USGAAP USD | #N/A | 2083927 | 9/6/22 11:54 AM IST | 9/6/22 11:58 AM IST | 44810.4958 | 44810.4986 | 0:04 | TH USGAAP THB | NA | 2084745 | 9/6/22 1:45 PM IST | 9/6/22 1:46 PM IST | 44810.5729 | 44810.5736 | 0:01
UY USGAAP USD | #N/A | 2083915 | 9/6/22 11:51 AM IST | 9/6/22 11:53 AM IST | 44810.4938 | 44810.4951 | 0:02 | TR USGAAP USD | EMEA | 2084690 | 9/6/22 1:43 PM IST | 9/6/22 1:44 PM IST | 44810.5715 | 44810.5722 | 0:01
| MF AR | CA Final |  |  |  |  | 0:18 | TT USGAAP USD | CALA | 2084675 | 9/6/22 1:40 PM IST | 9/6/22 1:41 PM IST | 44810.5694 | 44810.5701 | 0:01
| MF AR | CA Draft |  |  |  |  | 0:06 | TW USGAAP TWD | APAC | 2084650 | 9/6/22 1:37 PM IST | 9/6/22 1:38 PM IST | 44810.5674 | 44810.5681 | 0:01
| MF AR | Import ACCT |  |  |  |  | 288:08 | US USGAAP USD | NA | 2084602 | 9/6/22 1:33 PM IST | 9/6/22 1:38 PM IST | 44810.5646 | 44810.5681 | 0:05
| MF AR | Update Subledger Accounting Balances | [5 empty] | UY USGAAP USD | CALA | 2084578 | 9/6/22 1:31 PM IST | 9/6/22 1:32 PM IST | 44810.5632 | 44810.5639 | 0:01
|  | Total |  |  |  |  | 0:18 |  | MF AP-EMEA | CA Final |  |  |  |  | 0:26
[9 empty] | MF AP-EMEA | CA Draft |  |  |  |  | 0:10
[9 empty] | MF AP-EMEA | Import ACCT |  |  |  |  | 288:08
[9 empty] | MF AP-EMEA | Update Subledger Accounting Balances
[10 empty] | Total |  |  |  |  | 288:44
[9 empty] | MF AP-NA | CA Final |  |  |  |  | 288:21
[9 empty] | MF AP-NA | CA Draft |  |  |  |  | 288:21
[9 empty] | MF AP-NA | Import ACCT |  |  |  |  | 240:10
[9 empty] | MF AP-NA | Update Subledger Accounting Balances
[10 empty] | Total |  |  |  |  | 816:52

## RPT007 (hidden)
No | Date | Details | Email Sub | Action Pending on | ETA | Status | Comment | BR100/Lean Spec
1 | 2022-03-29 | Manisha to Provide control account list |  | Manisha | 2022-05-04 | Closed | List provided and updated BR100 | BR100
2 | 2022-03-29 | Three columns ( AHCS PTD Net activities, GL PTD Net activities and Difference of these two column ) need to be added for Entered currency in report layout |  | Deloitte |  | Closed | Added required columns and shared out put | Lean Spec

## MFINV (hidden)
No | Date | Details | Email Sub | Action Pending on | ETA | Status | Comment | BR100/Lean Spec
1 | 2022-02-21 | For ISI, CQI,ICI,AII @Mazo, Alla to provide the input data elements for event types |  | Alla |  | Closed | Updated Lean spec
2 | 2022-02-21 | For SSI, @Plummer, Ian @Farrington, Michael to confirm whether to keep it as single event type as per OnPrem BR100 or multiple events based on business requirement.(Refer the Event Types tab in the attached sheet) | [EXT] RE: MOM AHCS - Sprint 9 (Lean Specs) / IT session - Pre work for File layout & Fields -(MF Inventory-SSI, IRI, CQI, IBI, FTI, FII, ICI, AII, ISI ) | Ian, Michael |  | Closed | Checked with the regions and one region request to break out by SPEC and SPER. Please break out separately as feel need will increase by other regions in the future.
3 | 2022-02-21 | For IBI, @Plummer, Ian @Farrington, Michael to confirm on the event types. |  | Ian, Michael |  | Closed | Ok to keep as one event.
4 | 2022-02-21 | Location Balance enabled SR is 5 character, @Plummer, Ian will check and confirm with Regional leads and confirm if any changes are required |  | Ian |  | Closed | Checked with regions and ok to have 5 characters.
5 | 2022-02-21 | Srini to share inputs for source field mapping on the Yellow highlighted rows (Non-Balance enabled SR) in the attached sheet. |  | Alla+Srini |  | Closed | Removed from SR
6 | 2022-02-21 | @Mazo, Alla to verify the Orange highlighted rows (balanced enabled SR) in the attached supporting reference sheet and confirm whether the fields are mapped correctly. |  | Alla |  | Closed | Updated the SR
7 | 2022-02-21 | Srini to share inputs for INV_LINE_I and JRNL_LINE_R are not used in the MF files. @Srini.Nanduri@anixter.com to confirm how these fields are mapped in current FAH. |  | Alla+Srini |  | Closed | Removed from SR
8 | 2022-02-21 | @Mazo, Alla to provide the sample files for Accutech region for MF AP, AR and Inventory. |  | Alla |  | Closed | Alla provided the files
9 | 2022-02-21 | @Deloitte team to update the MF AP and MF AR Lean spec and resend for approval for Source code name and Accutech |  | Sravya, Ankur |  | Closed
10 | 2022-02-21 | For IRI, balance enable SR "Legacy Segment1-4" we will be kept blank as we are not receiving from source as IRI is event based and we are populating constant value for multiple segments in oracle COA. Attaching the screenshot for reference. |  | Deloitte Team |  | Closed | Omkar send a mail to Ian with details. If legacy provides COA information we will capture in legacy COA, but we will not “fabricate” /reverse map if legacy is not providing old COA details.
11 | 2022-02-21 | For AII, ICI, need to finalize the Debit line condition in AHCS. as Amount Type = ICP line is not send by Mainframe. |  | Deloitte Team |  | Closed | ICP will not come from MF and AHCS will add Offset line, POC is completed.
12 | 2022-03-04 | AII : Amount Type description to be added as Journal Line description. @Sijo John (CIAM)to validate and provide the full list of Amount types and corresponding description in the attached spreadsheet. (Refer worksheet ‘AII’) |  | Sijo |  | Closed | Lookup details available in Onprem BR100
13 | 2022-03-04 | AII : @Sijo John (CIAM)to confirm whether we can trim AXE_FAH from the file name. Currently the naming convention is being followed as: "AXE_FAH_AIIIB_AC_ ddmmyyyy_hhmmss" , "AXE_FAH_AIIB_AL_ ddmmyyyy_hhmmss" and "AXE_FAH_AIIB_EU_ddmmyyyy_hhmmss |  | Sijo/Alla | 2022-03-14 | Closed | File Name – All Mainframe file names will be changed by Alla’s team @Mazo, Alla. It will be “MF” in place of “AXE_FAH”. Example: MF_APIN_AL_ ddmmyyyy_hhmmss. This comes to 29 characters
14 | 2022-03-04 | CQI:@Farrington, Michael to revisit On Prem BR100 and Business requirement sheet and confirm on the Journal line rules. |  | Mike |  | Closed | Mike provide the confirmation on Inventory Line
15 | 2022-03-04 | CQI:@Farrington, Michaelto provide GL account mapping for Unvouchered Trade Payables account. (133010010). |  | Mike |  | Closed | Mike will add the rule in 1B requirement Sheet
16 | 2022-03-04 | IBI IC Payables and IBI IC Receivable should be created. @Farrington, Michael to provide the conditions to identify these journal line rules. |  | Mike |  | Closed
17 | 2022-03-04 | IBI @Farrington, Michaelto provide GL account mapping for Write off Account. (Refer worksheet IBI) |  | Mike |  | Closed | Mike will add the rule in 1B requirement Sheet
18 | 2022-03-04 | FII @Farrington, Michael/@Alla.Mazo@anixter.comto validate the Journal Line rules and respond to Deloitte comments. (Refer worksheet FII) |  | 2022-04-04 |  | Closed | Mike responded | BR100
19 | 2022-03-04 | IRI @Farrington, Michaelto provide the GL account mapping for PS accounts mentioned in worksheet ‘IRI’. |  | Mike |  | Closed
20 | 2022-03-04 | ISI @Sijo John (CIAM)/@Kapoor, Love to schedule a session with Infosys team to go over open questions for this. |  | Sijo |  | Closed | Call sheceduled on 03/16.
21 | 2022-03-04 | @Plummer, Ian to confirm regarding the Header Description logic for all interfaces. |  | Ian |  | Closed | Duplicate of #25
22 | 2022-03-07 | Trading Partner Number (Balance Enabled SR) needs to be followed by @Sijo John (CIAM) to provide massaging information |  | Sijo |  | Closed
23 | 2022-03-04 | 1. @Farrington, Michael to validate the attached sheet (ISI Tab – Orange highlighted lines) and provide the confirmation. | MOM Understand Inventory abbreviation to map with 1B Accounting rules | Mike |  | Closed |  | BR100
24 | 2022-03-04 | 2. @Farrington, Michael to provide GL account mappings for the PS Accounts mentioned in the attached sheet (ISI-AR tab). |  | Mike |  | Closed |  | BR100
25 | 2022-03-10 | 1. @Plummer, Ian to confirm the opportunity to add additional details in Journal Header Description and Line Description as shown below Journal Header Description – e.g. ‘AII-Invoice# 46789 - PO# 12345 – IC INVENTORY REVRS’ and remove Invoice# and PO# from Non balanced SR. Line Description: e.g. 'AII-Invoice Line# 001 - PO Line # 002 - Intercompany Line' and remove PO Line# and Invoice Line# from Non balanced SR. | RE: BR100 Inventory Demo session | Ian |  | Closed | Source System - MemoR - User I - Header Desc
26 | 2022-03-10 | 1. @Plummer, Ian to revisit Non Balance supporting references in order to make most effective use. |  | Ian |  | Closed | Discussed on SR Finalizaion call on 03/16.
26 | 2022-03-16 | 1. Reason Code needs to be reconfirmed, if this can be taken away from SR @Plummer, Ian to check and confirm by 03/18 EOD | Finalize Supporting reference - Follow up from 3/10 : BR100 Inventory Demo session | Ian | 2022-03-21 | Closed
27 | 2022-03-16 | 2. Memo R would be reconfirmed whether it can be removed from SR and added in Journal Header Description @Plummer, Ian to check and confirm by 03/18 EOD
28 | 2022-03-16 | 3. UOM Conversion Factor would be reconfirmed whether it can be removed from SR and added in Journal Header Description @Plummer, Ian to check and confirm by 03/18 EOD
29 | 2022-03-16 | 4. User I would be reconfirmed whether it can be removed from SR and added in Journal Header Description @Plummer, Ian to check and confirm by 03/18 EOD
30 | 2022-03-16 | 5. Invoice Line Number would be reconfirmed whether it can be removed from SR and added in Journal Header Description @Plummer, Ian to check and confirm by 03/18 EOD
26 | 2022-03-21 | Reversal identifier for Reversal Month end entries |  | Alla |  | Closed |  | BR100
25 | 2022-03-25 | SSI Event Type confirmation |  | Ian |  | Closed | Legacy MF will send 2 different files for SSI MF_SPEC_DATE_TIME and MF_SPER_DATE_TIME | Lean Spec
26 | 2022-03-25 | AII - Month End Reversal Transactions |  | Ian |  | Closed | We will use final destination field to identify AII – Reversal Transactions | Lean Spec
25 | 2022-03-04 | Description rule for Header & line to be validated |  | Ian |  | Closed |  | BR100
26 | 2022-04-13 | SSI BR100 Open Questions | SSI BR100 Questions | Mike/Sijo |  | Closed |  | BR100
Note on H33: Arun, Gheware Nilakanth: For AQI (in AP layout) there is a CROSS_BOARDER_F field set up as ‘B’. This is on header level. For AII (in AR layout) CRT_USER_I should be ‘AR0747’ (both Header and detail level. Only one could be used) AND LSI_LINE_DESCRIP_E field has value ‘REVERSAL’ in the detail.

## MFAP (hidden)
No | Date | Details | Email Sub | Action Pending on | ETA | Status | Comment | BR100/Lean Spec
1 | 2022-02-23 | Source code name needs to be 3 Char | MF INV call | Ankur | 2022-02-23 | Closed
2 | 2022-02-23 | Accutech region file section needs to be added | MF INV call | Ankur | 2022-02-23 | Closed
3 | 2022-02-23 | Accutech region sample file to be received | MF INV call | Sijo / Alla | 2022-02-23 | Closed
4 | 2022-02-24 | Accutech region sample file to be Updated | MF INV call | Ankur | 2022-02-24 | Closed
5 | 2022-02-24 | Bad file / Good File link needs to be added in lean spec | Good/Bad File call | Ankur | 2022-02-24 | Closed
6 | 2022-02-24 | Description rule for Header & line to be validated | RE: AHCS - Sprint 8 Roll Over (Config./Workaround) /Business & Financial Sys. Team - MF AR | Ian/Alla |  | Closed | IAN to confirm
7 | 2022-03-28 | Accounts Payable Intercompany - AQIN Invoice Tax Line (in on Pre BR100) |  | Mike |  | Closed | Mike to confirm
8 | 2022-03-29 | Legacy_Location_LN (Line level) this should be 5 digits for MF AP and MF AR. | MF INV Conversion session | Ian/Sijo |  | Closed | IAN to confirm | BR100
9 | 2022-04-07 | update Lean spec for file name CRESUS_EU_MMddyyyy_hhmmss.txt |  |  |  | Closed | Updated Lean Spec | Lean sepc
10
11
12
13
14
15
16
17
18
19
20
Open Points related to JLR
Business Events | Event Line Description | JLR prsent in BR-100 | Comments | Final Comments
|  |  | AQI - Reversal identifier for Reversal Month end entries | Closed
Accounts Payable Intercompany | M Freight & Brokerage Unvouchered | AQIN Invoice Tax Line | 03/31 : Accrued Sales Tax (Rule 46) line / Accrued GST Input Tax Credits (Rule 46) / Accrued Value Added Tax (Rule 46). Since AQI is passthrough interface for AHCS , let us simply setup and Invoice tax line with amount type = TAX Mike : Not sure which tax this is referring to? This is AP intercompany so some taxes do not applu Ankur : Not present in 1B business requirement sheet Added as per BR100 let us know if needs to be removed | Closed
Accounts Payable Intercompany | M Freight & Brokerage Unvouchered | AQIN Invoice Unvouchered DS Line | Mike : Adding to the 1B doc Ankur : Not present in 1B business requirement sheet | Closed
Accounts Payable Intercompany | M Freight & Brokerage Unvouchered | AQIN Invoice Freight Expense Line | Mike : Adding to the 1B doc Ankur : Not present in 1B business requirement sheet | Closed
Accounts Payable Intercompany | M Freight & Brokerage Unvouchered | AQIN Invoice Unvouchered FM Line | Mike : I assume this is Unvouchered Freight brokerage so I am adding to the 1B doc Ankur : Not present in 1B business requirement sheet | Closed
Accounts Payable Intercompany | M Freight & Brokerage Unvouchered | AQIN Expenses Line | Mike : Adding to the 1B doc Ankur : Not present in 1B business requirement sheet | Closed
Accounts Payable Intercompany | Accrued Sales Tax (Rule 46) | X | No Line is present in BR-100 | Closed
Accounts Payable Intercompany | Accrued Sales Tax (Rule 46) | X | No Line is present in BR-100 | Closed
Accounts Payable Intercompany | Accrued GST Input Tax Credits (Rule 46) | X | No Line is present in BR-100 | Closed
Accounts Payable Intercompany | Intercompany Payables | AQIN Invoice IC Payable Line | Not present in 1B business requirement sheet | Closed
Accounts Payable Intercompany |  | AQIN Other Charges Line |  | To be merged with other operating Expenses event description
Accounts Payable Intercompany (Rule 102)(Rule 104) | Intransit Inventory | AQIN Invoice Material Line | No Line is present in BR-100 | Mapped to Invoice Material Line
Accounts Payable Intercompany | M Freight & Brokerage Unvouchered | AQIN Charges Unvouch Brokerage Line | To check is this line belongs to this event only | Yes - Sorted
Accounts Payable Intercompany | M Freight & Brokerage Unvouchered | AQIN Invoice Freight Material | Not present in 1B business requirement sheet | To be Removed as JLR
Accounts Payable Intercompany | Freight Intercompany | AQIN Invoice Freight IC Expense Line | - | Closed
Accounts Payable Intercompany | Intercompany Payables | AQIN IC Payable Line | - | Closed
Accounts Payable Intercompany | Reels Unvouchered | AQIN Charges Inventory Reels Line | - | Closed
Accounts Payable Intercompany | Other Operating Expense | AQIN Charges Operating Expense Line | - | Closed
Accounts Payable Intercompany | Duties Unvouchered | AQIN Charges Duties and Customs Line | - | Closed
Accounts Payable Intercompany | Intercompany GP Markup | AQIN Charges COS Markup Line | To check is this line belongs to this event only | Yes - Sorted
Accounts Payable Intercompany | Line Charge | AQIN Charges Line Charges Line | - | Closed
Accounts Payable Intercompany | Cut Charge | AQIN Charges Cut Charges Line | - | Closed
Open Point related to Event Type
Business Event as per 1B business requirement sheet | Event Description | Business Event as per on Prem BR-100 | Comments | Final Comments
Accounts Payable Intercompany | Intercompany Material | AXE Payable Intercompany Invoices | As per 1B business requirement sheet two event types are mentioned ( Refer Col B ) but as per on Prem BR100 only one business event - are we going to follow the same | Agreed to have one Event type for AHCS
Accounts Payable Intercompany | Other Invoice Charges

## MFAR (hidden)
No | Date | Details | Email Sub | Action Pending on | ETA | Status | Comment | BR100/Lean Spec
1 | 2022-02-23 | Source code name needs to be 3 Char | MF INV call | Sravya | 2022-02-23 | Closed
2 | 2022-02-23 | Accutech region file section needs to be added | MF INV call | Sravya | 2022-02-23 | Closed
3 | 2022-02-23 | Accutech region sample file to be received | MF INV call | Sijo / Alla | 2022-02-23 | Closed
4 | 2022-02-14 | Latest On prem BR100 would be shared | RE: AHCS - Sprint 8 Roll Over (Config./Workaround) /Business & Financial Sys. Team - MF AR | Michael | 2022-02-14 | Closed | 3/1/2022 Received
5 | 2022-02-14 | Unapplied cash account (121200000) - need to be updated in Business requirement sheet @Farrington, Michael | RE: AHCS - Sprint 8 Roll Over (Config./Workaround) /Business & Financial Sys. Team - MF AR | Michael |  | Closed | The cloud account I have for 121200000 is 112125. Mike : This one is strange, when looking at transactions coming from FAH the 12120000 account is almost never used. The 12120001 account is used all the time and was listed in the requirements for CASH several times. I double checked with Finance and they see the 12120000 account is primarily used for manual journal entries. I think it should be 12120001 but I am concerned that the 12120000 is listed for the Onprem BR100. NG : Looks like we have to check this if 12120000 account is not used, then there should be some data massaging in FAH, @Sijo John (CIAM) this we need to check, why BR100 and expected output is not matching.
6 | 2022-02-14 | Sales tax account mapping sets present in on prem, same need to be updated in Business Requirement Sheet @Farrington, Michael | RE: AHCS - Sprint 8 Roll Over (Config./Workaround) /Business & Financial Sys. Team - MF AR | Michael |  | Closed
7 | 2022-02-14 | Description rule for Header & line to be validated | RE: AHCS - Sprint 8 Roll Over (Config./Workaround) /Business & Financial Sys. Team - MF AR | Ian/Alla |  | Closed | IAN to confirm
8 | 2022-02-24 | Accutech region sample file to be Updated | MF INV call | Sravya | 2022-02-24 | Closed
9 | 2022-02-24 | Bad file / Good File link needs to be added in lean spec | Good/Bad File call | Sravya | 2022-02-24 | Closed
10 | 2022-03-29 | Legacy_Location_LN (Line level) this should be 5 digits for MF AP and MF AR. | MF INV Conversion session | Ian/Sijo |  | Closed | IAN to confirm | BR100
11 | 2022-04-07 | update Lean spec for file name CRESUS_EU_MMddyyyy_hhmmss.txt |  |  |  | Closed | Updated Lean Spec | Lean Spec
12
13
14
15
16
17
18
19
20

## PSFA (hidden)
No | Date | Details | Email Sub | Action Pending on | ETA | Status | BR100/Lean Spec
1 | 2022-02-18 | confirm list of distribution types and description and provide relevant distribution types to be configured. | MOM AHCS - Sprint 9 (Config./Workaround) / Business & Finan Sys. Team (PS FA / Lease ) | Dave/Nina | 2022-02-28 | Closed
2 | 2022-02-18 | provide the sample source file for testing | MOM AHCS - Sprint 9 (Config./Workaround) / Business & Finan Sys. Team (PS FA / Lease ) | Sijo/Dave | 2022-04-15 | Closed
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19

## RPT006 (hidden)
No | Date | Details | Email Sub | Action Pending on | ETA | Status | Comment | BR100/Lean Spec
1 | 2022-03-24 | All records in a file needs to be extracted where few of related records are in error. To check seeded report or other options. | AHCS Error report RPT 0006 and RPT009 - Subledger Account Analysis Report (Retrofit) | Deloitte |  | Closed | Journal entries report to be used | Lean Spec
2 | 2022-03-24 | Source Transaction number for SXE, Eclipse Scott to confirm. |  | Scott |  | Closed | SXE and Eclipse does not have any field which can be used as source transaction number it is decided to keep this field blank for SXE and Eclipse source | Lean Spec
3 | 2022-03-24 | Source Transaction number for Leases, Cloud Pay, Treasury @Sijo John (CIAM) to confirm |  | Sijo | 2022-04-04 | Closed |  | Lean Spec
4 | 2022-03-24 | Source System for SXE, Eclipse @Evans, Rhonda and @Ingles, Anne to confirm. |  | Rhonda | 2022-04-04 | Closed |  | Lean Spec
5 | 2022-03-24 | Source System for Leases, Cloud Pay, Treasury @Sijo John (CIAM) to confirm |  | Sijo | 2022-04-04 | Closed |  | Lean Spec
6 | 2022-03-24 | @Kapoor, Love to schedule a next call for follow-up discussion |  | Love |  | Closed | Scheduled a session | Lean Spec
7 | 2022-03-24 | Source Transaction number for MF INV - Part number |  |  |  | Closed |  | Lean Spec
8 | 2022-03-24 | Source Transaction number for PSFA - Asset ID |  |  |  | Closed |  | Lean Spec
9 | 2022-03-24 | Source System for PSFA - will be blank |  |  |  | Closed |  | Lean Spec

## RPT009 (hidden)
No | Date | Details | Email Sub | Action Pending on | ETA | Status | Comment | BR100/Lean Spec
1 | 2022-03-24 | Finalize all columns before sharing this report | AHCS Error report RPT 0006 and RPT009 - Subledger Account Analysis Report (Retrofit) | Deloitte |  | Closed | Shared report Layout | Lean Spec
2 | 2022-03-24 | @Kapoor, Love to schedule a next call for follow-up discussion |  | Love |  | Closed | Call is scheduled
3 | 2022-03-24 | Will share report layout for business and IT review for next session prep. |  | Deloitte |  | Closed | Shared report Layout | Lean Spec
4 | 2022-03-24 | Add a parameter for 'Source System' (Interface ID) |  |  |  | Closed
5 | 2022-03-24 | Source System parameter will provide related values based on Journal Source. |  |  |  | Closed
6 | 2022-03-24 | PSFA columns period, Year , Date - need to have a separate columns |  |  |  | Closed
7 | 2022-03-24 | Asset ID needs to be added as one column as Supporting reference for two fields Asset number(Record ID) for Leases & Asset ID for PSFA |  |  |  | Closed
8 | 2022-03-24 | File name to be removed from Report column Legacy line # and Invoice line # is merged in one column for report. |  |  |  | Closed
9 | 2022-03-24 | Header sequence # needs to be removed |  |  |  | Closed
10 | 2022-03-31 | Accounting Class Is it needed for 1B? | Follow up from 3/24: AHCS Error report RPT 0006 and RPT009 - Subledger Account Analysis Report (Retrofit) |  |  | Closed |  | Lean Spec
11 | 2022-03-31 | Asset Book for PS FA required for this report. |  |  |  | Closed |  | Lean Spec
12 | 2022-03-31 | Line Type Do we require it for 1B? |  |  |  | Closed |  | Lean Spec
13 | 2022-03-31 | Cross Reference Number Do we require it for 1B? Source field -Refer Invoice |  |  |  | Closed | Can be removed | Lean Spec
14 | 2022-03-31 | Export Type Can we merge with Transaction Type? |  |  |  | Closed | Merge with Source Transaction Type | Lean Spec
15 | 2022-03-31 | Legacy Journal ID Do we require it for PS FA? |  | Rhonda |  | Closed | can be removed | Lean Spec
16 | 2022-03-31 | Lease Name Do we require it for Leases as we already used as part of line description |  | Rhonda |  | Closed | can be removed since it will be part of line description | Lean Spec
17 | 2022-03-31 | Account Description Do we require it for Leases? |  | Rhonda |  | Closed | will account description be included in account through G/L fields? If so, can remove. If not, would like to keep in report. keep amount tag in report | Lean Spec
18 | 2022-03-31 | Amount Tag Do we require it for Leases? |  | Rhonda |  | Closed |  | Lean Spec
19 | 2022-04-07 | Which field( Record ID or Capital Lease ID) for the leases to be merge with source transaction number |  | Rhonda |  | Closed | merge Record ID with the source transaction number; keep Capital Lease ID as separate SR Column | Lean Spec
20 | 2022-04-07 | Invoice Number can be merged with source transaction number for this report & invoice number can be removed for all Mainframe sources |  |  |  | Closed
21 | 2022-04-07 | Asset Description column for PS FA should be removed , as Line description was already included it. |  |  |  | Closed

## RPT208 (hidden)
No | Date | Details | Email Sub | Action Pending on | ETA | Status | Comment | BR100/Lean Spec
1 | 2022-04-06 | This is only applicable for MF AP, MF AR and MF INV | Follow up from 3/28: RPT007 - AHCS to GL Reconciliation Report (Retrofit) |  |  | Closed
2 | 2022-04-06 | Add a Variance Only (Yes/ No ) parameter (This needs to be for Ending balances, so all related rows can be shown) |  |  |  | Closed
3 | 2022-04-06 | LE, OP Grp, Account, Site all columns are needed |  |  |  | Closed
4 | 2022-04-06 | Control accounts will be same as RPT007 |  |  |  | Closed
5 | 2022-04-06 | Control account will be added as a parameter |  |  |  | Closed
6 | 2022-04-06 | Add a column for Project and Intercompany |  |  |  | Closed
7 | 2022-04-06 | Report will be scheduled on Weekly and sent over email from RPT007 distribution list |  |  |  | Closed
8 | 2022-04-06 | Report Layout is attached for the ready reference |  |  |  | Closed
9 | 2022-04-06 | Report Parameter defaults as below for RPT 208: 1. Ledger will be by default US USGAAP USD 2. Application will be default 'All ' 3. Period will be default last open period. 4. Variance will be default Yes. 5. Control Account will be 'All ' (Based on list provided by Manisha) |  |  |  | Closed

## EXT123 (hidden)
No | Date | Details | Email Sub | Action Pending on | ETA | Status | BR100/Lean Spec

## CloudPay (hidden)
No | Date | Details | Email Sub | Action Pending on | ETA | Status | Comment | BR100/Lean Spec
1 | Is Accounting and Transaction date same? | FileStamp date to be used. | Sprint 10 Prep work initiation | Dave | 2022-03-04 | Closed | Refer H22
2 | Will one file contain data only related to one BU? | The file contains data for BU 00807 and 00824. | Sprint 10 Prep work initiation | Dave | 2022-03-04 | Closed
3 | What is GL Code in source file? Is it required? | This is the Peoplesoft account number. It is required as one of the legacy chartfields. | Sprint 10 Prep work initiation | Dave | 2022-03-04 | Closed
4 | Volume of transactions? | 3000 | Sprint 10 Prep work initiation | Dave | 2022-03-04 | Closed
5 | How to derive COA segments? | Cost center column is BU/location/department concatenated together. GL Code is account number. | Sprint 10 Prep work initiation | Dave | 2022-03-04 | Closed
6 | How to derive Currency? | Currently its based off of currency of business units. 00807 is USD, 00824 is GBP | Sprint 10 Prep work initiation | Dave | 2022-03-04 | Closed
7 | Only one Event type will be defined as “PAYROLL” |  | Sprint 10 Prep work initiation | Dave | 2022-03-04 | Closed
8 | File naming convention will be as “PAYROLL_AXE_YYYYMMDD_HHMMSS” | Current file format is GL_Anixter_Limited_CCYYMMDD_HHMMSSUTC.csv | Sprint 10 Prep work initiation | Dave | 2022-03-04 | Closed
9 | Transaction number will be derived based on file name. |  | Sprint 10 Prep work initiation | Dave | 2022-03-04 | Closed
10 | Accounting date to be derived from the source filestamp date. | This should be fine. | Sprint 10 Prep work initiation | Dave | 2022-03-04 | Closed
11 | Please confirm which logic should be used deriving Cloud Pay accounting date a. Following legacy logic of deriving accounting date for CloudPay i.e. Accounting date = Date of file received - 1 b. Use File timestamp as Accounting date |  | Sprint 10 Prep work initiation | Ian | 2022-03-08 | Closed | Option B is confirmed
12 | Do we need to bring Legacy COA values in AHCS? Currently BU,location and department is coming as concatenated value in feed. It is also not mapped in data model as per KDD. |  | Sprint 10 Prep work initiation |  | 2022-03-10 | Closed | Legacy COA will be the concatenated value of BU,Location, Account and Department. This will be derived in OIC
13 | File name added at the header level in AHCS. Currently not mapped in data model as per KDD. |  | Sprint 10 Prep work initiation |  | 2022-03-10 | Closed | File Name will be added at Header level.
14 | Pay Code and Pay code description moved to line level. As per KDD it was mapped at header level. Please confirm, if this is ok. |  | Sprint 10 Prep work initiation |  | 2022-03-10 | Closed | Pay code and Pay code Description is moved to Line level.
15 | Transaction number will be as per this format: CCYYMMDD_HHMMSSUTC Please confirm, if this is ok. |  | Sprint 10 Prep work initiation |  | 2022-03-10 | Closed | Transaction number will be as per this format ''BU_CCYYMMDD_HHMMSSUTC".
16 | File Name to be added as supporting reference. Currently do we do not have any other SR, please confijrm if we need to add any supporting reference? |  | Sprint 10 Prep work initiation |  | 2022-03-10 | Closed | File name is added in Non balanced SR and Legacy COA as balance enabled SR. No additional SR needed.
17 | Oracle has seeded subledger name as “Payroll”. So we need to rename for this subledger as Payroll UK. Please confirm, if this is ok. |  | Sprint 10 Prep work initiation |  | 2022-03-10 | Closed | CloudPay' will be used as Subledger name
18 | Kapoor, Love to log a risk for the future layout with a sample file. |  | AHCS Sprint 10: Cloud Pay UK Lean Spec (IT Session) |  | 2022-03-11 | Closed
19 | Brett to confirm on entered currency for each BU and FX rate conversion logic. |  | AHCS Sprint 10: Cloud Pay UK Lean Spec (IT Session) |  | 2022-03-11 | Closed
20 | Bridge program logic implications needs to be discussed in follow up session |  | AHCS Sprint 10: Cloud Pay UK Lean Spec (IT Session) |  | 2022-03-11 | Closed
| CCYYMMDD_HHMMSSUTC_BU |  | 21

## IAP (hidden)
No | Date | Details | Email Sub | Action Pending on | ETA | Status | BR100/Lean Spec
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20

## Leases (hidden)
No | Date | Details | Email Sub | Action Pending on | ETA | Status | Comment | BR100/Lean Spec
1 | 2022-02-17 | Line description is finalized i.e. "FILE ID"-"NAME". Header Description is not required keep it as blank. | MOM AHCS - Sprint 9 (Config./Workaround) / Business & Finan Sys. Team (PS FA / Lease ) |  |  | Closed
2 | 2022-02-17 | Naming convention are followed as per 1A and everyone are aligned on the same. |  |  |  | Closed
3 | 2022-02-17 | @Mullin, Linda – to provide the Wesco sample lease file for testing |  |  |  | Closed
4 | 2022-02-17 | provide the sample WESCO source file for testing |  | Linda | 2022-03-16 | Closed | Files shared on Wed 3/16/2022 6:56 PM and forwarded to tech team
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20

## Treasury (hidden)
Date | Details | Email Sub | Action Pending on | ETA | Status | BR100/Lean Spec
Tech Team
1. Source field describes the transaction type but in the sample file it shows null so how that field looks like? (3 char length X 3rd place) |  |  |  |  | Closed
2. What is the Expected volume of the file – Average number of lines per day |  |  |  |  | Closed
3. Are we expecting one file for all regions or per region separate file? |  |  |  |  | Closed
4. In Future, Will it sent header, line & trigger files or only one file? |  |  |  |  | Closed
5. Control Total at end of file is verified against actual line total- what this mean? |  |  |  |  | Closed
7. GL Affliliate field was mentioned as not needed in AHCS Data model so will that mean that field is not at all required or its required but not mandatory i.e., it may not contains the value always |  |  |  |  | Closed
Business
| 1. Description Field will be used as supporting ref?, But in the sample file field is null |  |  |  | Closed
| 2. Leg 5-7(vendor & affiliate) will be used as supporting reference but vendor segment was not there in AHCS data model |  |  |  | Closed
| 3. Jrnl Desc as Treasury Management +post date TREASURY MANAGEMENT 01/03/2022 so will the header description be the same as Jrnl desc? |  |  |  | Closed
| 4. Current Line desc as PS-UnApp Cash ACH-Wire Ecl so will it be same for the future? If yes, How to derive this? |  |  |  | Closed
5. Can we remove source ledger and Ledger Group field AHCS data model? Or need for any specific business use? |  |  |  |  | Closed
6. There are two dates in the source file i.e., Accounting Date & transaction date . |  |  |  |  | Closed
7. Accounting Date(KDD Discussion) need to map with AHCS transaction date for determining the period in cloud. In that case we don’t require it as supporting reference but business recommend that in SR list .Accounting date in the sample file is null. Can you pls confirm that Accounting date field is mandatory or not? |  |  |  |  | Closed
8. How many event types required ? will it be one as it is direct feed to GL? |  |  |  |  | Closed
9. What will the file name? |  |  |  |  | Closed
10. Will 'File Name' be Transaction number ?. Does business want to see the detail lines , i.e. 20 debit line and 20 credit lines or summarize the lines for same LE/account/dept? |  |  |  |  | Closed | Rhonda
11. Is there any foreign currency transactions in treasury? |  |  |  |  | Closed
6. Is there any validation required for debit credit mismatch ? since its summarized file so entire file total amount should be Zero (all debits & credits are netted off for the entire file) |  |  |  |  | Closed

## SXE (hidden)
No | Date | Details | Email Sub | Action Pending on | ETA | Status | BR100/Lean Spec
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20

## Eclipse (hidden)
No | Date | Details | Email Sub | Action Pending on | ETA | Status | BR100/Lean Spec
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20

## Dev22 config (hidden)
[12 empty] | Subledger | Source | Pass Through / Event Based
[12 empty] | MF AP | ADI | Pass Through | Payments, Void Payments & Repayments
Subledger | Source | 2022-04-01 | 2022-04-04 | 2022-04-05 | 2022-04-06 | 2022-04-07 | 2022-04-08 | 2022-04-12 | 2022-04-13 | 2022-04-18 | On Hold | MF AP | AQI | Pass Through | Intercompany Invoices & reversals
PSFA | PSFA |  | PSFA | [8 empty] | MF AP | API | Pass Through | Material,Freight,RTV,Expense Invoices
LEASES | LEASES | LEASES | [9 empty] | MF AP | CAI | Event Based | Contra Invoices
SXEUS | SXEUS | SXEUS | [9 empty] | MF AP | BKIP | Pass Through | Bank Payments & Charges
ECLPS | ECLPS | ECLPS | [9 empty] | MF AP | LSIP |  | Liability switch
TREASURY | TREASURY |  | TREASURY | [8 empty] | MF AR | SII | Event Based | Trade invoices & Credits
CloudPay | CloudPay | CloudPay | [9 empty] | MF AR | SII | Event Based | Intercompany Invoices & Credits
MF AP |  | ADIN, CAIN | APIN, AQIN | BKIP | [6 empty] | LSIP | MF AR | CRI | Event Based | Cash Applications,allowances & Repayments
MF AR |  | ARIN | CASH | BKIR | SALE | [5 empty] | LSIR | MF AR | ARI | Pass Through | Adjustments
MF INV |  |  | AII, ICI | FII, FTI | DAIN, CQI | IBI | IRI | SSI | SSI | ISI |  | MF AR | BKIR | Pass Through | Bank Collections
Concur | Concur |  |  |  |  | Concur | [5 empty] | MF AR | LSIR | Pass Through | Liability Switch
[12 empty] | MF AR | SPER | Pass Through | Special Customer Invoices
[12 empty] | MF INV | ISI | Event Based | Trade invoices, Credits & Voids
[12 empty] | MF INV | ISI | Event Based | Intracompnay Invoices,credits & Adjustments
[12 empty] | MF INV | ISI | Event Based | Intercompnay Invoices,credits & Adjustments
[12 empty] | MF INV | ISI | Event Based | Trade Cost Adjustments
[12 empty] | MF INV | ICI | Event Based | Intransit Intercompany Invoices ,Credits & Reversal
[12 empty] | MF INV | CQI | Event Based | Cost quantity Adjustment
[12 empty] | MF INV | FTI | Pass Through | Freight Accrual Invoices
[12 empty] | MF INV | FII | Pass Through | Input Output freight Invoices
[12 empty] | MF INV | DAI | Pass Through | Dropped Accrual
[12 empty] | MF INV | IBI | Event Based | Cost Adjustment
[12 empty] | MF INV | SPEC | Pass Through | Special Customer Invoices
Note on I12: Arun, Gheware Nilakanth: MF AR completed for SPER
Note on J12: Arun, Gheware Nilakanth: MF INV pending for SPEC

## ADI - Defect CTPFS -7397 (hidden)
CTPFS -7397
Sources | As per Lean Spec | As per BR-100 | Confi in SIT -1
Legacy Transaction Type | Should be mapped to Invoice Type | Mapped with Legacy Transaction type - that is a BKI field | As per BR-100
Line Type | Should be mapped to Vendor Payment Type | Mapped with PO Type | As per BR-100
Solution
Sources | Rectification Needed | Explanation
Legacy Transaction Type | Change the Mapping of supporting reference from Legacy Transaction Type to Invoice Type | -
Line Type | Line Type is mapped with two source fields Copy PO_TYPE from APIN, AQIN Copy VENDOR_PAYMENT_TYPE from ADIN | Need to change supporting reference as we have two different source in that is PO type and Vendor Payment Type

## SL List (hidden)
Deloitte.
Manage Secondary Ledgers |  |  | Return to Setup Checklist
References:
Module | General Ledger | [5 empty] | KDD2 - Enterprise Structure
Task | Manage Secondary Ledgers | [5 empty] | WESCO Oracle Cloud Enterprise Structure
Navigation | Setup and Maintenance > Tasks > Search > Manage Secondary Ledgers
Setup Description | Allows to create Secondary Ledgers
Last Update Date | 2022-05-17
Updated By | Andres Romero
Status | Complete
Action | Primary Ledger | Name of Secondary Ledger | Description | Chart of Accounts | Accounting Calendar | Currency | Accounting Method | Data Conversion Level
Add | AT USGAAP EUR | AT ATGAAP EUR | AT ATGAAP EUR Secondary Ledger | Global COA | Corporate | EUR | WSC ATGAAP | Subledger
Add | DE USGAAP EUR | DE DEGAAP EUR | DE DEGAAP EUR Secondary Ledger | Global COA | Corporate | EUR | WSC DEGAAP | Subledger
Add | ES USGAAP EUR | ES ESGAAP EUR | ES ESGAAP EUR Secondary Ledger | Spain COA | Corporate | EUR | WSC ESGAAP | Subledger
Pending FEC Report configurations | FR USGAAP EUR | FR FRGAAP EUR | FR FRGAAP EUR Secondary Ledger | France COA | Corporate | EUR | WSC FRGAAP | Subledger
Add | NO USGAAP NOK | NO NOGAAP NOK | NO NOGAAP NOK Secondary Ledger | Norway COA | Corporate | NOK | WSC NOGAAP | Subledger
Add | PL USGAAP PLN | PL PLGAAP PLN | PL PLGAAP PLN Secondary Ledger | Poland COA | Corporate | PLN | WSC PLGAAP | Subledger
Add | SA USGAAP SAR | SA SAGAAP SAR | SA SAGAAP SAR Secondary Ledger | Global COA | Corporate | SAR | WSC SAGAAP | Subledger

## Open Questions (hidden)
Will all AHCS subledgers will be posting data to these secondary ledgers?
Open Question | Secondary Ledger - GAAP | Secondary Ledger - Currency | Secondary Ledger - COA | Secondary Ledger - Calendar | Secondary Ledger
| ATGAAP | EUR | Global COA | Global Calendar | AT ATGAAP EUR
| FRGAAP | EUR | France Local COA | Global Calendar | FR FRGAAP EUR
| DEGAAP | EUR | Global COA | Global Calendar | DE DEGAAP EUR
| DEGAAP | EUR | Global COA | Global Calendar | DE DEGAAP EUR
| NOGAAP | NOK | Norway local COA | Global Calendar | NO NOGAAP NOK
| PLGAAP | PLN | Poland local COA | Global Calendar | PL PLGAAP PLN
| SAGAAP | SAR | Global COA | Global Calendar | SA SAGAAP SAR
| ESGAAP | EUR | Spain local COA | Global Calendar | ES ESGAAP EUR
| NOGAAP | NOK | Norway local COA | Global Calendar | NO NOGAAP NOK
| PLGAAP | PLN | Poland local COA | Global Calendar | PL PLGAAP PLN
| ATGAAP | EUR | Global COA | Global Calendar | AT ATGAAP EUR
| FRGAAP | EUR | France Local COA | Global Calendar | FR FRGAAP EUR
| DEGAAP | EUR | Global COA | Global Calendar | DE DEGAAP EUR
| ESGAAP | EUR | Spain local COA | Global Calendar | ES ESGAAP EUR

## SIT1 Ramp up (hidden)
Ramp-up plan
1. Load complete month of Mar-2022 to Oracle Cloud SIT1 instance in 5 working days starting 23rd May 2022
2. 7 calendar day files will be loaded each day
3. Processing Schedule (Refer second table)
a. Cresus system to send all planned files for the day at once (2:30 am CST)
b. Treasury system to send all planned files for the day at once (10:00 CST)
c. All other systems/ interfaces following daily schedule to send daily files at 60 minutes interval
d. Leases, PSFA and Cloud Pay following monthly schedule and will send file by designated time on May 25th, 2022
e. OIC Jobs to be scheduled at 60 minutes interval
File Processing Date | Transaction (Accounting) Date - MF/ 3rd Party
2022-05-23 | 28 Feb, 1 Mar, 2 Mar, 3 Mar, 4 Mar, 5 Mar, 6 Mar
2022-05-24 | 7 Mar, 8 Mar, 9 Mar, 10 Mar, 11 Mar, 12 Mar, 13 Mar
2022-05-25 | 14 Mar, 15 Mar, 16 Mar, 17 Mar, 18 Mar, 19 Mar, 20 Mar
2022-05-26 | 21 Mar, 22 Mar, 23 Mar, 24 Mar, 25-Mar, 26-Mar, 27-Mar
2022-05-27 | 28-Mar, 29-Mar, 30-Mar, 31-Mar, 1-Apr
Source | Frequency** | Legacy Extract – D1 | Legacy Extract -D2 | Legacy Extract - D3 | Legacy Extract -D4 | Legacy Extract -D5 | OIC File Receiving Integration (Receiving the File in OIC)
|  | (Time in CST) |  |  |  |  | Scheduled at 60 mins gap*
Daily files (by region/interface) at 60 min interval
MF AP - API (EU /NA/ AC) | Daily | 8:00 AM - 8:30 AM | 9:00 - 9:30 AM | 10:00 - 10:30 AM | 11:00 - 11:30 AM | 12:00 - 12:30 PM | 8:30
MF AP - ADI (EU /NA/ AC) | Daily | 8:00 AM - 8:30 AM | 9:00 - 9:30 AM | 10:00 - 10:30 AM | 11:00 - 11:30 AM | 12:00 - 12:30 PM | 8:30
MF AP - CAI (EU/NA/ AC) | Daily | 8:00 AM - 8:30 AM | 9:00 - 9:30 AM | 10:00 - 10:30 AM | 11:00 - 11:30 AM | 12:00 - 12:30 PM | 8:30
MF AP - AQI (EU/NA/ AC) | Daily | 8:00 AM - 8:30 AM | 9:00 - 9:30 AM | 10:00 - 10:30 AM | 11:00 - 11:30 AM | 12:00 - 12:30 PM | 8:30
MF AP - LSIP (EU/NA/ AC) | Weekly | NA | NA | NA | NA | 12:00 - 12:30 PM | 12:30
MF AR - ARI (EU /NA /AC) | Daily | 8:30 AM - 9:00 AM | 9:30 - 10:00 AM | 10:30 - 11:00 AM | 11:30 - 12:00 PM | 12:30 - 1:00 PM | 9:00
MF AR - CRI (EU /NA /AC) | Daily | 8:30 AM - 9:00 AM | 9:30 - 10:00 AM | 10:30 - 11:00 AM | 11:30 - 12:00 PM | 12:30 - 1:00 PM | 9:00
MF AR - SII (EU /NA /AC) | Daily | 8:30 AM - 9:00 AM | 9:30 - 10:00 AM | 10:30 - 11:00 AM | 11:30 - 12:00 PM | 12:30 - 1:00 PM | 9:00
MF AR - SPER (EU /NA /AC) | Daily | 8:30 AM - 9:00 AM | 9:30 - 10:00 AM | 10:30 - 11:00 AM | 11:30 - 12:00 PM | 12:30 - 1:00 PM | 9:00
MF AR - LSIR (EU/NA/ AC) | Weekly | NA | NA | NA | NA | 12:30 - 1:00 PM | 9:00
Cresus (BKI) | Daily | 2:00 - 2:30 AM |  |  |  |  | 2:30
Treasury | Daily | 10:00 |  |  |  |  | 10:00
SXE | Daily | 6:00 AM - 6:30 AM | 6:30 AM - 7:00 AM | 7:00 AM - 7:30 AM | 7:30 AM - 8:00 AM | 8:00 AM - 8:30 AM | 15:00
Eclipse | Daily | 6:00 AM - 6:30 AM | 6:30 AM - 7:00 AM | 7:00 AM - 7:30 AM | 7:30 AM - 8:00 AM | 8:00 AM - 8:30 AM | 15:00
Leases | Monthly | 9am (25th May) |  |  |  |  | 9:00
Cloud Pay | Monthly | 9:30 AM (25th May) |  |  |  |  | 9:30
PS FA | Monthly | 9am (25th May) |  |  |  |  | 9:15

## SIT1 Config (hidden)
Subledger | 2022-05-13 | 2022-05-16 | 2022-05-17 | 2022-05-18 | 2022-05-19 | Subledegr | Type | Source
PSFA | PSFA |  |  |  |  | MF INV | Event Based | CQI
LEASES | LEASES |  |  |  |  | MF INV | Event Based | IRI
SXEUS | SXEUS |  |  |  |  | MF INV | Event Based | ISI, FII, FTI, ICI,AII
ECLPS | ECLPS |  |  |  |  | MF INV | Event Based | IBI
TREASURY | TREASURY |  |  |  |  | MF INV | Pass Through | DAI
CloudPay | CloudPay |  |  |  |  | MF INV | Pass Through | SSI - SPEC
MF AP |  |  | ADI, API, BKI | AQI, CAI, LSIP |  | MF AP | Event Based | CAI
MF AR |  |  | BKI, ARI, SSI (SPER) | CRI, SII, LSIR |  | MF AP | Pass Through | ADI
MF INV | [5 empty] | MF AP | Pass Through | API
Oracle LSI | [5 empty] | MF AP | Pass Through | AQI
Conversion |  |  |  | MF AP, MF AR |  | MF AP | Pass Through | BKIP
Concur | Concur |  |  |  |  | MF AP | Pass Through | LSIP
[6 empty] | MF AR | Pass Through | BKIR
[6 empty] | MF AR | Event Based | CRI , SII
[6 empty] | MF AR | Pass Through | LSIR
[6 empty] | MF AR | Pass Through | ARI
[6 empty] | MF AR | Pass Through | SSI - SPER

## RICE List (hidden)
Phase | Description | Lean Spec Owner | FUT Owner | Lean Spec Status | Config/ Test Status | Comments
1A | RPT006 - AHCS Error Report | Vishnu | Vishnu / Vivek |  | UAT2
1A | RPT007 - AHCS to GL Reconciliation Report |  | Aashutosh |  | UAT2
1A | EXT010 / EXT011 - Dashboard | Aashutosh | Aashutosh / Manosh |  | UAT2
1A | INT002 EBS AP to AHCS | Manosh | Manosh |  | UAT2
1A | INT005 EBS AR to AHCS | Shubham | Shubham |  | UAT2
1A | INT004 EBS FA to AHCS | Shubham | Ankur |  | UAT2
1A | INT122 POC to AHCS | Manosh | Manosh |  | UAT2
1A | INT033 / INT038 Central to AHCS | Aashutosh | Aashutosh |  | UAT2
1A | INT041- AHCS Data to Tera Data - AHCS Reconciliation Balances | Shubham | Vishnu |  | UAT2
1A | INT012 - AHCS Data to Tera Data - AHCS Details | Shubham |  |  | UAT2
1A | RPT009 - Subledger Account Analysis Report | Vishnu | Vishnu |  | UAT2
1A | RPT41 drill down erroring out
1B | MF AP to AHCS | Ankur | Ankur | Approved | FUT in Progress | Unit test/ Demo Complete
1B | MF AR to AHCS | Sravya | Sravya | Approved | FUT in Progress
1B | MF INV to AHCS | Kathir | Kathir | Approved | WIP | Sent for approval
1B | INT020 Leases to AHCS | Kathir | Kathir | Approved | Ready for FUT
1B | INT045 Treasury (PowerSolutions) | Sravya | Sravya | Approved | Ready for FUT | Demo completed
1B | INT018 Cloud Pay to AHCS | Rajesh | Rajesh | Approved | FUT completed | Demo completed
1B | INT044 AHCS to IAP Balances Feed | Ankur | Ankur | Approved | NA
1B | PS FA to AHCS | Sravya | Sravya | Approved | Ready for FUT
1B | INT123 Anixter SXE to AHCS | Ankur | Ankur | Approved | Ready for FUT
1B | INT124 Anixter Eclipse to AHCS | Ankur | Ankur | Approved | Ready for FUT
1B | LSI to AHCS | Rajesh | Rajesh | On Hold | Not Started | S11
1B | INT016 - Concur inbound | Manosh/ Neha | Manosh/ Neha | WIP | Not Started
1B | CNV041 MF AP Conversion | Ankur | Ankur | Approved | Not Started
1B | CNV042 MF AR Conversion | Sravya | Sravya | Approved | Not Started
1B | CNV043 MF Inv Conversion | Kathir | Kathir | Approved | Not Started | Planned for S11
1B | EXT123 - Dashboard (Retrofit) | Rajesh | Rajesh | Approved | Not Started | Planned for S11
1B | RPT006 - AHCS Error Report (Retrofit) | Ankur | Ankur | Approved | Not Started | Planned for S11
1B | RPT007 - AHCS to GL Reconciliation Report (Retrofit) | Ankur | Ankur | Approved | Not Started | Planned for S11
1B | RPT009 - Subledger Account Analysis Report (Retrofit) | Sravya | Sravya | Approved | Not Started | Planned for S11
1B | INT043 AHCS to IAP Details Feed | Kathir | Kathir | Approved | NA | Planned for S11
1B | RPT208 - AHCS to GL Balances Recon | Ankur | Ankur | WIP | Not Started
1B | RPT008 : Subledger Period Close Exception Report by Ledger Set |  |  | Approved | Not Started | Walk through

## Location changes (hidden)
CTPFS-4856 | [7 empty] | CTPFS-4910 | [13 empty] | Subledger | Source | Pass Through / Event Based
| Subledger | Sources | Position | Source Field Name | AHCS Field Name | Comment | New MF Sample required |  | MF AP | ADI | Header | LOCATION | VARCHAR2(3 CHAR) |  | AHCS Field (Line level) | Subledegr | Source | Type | Source Field | OIC logic | SIT 1 Status | MF AP | ADI | Pass Through | Payments, Void Payments & Repayments
| MF AP | CAI (Event Based) | Header | LOCATION | LEG_LOCATION | AHCS will copy and use for Non-Balance SR 'LEG_LOC_SR' | No |  | MF AP | API | Header | LOCATION | VARCHAR2(3 CHAR) |  | LEG_LOC_SR | MF INV | CQI | Event Based | PS_Location | Copy from Line Level PS_Location | Not in Scope | MF AP | AQI | Pass Through | Intercompany Invoices & reversals
|  | CAI (Event Based) | Line | GL_Location | LEG_LOC (Leg Seg 1-4) | MF will send 5 digit code used for COA transformation | No |  | MF AP | AQI | Header | LOCATION | VARCHAR2(3 CHAR) |  | LEG_LOC_SR | MF INV | IRI | Event Based | PS_Location | Copy from Header Level PS_Location | Not in Scope | MF AP | API | Pass Through | Material,Freight,RTV,Expense Invoices
| MF AR | CRI and SII (Event Based) | Header | LOCATION | LEG_LOC_HDR | AHCS will copy and use for Non-Balance SR 'LEG_LOC_SR' | SII New Sample Received |  | MF AR | ARI | Header | LOCATION | VARCHAR2(5 CHAR) |  | LEG_LOC_SR | MF INV | ISI, FII, FTI, ICI,AII | Event Based | LOCATION | Copy from Header Level Location | Not in Scope | MF AP | CAI | Event Based | Contra Invoices
[7 empty] | CRI-No change |  | MF AR/AP | BKI | Line | LOCATION | VARCHAR2(5 CHAR) |  | LEG_LOC_SR | MF INV | IBI | Event Based | SHIP_FROM_LOC | Copy from Header SHIP_FROM_LOC | Not in Scope | MF AP | BKIP | Pass Through | Bank Payments & Charges
|  | CRI and SII (Event Based) | Line | LOCATION | LEG_LOC_LN | Not used in AHCS | SII New Sample - Received |  | Concur | ERI | Header | LOCATION | VARCHAR2(3 CHAR) |  | LEG_LOC_SR | MF INV | DAI | Pass Through | LOCATION | Copy from Header Level Location | Not in Scope | MF AP | LSIP |  | Liability switch
[7 empty] | CRI-No change |  | MF AR | LSIR | Line | LOCATION | VARCHAR2(5 CHAR) |  | LEG_LOC_SR | MF INV | SSI - SPEC | Pass Through | LOCATION | Copy from Header Level Location | Not in Scope | MF AR | SII | Event Based | Trade invoices & Credits
|  | CRI and SII (Event Based) | Line | GL_AXE_LOCATION | LEG_LOC (Leg Seg 1-4) | MF will send 5 digit code used for COA transformation | No Change |  | MF AP | LSIP | Header | LOCATION | VARCHAR2(3 CHAR) |  | LEG_LOC_SR | MF AP | CAI | Event Based | LOCATION | Copy from Header Level Location | In progress | MF AR | SII | Event Based | Intercompany Invoices & Credits
| MF INV | CQI (Event Based) | Header | PS_Location | LEG_LOCATION_HDR | Not used in AHCS | No Change |  | MF INV | DAI | Header | LOCATION | VARCHAR2(3 CHAR) |  | LEG_LOC_SR | MF AP | ADI | Pass Through | LOCATION | Copy from Header Level Location | In progress | MF AR | CRI | Event Based | Cash Applications,allowances & Repayments
|  |  | Line | PS_Location | LEG_LOCATION_LN (Leg Seg 1-4) | PS_Location will be used for COA transformation MF will send 5 digit code. | No Change |  | MF INV | SSI | Header | LOCATION |  |  | LEG_LOC_SR | MF AP | API | Pass Through | LOCATION | Copy from Header Level Location | In progress | MF AR | ARI | Pass Through | Adjustments
[6 empty] | AHCS will copy and use for Non-Balance SR 'LEG_LOC_SR' |  |  | MF AR | SSI | Header | LOCATION |  |  | LEG_LOC_SR | MF AP | AQI | Pass Through | LOCATION | Copy from Header Level Location | In progress | MF AR | BKIR | Pass Through | Bank Collections
|  |  | Line | LOC_CODE |  | Not used in AHCS | No Change | [7 empty] | LEG_LOC_SR | MF AP | BKIP | Pass Through | LOCATION | Copy from Line Level Location | Hold for Integ | MF AR | LSIR | Pass Through | Liability Switch
|  | IRI (Event Based) | Header | PS_Location | LEG_LOCATION_HDR | MF will send 5 digit code used for COA transformation | No Change | [7 empty] | LEG_LOC_SR | MF AP | LSIP | Pass Through | LOCATION | Copy from Header Level Location | In progress | MF AR | SPER | Pass Through | Special Customer Invoices
[6 empty] | AHCS will copy and use for Non-Balance SR 'LEG_LOC_SR' | [8 empty] | LEG_LOC_SR | MF AR | BKIR | Pass Through | LOCATION | Copy from Line Level Location | In progress | MF INV | ISI | Event Based | Trade invoices, Credits & Voids
|  | ISI,IBI, FII, FTI, ICI,AII (Event Based) | Header | LOCATION | LEG_LOCATION_HDR | MF will send 5 digit code, AHCS will copy and use for Non-Balance SR 'LEG_LOC_SR' | FII, ICI - New Sample needed | [7 empty] | LEG_LOC_SR | MF AR | CRI , SII | Event Based | LOCATION | Copy from Header Level Location | In progress | MF INV | ISI | Event Based | Intracompnay Invoices,credits & Adjustments
[6 empty] | IBI this will be from SHIP_FROM_LOC | ISI New Sample - received | [7 empty] | LEG_LOC_SR | MF AR | LSIR | Pass Through | LOCATION | Copy from Line Level Location | Hold for Integ | MF INV | ISI | Event Based | Intercompnay Invoices,credits & Adjustments
|  |  | Line | LOCATION | LOCATION_LN | Not used in AHCS | [8 empty] | LEG_LOC_SR | MF AR | ARI | Pass Through | LOCATION | Copy from Header Level Location | In progress | MF INV | ISI | Event Based | Trade Cost Adjustments
|  |  | Line | GL_AXE_LOCATION | LEG_LOCATION_LN (Leg Seg 1-4) | MF will send 5 digit code used for COA transformation | [8 empty] | LEG_LOC_SR | MF AR | SSI - SPER | Pass Through | LOCATION | Copy from Header Level Location | In progress | MF INV | ICI | Event Based | Intransit Intercompany Invoices ,Credits & Reversal
[16 empty] | PSFA |  | Pass Through |  |  |  | MF INV | CQI | Event Based | Cost quantity Adjustment
[14 empty] | Month End (Prior Month) |  | LEASES |  | Pass Through |  |  |  | MF INV | FTI | Pass Through | Freight Accrual Invoices
[16 empty] | SXEUS |  | Pass Through |  |  |  | MF INV | FII | Pass Through | Input Output freight Invoices
[16 empty] | ECLPS |  | Pass Through |  |  |  | MF INV | DAI | Pass Through | Dropped Accrual
[16 empty] | TREASURY |  | Pass Through |  |  |  | MF INV | IBI | Event Based | Cost Adjustment
[16 empty] | CloudPay |  | Pass Through |  |  |  | MF INV | SPEC | Pass Through | Special Customer Invoices
Note on B3: Arun, Gheware Nilakanth: LEG_LOC_SR is at line level in AHCS. OIC would copy from heder to Line except for BKI, as for BKI this is already coming as Line level inpur from source
Note on B5: Arun, Gheware Nilakanth: LEG_LOC_SR is at line level in AHCS. OIC would copy from heder to Line except for BKI and LSIR, as for BKI this is already coming as Line level inpur from source

## FIT DEMO (hidden)
Unique ID | JIRA Status | User Story Disposition | User Story | Comments / High-level Approach Notes | Notes | TRX # - Dev22 | Ledger | Owner
DP-RTR-AHCS-005 |  | 1-Fit-Configuration-Functional | As a GL accountant, I want to view SPER event types as part of MF AR subledger and SPEC event type as MF Inventory subledger. split SSI mainframe interface across MF AR and MF Inventory subledger as two different event types SPER and SPEC respectively so that WO, RTV etc. net / balance at Invoice level | Split SSI mainframe interface across MF AR and MF Inventory subledger as two different event types SPER and SPEC respectively so that WO, RTV etc. net / balance at Invoice level Based on File Name | SIT1 Tested
DP-RTR-AHCS-013 |  | 1-Fit-Configuration-Functional | As a GL accountant, For MF AR subledger event based interfaces CRI and SII use GL loc as BSR and location value as NSR. Then constant values to derive future segment using the business rules. | For MF AR subledger event based interfaces CRI and SII, use 5 digit GL loc as Balance SR and HQ/Sales location value(will come as 5 digits) as Non Balance SR. | Demo | CRI509396956_N3 | US USGAAP USD | Sravya
DP-RTR-AHCS-014 |  | 1-Fit-Configuration-Functional | As a GL accountant, For MF AP subledger event based interfaces CAI use GL loc as BSR and location value as NSR. Then constant values to derive future segment using the business rules. | For MF AP subledger event based interfaces CAI, use 5 digit GL loc as Balance SR and HQ/Sales location value(will come as 5 digits) as Non Balance SR. | Demo | CAI020641331 | FR USGAAP EUR | Ankur
DP-RTR-AHCS-015 |  | 1-Fit-Configuration-Functional | As a GL accountant, For MF INV subledger event based interfaces ISI,CQI,IBI,AII,ICI,IRI, FII, FTI use GL loc as BSR and location value as NSR. Then constant values to derive future segment using the business rules. | For MF Inventory subledger event based interfaces ISI,CQI,IBI,AII,ICI,IRI, FTI,FII uuse 5 digit GL loc as Balance SR and location value(will come as 5 digits) as Non Balance SR. | Demo | AII153141601FT | MX USGAAP MXN | Kathiravan
DP-RTR-AHCS-017 |  | 1-Fit-Configuration-Functional | As a GL accountant, Unvouchered – Freight & Duty for AP subledger and Inventory subledger to be added in the beginning balance load for FAH onprem for CALA Region | For MF AP Subledger and Inventory Subledger able to view Unouchered Freight and Duty via onprem fah source for CALA | SIT1 Tested
DP-RTR-AHCS-019 |  | 1-Fit-Configuration-Functional | As an IT Administrator, I want CQI mapping to be revised for GL_LOCATION and GL_VENDOR and to be replaced by PS_LOCATION and AXE_VENDOR respectively. | In CQI Template the fields GL_LOCATION and GL_VENDOR should be replaced by PS_LOCATION and AXE_VENDOR respectively. PS_LOCATION will be used for Location COA transformaion and AXE_VENDOR will have the Legacy Vendor Number. | Demo completed
DP-RTR-AHCS-021 |  | 1-Fit-Configuration-Functional | As a GL accountant, I want to make sure For MF AR subledger pass through interfaces to have GL loc as BSR and location value as Non Supporting Reference. | For MF AR subledger pass through interfaces no change to GL loc as BSR (Leg Seg 1-4) and HQ/Sales location SR will be moved to Non Balance SR. | Demo | BKI000832569 | AE USGAAP USD | Sravya
DP-RTR-AHCS-022 |  | 1-Fit-Configuration-Functional | As a GL accountant, I want to make sure For MF AP subledger pass through interfaces to have GL loc as BSR and location value as Non Supporting Reference. | For MF AP subledger pass through interfaces no change to GL loc as BSR (Leg Seg 1-4) and location SR will be moved to Non Balance SR. | Demo | API020689580 | ES USGAAP EUR | Ankur
DP-RTR-AHCS-023 |  | 1-Fit-Configuration-Functional | As a GL accountant, I want to make sure For MF INV subledger pass through interfaces to have GL loc as BSR and location value as Non Supporting Reference. | For MF INV subledger pass through interfaces no change to GL loc as BSR (Leg Seg 1-4) and location SR will be moved to Non Balance SR. | Demo | FII123242033FT | US USGAAP USD | Kathiravan
DP-RTR-AHCS-026 |  | 1-Fit-Configuration-Functional | As a GL accountant, I want to Remove Unvouchered – Freight & Duty from AP subledger and Inventory subledger from the beginning balance load for EMEA Region | NG 05/10 : Removed Unvouchered – Freight & Duty from AP subledger and Inventory subledger from the beginning balance load for EMEA Region | SIT1 Tested
DP-RTR-AHCS-027 |  | 1-Fit-Configuration-Functional | As a GL accountant, I want to Remove Freight Accrual from Inventory subledger from the beginning balance load for all regions | NG 05/10 :Removed Freight Accrual from Inventory subledger from the beginning balance load for all Region | SIT1 Tested
DP-RTR-AHCS-044 |  | 1-Fit-Configuration-Functional | As a GL Accountant, I want to enable Invoice date as balance enabled supporting reference for AP Subledger so that balances can be maintained at Invoice number and Invoice date level | Need balance Enabled Supporting Reference "Invoice date" MF AP Subledger. | Demo | API020689580 | ES USGAAP EUR | Ankur
DP-RTR-AHCS-051 |  | 1-Fit-Configuration-Functional | As GL Accountant, I need to view subledger balances by Legacy Location (under COA 1-4), and not by BU, Account and Department for AP, AR, Cresus and Inventory | I need to view subledger balances by Legacy Location (under COA 1-4), and not by BU, Account and Department for AP, AR, Cresus and Inventory | Demo | CRI509396956_N3 | US USGAAP USD
DP-RTR-AHCS-052 |  | 1-Fit-Configuration-Functional | As GL Accountant, I do not need to maintain subledger balances by Legacy COA 1-4 for PSFA, SXE, Eclipse, Cloud pay and Treasury (APS) | Do not need to maintain subledger balances by Legacy COA 1-4 for PSFA, SXE, Eclipse, Cloud pay and Treasury (APS) | Demo | SXE -SXEUS_20220410_03301220220409 | US USGAAP USD | Ankur
DP-RTR-AHCS-030 |  |  | As an IT Administrator, I want to make sure for Treasury COA Engine send Legacy COA in correct order "Business Unit-Location-Deaprtment-Account-Vendor-Affiliate". | Treasury -After changing the mapping COA order, AHCS integration is still bring the right COA data to the Legacy COA fields. as below Legacy 1-4 SR is “BU-Location-Account-Dept”. | SIT1 Tested
DP-RTR-AHCS-031 |  |  | As an IT Administrator, I want to make sure for SXE COA Engine send Legacy COA in correct order "Business Unit-Location-Deaprtment-Account-Vendor-Affiliate". | SXE -After changing the mapping COA order, AHCS integration is still bring the right COA data to the Legacy COA fields. as below Legacy 1-4 SR is “BU-Location-Account-Dept”. | SIT1 Tested
DP-RTR-AHCS-032 |  |  | As an IT Administrator, I want to make sure for ECLIPSE COA Engine send Legacy COA in correct order "Business Unit-Location-Deaprtment-Account-Vendor-Affiliate". | Eclipse -After changing the mapping COA order, AHCS integration is still bring the right COA data to the Legacy COA fields. as below Legacy 1-4 SR is “BU-Location-Account-Dept”. | SIT1 Tested
DP-RTR-AHCS-033 |  |  | As an IT Administrator, I want to make sure for CLOUDPAY COA Engine send Legacy COA in correct order "Business Unit-Location-Deaprtment-Account-Vendor-Affiliate". | CloudPay -After changing the mapping COA order, AHCS integration is still bring the right COA data to the Legacy COA fields. as below Legacy 1-4 SR is “BU-Location-Account-Dept”. | SIT1 Tested
DP-RTR-AHCS-034 |  |  | As an IT Administrator, I want to make sure for LEASES COA Engine send Legacy COA in correct order "Business Unit-Location-Deaprtment-Account-Vendor-Affiliate". | Leases -After changing the mapping COA order, AHCS integration is still bring the right COA data to the Legacy COA fields. as below Legacy 1-4 SR is “BU-Location-Account-Dept”. | SIT1 Tested
DP-RTR-AHCS-035 |  |  | As an IT Administrator, I want to make sure for MF AP COA Engine send Legacy COA in correct order "Business Unit-Location-Deaprtment-Account-Vendor-Affiliate". | MF AP -After changing the mapping COA order, AHCS integration is still bring the right COA data to the Legacy COA fields. as below Legacy 1-4 SR is “BU-Location-Account-Dept”. | SIT1 Tested
DP-RTR-AHCS-036 |  |  | As an IT Administrator, I want to make sure for MF AR COA Engine send Legacy COA in correct order "Business Unit-Location-Deaprtment-Account-Vendor-Affiliate". | MF AR -After changing the mapping COA order, AHCS integration is still bring the right COA data to the Legacy COA fields. as below Legacy 1-4 SR is “BU-Location-Account-Dept”. | SIT1 Tested
DP-RTR-AHCS-037 |  |  | As an IT Administrator, I want to make sure for MF INV COA Engine send Legacy COA in correct order "Business Unit-Location-Deaprtment-Account-Vendor-Affiliate". | MF INV -After changing the mapping COA order, AHCS integration is still bring the right COA data to the Legacy COA fields. as below Legacy 1-4 SR is “BU-Location-Account-Dept”. | Demo completed
DP-RTR-AHCS-038 |  |  | As an IT Administrator, I want to make sure forConcur COA Engine send Legacy COA in correct order "Business Unit-Location-Deaprtment-Account-Vendor-Affiliate". | Concur -After changing the mapping COA order, AHCS integration is still bring the right COA data to the Legacy COA fields. as below Legacy 1-4 SR is “BU-Location-Account-Dept”. | TBD
DP-RTR-AHCS-039 |  |  | As a GL accountant, I want to make sure for RPT008 , Source Transaction Number will be updated with separator ~ and its as per logic provided by Mike | For RPT 008, Source Transaction Number will be updated with separator ~ and its as per logic provided by Mike F. | SIT1 Tested
Note on D11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Need to confirm

## 1. User Stories
|  |  |  | AutoGenerated on load | Mandatory |  | Mandatory | Mandatory | Mandatory |  | Mandatory | Optional | Mandatory | Mandatory | Mandatory | Mandatory | Mandatory |  | Optional | Mandatory |  |  | Mandatory | Mandatory | Mandatory | Mandatory | Mandatory |  |  | Mandatory | Mandatory | Mandatory | Mandatory
|  |  |  | ID associated with User Story in Octane | Enter a unique next number for each user story. This number should be unique for each story and should not be repeated E.g GL-001 |  | Enter the name of the Level 0 Process to align with the process flow | Enter the name of the Level 1 Process to align with the process flow | Enter the name of the Level 2 Process to indicate the high-level requirement. | Enter a description of the User Story, identifying “who," “what,” and “why” in a simple and concise way (Note: it does not capture “how”). | Priority Must Have Should Have Could Have Won't Have | Select country if user story is applicable to specific country / countries | Specify which release the user story is part of (1A or 1B or Both) | Update user story disposition | Autofilled based on "User Story Disposition" column Classify if the user story is a 1. Fit or 2. Gap | Autofilled based on "User Story Disposition" column Classify how the user story will be achieved: 1. Build 2. Configuration 3. Work Around 4. Gap (used for temporary purposes during architect and updated to one of the three valid values as open items are resolved) 5. Out of scope (for gap items that were dispositioned as no longer in scope) | Autofilled based on "User Story Disposition" column If the user story type is Build or Configuration or Gap or Work Around, classify the Subtype as one of the following: 1. Build: A. Report B. Interface C. Conversions D. Extension 2. Configuration: A. Functional 3. Gap A. Gap 4. Work Around A. Work Around | If the user story type is Build, populate the Build ID (RICE ID) of the object once known. | To be used by project teams for additional comments and notes. | Enter the criteria (quantifiable result) that the user story must meet in order to be considered complete. Enter one acceptance criteria in one field. For more than one acceptance criteria, please use Acceptance Criteria 2 and Acceptance Criteria 3 fields. |  |  | The Due Date for getting approval for the User Story | Identified In Progress Submitted for Approval Approved TBD | Approved By |  | Story Points XS S M L XL |  |  | Track | SubTrack | Oracle Module | ABC Corp if based on a ABC Corp requirement. Deloitte if based on typically seen user stories
Aggregate Epic ID | JIRA ID Functional | JIRA ID Tech Build | JIRA ID TUT/FUT | JIRA ID | Unique ID | Updated Unique ID (BI Only) | L0 | L1 | L2 | User Story | Priority | Country | Release | User Story Disposition | Fit/Gap | Type | Subtype | Build ID | Comments / High-level Approach Notes | Acceptance Criteria 1 | Acceptance Criteria 2 | Acceptance Criteria 3 | User Story Due Date | Subtype Status | Approved By | Acutal User Story Approval Date | User Story Size | OSS Type for 1B JIRA analysis | OSS Sprint Plan Notes | Track | SubTrack | Oracle Module | Based on | Source | Reference ID | Legacy ABC Corp Review Status (ABC Corp internal column, not used by PMO) | Legacy ABC Corp Review Status (ABC Corp internal column, not used by PMO) | ABC Corp - EMEA (ABC Corp internal column, not used by PMO) | ABC Corp - APAC (ABC Corp internal column, not used by PMO) | ABC Corp - NA (ABC Corp internal column, not used by PMO) | ABC Corp - CALA (ABC Corp internal column, not used by PMO) | Discussion Questions during User Story review - Logged by ABC Corp/ABC Corp | Discussion Questions during User Story review - Logged by Deloitte | Process owner ETA | Approval Email Tracker for GPO Approval | Number
CSTONE-5287 | CSTONE-517 |  |  | CSTONE-517 | RTR-GL-001 |  | Record to Report | Manage General Ledger Accounting | Maintain Chart of Accounts | As a GL Accountant Financial Systems Analyst, I want to be able to define and update chart of accounts segment values so that the values defined reflect in the accounting. |  |  | Phase 1A+1B | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | USGAAP COA values will integrate from EDMCS. Local GAAP COA values is TBD. If not maintained in EDMCS can be maintained / updated directly in ERP User story GL-006 tracks a report for creating COA value extract with created by and last updated by column. Can be used for comparison process with EDMCS | Successfully updated chart of account segments which includes creation of new value and end dating existing values. Validate all business segments were created per business design. |  |  |  | Approved | Erica | 2021-05-04 |  |  |  | RTR | RTR-GL | GL | Deloitte |  |  | Ian/Vitaliy | [7 empty] | W1 | User Stories - Approval - GL Batch 1
CSTONE-5288 | CSTONE-518 |  |  | CSTONE-518 | RTR-GL-002 |  | Record to Report | Manage General Ledger Accounting | Maintain Chart of Accounts | As As a GL Accountant Financial Systems Analyst, I need to ensure we have the ability to configure the parent child relationship within segments of the COA so that roll up reporting is supported. |  |  | Phase 1A+1B | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Account hierarchies are defined in Oracle Cloud applications using tree functionality. Each account hierarchy is defined as a tree with one or more versions. Chart of accounts values can be associated with multiple hierarchies by defining multiple trees. Using multiple trees enable create financial reports for different target audiences. Amounts at each hierarchy node are pre-aggregated. Using account inquiry screen or smartview etc. balances can be validated | Successfully updated tree hierarchies | Successfully validated amounts of roll-ups |  |  | Approved | Erica | 2021-05-04 |  |  |  | RTR | RTR-GL | GL | Deloitte |  |  | Ian/Vitaliy | [7 empty] | W1 | User Stories - Approval - GL Batch 1
CSTONE-5289 | CSTONE-519 |  |  | CSTONE-519 | RTR-GL-003 |  | Record to Report | Manage General Ledger Accounting | Maintain Chart of Accounts | As a GL Accountant Financial Systems Analyst, I want to be able to restrict access to COA segments during journal entry so that I can prevent users from accessing values that they should not been accessing, specifically Branch values |  |  | Phase 1A+1B | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | For LE / Primary balancing segment, use PBSV data access set. For security on other COA segments: Set up segment value security rules on value sets to control access to parent or detail segment values for chart of accounts segments, also called flexfield segments. Segment value security rules restrict data entry, online inquiry, and reporting. For acceptance criteria 1&2: perform required testing aligned to roles & data access access setup as part of config values | Successfully added access restrictions to COA business segments based on business design | Validate data restrictions for each defined role |  |  | Approved | Erica | 2021-05-04 |  |  |  | RTR | RTR-GL | GL | Deloitte |  |  | Ian/Vitaliy | [7 empty] | W1 | User Stories - Approval - GL Batch 1
CSTONE-5290 | CSTONE-520 |  |  | CSTONE-520 | RTR-GL-004 |  | Record to Report | Manage General Ledger Accounting | Maintain Chart of Accounts | As a GL Accountant Financial Systems Analyst, I want to be able to define and maintain cross validation rules so that only correct code combinations are entered. |  |  | Phase 1A+1B | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | In Oracle Cloud General Ledger, cross validation rules are used to determine the account combinations that users can create dynamically when they enter transactions or journal entries. Once enabled, cross validation rule determines whether a selected value for a particular segment of the account combination can be combined with specific values in the other segments to form a new account combination. For acceptance criteria 2: CVR rules can be reviewed from Setup and Maintenance access | Successfully created cross validation rules based on business design. Also ability to add or removed existing CVRs. | Validate cross-validation rules |  |  | Approved | Erica | 2021-05-04 |  |  |  | RTR | RTR-GL | GL | Deloitte |  |  | Ian/Vitaliy | [7 empty] | W1 | User Stories - Approval - GL Batch 1
CSTONE-5291 | CSTONE-5112 |  |  | CSTONE-5112 | RTR-GL-005 |  | Record to Report | Manage General Ledger Accounting | Maintain Chart of Accounts | As a GL Accountant Financial Systems Analyst, I want to be able to maintain an alternative account structure, so that adjustments required for external regulatory reporting are supported. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Create Alternate Chart of account and assign i to secondary ledger to fulfill LOCAL GAAP reporting requirements as per Enterprise Structure KDD For acceptance criteria 2: TB report on primary ledger and then on secondary ledger can be used to extract balances & document required reconciliation between primary vs secondary ledger. For this either standard TB can be used or a custom TB proposed as part of RTR-GL-090 [if approved] can be leveraged | Successfully added and updated alternate structure. | Validate alternate account structure and reconcile to primary ledger |  | Sprint 7 | Approved | Erica | 2021-05-04 |  | #REF! |  | RTR | RTR-GL | GL | Deloitte |  |  | Ian/Vitaliy | [7 empty] | N/A for 1A | User Stories - Approval - GL Batch 1
CSTONE-5292 | CSTONE-3624 | CSTONE-4393 | CSTONE-4411 | CSTONE-4411 | RTR-GL-006 |  | Record to Report | Manage General Ledger Accounting | Maintain Chart of Accounts | As GL Manager Financial Systems Analyst, I need to confirm that the system supports viewing the chart of accounts segment, value, description online (COA screen) and through reports (COA report) so that account review and analysis is supported. |  |  | Phase 1A+1B | 2-Gap-Build-Report | Gap | Build | Report | RPT001 | COA value Details can be viewed from Manage Chart of Accounts Value set values. Seeded Enterprise Structure report pulls too many details as compared to COA only. If COA report is required from ERP, custom report needs to be built. Report should pull in WHO columns [Created by, creation date, updated by, update date] to enable review with EDMCS For acceptance criteria 1: Use Setup and Maintenance - Manage Chart of Account Values | View COA in real time on screen | Validate report |  |  | Approved | Erica | 2021-05-04 |  |  |  | RTR | RTR-GL | GL | Deloitte |  |  | Ian/Vitaliy | [7 empty] | W1 | User Stories - Approval - GL Batch 1
CSTONE-5293 | CSTONE-62 |  |  | CSTONE-62 | RTR-GL-007 |  | Record to Report | Manage General Ledger Accounting | Process Manual Journal Entries | As a GL Accountant, I want to be able to enter manual journal entries (monetary or statistical) |  |  | Phase 1A+1B | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Enter journals using monetary (non STAT) currency and STAT currency as the case may be KDD of COA structure to confirm balancing segment & in turn drive balancing behavior by currencies. JE will be by ledger [header level field] for US & CA, by LE for rest of countries to align to sequencing requirement. In US & CA, user can still choose to only enter for one LE by using it as a BSV [assuming KDD of COA makes LE as Primary balancing segment]. Journal Source & Category are mandatory fields on journal | Enter JE's by LE and in functional currency, foreign currency or stat currency. It is critical that for monetary JE's both foreign and functional currencies balance. Identify the JE category (source code in AXE legacy PS) for the entry and also the JE source as well. Validate journal after posted | Validate unbalanced STAT entries post | Validate users can change currency of entry, change period, add multiple journal attachments, change Fx rate. Test CVR rules Test prior period posting Test disabled account string | Ledger with suspense: Validate unbalanced journals post amount to correct suspense code. Ledger without suspense: Validate unbalanced journal errors. | Approved | Erica | 2021-05-04 |  |  |  | RTR | RTR-GL | GL | Deloitte |  |  | Ian/Vitaliy | [7 empty] | W1 | User Stories - Approval - GL Batch 1
CSTONE-5294 | CSTONE-63 |  |  | CSTONE-63 | RTR-GL-008 |  | Record to Report | Manage General Ledger Accounting | Process Manual Journal Entries | As a GL Accountant, I want to be able to upload journals from excel or .csv formats, including verification, validation and correction of individual entries so that I can experience efficient journal processing |  |  | Phase 1A+1B | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Use ADFDI template to load data. Validate system performance and practice field mapping using files that will mimic post go-live scenarios including anticipated journal line volume Standard ADFDI shows error messages and status in spreadsheet once load is attempted. Journal approval will be based on KDD7 Journal approval [Spreadsheet source i.e. source used by ADFDI spreadsheet is currently planned to enabled for journal approval. Approval hierarchy etc. will be based on KDD7 Journal approval] If there are system performance impacts, WESCO IT will need to work with Oracle via SR for system slowness. Snippet from Oracle note Doc ID 1622476.1 around performance expectations: Typical performance is 1,000 rows in 1 minute but this depends on the chart of accounts setup, number of new combinations in the sheet and number of distinct combination in the spreadsheet. So for example, if the columns like journal name, batch name, descriptions are not as verbose then the number of rows uploaded would be higher. The number of rows that can be processed depends on how much data is present in each row. In general it is recommended to use File Based Import (FBDI) if data being entered is in thousands of rows (approximately over 30K rows) since this sheet does not have any validations Based on volumes of lines per journal shared so far (<20K per upload) there is no plan to enable FBDI to users. Enabling FBDI to users may pose challenge around approvals & should be used as a last option once other performance options like Disabling validations, reviewing size of journals, Oracle SR etc. have been eliminated | File uploaded via excel and once uploaded identified if successful or any errors associated with the upload. Once uploaded JE should follow the appropriate levels of approvals based on established criterias (dollar threshold, loa, etc). Also when uploading large volume of data should not take a long time to process through the system. Validate all journals, including journals over 10k + lines for accuracy and performance once posted. | Validate unbalanced STAT entries post | Test CVR rules Test prior period posting Test disabled account string | Ledger with suspense: Validate unbalanced journals post amount to correct suspense code. Ledger without suspense: Validate unbalanced journal errors. | Approved | Erica | 2021-05-04 |  |  |  | RTR | RTR-GL | GL | Deloitte |  |  | Ian/Vitaliy | [7 empty] | W1 | User Stories - Approval - GL Batch 1
CSTONE-5295 | CSTONE-64 |  |  | CSTONE-64 | RTR-GL-009 |  | Record to Report | Manage General Ledger Accounting | Process Manual Journal Entries | As a GL Accountant Financial Systems Analyst I need the ability to import journal entries from subledger modules (Create Accounting for Cloud Subledgers), so that I can see subledger balances coming to GL |  |  | Phase 1A+1B | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Subledger journals can be imported with source subledger. Approval design will be driven based on GL Journal approval | Journals from subledgers should go through auto approve process. Validate subledger journals posted correctly. Compare posted journals to legacy system to ensure completeness. |  |  |  | Approved | Erica | 2021-05-14 |  |  |  | RTR | RTR-GL | GL | Deloitte |  |  | Ian/Vitaliy | [7 empty] | W1 | User Stories - Approval - GL Batch 1
CSTONE-5296 | CSTONE-581 | CSTONE-3626 | CSTONE-3649 | CSTONE-3649 | RTR-GL-010 |  | Record to Report | Manage General Ledger Accounting | Process Manual Journal Entries | As a GL Accountant, I want to be able to review journal entries so that I am aware of what has been entered and posted in the system |  |  | Phase 1A+1B | 2-Gap-Build-Report | Gap | Build | Report | RPT002 | Go to Manage Journal Entries task --> search the journals and extract the data in Excel. You may additionally run standard Journal details report to review the journals that are posted Discuss: Build a custom flat excel journal extract report with custom parameters for review. Report output should inlcude columns like posting status, approval status, reversed yes/no, WHO columns etc. Ensure report parameter includes Created By [Journal Batch + Journal Header report] | Run real time data as part of my analysis when reviewing entered and posted entries. Review entered and posted journals via report. | Validate Journals>Enter query (Manage Journal) |  |  | Approved | Erica | 2021-05-04 |  |  |  | RTR | RTR-GL | GL | Deloitte |  |  | Ian/Vitaliy | [7 empty] | W1 | User Stories - Approval - GL Batch 1
CSTONE-5297 | CSTONE-67 |  |  | CSTONE-67 | RTR-GL-011 |  | Record to Report | Manage General Ledger Accounting | Approve and Post Journal Entries | As a GL Accountant, I need the ability to review unposted entries so that I can determine the appropriate action to get the entries posted |  |  | Phase 1A+1B | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | System allows to select unposted/posted/error journals from the search tile of Manage Journal Entries. Additionally details can be extracted in Excel. Fields that are available for view standard Oracle provided and do include Created By [based on HR record], Posting Status, Approval Status, Ledger name | Run real time data as part of my analysis when reviewing entered and posted entries. | Identify all entries not having a 'posted' status using a single filter that allows for a single export of data. The data elements should include enough information to follow-up on the open item (i.e. user, ledger, journal status, etc.) |  |  | Approved | Erica | 2021-05-04 |  |  |  | RTR | RTR-GL | GL | Deloitte |  |  | Ian/Vitaliy | [7 empty] | W1 | User Stories - Approval - GL Batch 1
CSTONE-5298 | CSTONE-68 |  |  | CSTONE-68 | RTR-GL-012 |  | Record to Report | Manage General Ledger Accounting | Approve and Post Journal Entries | As a GL Accountant Financial Systems Analyst, I need the ability to post entries to general ledger so that the GL balances can be updated |  |  | Phase 1A+1B | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | System allows to post subledger and manual/spreadsheet journals. AutoPost will post journals that are already approved or don’t need approval. It will also initiate approval for journals that need approval & approval has not been initiated. In such a case, approval will go through as per KDD on Journal approval. For manual post, posting will not be allowed if journal needs approval & is not yet approved For acceptance criteria 2: It is not possible to configure autopost to not trigger approval. System behavior as noted above. Based on accceptance criteria 2 marking as a Gap. Workaround would be to turn off auto-post | If entry is below indicated threshold then allow auto approval. If outside threshold then submit to next level approval based on approval rules and thresholds set up. Validate posted entries. | Confirm Posting functionality for entry above indicated threshold is disabled. Confirm AutoPost does not capture an entry above indicated threshold. |  |  | Approved | Erica | 2021-05-14 |  |  |  | RTR | RTR-GL | GL | Deloitte |  |  | Ian/Vitaliy | [7 empty] | W1 | User Stories - Approval - GL Batch 1
CSTONE-5299 | CSTONE-1357 | CSTONE-3627 | CSTONE-3650 | CSTONE-3650 | RTR-GL-013 |  | Record to Report | Manage General Ledger Accounting | Approve and Post Journal Entries | As a GL Accountant, I need the ability to inform my manager to approve journal entries, so that they can be posted |  |  | Phase 1A+1B | 2-Gap-Build-Report | Gap | Build | Report | RPT003 | Journal can be sent for approval by requesting for approval as per Journal approval KDD For acceptance criteria 2, need to build a new report that shows journals and action history log for journals pending approval | There should be email notification and a flag in cloud as well to alert approver that an approval is needed. Ensure notification includes all the criterias per business design. | Requirement to build a report that identifies all unposted journals and current level of approval. |  |  | Approved | Erica | 2021-05-12 |  |  |  | RTR | RTR-GL | GL | Deloitte |  |  | Ian/Vitaliy | [7 empty] | W1 | User Stories - Approval - GL Batch 1
CSTONE-5300 | CSTONE-71 |  |  | CSTONE-71 | RTR-GL-014 |  | Record to Report | Manage General Ledger Accounting | Approve and Post Journal Entries | As a GL Manager, I want to be able to review and approve the allocation journals (Calc Manager)before posting so that I can ensure their accuracy |  |  | Phase 1A+1B | 6-Gap-Work Around-Work Around | Gap | Work Around | Work Around |  | 1-Approvals are not applicable for allocations. Allocation source will be freeze. In such case users are not allowed to do any changes. Any updates would be separate journal entry, which would route for approval as it is a manual entry. 2- Use lower test environment to test allocation and approve outputs prior to loading in PROD. Acceptance Criteria 1 will be implemented in a lower (non-production) instance | Review allocation journals prepared prior to posting. Validate journal after it has been posted. |  |  |  | Approved | Erica | 2021-05-12 |  |  |  | RTR | RTR-GL | GL | Deloitte |  |  | Ian/Vitaliy | [7 empty] | W1 | User Stories - Approval - GL Batch 1
CSTONE-5301 | CSTONE-72 |  |  | CSTONE-4695 | RTR-GL-015 |  | Record to Report | Manage General Ledger Accounting | Approve and Post Journal Entries | As a GL Accountant, I need the ability to make necessary revisions to journals so that I can send the corrected entry for approval. |  |  | Phase 1A+1B | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | System does not allow to edit posted journal. If the journals are not posted, user can make changes or withdraw journal if it is sent for an approval and make the changes. | Once Journal is posted it should not be editted. If changes are required to post the journal, need to book a separate entry to make corrections. Make appropriate revisions to unposted journals and submit for approval. Validate posted journal. | Test a reversing entry. Test auto-copy entry followed by editing entry. |  |  | Approved | Erica | 2021-05-04 |  |  |  | RTR | RTR-GL | GL | Deloitte |  |  | Ian/Vitaliy | [7 empty] | W1 | User Stories - Approval - GL Batch 1
CSTONE-5302 | CSTONE-73 |  |  | CSTONE-73 | RTR-GL-016 |  | Record to Report | Manage General Ledger Accounting | Approve and Post Journal Entries | As a GL Manager, I want to be able to receive email and in-application notifications so that I don't have to go out of the application to see notification |  |  | Phase 1A+1B | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Through approval workflow, Email notification and Oracle notification (bell icon) is sent to the manager as and when journals are requested for an approval. Journal approval notifications can also be sent to submitter of approval [not necessarily created by] For Acceptance Criteria 2, for internal audit and PwC review of journal flow, Front End Action Log to be used | Receive email notification and oracle notification when journals are requested for an approval. Ensure notification includes all the criterias per business design. | Test journal approval rejections and confirm preparer is able to edit the journal. Preparer should also receive notifications as the entry routes through the approval. Consider developing a report for the audit trail of the journal approval hierarchies; PwC and IA request support. | As an approver, test journal workflow vacation rules and confirm delegation of approval and journal limit is successful. | As an approver, test journal workflow reassignment and confirm reassignment is successful. (I don't believe limit is reassigned) | Approved | Erica | 2021-05-12 |  |  |  | RTR | RTR-GL | GL | Deloitte |  |  | Ian/Vitaliy | [7 empty] | W1 | User Stories - Approval - GL Batch 1
CSTONE-5303 | CSTONE-582 | CSTONE-3628 | CSTONE-3651 | CSTONE-3651 | RTR-GL-017 |  | Record to Report | Manage General Ledger Accounting | Approve and Post Journal Entries | As a GL Manager Financial System Analyst, I want to be able to modify approval notifications template for GL workflows so that the predefined template can be updated to display information based on specific business requirements and policies. |  |  | Phase 1A+1B | 2-Gap-Build-Report | Gap | Build | Report | RPT004 | Approval notification template can be updated as per requirement. Requirement to have code combination string added to output For acceptance criteria 1: Customization of notification template to be discussed in RICE lean spec once user story is approved & RICE build is scheduled | Notification contains all the required information previously defined by users. |  |  |  | Approved | Erica | 2021-05-04 |  |  |  | RTR | RTR-GL | GL | Deloitte |  |  | Ian/Vitaliy | [7 empty] | W1 | User Stories - Approval - GL Batch 1
CSTONE-5304 | CSTONE-583 | CSTONE-3629 | CSTONE-3652 | CSTONE-3652 | RTR-GL-018 |  | Record to Report | Manage General Ledger Accounting | Approve and Post Journal Entries | As a GL Manager (an approver of journal) like to know the Journal created creator and submitter so that I know who is creating and submitting the batch for approval |  |  | Phase 1A+1B | 2-Gap-Build-Report | Gap | Build | Report | RPT004 | Submitted by details (with time and date stamp) are captured in the standard approval workflow. Customize template to add Created by | Review Journal creator and submitter including date and time stamp at time of approval. |  |  |  | Approved | Erica | 2021-05-07 |  |  |  | RTR | RTR-GL | GL | Deloitte |  |  | Ian/Vitaliy | [7 empty] | W1 | User Stories - Approval - GL Batch 1
CSTONE-5305 | CSTONE-78 |  |  | CSTONE-78 | RTR-GL-019 |  | Record to Report | Manage General Ledger Accounting | Process Recurring Journal Entries | As a GL Accountant, I want to be able to create and save journal entry templates so that I can take advantage of quick and efficient data entry [Flavors: Standard, Skeleton, Formula] |  |  | Phase 1A+1B | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Three options: 1. Excel template - User can upload it every month [Ensure to check template for changes as part of upgrade regression testing] 2. Allocations - This will not flow through approval process per current functionality 3. Auto Copy 1 future open period is planned. Entries can be booked to it but not posted | Create and save entry templates based on specific criterias (amortize, month to month, budget). Load the saved template to the Cloud GL. Review for any load errors and correct is required. Validate posted entry. |  |  |  | Approved | Erica | 2021-05-12 |  |  |  | RTR | RTR-GL | GL | Deloitte |  |  | Ian/Vitaliy | [7 empty] | W2 | User Stories - Approval - GL Batch 1
CSTONE-5306 |  |  |  | N/A | RTR-GL-020 |  | Record to Report | Manage General Ledger Accounting | Process Recurring Journal Entries | As a GL Accountant I need the ability to enter standard journal entry lines so that respective recurring entries can be taken care of |  |  | Not Required | 10-Not Required-Not Required-Not Required | Not Required | Not Required | Not Required |  | Excel template - User can upload it every month Not required as combined with RTR-GL-019 |  |  |  |  | Approved | Erica | 2021-05-14 |  |  |  | RTR | RTR-GL | GL | Deloitte |  |  | Ian/Vitaliy | [7 empty] | W2 | User Stories - Approval - GL Batch 1
CSTONE-5307 |  |  |  | N/A | RTR-GL-021 |  | Record to Report | Manage General Ledger Accounting | Process Recurring Journal Entries | As a GL Accountant I need the ability to enter formula journal entry lines so that complex recurring entries can be taken care of |  |  | Not Required | 10-Not Required-Not Required-Not Required | Not Required | Not Required | Not Required |  | Allocations - This will not flow through approval process per current functionality Not required as combined with RTR-GL-019 |  |  |  |  | Approved | Erica | 2021-05-14 |  |  |  | RTR | RTR-GL | GL | Deloitte |  |  | Ian/Vitaliy | [7 empty] | W2 | User Stories - Approval - GL Batch 1
CSTONE-5308 |  |  |  | N/A | RTR-GL-022 |  | Record to Report | Manage General Ledger Accounting | Process Recurring Journal Entries | As a GL Accountant I need the ability to enter skeleton journal entry lines so that recurring entries where amounts change monthly can be taken care of |  |  | Not Required | 10-Not Required-Not Required-Not Required | Not Required | Not Required | Not Required |  | Three options: 1. Excel template - User can upload it every month 2. Allocations - This will not flow through approval process per current functionality [will need dummy amounts] 3. Auto Copy 1 future open period is planned. Entries can be booked to it but not posted Not required as combined with RTR-GL-019 |  |  |  |  | Approved | Erica | 2021-05-14 |  |  |  | RTR | RTR-GL | GL | Deloitte |  |  | Ian/Vitaliy | [7 empty] | W2 | User Stories - Approval - GL Batch 1
CSTONE-5309 | CSTONE-79 |  |  | CSTONE-79 | RTR-GL-023 |  | Record to Report | Manage General Ledger Accounting | Process Recurring Journal Entries | As a GL Manager I need the ability to review template entries sent for my approval so that I can approve / reject them |  |  | Phase 1A+1B | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Excel template (ADFDI Journal upload) - User can upload it every month. User may additionally attach the template as an attachment for review during journal approval. For acceptance criteria 1: Calc manager entries do not route for approval. As per KDD5 discussion, interpreted Acceptance criteria 1 as ADFDI manual journal entry upload | Review template entries through approval process related to recurring entries. Ensure the approval notification contains all the required fields based on business design. Validate journal after posted. |  |  |  | Approved | Erica | 2021-05-14 |  |  |  | RTR | RTR-GL | GL | Deloitte |  |  | Ian/Vitaliy | [7 empty] | W2 | User Stories - Approval - GL Batch 1
CSTONE-5310 |  |  |  | N/A | RTR-GL-024 |  | Record to Report | Manage General Ledger Accounting | Process Recurring Journal Entries | As a GL Manager, I want to be able to define recurring journals so that I can quickly enter journal lines for recurring expenses |  |  | Not Required | 10-Not Required-Not Required-Not Required | Not Required | Not Required | Not Required |  | Three options: 1. Excel template - User can upload it every month 2. Allocations - This will not flow through approval process per current functionality 3. Auto Copy 1 future open period is planned. Entries can be booked to it but not posted Not required as covered in RTR-GL-019 |  |  |  |  | Approved | Erica | 2021-05-14 |  |  |  | RTR | RTR-GL | GL | Deloitte |  |  | Ian/Vitaliy | [7 empty] | W2 | User Stories - Approval - GL Batch 1
CSTONE-5311 | CSTONE-80 |  |  | CSTONE-80 | RTR-GL-025 |  | Record to Report | Manage General Ledger Accounting | Process Recurring Journal Entries | As a GL Accountant I need the ability to review recurring journal entries so that I can confirm their accuracy before sending for approval |  |  | Phase 1A+1B | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Three options: 1. Excel template - User can upload it every month 2. Allocations - This will not flow through approval process per current functionality 3. Auto Copy 1 future open period is planned. Entries can be booked to it but not posted For acceptance criteria 1: Calc manager entries do not route for approval. As per KDD5 discussion, interpreted Acceptance criteria 1 as ADFDI manual journal entry upload | Review recurring journal entries and make any modifications prior to sending for approval. |  |  |  | Approved | Erica | 2021-05-14 |  |  |  | RTR | RTR-GL | GL | Deloitte |  |  | Ian/Vitaliy | [7 empty] | W2 | User Stories - Approval - GL Batch 1
CSTONE-5312 | CSTONE-81 |  |  | CSTONE-81 | RTR-GL-026 |  | Record to Report | Manage General Ledger Accounting | Process Reversing Journal Entries | As a GL Accountant, I want to enable the auto-reversal for certain journal categories so that balances are accurately reflected and redundant manual effort is reduced |  |  | Phase 1A+1B | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Use appropriate category (e.g. accrual) for reverse. Auto Reverse will be configured to be triggered when next period is opened. One of the two approaches to auto reverse will be selected: 1. Set all commonly used categories to auto-reverse with reversal period as blank in auto-reverse criteria set. Users to enter reversal period to ensure it is picked for autoreversal [Note: If reversal period is added after journal approval, auto-reversed journal will not be routed for approval] 2. Set specific categories to autoreverse with reversal period identified as next non adjusting period. User needs to select appropriate category that is set for reversal and dont need to enter reversal period [Since rule is category driven, can review using report referred to in RTR-GL-010 for such journals in a given categories that did not get reversed due to user manually making reversal period blank before or after approval]. 5/3: Core team call alignment to use approach 2. Report requested as part of user story RTR_GL_106 | Key conditions for Journal to be picked for auto reversal are Category should be enabled for auto reversal, Journal should be posted, Journal should not be a subledger Journal (Frozen). Ensure reversal posted is exact value as the original if original was posted in multiple currencies. |  |  |  | Approved | Erica | 2021-05-07 |  |  |  | RTR | RTR-GL | GL | Deloitte |  |  | Ian/Vitaliy | [7 empty] | W1 | User Stories - Approval - GL Batch 1
CSTONE-5313 | CSTONE-521 |  |  | CSTONE-521 | RTR-GL-027 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | As a GL Accountant Financial Systems Analyst, I need the ability to open a new accounting period so that users can start transaction entry for the month |  |  | Phase 1A+1B | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Use period open functionality. | Open 1 future accounting period |  |  |  | Approved | Erica | 2021-05-14 |  |  |  | RTR | RTR-GL | GL | Deloitte |  |  | Ian/Vitaliy | [7 empty] | W2 | User Stories - Approval - GL Batch 1
CSTONE-5314 | CSTONE-82 |  |  | CSTONE-82 | RTR-GL-028 |  | Record to Report | Manage General Ledger Accounting | Process Reversing Journal Entries | As a GL Accountant I want to auto-reverse current month accruals in the next month so that I can reduce the amount of time my team spends manually reversing journal entries at the beginning of a new period. |  |  | Phase 1A+1B | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Use appropriate category (e.g. accrual) for reverse. Auto Reverse will be configured to be triggered when next period is opened. One of the two approaches to auto reverse will be selected: 1. Set all commonly used categories to auto-reverse with reversal period as blank in auto-reverse criteria set. Users to enter reversal period to ensure it is picked for autoreversal [Note: If reversal period is added after journal approval, auto-reversed journal will not be routed for approval] 2. Set specific categories to autoreverse with reversal period identified as next non adjusting period. User needs to select appropriate category that is set for reversal and dont need to enter reversal period [Since rule is category driven, can review using report referred to in RTR-GL-010 for such journals in a given categories that did not get reversed due to user manually making reversal period blank before or after approval]. 5/3: Core team call alignment to use approach 2. Report requested as part of user story RTR_GL_106 | Key conditions for Journal to be picked for auto reversal are Category should be enabled for auto reversal, Journal should be posted, Journal should not be a subledger Journal (Frozen) |  |  |  | Approved | Erica | 2021-05-07 |  |  |  | RTR | RTR-GL | GL | Deloitte |  |  | Ian/Vitaliy | [7 empty] | W1 | User Stories - Approval - GL Batch 1
CSTONE-5315 | CSTONE-83 |  |  | CSTONE-83 | RTR-GL-029 |  | Record to Report | Manage General Ledger Accounting | Process Reversing Journal Entries | As a GL Accountant, I need the ability to create manual journal reversals so that entries posted by mistake can be corrected |  |  | Phase 1A+1B | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Manually reverse the journal in manage journal page. Enter reversal period and reverse. User can also manually reverse by loading a new journal entry Acceptance criteria 2: Keep Manual, AutoCopy and Spreadsheet source's "Freeze" as No | Once entry has posted, system should not allow user to reverse the entry. Validate the new entry has been posted to correct prior entry. | Users require the ability to manually reverse entries that are non-subledger, non-allocation sourced. |  |  | Approved | Erica | 2021-05-04 |  |  |  | RTR | RTR-GL | GL | Deloitte |  |  | Ian/Vitaliy | [7 empty] | W1 | User Stories - Approval - GL Batch 1
CSTONE-5316 | CSTONE-84 |  |  | CSTONE-84 | RTR-GL-030 |  | Record to Report | Manage General Ledger Accounting | Process Reversing Journal Entries | As a GL Accountant, I need the ability to select journals to be reversed so that I can quickly reverse selected journal entries. |  |  | Phase 1A+1B | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Use ADFDI template to reverse large number of journals by passing new entry for equivalent reversal details. Oracle Cloud now also supports ability to reverse Journal batch | Able to confirm batch/ journal reversal. |  |  |  | Approved | Erica | 2021-05-07 |  |  |  | RTR | RTR-GL | GL | Deloitte |  |  | Ian/Vitaliy | [7 empty] | W1 | User Stories - Approval - GL Batch 1
CSTONE-5317 | CSTONE-85 |  |  | CSTONE-85 | RTR-GL-031 |  | Record to Report | Manage General Ledger Accounting | Process Reversing Journal Entries | As a GL Accountant, I need the ability to open enter journal window and search for journals to be reversed so that I can proceed with reversing these entries |  |  | Phase 1A+1B | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Search for the journal from Manage Journals Search task and open the journal. System allows to - Manually select for reversal and generate in the current period - Manually select for reversal and generate in a later period - Automatically using Journal Reversal Criteria Sets One consistent global reversal criteria set to be used. 1 future enterable period | Review ability to search journal real time. Enter the reversal. Validate posted entry. |  |  |  | Approved | Erica | 2021-05-04 |  |  |  | RTR | RTR-GL | GL | Deloitte |  |  | Ian/Vitaliy | [7 empty] | W1 | User Stories - Approval - GL Batch 1
CSTONE-5318 | CSTONE-86 |  |  | CSTONE-86 | RTR-GL-032 |  | Record to Report | Manage General Ledger Accounting | Process Reversing Journal Entries | As a GL Accountant, I need the ability to review reversed journal entries so that I can determine whether they are correct before submitting for approval |  |  | Phase 1A+1B | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Manually reversed journal entries follow approval yes/no flag as original journal entries. Auto-Reversed journal entries do no go through approval process For acceptance criteria 1: Once a journal is tagged for approval, it will follow journal approval rules prevalent in system. These rules iwll be configured as per KDD | If entry is below indicated threshold then allow auto approval. If outside threshold then submit to next level approval based on approval rules and thresholds set up. |  |  |  | Approved | Erica | 2021-05-04 |  |  |  | RTR | RTR-GL | GL | Deloitte |  |  | Ian/Vitaliy | [7 empty] | W1 | User Stories - Approval - GL Batch 1
CSTONE-5319 | CSTONE-5105 |  |  | CSTONE-5105 | RTR-GL-033 |  | Record to Report | Manage General Ledger Accounting | Process Reversing Journal Entries | As a GL Manager I would need to automatically approve reversal journals in a secondary ledger when the corresponding reversal journal in the primary ledger is approved so that a separate approval is not required in secondary ledger. As a GL manager all reversing Journals in the primary ledger should be automatically approved and posted in the secondary ledger ( for journals that need to be posted in both primary and secondary ledger). |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Setup synchronize reversals to secondary | Reversing journal posted in primary ledger has automatically posted in secondary ledger (for journals that need to be posted in both primary and secondary ledgers) |  |  | Sprint 7 | Approved | Erica | 2021-05-04 |  | #REF! |  | RTR | RTR-GL | GL | Deloitte |  |  | Ian/Vitaliy | [7 empty] | W1 | User Stories - Approval - GL Batch 1
CSTONE-5320 | CSTONE-88 |  |  | CSTONE-88 | RTR-GL-034 |  | Record to Report | Manage General Ledger Accounting | Process Manual Journal Entries | As a GL Accountant Financial System Analyst, I need the ability to auto post entries to the GL so that the posting process can be made more efficient |  |  | Phase 1A+1B | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Schedule AutoPost | Schedule journal entries that meet the necessary requirements based on period, source, category to post based on scheduled processes. Any journals which require approvals should be routed as part of the process. Any journals which are rejected should not be picked up as part of process. Validate posted entry. | Validate only approved journals are posted Validate journal sources set as freeze post without approval via AutoPost. |  |  | Approved | Erica | 2021-05-07 |  |  |  | RTR | RTR-GL | GL | Deloitte |  |  | Ian/Vitaliy | [7 empty] | W1 | User Stories - Approval - GL Batch 1
CSTONE-5321 | CSTONE-559 |  |  | CSTONE-559 | RTR-GL-035 |  | Record to Report | Manage General Ledger Accounting | Perform Allocations | As a GL Accountant, I need the ability to send a request for review and approval for allocation rules so that I can be certain that they are defined as per management expectations |  |  | Phase 1A+1B | 6-Gap-Work Around-Work Around | Gap | Work Around | Work Around |  | This would be achieved via offline review and approval process. Approvals are not applicable for allocations. Allocation source will be freeze. In such case users are not allowed to do any changes. Any updates would be separate journal entry, which would route for approval as it is a manual entry. | Offline review and approval of global allocation rules for combined company. Review allocation results to ensure accuracy. |  |  |  | Approved | Erica | 2021-05-14 |  |  |  | RTR | RTR-GL | GL | Deloitte |  |  | Ian/Vitaliy | [7 empty] | W2 | User Stories - Approval - GL Batch 1
CSTONE-5322 | CSTONE-560 |  |  | CSTONE-560 | RTR-GL-036 |  | Record to Report | Manage General Ledger Accounting | Perform Allocations | As a GL Manager, I want to be able to perform what-if analysis on the allocations to ensure accurate allocations calculations and I need the ability to review new allocation rules so that I can validate them before sending for approval |  |  | Phase 1A+1B | 6-Gap-Work Around-Work Around | Gap | Work Around | Work Around |  | This would be achieved via offline review and approval process. Approvals are not applicable for allocations. Allocation source will be freeze. In such case users are not allowed to do any changes. Any updates would be separate journal entry, which would route for approval as it is a manual entry. | After agreed global allocation rules are approved, any new or additional rules are reviewed and approved offline prior to being added and implemented. Review new allocation results for accuracy. |  |  |  | Approved | Erica | 2021-05-14 |  |  |  | RTR | RTR-GL | GL | Deloitte |  |  | Ian/Vitaliy | [7 empty] | W2 | User Stories - Approval - GL Batch 1
CSTONE-5323 | CSTONE-522 |  |  | CSTONE-522 | RTR-GL-037 |  | Record to Report | Manage General Ledger Accounting | Perform Allocations | As a GL Accountant Financial Systems Analyst, I want the ability to generate allocation Journals so that costs can be transferred from a source to a target |  |  | Phase 1A+1B | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Allocation Manager feature is used to create allocation and other formulaic journal templates for generating periodic journal entries automatically. | Generated allocation journals for specified process based on defined source criterias which resulted in appropriate target outcome. |  |  |  | Approved | Erica | 2021-05-14 |  |  |  | RTR | RTR-GL | GL | Deloitte |  |  | Ian/Vitaliy | [7 empty] | W2 | User Stories - Approval - GL Batch 1
CSTONE-5324 | CSTONE-523 |  |  | CSTONE-523 | RTR-GL-038 |  | Record to Report | Manage General Ledger Accounting | Perform Allocations | As a GL Accountant I want the ability to review allocation Journals so that I can confirm that they are correctly generated |  |  | Phase 1A+1B | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Review the allocation journals with source Allocation from Manage Journal Entries task | Review allocation journals using Manage Journal Entries task. | Business owners to review and validate financials (detective control). |  |  | Approved | Erica | 2021-05-14 |  |  |  | RTR | RTR-GL | GL | Deloitte |  |  | Ian/Vitaliy | [7 empty] | W2 | User Stories - Approval - GL Batch 1
CSTONE-5325 | CSTONE-524 |  |  | CSTONE-524 | RTR-GL-039 |  | Record to Report | Manage General Ledger Accounting | Perform Allocations | As a GL Accountant Financial Systems Analyst, I need the ability to define new rules in create allocation rules so that any new allocations can be taken care of |  |  | Phase 1A+1B | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Allocation Manager feature is used to create allocation and other formulaic journal templates for generating periodic journal entries automatically. | Define and create new allocation rules using Allocation Manager feature. Completed once new allocation rules have been approved offline. Review allocation results for accuracy. |  |  |  | Approved | Erica | 2021-05-14 |  |  |  | RTR | RTR-GL | GL | Deloitte |  |  | Ian/Vitaliy | [7 empty] | W2 | User Stories - Approval - GL Batch 1
CSTONE-5326 | CSTONE-525 |  |  | CSTONE-525 | RTR-GL-040 |  | Record to Report | Manage General Ledger Accounting | Perform Allocations | As a GL Accountant Financial Systems Analyst, I need the ability to use wizard to select source, Range, Target, Offset, Exclude, Basis details |  |  | Phase 1A+1B | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Allocation Wizard is available while defining the allocation to select source, Range, Target, Offset, Exclude, Basis details. Defining a rule, the user can define a run-time prompt (RTP) variable. An RTP variable is an optional component of a rule. When the user generates an allocation based on a rule with an RTP variable, the user is prompted at run-time to specify a dimension member for which an RTPhas been defined to use in the allocation calculation. A Point of View is used to define dimension values that remain fixed throughout the entire allocation rule. | Used allocation wizard to create allocation rules so as to achieve allocation outcome by inputing source, range, target, offset, exclude and basis criterias. |  |  |  | Approved | Erica | 2021-05-14 |  |  |  | RTR | RTR-GL | GL | Deloitte |  |  | Ian/Vitaliy | [7 empty] | W2 | User Stories - Approval - GL Batch 1
CSTONE-5327 | CSTONE-526 |  |  | CSTONE-526 | RTR-GL-041 |  | Record to Report | Manage General Ledger Accounting | Perform Allocations | As a GL Accountant Financial Systems Analyst, I want the ability to correct allocation formula as required so that I can ensure that they are accurate |  |  | Phase 1A+1B | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Allocations can be edited from Allocation manager. Once the update is complete , it is mandatory to validate and deploy the allocation for it adhere the changes | Able to update allocation formula. Once updated, review results. |  |  |  | Approved | Erica | 2021-05-14 |  |  |  | RTR | RTR-GL | GL | Deloitte |  |  | Ian/Vitaliy | [7 empty] | W2 | User Stories - Approval - GL Batch 1
CSTONE-5328 | CSTONE-527 |  |  | CSTONE-527 | RTR-GL-042 |  | Record to Report | Manage General Ledger Accounting | Perform Allocations | As a GL Accountant, I want to be able to run validation and deploy the rules so that accuracy is ensured |  |  | Phase 1A+1B | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | All allocation rules are required to be Validated and Deploy using validate and deployed icon respectively. Only then the allocation will be active for use | Run validation and deployment prior to allocation being active. Once completed execute allocation. |  |  |  | Approved | Erica | 2021-05-14 |  |  |  | RTR | RTR-GL | GL | Deloitte |  |  | Ian/Vitaliy | [7 empty] | W2 | User Stories - Approval - GL Batch 1
CSTONE-5329 | CSTONE-672 |  |  | CSTONE-672 | RTR-GL-043 |  | Record to Report | Manage General Ledger Accounting | Perform Currency Revaluations | As a GL Accountant, I need the ability to request for update of revaluation definition (Add/remove accounts to be revalued) so that all changes are included in that |  |  | Phase 1A+1B | 6-Gap-Work Around-Work Around | Gap | Work Around | Work Around |  | This would be achieved by offline review and approval process | Review the revaluation definitions as per business design Validate that revaluation has run on all required accounts |  |  |  | Approved | Erica | 2021-05-14 |  |  |  | RTR | RTR-GL | GL | Deloitte |  |  | Ian/Vitaliy | [7 empty] | W2 | User Stories - Approval - GL Batch 1
CSTONE-5330 | CSTONE-673 |  |  | CSTONE-673 | RTR-GL-044 |  | Record to Report | Manage General Ledger Accounting | Perform Currency Revaluations | As a GL Manager, I need the ability to review request for change of revaluation (Add/remove accounts to be revalued) so that nothing is implemented before the review |  |  | Phase 1A+1B | 6-Gap-Work Around-Work Around | Gap | Work Around | Work Around |  | This would be achieved by offline review and approval process | Review the revaluation definitions as per business design Validate that revaluation has run on all required accounts |  |  |  | Approved | Erica | 2021-05-14 |  |  |  | RTR | RTR-GL | GL | Deloitte |  |  | Ian/Vitaliy | [7 empty] | W2 | User Stories - Approval - GL Batch 1
CSTONE-5331 | CSTONE-528 |  |  | CSTONE-528 | RTR-GL-045 |  | Record to Report | Manage General Ledger Accounting | Perform Currency Revaluations | As a GL Accountant Financial Systems Analyst, I want to be able to configure, modify and apply the revaluation criteria so that I can ensure timely and accurate revaluation of the applicable accounts |  |  | Phase 1A+1B | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Revaluation rules can be updated on need basis | Configure revaluation per busness design. Validate that revaluation was calculated and posted correctly in the ledger. |  |  |  | Approved | Erica | 2021-05-14 |  |  |  | RTR | RTR-GL | GL | Deloitte |  |  | Ian/Vitaliy | [7 empty] | W2 | User Stories - Approval - GL Batch 1
CSTONE-5332 | CSTONE-529 |  |  | CSTONE-529 | RTR-GL-046 |  | Record to Report | Manage General Ledger Accounting | Perform Currency Revaluations | As a GL Accountant Financial Systems Analyst, want to be able to run foreign currency revaluations and record revaluation gain/loss so that foreign currency account balances are revalued accurately at the defined COA level |  |  | Phase 1A+1B | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Run Revaluation, gain loss account will be picked from configured revaluation rules. Run a given revaluation template by Ledger Set. Revaluation template consists of accounts being revalued and rate type to be used etc. If multiple templates are required due to specific requirements, run each revaluation template by ledger set. Ledger set cannot span ledgers with different COA or calendar. Hence some secondary ledgers will need separate revaluation execution For acceptance criteria 1: Revaluation can be executed multiple times. Subsequent runs will create additional incremental revaluation journals leading to muliple journal entries. All multiple run revals will reverse in next month. Essentially multiple runs of revals do not impact correctness of data, but impact number of journal entries created. Also reval will need last calendar day's rate to be available for month being revalued as per KDD3A | Run revaluation and post to offset revaluation gain/loss. Revaluation should run frequently during close period as multiple entries are being posted. Review and validate results of revaluation |  |  |  | Approved | Erica | 2021-05-14 |  |  |  | RTR | RTR-GL | GL | Deloitte |  |  | Ian/Vitaliy | [7 empty] | W2 | User Stories - Approval - GL Batch 1
CSTONE-5333 |  |  |  | N/A | RTR-GL-047 |  | Record to Report | Manage General Ledger Accounting | Perform Currency Revaluations | As a GL Accountant Financial Systems Analyst, want to be able to run foreign currency revaluations and record revaluation gain/loss so that foreign currency account balances are revalued accurately at branch level |  |  | Not Required | 10-Not Required-Not Required-Not Required | Not Required | Not Required | Not Required |  | Assuming Branch is a segment in COA structure, Revaluation label will be assigned and optional feature of multiple segment revaluation tracking will be enabled to track revaluation at LE and Branch level Marked as not required as duplicate of RTR-GL-046 |  |  |  |  | Approved | Erica | 2021-05-14 |  |  |  | RTR | RTR-GL | GL | Deloitte | [10 empty] | W2 | User Stories - Approval - GL Batch 1
CSTONE-5334 | CSTONE-530 |  |  | CSTONE-530 | RTR-GL-048 |  | Record to Report | Manage General Ledger Accounting | Perform Currency Revaluations | As a GL Accountant, I need the ability to review revaluation journals so that I can determine whether they are accurately generated |  |  | Phase 1A+1B | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Use the Revaluation Execution Report to review the status of your account revaluation. General Ledger automatically generates this report when you run revaluation. Can also use Journal Entry report | Review revaluation results to ensure accuracy. |  |  |  | Approved | Erica | 2021-05-14 |  |  |  | RTR | RTR-GL | GL | Deloitte |  |  | Ian/Vitaliy | [7 empty] | W2 | User Stories - Approval - GL Batch 1
CSTONE-5335 | CSTONE-531 |  |  | CSTONE-531 | RTR-GL-049 |  | Record to Report | Manage General Ledger Accounting | Perform Currency Revaluations | As a GL Accountant Financial Systems Analyst, I want to be able to configure revaluation as per statutory regulations so that I can ensure accurate revaluation results and gain/loss calculations |  |  | Phase 1A+1B | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Configure revaluation rules & rate types as per need. Rate types to be configured as per approved KDD For acceptance criteria 1: Revaluation template is for a COA structure. Reval templates created for global COA will also be available for secondary ledger having global COA . While executing revaluation select appropriate ledger set for which reval template is applicable | Configure revaluation in primary ledger based on business design. Configure revaluation in secondary ledger based on business design. Review results |  |  |  | Approved | Erica | 2021-05-14 |  |  |  | RTR | RTR-GL | GL | Deloitte |  |  | Ian/Vitaliy | [7 empty] | W2 | User Stories - Approval - GL Batch 1
CSTONE-5336 | CSTONE-561 |  |  | CSTONE-561 | RTR-GL-050 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | As a GL Manager, I want to be able to establish a period closing schedule so that I can have an efficient period closing |  |  | Phase 1A+1B | 6-Gap-Work Around-Work Around | Gap | Work Around | Work Around |  | This has to be agreed upon and schedule to be maintained outside the ERP | Review and approve period closing schedule offline. |  |  |  | Approved | Erica | 2021-05-14 |  |  |  | RTR | RTR-GL | GL | Deloitte |  |  | Ian/Vitaliy | [7 empty] | W2 | User Stories - Approval - GL Batch 1
CSTONE-5337 |  |  |  | N/A | RTR-GL-051 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | As a GL Accountant Financial Systems Analyst, I want to be able to initiate the month close so that I can have a smooth period closing |  |  | Future Phase | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope |  | Period opening and closing is by ledger in GL, AP, AR. FA close is by books. Moved user story to future phase [Out of scope] based on acceptnance criteria 1 & Erica's question "Also unsure why this is a user story?" | Move user story to future subledger implementations. |  |  |  | Approved | Erica | 2021-05-14 |  |  |  | RTR | RTR-GL | GL | Deloitte |  |  | Ian/Vitaliy | [7 empty] | W2 | User Stories - Approval - GL Batch 1
CSTONE-5338 |  |  |  | N/A | RTR-GL-052 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | As a GL Accountant, I want to be able to view the subledger period closing status so that I can follow up to expedite the close |  |  | Future Phase | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope |  | Gl Period Close Dashboard gives an overall view of period close activity for both GL and subledgers. Navigate to the Close Monitor by clicking the Open Subledgers info let on the General Accounting Info lets page, or by selecting the Close Monitor task from the Period Close work area. Updated status to Out of Scope to move it to future phase as it pertains to Subledger close |  |  |  |  | Approved | Erica | 2021-05-14 |  |  |  | RTR | RTR-GL | GL | Deloitte | [8 empty] | Will be updated during phase 1B discussions |  | W2 | User Stories - Approval - GL Batch 1
CSTONE-5339 |  |  |  | N/A | RTR-GL-053 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | As a GL Accountant, I want to be able to reconcile GL balance with subledger account balance so that I can tie up their balances. |  |  | Not Required | 10-Not Required-Not Required-Not Required | Not Required | Not Required | Not Required |  | Need to add relevant reports (may be more than one) for GL to AHCS reconciliation Reconciliation Tools exist in Oracle Cloud AR and AP Note: Marked as Not Required as relevant user stories as discussed in AHCS workshops as per recon approach being aligned in KDD6A and KDD6B will be added | Review the GL to AHCS reconciliation report. Identify cause of variance. Resolve variance. Review results once corrected. | Ability to reconcile four levels: (1) HUB to Subledger, (2) HUB to Cloud, (3) HUB to EBS/Peoplesoft, (4) EBS/PS to Subledger. |  |  | Approved | Erica | 2021-05-14 |  |  |  | RTR | RTR-GL | GL | Deloitte |  |  | Ian/Vitaliy | [6 empty] | Note: Marked as Not Required as relevant user stories as discussed in AHCS workshops as per recon approach being aligned in KDD6A and KDD6B will be added | W2 | User Stories - Approval - GL Batch 1
CSTONE-5340 | CSTONE-532 |  |  | CSTONE-532 | RTR-GL-054 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | As a GL Accountant, I want to be able to make sure all the journal entries are posted so that I can experience an error free period closing |  |  | Phase 1A+1B | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Unposted Journals can be queried from Manual journal entries screen with status unposted. More over , one of the mandatory Period end report i.e. Subledger exception report will show case subledger transactions are in error state or incase have not been posted to GL | Review all journals that are not posted via report. |  |  |  | Approved | Erica | 2021-05-14 |  |  |  | RTR | RTR-GL | GL | Deloitte |  |  | Ian/Vitaliy | [7 empty] | W2 | User Stories - Approval - GL Batch 1
CSTONE-5341 | CSTONE-533 |  |  | CSTONE-533 | RTR-GL-055 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | As a GL Manager Financial Systems Analyst, I want to be able to perform period closing for each ledger so that I can experience an efficient and smooth period closing |  |  | Phase 1A+1B | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Period closing is performed at Ledger level and has to be performed for every ledger. You can use ledger set to close multiple ledgers in one go | Use the defined ledger sets to close all primary ledgers. |  |  |  | Approved | Erica | 2021-05-14 |  |  |  | RTR | RTR-GL | GL | Deloitte |  |  | Ian/Vitaliy | [7 empty] | W2 | User Stories - Approval - GL Batch 1
CSTONE-5342 | CSTONE-534 |  |  | CSTONE-534 | RTR-GL-056 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | As a GL Manager, I want to be able to reuse search criteria on the inquire on detail balances page so that I am able to retrieve account balances quickly and efficiently |  |  | Phase 1A+1B | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Search criteria can be saved | Use the saved search criteria to view results. |  |  |  | Approved | Erica | 2021-05-14 |  |  |  | RTR | RTR-GL | GL | Deloitte |  |  | Ian/Vitaliy | [7 empty] | W2 | User Stories - Approval - GL Batch 1
CSTONE-5343 | CSTONE-5104 |  |  | CSTONE-5104 | RTR-GL-057 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | As a GL Accountant, I want to be able to run and review preliminary reports in the secondary ledger so that I can verify the accuracy of the accounts |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Seeded GL reports will be operational for Secondary Ledger as well. Custom reports in lean specs conversations can be required to be made available for secondary. Assumption is as part of this user story there is no specific report being requested | Review seeded GL reports. Ensure secondary ledger data is available, complete and accurate in the reports. Review custom reports built. Ensure secondary ledger data is available(if needed for secondary ledger per business design). Validate accuracy and completeness of custom report. |  |  | Sprint 7 | Approved | Erica | 2021-07-11 |  | #REF! |  | RTR | RTR-GL | GL | Deloitte |  |  | Ian/Vitaliy |  | Bhim | [5 empty] | N/A for 1A | RTR-GL Batch 6 - GPO Approval Requested
CSTONE-5344 | CSTONE-5101 |  |  | CSTONE-5101 | RTR-GL-058 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | As a GL Manager Financial Systems Analyst, I want to be able to close the period in the secondary ledger so that no further entries can be posted. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | This depends on the security roles provided to user.Once period is closed no journals can be posted to the journal | Successfully closed period in secondary ledger. Verify that no journals can be posted in the close period. Validate ability to close primary ledger but keep secondary ledger open. Validate journals can be posted only to the secondary ledger and not the primary ledger. |  |  | Sprint 7 | Approved | Erica | 2021-07-11 |  | #REF! |  | RTR | RTR-GL | GL | Deloitte |  |  | Ian/Vitaliy |  | Bhim | [5 empty] | N/A for 1A | User Stories - GL Batch 6 GPO Approval
CSTONE-5345 | CSTONE-5100 |  |  | CSTONE-5100 | RTR-GL-059 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | As a GL Manager, Financial Systems Analyst, I want to be able to open the period in the secondary ledger so that transactions can flow into it from the primary ledger. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | This depends on the security roles provided to user | Successfully opened the period for the secondary ledger. |  |  | Sprint 7 | Approved | Erica | 2021-07-11 |  | #REF! |  | RTR | RTR-GL | GL | Deloitte |  |  | Ian/Vitaliy | [7 empty] | N/A for 1A | User Stories - GL Batch 6 GPO Approval
CSTONE-5346 | CSTONE-5106 |  |  | CSTONE-5106 | RTR-GL-060 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | As a GL Accountant, I want to be able to generate reversal entries in secondary ledger after opening new period so that any journal not reversed in secondary ledger is taken care of |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Create auto-reversing journals to enter adjustments that you want to reverse in the next period. Synchronize reversals between primary and secondary will be enabled i.e. journals that are copied from primary and reversed in primary, will also reverse in secondary Acceptance criteria 1: Note that in current ent structure design all secondary ledger functional currencies are same as primary ledger functional currencies & hence "Ensure the entered and accounted currency exchange matches the original journal." from acceptance criteria is valid | Validate that reversal journals posted in primary ledger also posted in secondary ledger. Ensure the entered and accounted currency exchange matches the original journal. Validate that the reversing journal posted only in secondary ledger reverses only in the secondary ledger (validate entered and accounted currency). |  |  | Sprint 7 | Approved | Erica | 2021-07-11 |  | #REF! |  | RTR | RTR-GL | GL | Deloitte |  |  | Ian/Vitaliy | [7 empty] | N/A for 1A | User Stories - GL Batch 6 GPO Approval
CSTONE-5347 | CSTONE-89 |  |  | CSTONE-89 | RTR-GL-061 |  | Record to Report | Manage General Ledger Accounting | Approve and Post Journal Entries | As a GL Manager, I want to be able to verify and see the error message in journal spreadsheet so that the reason for the failure when journals are created using the ADFdi Create Journals spreadsheet and some transactions fail can be tracked and corrected accordingly. |  |  | Phase 1A+1B | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | When upload fails, Create Journal ADFDI shows error. If upload is successful but improt fails, journal Interface captures all errors encountered. System allows users to review and correct those journals by downloading the error record sheet | Identify any journal uploads that failed. Identify the source of the error. In addition correct them and resubmit the entry. Validate journal after posted. |  |  |  | Approved | Erica | 2021-05-07 |  |  |  | RTR | RTR-GL | GL | Deloitte |  |  | Ian/Vitaliy | [7 empty] | W1 | User Stories - Approval - GL Batch 1
CSTONE-5348 | CSTONE-535 |  |  | CSTONE-535 | RTR-GL-062 |  | Record to Report | Manage General Ledger Accounting | Maintain Chart of Accounts | As GL Administrator Financial Systems Analyst I want to create and manage multiple legal entities and assign the company code as the balancing segment so that I can ensure proper legal entity accounting & reporting |  |  | Phase 1A+1B | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Setup Legal Entities from Manage Legal Entities using manual or rapid method. Assign BSV's as a part of configuration finalization. Pending COA design finalization | Created balancing segments for multiple LE's. Validate that all LE's have been setup per business design. | Validate applicable intercompany balancing rules. Validate new legal entity and related BSVs with a test journal followed by reversal. Validate CVR and data access rules. Validate applicable reports. |  |  | Approved | Erica | 2021-05-07 |  |  |  | RTR | RTR-GL | GL | Deloitte |  |  | Ian/Vitaliy | [7 empty] | W1 | User Stories - Approval - GL Batch 1
CSTONE-5349 | CSTONE-536 |  |  | CSTONE-536 | RTR-GL-063 |  | Record to Report | Manage General Ledger Accounting | Maintain Chart of Accounts | As a GL Accountant Financial Systems Analyst, I want to be able to define multiple ledgers so that various statutory and management reporting requirements are supported |  |  | Phase 1A+1B | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | This will be based on KDD for Enterprise Structure . System allows you to create various ledgers for US GAAP and LOCAL GAAP reporting For Acceptance Criteria 2, security track to add user stories and validate roles / access | Create ledgers based on country, currency combination for primary and secondary ledgers, Validate ledger setup as per business design. | Validate data access rules and defined roles. Validate applicable reports. |  |  | Approved | Erica | 2021-05-07 |  |  |  | RTR | RTR-GL | GL | Deloitte |  |  | Ian/Vitaliy | [7 empty] | W1 | User Stories - Approval - GL Batch 1
CSTONE-5350 | CSTONE-5113 |  |  | CSTONE-5113 | RTR-GL-064 |  | Record to Report | Manage General Ledger Accounting | Maintain Chart of Accounts | As a GL Manager Financial Systems Analyst, I want to be able to maintain flexible and multiple accounting calendars so that I am able to cater for statutory reporting requirements |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Create Alternative calendar (different from US GAAP) and assign it to Secondary Ledger as per LOCAL GAAP reporting requirement For acceptance criteria 1: As per approved KDD on Ent Structure for phase 1 there is no separate calendar for any secondary ledgers | Maintained Accounting calendar in both primary and secondary ledger |  |  | Sprint 7 | Approved | Erica | 2021-05-04 |  | #REF! |  | RTR | RTR-GL | GL | Deloitte |  |  | Ian/Vitaliy | [7 empty] | W1 | User Stories - Approval - GL Batch 1
CSTONE-5351 | CSTONE-537 |  |  | CSTONE-537 | RTR-GL-065 |  | Record to Report | Manage General Ledger Accounting | Maintain Chart of Accounts | As GL Manager Financial Systems Analyst, I need the ability to validate enterprise structure before loading it into the system so that I can be sure that system expectations are met correctly. |  |  | Phase 1A+1B | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Define Enterprise Structure as per approved KDD. Review Config documents prior to configurations in system as part of program governance process. Use various testing cycles prior to production to confirm Ent Structure config | Review and sign off on enterprise structure | Validate test / prod instances |  |  | Approved | Erica | 2021-05-04 |  |  |  | RTR | RTR-GL | GL | Deloitte |  |  | Ian/Vitaliy | [7 empty] | W1 | User Stories - Approval - GL Batch 1
CSTONE-5352 | CSTONE-5114 |  |  | CSTONE-5114 | RTR-GL-066 |  | Record to Report | Manage General Ledger Accounting | Maintain Chart of Accounts | As GL Manager Financial Systems Analyst, I want to ensure the system facilitates the addition of a new entity with an existing or a different chart of accounts so that to I can support future growth |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Create new primary or secondary ledger with different COA, Currency, Calendar and accounting standards as per requirement. Design COA value size and ranges with future expansion scope in consideration | Review secondary ledger for France which contains alternate chart of accounts. Ensure chart of accounts are compliant with local requirements. |  |  | Sprint 7 | Approved | Erica | 2021-05-04 |  | #REF! |  | RTR | RTR-GL | GL | Deloitte |  |  | Ian/Vitaliy | [7 empty] | W1 | User Stories - Approval - GL Batch 1
CSTONE-5353 | CSTONE-90 |  |  | CSTONE-90 | RTR-GL-067 |  | Record to Report | Manage General Ledger Accounting | Approve and Post Journal Entries | As a GL Manager Financial Systems Analyst, I want to be able to post 24/7 to the general ledger for efficient journal processing |  |  | Phase 1A+1B | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Users with posting access can post anytime. Schedule AutoPost Acceptance criteria 1: Oracle allows posting only to open periods | Post/upload via spreadsheet. Validate posted entry. |  |  |  | Approved | Erica | 2021-05-04 |  |  |  | RTR | RTR-GL | GL | Deloitte |  |  | Ian/Vitaliy | [7 empty] | W1 | User Stories - Approval - GL Batch 1
CSTONE-5354 | CSTONE-91 |  |  | CSTONE-91 | RTR-GL-068 |  | Record to Report | Manage General Ledger Accounting | Approve and Post Journal Entries | As a GL Manager, I want to be able to restrict updates to posted journals for accurate balances and appropriate audit trail. |  |  | Phase 1A+1B | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | System does not allow to edit posted journal | Once entry has posted, system should not allow user to modify the entry. |  |  |  | Approved | Erica | 2021-05-04 |  |  |  | RTR | RTR-GL | GL | Deloitte |  |  | Ian/Vitaliy | [7 empty] | W1 | User Stories - Approval - GL Batch 1
CSTONE-5355 | CSTONE-92 |  |  | CSTONE-92 | RTR-GL-069 |  | Record to Report | Manage General Ledger Accounting | Process Reversing Journal Entries | As a GL Accountant, I want to be able to copy journal entries and to reverse signs switch debit/credit or ability to automatically reverse a journal entry to make the journal process more accurate and efficient |  |  | Phase 1A+1B | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Use Accrual category to reverse next month (auto-reverse) or manually reverse the journal in manage journal page. Enter reversal period and reverse. User can also manually reverse by loading a new journal entry | Reverse journal by reversing debits and credits. Validate that reversed following month. |  |  |  | Approved | Erica | 2021-05-12 |  |  |  | RTR | RTR-GL | GL | Deloitte |  |  | Ian/Vitaliy | [7 empty] | W1 | User Stories - Approval - GL Batch 1
CSTONE-5356 | CSTONE-93 |  |  | CSTONE-93 | RTR-GL-070 |  | Record to Report | Manage General Ledger Accounting | Process Manual Journal Entries | As a GL Accountant, I want to be able to create transactions in future periods (e.g., reversing entries) so that I can timely capture future journal entries |  |  | Phase 1A+1B | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | 1 future open period is planned. Entries can be booked to it but not posted. Use Accrual category for entries reversing in next period. If for some type of accruals reversals are not required than need to create different accrual categories in Oracle and non-reversing journal should be booked on this category | Create transaction in the available future period. Validate once entry has posted. |  |  |  | Approved | Erica | 2021-05-07 |  |  |  | RTR | RTR-GL | GL | Deloitte |  |  | Ian/Vitaliy | [7 empty] | W1 | User Stories - Approval - GL Batch 1
CSTONE-5357 | CSTONE-94 |  |  | CSTONE-94 | RTR-GL-071 |  | Record to Report | Manage General Ledger Accounting | Process Manual Journal Entries | As a GL Manager , I want to be able to access multiple ledgers within Journal entry and other pages for quick transaction entry and reporting purposes |  |  | Phase 1A+1B | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Data access security - part of security design | Access and review multiple ledgers sets & validate security setup based on business design |  |  |  | Approved | Erica | 2021-05-04 |  |  |  | RTR | RTR-GL | GL | Deloitte |  |  | Ian/Vitaliy | [7 empty] | W1 | User Stories - Approval - GL Batch 1
CSTONE-5358 | CSTONE-95 |  |  | CSTONE-95 | RTR-GL-072 |  | Record to Report | Manage General Ledger Accounting | Process Manual Journal Entries | As a GL Manager, I want to be able to record statistical journal entries with no offset(i.e. on side statistical journal entries) in order to capture and maintain non-monetary metrics and also to leverage these for allocation purposes |  |  | Phase 1A+1B | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Book journal in STAT currency | Book stat entries in stat currency which may not balance. Validate posted entry. |  |  |  | Approved | Erica | 2021-05-07 |  |  |  | RTR | RTR-GL | GL | Deloitte |  |  | Ian/Vitaliy | [7 empty] | W1 | User Stories - Approval - GL Batch 1
CSTONE-5359 | CSTONE-96 |  |  | CSTONE-96 | RTR-GL-073 |  | Record to Report | Manage General Ledger Accounting | Process Manual Journal Entries | As a GL Manager , I want to be able to maintain primary ledgers and secondary ledgers for US GAAP and local regulatory reporting by country and currency |  |  | Phase 1A+1B | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Define Enterprise Structure as per approved KDD | Validate required primary and secondary ledgers have been created in the system by country and currency. Per business design. |  |  |  | Approved | Erica | 2021-05-12 |  |  |  | RTR | RTR-GL | GL | Deloitte |  |  | Ian/Vitaliy | [7 empty] | W1 | User Stories - Approval - GL Batch 1
CSTONE-5360 |  |  |  | N/A | RTR-GL-074 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | As an accountant, I will need to have availability to both IDR secondary ledger for Indonesia and USD reporting ledger generation from the IDR secondary ledger. These ledgers will need to be available once ERP modules such as AR/AP and Inv are enabled in Oracle cloud. These new ledger will be used for statutory reporting. |  |  | Future Phase | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | [6 empty] | Approved | Erica | 2021-05-14 |  |  |  | RTR | RTR-GL | GL | WESCO | [8 empty] | Will be updated during phase 1B discussions |  | W2 | User Stories - Approval - GL Batch 1
CSTONE-5361 | CSTONE-1358 | CSTONE-3630 | CSTONE-3653 | CSTONE-3653 | RTR-GL-075 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | As an accountant, I need a Journal approval audit compliance report that pulls 1. Journals with negative dr or cr 2. Journals where created by = final approver 3. Journals where first stage and 2nd stage approver are same |  |  | Phase 1A+1B | 2-Gap-Build-Report | Gap | Build | Report | RPT005 | Custom report based GL_JE_ACTION_LOG & GL_JE_BATCHES table | Review results of report to ensure accuracy. | KDD4 Report to identify (1) batches with negative DR and negative CR, (2) journals whose created by = final approver, (3) journals where step 1 approver = step 2 approver. Validate report by testing all three scenarios. |  |  | Approved | Erica | 2021-05-14 |  |  |  | RTR | RTR-GL | GL | WESCO |  |  | Ian/Vitaliy | [7 empty] | W2 | User Stories - Approval - GL Batch 1
CSTONE-5362 | CSTONE-11743 | CSTONE-9640 | CSTONE-9719 | Sprint 12 | RTR-GL-076 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | As an accountant, I need to be able to create FEC reporting |  |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report | RPT026 | Custom report to be built for FEC report. Confirm if standard report does not meet requirement as part of lean spec design | Review results of report to ensure accuracy. |  |  | Sprint 12 | Approved | Erica | 2021-07-11 |  | #REF! |  | RTR | RTR-GL | GL | Deloitte |  |  | Ian/Vitaliy | [7 empty] | N/A for 1A | User Stories - GL Batch 6 GPO Approval
CSTONE-5363 | CSTONE-584 | CSTONE-3631 | CSTONE-3654 | CSTONE-3654 | RTR-GL-077 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | As an accountant, I need a report which can bring GL journal and SLA journal line details together in a single output |  |  | Phase 1A+1B | 2-Gap-Build-Report | Gap | Build | Report | RPT009 | Custom report to bring GL and SLA details together. This report will not go to seeded subledger tables, but will only pull details avaiable in GL and SLA tables | Review results of report to ensure accuracy. |  |  |  | Approved | Erica | 2021-05-14 |  |  |  | RTR | RTR-GL | GL | Deloitte |  |  | Ian/Vitaliy | [7 empty] | W2 | User Stories - Approval - GL Batch 1
CSTONE-5364 | CSTONE-538 |  |  | CSTONE-538 | RTR-GL-078 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | As an accountant, I want to make sure journal entries from subledger cannot be edited |  |  | Phase 1A+1B | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Enable Freeze flag on subledger source | review that 'Freeze' flag was enabled on subledger source | Validate subledger source journals cannot be edited, reversed, unapproved, etc. |  |  | Approved | Erica | 2021-05-14 |  |  |  | RTR | RTR-GL | GL | Deloitte |  |  | Ian/Vitaliy | [7 empty] | W2 | User Stories - Approval - GL Batch 1
CSTONE-5365 | CSTONE-97 |  |  | CSTONE-97 | RTR-GL-079 |  | Record to Report | Manage General Ledger Accounting | Process Manual Journal Entries | As an accountant, I need ability to categorize journal entries |  |  | Phase 1A+1B | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Create journal categories as per requirement to categorize journals. Assign journal category to them. AHCS journal entry will have one unique category per AHCS subledger | Review available journal categories to ensure they align with business design. Validate category within the posted journal. |  |  |  | Approved | Erica | 2021-05-12 |  |  |  | RTR | RTR-GL | GL | Deloitte |  |  | Ian/Vitaliy | [7 empty] | W1 | User Stories - Approval - GL Batch 1
CSTONE-5366 |  |  |  | N/A | RTR-GL-080 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | As a statutory accountant, I need ability to sequence my GL and Subledger journals by Source / Category |  |  | Not Required | 10-Not Required-Not Required-Not Required | Not Required | Not Required | Not Required |  | As per confirmation from International team separate sequencing by source/category is not required. Lowest level of sequencing is LE. Dispositioned as Not Required user story | Review sequencing in GL and subledger to ensure compliance with local requirments |  |  |  | Approved | Erica | 2021-07-11 |  |  |  | RTR | RTR-GL | GL | Deloitte | [10 empty] | N/A for 1A | User Stories - GL Batch 6 GPO Approval
CSTONE-5367 |  |  |  | N/A | RTR-GL-081 |  | Record to Report | Manage General Ledger Accounting | Maintain Chart of Accounts | As a GL administrator, I need to minimize need to create code combinations manually by allowing users to create them subject to accounting policies that govern usage of values in one segment with values in other segment |  |  | Not Required | 10-Not Required-Not Required-Not Required | Not Required | Not Required | Not Required |  | Before strike-through: Enable dynamic inserts, configure CVRs as per accounting policies to govern cross segment value usage. CVRs will be enable during conversion cycles as well to avoid creation of code combination and subsequent cleanup due to data conversion process. Data violating accounting policy must be cleaned up in legacy system prior to conversion After strike through: This is no longer required as business has strike-through user story i.e. not required |  |  |  |  | Approved | Erica | 2021-05-12 |  |  |  | RTR | RTR-GL | GL | Deloitte |  |  | Ian/Vitaliy | [7 empty] | W1 | User Stories - Approval - GL Batch 1
CSTONE-5368 | CSTONE-98 |  |  | CSTONE-98 | RTR-GL-082 |  | Record to Report | Manage General Ledger Accounting | Process Manual Journal Entries | As a GL accountant, I should have ability to create journal entries in various currencies |  |  | Phase 1A+1B | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Enable currencies as per requirement [In upgrade, as part of regression validate any new currency being enabled]. Currency precision to be set to ISO precision | Book journal entries in various foreign currencies as well as functional currencies. Validate posted journal. |  |  |  | Approved | Erica | 2021-05-04 |  |  |  | RTR | RTR-GL | GL | Deloitte |  |  | Ian/Vitaliy | [7 empty] | W1 | User Stories - Approval - GL Batch 1
CSTONE-5369 | CSTONE-99 |  |  | CSTONE-99 | RTR-GL-083 |  | Record to Report | Manage General Ledger Accounting | Process Manual Journal Entries | As a GL accountant, I need ability to book USGAAP only entries which do not copy to local GAAP ledgers |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Create Journal category & at ledger level turn off its copy to secondary ledger | Book journal in primary ledger that did not copy to secondary ledger. Validate journal did not post in secondary ledger. Also book a journal in the secondary ledger that did not copy to the primary ledger. Validate that journal did not post to the primary ledger. |  |  | Sprint 7 | Approved | Erica | 2021-05-12 |  | #REF! |  | RTR | RTR-GL | GL | Deloitte |  |  | Ian/Vitaliy | [7 empty] | W1 | User Stories - Approval - GL Batch 1
CSTONE-5370 |  |  |  | N/A | RTR-GL-084 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | As a GL administrator, I need ability to close multiple ledgers |  |  | Not Required | 10-Not Required-Not Required-Not Required | Not Required | Not Required | Not Required |  | Design ledger set as required groupings. Use ledger sets to close / open periods, execute revaluation. Marked as not required as Reference RTR-GL-055 which captures this user story | Delete user story, already exists. |  |  |  | Approved | Erica | 2021-05-14 |  |  |  | RTR | RTR-GL | GL | Deloitte |  |  | Ian/Vitaliy | [7 empty] | W2 | User Stories - Approval - GL Batch 1
CSTONE-5371 | CSTONE-100 |  |  | CSTONE-100 | RTR-GL-085 |  | Record to Report | Manage General Ledger Accounting | Process Manual Journal Entries | As a GL accountant, I need ability to book journal entries in foreign currency using daily exchange rates OR month end or month average rates or central bank rates |  |  | Phase 1A+1B | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Design rate types as per KDD3A Clarification on Acceptance Criteria 2 from Erica - User Rate pertains to rate type of 'User' and rate entered by user manually | Book journal entries in various foreign currencies as well as functional currencies using daily,monthly, average or central bank rates. Validate journal after posted. | Add user rate to support bank rates specific to transaction / journal. |  |  | Approved | Erica | 2021-05-12 |  |  |  | RTR | RTR-GL | GL | Deloitte |  |  | Ian/Vitaliy | [7 empty] | W1 | User Stories - Approval - GL Batch 1
CSTONE-5372 | CSTONE-539 |  |  | CSTONE-539 | RTR-GL-086 |  | Record to Report | Manage General Ledger Accounting | Process Manual Journal Entries | As a GL administrator, I need ability to automate exchange rate load process |  |  | Phase 1A+1B | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Implement exchange rate integration as per KDD3B. Since FXLoader will be loading rates automatically as per KDD3A & also doing any computations required for cross-currency, this is marked as Fit as there is no integration to be buitl | Exchange rates have been loaded automatically. Validate rates are correctly reflected in the system. |  |  |  | Approved | Erica | 2021-05-14 |  |  |  | RTR | RTR-GL | GL | Deloitte |  |  | Ian/Vitaliy | [7 empty] | W1 | User Stories - Approval - GL Batch 1
CSTONE-5373 | CSTONE-540 |  |  | CSTONE-540 | RTR-GL-087 |  | Record to Report | Manage General Ledger Accounting | Perform Currency Revaluations | As GL Accountant, I would like to build consistent revaluation rules to align with accounting policies of WESCO [combined legacy WESCO and legacy Anixter]. As a Financial Systems Analyst, I would like the revaluation to be generated and posted in the ledger to specified COA determined in the business design. |  |  | Phase 1A+1B | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Common revaluation template to be built Assumption: COA account mapping from legacy COA supports consistent revaluation templates | Reviewed the revaluation rules to ensure accounts revalued aligned with the business design. |  |  |  | Approved | Erica | 2021-05-14 |  |  |  | RTR | RTR-GL | GL | Deloitte |  |  | Ian/Vitaliy | [7 empty] | W2 | User Stories - Approval - GL Batch 1
CSTONE-5374 |  |  |  | N/A | RTR-GL-088 |  | Record to Report | Manage General Ledger Accounting | Perform Allocations | As GL Accountant Financial Systems Analyst, I would like to build consistent allocation rules in system to help allocate costs to align with accounting policies of WESCO [combined legacy WESCO and legacy Anixter] |  |  | Not Required | 10-Not Required-Not Required-Not Required | Not Required | Not Required | Not Required |  | Define rules in Calc Manager as per WESCO accounting requirements 5/14 Not required - Duplicate | Review all allocations that were set up per business design. Validate all allocations posted correctly in ledger. |  |  |  | Approved | Erica | 2021-05-14 |  |  |  | RTR | RTR-GL | GL | Deloitte |  |  | Ian/Vitaliy | [7 empty] | W2 | User Stories - Approval - GL Batch 1
CSTONE-5375 | CSTONE-4682 | CSTONE-562 | Not in Jira | CSTONE-4682 | RTR-GL-089 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | As a GL Accountant IT, I need ability to initialize GL balances when we migrate to new system |  |  | Phase 1A+1B | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV001, CNV003, CNV004, CNV010 | Build GL actual balance conversion as per KDD | Review beginning balance load in new system. Complete reconciliation between Oracle and legacy system. |  |  | Sprint 8 | Approved | Erica | 2021-05-14 |  |  |  | RTR | RTR-GL | GL | Deloitte |  |  | Ian/Vitaliy | [7 empty] | W2 | User Stories - Approval - GL Batch 1
CSTONE-5376 | CSTONE-585 | CSTONE-633 | CSTONE-4265 | CSTONE-4265 | RTR-GL-090 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | As a GL Accountant, I need a GL Trial Balance from which I can drill down to a report that shows GL and Subledger lines together |  |  | Phase 1A+1B | 2-Gap-Build-Report | Gap | Build | Report | RPT041 | Will develop a report that pulls TB in excel. When clicking on amount, it will drill down to GL/SLA report to be built as part of user story RTR-GL-077 | Review results of report to ensure accuracy. |  |  |  | Approved | Erica | 2021-05-14 |  |  |  | RTR | RTR-GL | GL | Deloitte |  |  | Ian/Vitaliy | [7 empty] | W2 | User Stories - Approval - GL Batch 1
CSTONE-5377 | CSTONE-5103 |  |  | CSTONE-5103 | RTR-GL-091 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | As a GL accountant, I need the capability to view all journal entries by a unique indentifier in sequential order |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Journal sequencing will be configured as per aligned sequencing for all USGAAP Ledgers & secondary ledgers. For US & CA sequencing at Ledger level. For rest of world sequencing at LE level. No requirement to sequence by source / category & accordingly impact to AHCS was discussed in AHCS workshops For acceptance criteria 1: Awaiting accounting vs reporting requiremetn confirmation from Patrick | View the reporting sequence for journals in sequential order. |  |  | Sprint 7 | Approved | Erica | 2021-07-11 |  | #REF! |  | RTR | RTR-GL | GL | WESCO |  |  | Ian/Vitaliy | [7 empty] | W2 | User Stories - GL Batch 6 GPO Approval
CSTONE-5378 | CSTONE-103 |  |  | CSTONE-103 | RTR-GL-092 |  | Record to Report | Manage General Ledger Accounting | Process Manual Journal Entries | As a GL accountant, I would like to enter journal with multiple LE's, all lines balanced at LE level. |  |  | Phase 1A+1B | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Use ADFDI spreadsheet with appropriate PBSV values corresponding to various LEs. If entry is balanceed for each LE, Oracle will not add any balancing lines | Review posted journals, there should be no I/C balancing created | Review posted journals, I/C balancing will exist for cross-legal-entity transactions |  |  | Approved | Erica | 2021-05-07 |  |  |  | RTR | RTR-GL | GL | WESCO |  |  | Ian/Vitaliy | [7 empty] | W1 | User Stories - Approval - GL Batch 1
CSTONE-5379 | CSTONE-104 |  |  | CSTONE-104 | RTR-GL-093 |  | Record to Report | Manage General Ledger Accounting | Process Manual Journal Entries | As a GL accountant, I would like to enter journals with multiple LE's, lines not balances at LE level, only balanced in total |  |  | Phase 1A+1B | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Decision for non-US & Canada ledger: Enable sequencing for LE level. LE will be field at header level. If you create journal from front end, you cannot see PBSV for any other LE at line level. If you create journal from spreadsheet, while importing oracle will split journal by LE. IC balancing rules for GL sources will not be enabled for non-US & CA Ledgers Decision for US & Canada ledger: Enable sequencing at Ledger level. IC balancing rules at ledger level will be setup allowing journals that are unbalanced by LE [but balanced in totality] to be created. Acceptance criteria 1: It does not seem to consider US & Canada entities | Journal should not be allowe for international entitiesd. I/C lines should be inserted for US and Canada. |  |  |  | Approved | Erica | 2021-05-12 |  |  |  | RTR | RTR-GL | GL | WESCO |  |  | Ian/Vitaliy | [7 empty] | W1 | User Stories - Approval - GL Batch 1
CSTONE-5380 | CSTONE-105 |  |  | CSTONE-105 | RTR-GL-094 |  | Record to Report | Manage General Ledger Accounting | Process Manual Journal Entries | As a GL accountant, I cannot post journal that do not follow the predetermined CVR rules. |  |  | Phase 1A+1B | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | If Code combination is not already created, JE will be blocked as part of CVR validation If code combination already exists, when a new CVR is being deployed as part of COA maintenance process please ensure to disable code combinations violating CVRs to achieve this user story. Else system will process such journals successfully | Entered journal that does not meet CVR. Ensure journal cannot be posted. |  |  |  | Approved | Erica | 2021-05-04 |  |  |  | RTR | RTR-GL | GL | WESCO |  |  | Ian/Vitaliy | [7 empty] | W1 | User Stories - Approval - GL Batch 1
CSTONE-5381 | CSTONE-3625 | CSTONE-4394 | CSTONE-4412 | CSTONE-4412 | RTR-GL-095 |  | Record to Report | Manage General Ledger Accounting | Process Manual Journal Entries | As a GL Accountant, I want to be able to prevent the posting of manual journal entries to control accounts as a means of ensuring that control accounts reconcile to the applicable subledger |  |  | Phase 1A+1B | 2-Gap-Build-Report | Gap | Build | Report | RPT042 | Oracle cloud allows ability to define COA natural account values as control accounts. These accounts then cannot be posted to from front end in GL. But when using spreadsheet [ADFDI] approach Oracle allows users to select "delay validation" option. In this case Control account validaiton is not performed in spreadsheet. At this point in time Journal Import process does not perform Control account validation i.e. this validaiton will not be performed. Currently ORacle does not allow ability to take away this ability to "delay validations" from users. Hence a custom reprot needs to be built to reivew non subledger source entries hitting control accounts | Entered journal in restricted account. Ensure journal cannot be posted. |  |  |  | Approved | Erica | 2021-05-14 |  |  |  | RTR | RTR-GL | GL | WESCO |  |  | Ian/Vitaliy | [7 empty] | W1 | User Stories - Approval - GL Batch 1
CSTONE-5382 | CSTONE-108 |  |  | CSTONE-108 | RTR-GL-096 |  | Record to Report | Manage General Ledger Accounting | Process Manual Journal Entries | As a GL accountant, I would like to enter a batch with multiple journals in the batch. |  |  | Phase 1A+1B | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | In ADFDI Multiple spreadsheet can be used to enter multiple journals under batch by appropriately populating batch name. ADFDI spreadsheet allows upload within a given Data Access | Successfully entered batch containing multiple JE's. Validate journal after posted. |  |  |  | Approved | Erica | 2021-05-12 |  |  |  | RTR | RTR-GL | GL | WESCO |  |  | Ian/Vitaliy | [7 empty] | W1 | User Stories - Approval - GL Batch 1
CSTONE-5383 | CSTONE-109 |  |  | CSTONE-109 | RTR-GL-097 |  | Record to Report | Manage General Ledger Accounting | Process Manual Journal Entries | As a GL accountant, I should not be able to book journal with category designated to subledger. |  |  | Phase 1A+1B | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Ability to restrict journal categories is currently not available. In 21B release notes functionality to make journal categories unavailable for manual entries is confirmed. We anticipate to use this functionality [have not tested as don’t have a 21B instance yet] & hence marked as Fit based on anticipated functionality meeting this requirement | Entered journal with subledger category(all subledger categories should be tested). Ensure journal cannot be posted. |  |  |  | Approved | Erica | 2021-05-12 |  |  |  | RTR | RTR-GL | GL | WESCO |  |  | Ian/Vitaliy | [7 empty] | W1 | User Stories - Approval - GL Batch 1
CSTONE-5384 | CSTONE-110 |  |  | CSTONE-110 | RTR-GL-098 |  | Record to Report | Manage General Ledger Accounting | Process Manual Journal Entries | As a GL accountant, I cannot post journal in LE I do not have access. |  |  | Phase 1A+1B | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | JE entry is based on Data Access Set | JE was unsuccessful |  |  |  | Approved | Erica | 2021-05-04 |  |  |  | RTR | RTR-GL | GL | WESCO |  |  | Ian/Vitaliy | [7 empty] | W1 | User Stories - Approval - GL Batch 1
CSTONE-5385 | CSTONE-111 |  |  | CSTONE-111 | RTR-GL-099 |  | Record to Report | Manage General Ledger Accounting | Process Manual Journal Entries | As a GL Accountant, I want to be able to enter manual journal entries with two or more journal lines. |  |  | Phase 1A+1B | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | ADFDI or front end approach can be used to create journal entries with multiple lines as required | Successfully entered JE with multiple lines. Validate after posted |  |  |  | Approved | Erica | 2021-05-04 |  |  |  | RTR | RTR-GL | GL | WESCO |  |  | Ian/Vitaliy | [7 empty] | W1 | User Stories - Approval - GL Batch 1
CSTONE-5386 |  |  |  | N/A | RTR-GL-100 |  | Record to Report | Manage General Ledger Accounting | Process Recurring Journal Entries | As a GL Accountant I need the ability to view/identify all recurring entries that have posted or future dated. |  |  | Not Required | 10-Not Required-Not Required-Not Required | Not Required | Not Required | Not Required |  | 5/14 Duplicate as one future period already confirmed in other user stories | Review recurring entries posted and future dated. |  |  |  | Approved | Erica | 2021-05-14 |  |  |  | RTR | RTR-GL | GL | WESCO |  |  | Ian/Vitaliy | [7 empty] | W2 | User Stories - Approval - GL Batch 1
CSTONE-5387 | CSTONE-541 |  |  | CSTONE-541 | RTR-GL-101 |  | Record to Report | Manage General Ledger Accounting | Perform Allocations | As a GL Accountant I need the ability to allocate based on percentage or formulas |  |  | Phase 1A+1B | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Use allocation percentage / formula Awaiting allocation listing | Use percentage basis to perform allocation. Also use formula basis to perform allocation. |  |  |  | Approved | Erica | 2021-05-20 |  |  |  | RTR | RTR-GL | GL | WESCO |  |  | Ian/Vitaliy | [7 empty] | W2 | Cornerstone User Stories (RTR-GL) - GPO Approval (Batch 2)
CSTONE-5388 | CSTONE-11745 | CSTONE-6254 | CSTONE-11744 | Sprint 12 | RTR-GL-102 |  | Record to Report | Manage General Ledger Accounting | Perform Allocations | As GL Accountant I need the ability to perform allocations in different currencies |  |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report | RPT047 | Allocations can be built to extract data and generate entries based on entered currencies. Actual rate type will be used to convert these allocation journals to functional currency Allocations cannot pull both entered and accounted amounts. Based on conversation understanding of expectation here is that "Allocation takes the Entered Amounts and the already converted Accounting Amounts and moves these balances to HQ location". This is not achieveable through standard allocations Workaround: Use Entered and accounted currency TB report [RPT047] and pass manual journal entries | Able to allocate balance based on specified conversion rate criteria. |  |  | Sprint 12 | Approved | Erica | 2021-07-11 |  | 1-Fit-Configuration-Functional | Sprint Manually overridden - 1A RICE Demo | RTR | RTR-GL | GL | WESCO |  |  | Ian/Vitaliy | [7 empty] | W2 | User Stories - GL Batch 6 GPO Approval
CSTONE-5389 | CSTONE-542 |  |  | CSTONE-542 | RTR-GL-103 |  | Record to Report | Manage General Ledger Accounting | Perform Allocations | As a GL Accountant, I want to be able to allocate a specific balance at the end of each period and then reverses the same balance at the beginning of the following period. |  |  | Phase 1A+1B | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Create relevant allocation formula in Calc Manager. While Generating Allocation entries select a category that is set to auto-reverse as per auto-reverse setup | Allocated balance in functional currency. Reversal of balance beginning of next period. |  |  |  | Approved | Erica | 2021-05-14 |  |  |  | RTR | RTR-GL | GL | WESCO |  |  | Ian/Vitaliy | [7 empty] | W2 | User Stories - Approval - GL Batch 1
CSTONE-5390 | CSTONE-543 |  |  | CSTONE-543 | RTR-GL-104 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | As a GL Accountant, I would like to ensure that GL account cannot be overwritten once journal is posted |  |  | Phase 1A+1B | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Using role security feature ensure: Override account in subledger is disabled | Verify that account override feature has been disabled |  |  |  | Approved | Erica | 2021-05-14 |  |  |  | RTR | RTR-GL | GL | WESCO |  |  | Ian/Vitaliy | [7 empty] | W2 | User Stories - Approval - GL Batch 1
CSTONE-5391 | CSTONE-5102 |  |  | CSTONE-5102 | RTR-GL-105 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | As a GL Accountant Financial Systems Analyst, I would need the ability to open previously closed periods for subsequent adjustments. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Users having access to open period can open periods. For this , ensure GL period is not set to "Permanent Close" as periods in this status cannot be re-opened [Created a separate user story to track security requirement to remove access] Note: This is typically not used in USGAAP ledger but in secondary ledgers as it otherwise impacts consolidated numbers in EPM. Hence changed to Phase 1B | Ensure prior period adjustments are posted accurately |  |  | Sprint 7 | Approved | Erica | 2021-05-14 |  | #REF! |  | RTR | RTR-GL | GL | WESCO |  |  | Ian/Vitaliy | [7 empty] | W2 | User Stories - Approval - GL Batch 1
CSTONE-5392 | CSTONE-1359 | CSTONE-3632 | CSTONE-4413 | CSTONE-4413 | RTR-GL-106 |  | Record to Report | Manage General Ledger Accounting | Process Reversing Journal Entries | As a GL Accountant, I need a report that shows journal entries that have reversal period captured but is not reversed or journal entries that have categories that are marked for autoreversal but are not yet reversed even when relevant period has been opened |  |  | Phase 1A+1B | 2-Gap-Build-Report | Gap | Build | Report | RPT043 | Create a new custom report to pull journal details satisfying relevant criteria Related to user story RTR-GL-026 | Validate journals in the report. |  |  |  | Approved | Erica | 2021-05-12 |  |  |  | RTR | RTR-GL | GL | WESCO |  |  | Ian/Vitaliy | [7 empty] | W1 | User Stories - Approval - GL Batch 1
CSTONE-5393 | CSTONE-5108 |  |  | CSTONE-5108 | RTR-IC-001 |  | Record to Report | Manage Intercompany Accounting | Process Intercompany Journal Entries | As a Intercompany Accountant, I need the ability to create manual intercompany journal entries in the General Ledger module |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Using IC Module: IC batch can be created as required. Whether it creates invoices or journals based on approved batch will be dependent on IC Transaction type. IC batch can be created using front end or using ADFDI spreadsheet Using GL: 1. For US & CA journal entries within a single ledger can span legal entities. Auto-Balancing rules will be used if entry is unbalanced 2. For other International ledgers: Journal entry will be restricted to one LE. Users can choose to create separate journal entries in each LE Note: In IC batch you cannot use "user" rate type | Validate IC journal was correctly entered and posted in GL without generating an IC invoice. Validate all values including entered and accounted currencies. Ensure capability to enter IC journal in GL module only exist between US and Canada entities |  |  | Sprint 7 | Approved | Erica | 2021-07-11 |  | #REF! |  | RTR | RTR-GL | IC | Deloitte |  |  | Ian/Vitaliy | [7 empty] | W2 | User Stories - GL Batch 6 GPO Approval
CSTONE-5394 | CSTONE-5109 |  |  | CSTONE-5109 | RTR-IC-002 |  | Record to Report | Manage Intercompany Accounting | Process Intercompany Journal Entries | As a Intercompany GL Accountant, I need the ability to create intercompany journal entries using a spreadsheet in GL Module |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Using IC Module: IC batch can be created as required. Whether it creates invoices or journals based on approved batch will be dependent on IC Transaction type. IC batch can be created using front end or using ADFDI spreadsheet Using GL: 1. For US & CA journal entries within a single ledger can span legal entities. Auto-Balancing rules will be used if entry is unbalanced 2. For other International ledgers: Journal entry will be restricted to one LE. Users can choose to create separate journal entries in each LE Note: In IC batch you cannot use "user" rate type | Validate IC journal was correctly entered and posted in GL without generating an IC invoice. Validate all values including entered and accounted currencies. Ensure capability to enter IC journal in GL module only exist between US and Canada entities |  |  | Sprint 7 | Approved | Erica | 2021-07-11 |  | #REF! |  | RTR | RTR-GL | IC | Deloitte |  |  | Ian/Vitaliy | [7 empty] | W2 | User Stories - GL Batch 6 GPO Approval
CSTONE-5395 | CSTONE-5734 |  |  | CSTONE-5734 | RTR-IC-003 |  | Record to Report | Manage Intercompany Accounting | Process Intercompany Journal Entries | As a Intercompany Accountant, I need the ability to create manual intercompany journal entries in the Intercompany Accounting Module |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Using IC Module: IC batch can be created as required. Whether it creates invoices or journals based on approved batch will be dependent on IC Transaction type. IC batch can be created using front end or using ADFDI spreadsheet Using GL: 1. For US & CA journal entries within a single ledger can span legal entities. Auto-Balancing rules will be used if entry is unbalanced 2. For other International ledgers: Journal entry will be restricted to one LE. Users can choose to create separate journal entries in each LE Note: In IC batch you cannot use "user" rate type | Validate IC journal was correctly entered and posted in GL without generating an IC invoice. Validate IC journal was entered correctly and generated IC invoice which when posted created journals. Validate all values including entered and accounted currencies. |  |  | Sprint 8 | Approved | Erica | 2021-07-11 |  | #REF! |  | RTR | RTR-GL | IC | Deloitte |  |  | Ian/Vitaliy | [7 empty] | W2 | User Stories - GL Batch 6 GPO Approval
CSTONE-5396 | CSTONE-5735 |  |  | CSTONE-5735 | RTR-IC-004 |  | Record to Report | Manage Intercompany Accounting | Process Intercompany Journal Entries | As an Intercompany Accountant , I want to be able to access multiple ledgers within Journal entry and other pages for quick transaction entry and reporting purposes |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | GL: Data Access Set can be assigned to user using appropriate ledger set as applicable based on security requirement. Ledger Set to be designed as per GL workshop discussions on ledger sets IC: Intercompany Org access to be assigned to user based on security requirement i.e. same user can have multiple IC org access BU: Appropriate BU access to be assigned for ability of IC user to access IC AR and IC AP invoices i.e. same user can have multiple BU access. Note: In future phase, third party BU design should consider whether its okay to have IC team access to third party transactions and vice versa | Ensure access is granted as per role and business design |  |  | Sprint 8 | Approved | Erica | 2021-07-11 |  | #REF! |  | RTR | RTR-GL | IC | Deloitte |  |  | Ian/Vitaliy | [7 empty] | W2 | User Stories - GL Batch 6 GPO Approval
CSTONE-5397 | CSTONE-6836 | Not in Jira | CSTONE-11084 | Sprint 11 | RTR-IC-005 |  | Record to Report | Manage Intercompany Accounting | Process Intercompany Journal Entries | As an Intercompany Accountant, I want my journal entries to route for approvals if necessary |  |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report | RPT017 | GL Journals will follow approvals as per KDD4. Autopost will initiate approvals for complete journals which are not yet routed for approvals IC Batches will need to be submitted for users for approvals. Need update to IC approval notificaiton to include "submitted by" details to meet acceptance criteria 1 comment on formats [Discussed with Vitaliy] | Validate that IC journals routed correctly for approval per business design. Validate the format of the approval request matches the business design and contains all the required information. Ensure reviewers have the ability to open attachments and reject journals if required. |  |  | Sprint 11 | Approved | Erica | 2021-07-15 |  | #REF! |  | RTR | RTR-GL | IC | Deloitte |  |  | Ian/Vitaliy | [7 empty] | W2 | User Stories - GL Batch 6 GPO Approval
CSTONE-5398 | CSTONE-5110 |  |  | CSTONE-5110 | RTR-IC-006 |  | Record to Report | Manage Intercompany Accounting | Process Intercompany Journal Entries | As an Intercompany Accountant, I want my journal entries to automatically create an intercompany balancing line to streamline and speed processing |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | GL Auto-balancing: In US & CA for journals that are unbalanced by LE but balanced as such, will use auto-balancing. 1B only -> IC batch: Balancing setup will add IC AR and IC AP lines which cannot be edited by users | Validate that balancing lines were correctly created for each IC journal. Validate both entered and accounted currencies. Validate balancing is only enabled for US and Canadian entities. |  |  | Sprint 7 | Approved | Erica | 2021-07-14 |  | #REF! |  | RTR | RTR-GL | IC | Deloitte |  |  | Ian/Vitaliy | [5 empty] | Should this be two user stories? One for GL module and one for IC module. GL module should be moved to 1A. | Created DP-RTR-GL-002 which will be loaded to JIRA once approved for 1A | W2 | User Stories - GL Batch 6 GPO Approval
CSTONE-5399 | CSTONE-5736 |  |  | CSTONE-5736 | RTR-IC-007 |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As an Intercompany Accountant, I need an automated process that will create Intercompany AP transaction invoices |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | In intercompany module user will create IC batch & select a transaction type that is tagged for invoicing or journals. When submitted, IC transaction would go through approval. Once approved & if invoicing is required: Next run of Transfer to AR would transfer IC transaction to AR. This scheduled run will be followed by another scheduled run to transfer invoice to AP. Create Accounting on AR & AP invoices will create journals in GL. Once approved & if invoicing is not required: Next run of Transfer to GL would create journals 7/29: As per discussion on invoice template, separate template for AP invoice will not be built. AR Invoice will be sent to SFTP server by AR invoice print program. WESCO IT to then pick from SFTP server and archive as required. This would then be used by AP IC team as well | Review AP invoice has been created. Validate the amounts (both entered and functional), the provider listed on the invoice and format of the invoice. Ensure format of invoice is created as per business design. |  |  | Sprint 8 | Approved | Erica | 2021-08-05 |  | #REF! |  | RTR | RTR-GL | IC | Deloitte |  |  | Ian/Vitaliy | [6 empty] | Invoice print | W2 | WESCO -User Stories - GL - Batch7 - GPO Approval
CSTONE-5400 | CSTONE-6837 | Not in Jira | CSTONE-9720 | Sprint 11 | RTR-IC-008A |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As an Intercompany Accountant, I need an automated process that will create Intercompany AR transaction invoices |  |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report | RPT102 | In intercompany module user will create IC batch & select a transaction type that is tagged for invoicing or journals. When submitted, IC transaction would go through approval. Once approved & if invoicing is required: Next run of Transfer to AR would transfer IC transaction to AR. This scheduled run will be followed by another scheduled run to transfer invoice to AP. Create Accounting on AR & AP invoices will create journals in GL. Once approved & if invoicing is not required: Next run of Transfer to GL would create journals As per acceptance criteria 1 moving to Gap as business wants to validate AR invoice layout in this user story. 2 invoice templates in AR need to be planned based on approval of assumptions on invoice templates by Patrick/Vitaliy/Jess. | Review AR invoice has been created. Validate the amounts (both entered and functional), the customer listed on the invoice and format of the invoice. Ensure format of invoice is created as per business design. |  |  | Sprint 11 | Approved | Erica | 2021-08-05 |  | #REF! |  | RTR | RTR-GL | IC | Deloitte |  |  | Ian/Vitaliy | [6 empty] | Invoice print | W2 | WESCO -User Stories - GL - Batch7 - GPO Approval
CSTONE-5400 | CSTONE-6838 | Not in Jira | CSTONE-9721 | Sprint 11 | RTR-IC-008B |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As an Intercompany Accountant, I need an automated process that will create Intercompany AR transaction invoices |  |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report | RPT103 | In intercompany module user will create IC batch & select a transaction type that is tagged for invoicing or journals. When submitted, IC transaction would go through approval. Once approved & if invoicing is required: Next run of Transfer to AR would transfer IC transaction to AR. This scheduled run will be followed by another scheduled run to transfer invoice to AP. Create Accounting on AR & AP invoices will create journals in GL. Once approved & if invoicing is not required: Next run of Transfer to GL would create journals As per acceptance criteria 1 moving to Gap as business wants to validate AR invoice layout in this user story. 2 invoice templates in AR need to be planned based on approval of assumptions on invoice templates by Patrick/Vitaliy/Jess. | Review AR invoice has been created. Validate the amounts (both entered and functional), the customer listed on the invoice and format of the invoice. Ensure format of invoice is created as per business design. |  |  | Sprint 11 | Approved | Erica | 2021-08-05 |  | #REF! |  | RTR | RTR-GL | IC | Deloitte |  |  | Ian/Vitaliy | [6 empty] | Invoice print | W2 | WESCO -User Stories - GL - Batch7 - GPO Approval
CSTONE-5401 | CSTONE-5737 |  |  | CSTONE-5737 | RTR-IC-009 |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As an Intercompany Accountant, I need an automated process that will create Intercompany GL transactions from IC module |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | In intercompany module user will create IC batch & select a transaction type that is tagged for invoicing or journals. When submitted, IC transaction would go through approval. Once approved & if invoicing is required: Next run of Transfer to AR would transfer IC transaction to AR. This scheduled run will be followed by another scheduled run to transfer invoice to AP. Create Accounting on AR & AP invoices will create journals in GL. Once approved & if invoicing is not required: Next run of Transfer to GL would create journals | Validate that IC journal correctly posted to GL. Validate both entered and accounted currencies. Ensure no IC AR/AP invoices were created. |  |  | Sprint 8 | Approved | Erica | 2021-07-14 |  | #REF! |  | RTR | RTR-GL | IC | Deloitte |  |  | Ian/Vitaliy | [7 empty] | W2 | User Stories - GL Batch 6 GPO Approval
CSTONE-5402 | CSTONE-5402 | CSTONE-6851 | CSTONE-8108 | CSTONE-5402 | RTR-IC-010 |  | Record to Report | Manage Intercompany Accounting | Perform Intercompany Netting & Reconciliation | As an intercompany Accountant, I need to be able to process liability switching of Payables and Receivables transactions for related intercompany organizations |  |  | Phase 1B only | 5-Gap-Build-Extension | Gap | Build | Extension | EXT041, EXT042 | Netting and LSI will be designed as per KDD22 approvals 6/29: KDD22 is now approved. Multiple RICE components to be added by TECH team for this solution. Separate user story for each RICE will be added once RICE IDs are generated | Validate that liability switching process accurately closed the required AP and AR invoices and posted to the GL. Ensure new intercompany relationship was accurately established with the switching entities. Ensure FX exposure is recorded on the switching entity as per business design. Ensure the liability was switched to the correct entities as per business design. Ensure all clearing accounts used for liability switching nets to zero. Validate proper FX gain/loss was recognized. Ensure transactions posted in both primary and secondary ledger. |  |  | Sprint 9 | Approved | Erica | 2021-07-11 |  | Extension | Sprint Manually overridden | RTR | RTR-GL | IC | Deloitte |  |  | Ian/Vitaliy | [7 empty] | W2 | User Stories - GL Batch 6 GPO Approval
CSTONE-5403 | CSTONE-5738 |  |  | CSTONE-5738 | RTR-IC-011 |  | Record to Report | Manage Intercompany Accounting | Process Intercompany Settlements | As an Intercompany Accountant, I need to be able to settle intercompany accounts |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | True cash movement will happen offline & will be recorded as manual receipt / payment in Oracle cloud for settlement using the dummy bank accounts that are setup [no payment or receipt integration with banks and no check printing]. These receipts / payments will account against clearing accounts & which would be offset against treasury files/treasury process | Validate that IC AR and IC AP invoices were accurately closed after settlement was processed. Ensure all settlements were recorded to the correct GL Accounts as per business design. Validate both entered and functional currencies were recorded. Ensure transactions posted in both primary and secondary ledger. |  |  | Sprint 8 | Approved | Erica | 2021-07-11 |  | #REF! |  | RTR | RTR-GL | IC | Deloitte |  |  | Ian/Vitaliy | [7 empty] | W2 | User Stories - GL Batch 6 GPO Approval
CSTONE-5404 | CSTONE-9088 | CSTONE-9089 | CSTONE-9090 | Sprint 12 | RTR-IC-012 |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As a GL accountant, I need a non-material I/C TB report by legal entity. Report should provide a detail at invoice level. |  |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report | RPT209 | non-material I/C TB report by legal entity. Report should provide a detail at invoice level. 4/15/22: This will be used for AR extract | Reviewed detailed non-material I/C TB report |  |  | Sprint 12 | Approved | Erica | 2021-07-11 |  | #REF! |  | RTR | RTR-GL | IC |  |  |  | Ian/Vitaliy | [7 empty] | W2 | User Stories - GL Batch 6 GPO Approval
CSTONE-5405 | CSTONE-9091 | CSTONE-9092 | CSTONE-9093 | Sprint 12 | RTR-IC-013 |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As a GL accountant, I need a non-material I/C TB report by legal entity. Report should provide a summary at account level. |  |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report | RPT210 | need a non-material I/C TB report by legal entity. Report should provide a summary at account level. 4/15/22: This will be used for AR extract | Reviewed summarized non-material I/C TB report |  |  | Sprint 12 | Approved | Erica | 2021-07-11 |  | #REF! |  | RTR | RTR-GL | IC |  |  |  | Ian/Vitaliy | [7 empty] | W2 | User Stories - GL Batch 6 GPO Approval
CSTONE-5406 | CSTONE-6839 | Not in Jira | Not in Jira | Sprint 11 | RTR-IC-014A |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As a I/C GL accountant, I need a report of all non-material I/C AR invoices created by LE and period. |  |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report | RPT027 | Need a report of all non-material I/C AR invoices created by LE and period. | Reviewed non-material I/C AR invoices report. Ensure all AR invoices generated by period is captured in the report. Ensure format of report matches business design. |  |  | Sprint 11 | Approved | Erica | 2021-07-15 |  | #REF! |  | RTR | RTR-GL | IC | WESCO |  |  | Ian/Vitaliy | [7 empty] | W2 | User Stories - GL Batch 6 GPO Approval
CSTONE-5407 | CSTONE-6840 | Not in Jira | Not in Jira | Sprint 11 | RTR-IC-014B |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As a I/C GL accountant, I need a report of all non-material I/C AP invoices created by LE and period. |  |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report | RPT028 | need a report of all non-material I/C AP invoices created by LE and period. | Reviewed non-material I/C AP invoices report. Ensure all AP invoices generated by period is captured in the report. Ensure format of report matches business design. |  |  | Sprint 11 | Approved | Erica | 2021-07-15 |  | #REF! |  | RTR | RTR-GL | IC | WESCO |  |  | Ian/Vitaliy | [7 empty] | W2 | User Stories - GL Batch 6 GPO Approval
CSTONE-5408 | CSTONE-11746 | CSTONE-9641 | CSTONE-9722 | Sprint 12 | RTR-GL-107 |  | Record to Report | Manage General Ledger Accounting | Process Manual Journal Entries | As a GL Accountant, I need a report which shows exchange rates used to convert entered currency to functional currency of more than 10% based on daily rate. |  |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report | RPT016 | Build a custom report based on effective rate computed from entered and accounted amounts which can be compared against configured threshold in lookup | Entered journal where exchange rate is significantly different from the daily rate. Validate journal after posted. Have the ability to select specific percentages or multiple predetermined percentages in the report. |  |  | Sprint 12 | Approved | Erica | 2021-05-12 |  | #REF! |  | RTR | RTR-GL | GL | WESCO |  |  | Ian/Vitaliy | [7 empty] | W1 | User Stories - Approval - GL Batch 1
CSTONE-5409 | CSTONE-544 |  |  | CSTONE-544 | RTR-GL-108 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | As a GL Accountant, I would like to ensure manual SLA entry cannot be posted to ensure SLA traceability to legacy subledgers |  |  | Phase 1A+1B | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Using role based security ensure ability to create a manual SLA entry is taken away [not allowed]. Any subledger entry should always originate from legacy | Validate that user cannot enter a manual SLA journal entry |  |  |  | Approved | Erica | 2021-05-14 |  |  |  | RTR | RTR-GL | GL | Deloitte |  |  | Ian/Vitaliy | [7 empty] | W2 | User Stories - Approval - GL Batch 1
CSTONE-5410 | CSTONE-545 |  |  | CSTONE-545 | RTR-GL-109 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | As a GL Accountant, I would need the to restrict ability to permenantely close GL periods |  |  | Phase 1A+1B | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Using role based security ensure ability to permanently close GL period is taken away. This includes 1. Access to Permanent Close Program 2. Access to Permanent close button on Period management screen | Validate that GL Periods cannot be permanently closed, either vis concurrent program or button |  |  |  | Approved | Erica | 2021-05-14 |  |  |  | RTR | RTR-GL | GL | Deloitte |  |  | Ian/Vitaliy | [7 empty] | W2 | User Stories - Approval - GL Batch 1
CSTONE-5411 | CSTONE-6841 | Not in Jira | Not in Jira | Sprint 11 | RTR-GL-110 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | As a GL Accountant, I need a report that shows all balances from Primary Ledger has been copied to the Secondary Ledger. |  |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report | RPT011 | 6/22: Changed release to 1B only as per email confirmation from Erica with subject "GL Reports Prioritization" | Verified that balances in Primary Ledger copied over to Secondary Ledger. |  |  | Sprint 11 | Approved | Erica | 2021-05-14 |  | #REF! |  | RTR | RTR-GL | GL | WESCO |  |  | Ian/Vitaliy | [7 empty] | W2 | User Stories - Approval - GL Batch 1
CSTONE-5412 |  |  |  | TBD | RTR-GL-111 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | As a Tax Accountant / Manager / Director, I need to be able to efficiently extract transactional level detail (journals) from multiple systems for 2022 and map the data to the new COA string to support numerous tax audits. |  |  | Phase 1A+1B | 2-Gap-Build-Report | Gap | Build | Report |  |  | Validate and reconcile data extractions between legacy and Cloud systems |  |  |  | Drafted | [5 empty] | RTR | LEGACY | LEGACY | WESCO |  |  | Ian/Vitaliy | [7 empty] | W2
CSTONE-5413 |  |  |  | TBD | RTR-GL-112 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | As a GL and HR Manager, the access to value sets in Oracle Cloud products either need to be segregated by role or a report needs to exist to monitor updates / additions / end dates to support SOD analysis. Refer to Oracle EBS current SOD report GL SOD Extract - Value Set History Query. |  |  | Phase 1A+1B | 2-Gap-Build-Report | Gap | Build | Report |  | Security team to Valildate | Verify access restrictions across Oracle defined roles and/or verify report output. |  |  |  | Drafted | [5 empty] | RTR | SECURITY | GL | WESCO |  |  | Ian/Vitaliy | [7 empty] | W2
CSTONE-5414 | CSTONE-546 |  |  | CSTONE-546 | REP-RTR-GL-61 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | Legacy Report Name:Numerous Legacy Report Description:Oracle offers standard / seeded reports such as Account Analysis, TBs, Journals, etc. |  |  | Phase 1A only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | List of standard reports published as part of reporting workshop. Please review and advise if any new custom needs to be built 5/26: 5 reports shared by Erica confirmed to have excel output available [not flat table excel, but same output as seen in PDF published to excel is available out of box] |  |  |  |  | Approved |  | 2021-05-27 |  |  |  | RTR | RTR-GL | GL | WESCO |  | WES-SUM-2 | Ian/Vitaliy | [6 empty] | Excel output requested Erica to provide list | W1 | Cornerstone User Stories (RTR-GL) - GPO Approval (Batch 2)
CSTONE-5415 | CSTONE-547 |  |  | CSTONE-547 | REP-RTR-GL-62 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | Legacy Report Name:WES_ACCOUNT_DETAIL_PTD_YTD WES_ACCOUNT_DETAIL_MULITPLE YEARS BY PERIOD Legacy Report Description:Description is contained within each concurrent request name. Prior to GL Wand, this was the only method to extract data from the GL by branch, account, periods, mgt rollups, journal detail, etc. Users continue to use reports today. |  |  | Phase 1A only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Use SmartView to pull GL balances Assumption: Required COA hierarchy is built in Cloud ERP [Hierarchy is Branch hierarchy - District, Region, Group] |  |  |  |  | Approved | Erica | 2021-05-12 |  |  |  | RTR | RTR-GL | GL | WESCO |  | WES-SUM-3A | [8 empty] | W1 | User Stories - Approval - GL Batch 1
CSTONE-5416 | CSTONE-586 | CSTONE-3633 | CSTONE-3655 | CSTONE-3655 | REP-RTR-GL-63 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | Legacy Report Name:WES_JOURNAL_DETAIL_EXTRACT CP Legacy Report Description:Description is contained within each concurrent request name. Prior to GL Wand, this was the only method to extract data from the GL by branch, account, periods, mgt rollups, journal detail, etc. Users continue to use reports today. |  |  | Phase 1A only | 2-Gap-Build-Report | Gap | Build | Report | RPT002 | Journal Details report (Journal Batch + Journal Header). Merge RICE with user story RTR-GL-010 |  |  |  |  | Approved | Erica | 2021-05-12 |  |  |  | RTR | RTR-GL | GL | WESCO |  | WES-SUM-3B | [8 empty] | W1 | User Stories - Approval - GL Batch 1
CSTONE-5417 | CSTONE-548 |  |  | CSTONE-548 | REP-RTR-GL-64 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | Legacy Report Name:Numerous Legacy Report Description:Tom Johnson in field accounting uses Discoverer for 18 GL extracts. |  |  | Phase 1A only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Use SmartView to pull GL balances |  |  |  |  | Approved | Erica | 2021-05-12 |  |  |  | RTR | RTR-GL | GL | WESCO |  | WES-SUM-4 | [8 empty] | W1 | User Stories - Approval - GL Batch 1
CSTONE-5418 |  |  |  | N/A | REP-RTR-GL-65 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | Legacy Report Name:FSGs with content sets WES_TD_EXTRACT_BS "LEDGER" WES_TD_EXTRACT_IS "LEDGER" WES_TD_EXTRACT_IS(STDCST) "LEDGER" Legacy Report Description:Request sets reference FSGs with content sets to build a flat file of financial actual & budget data and stage for Teradata. The balance sheet does not reflect all balance sheet COA parent values and the income statement reflects operating only, not GAAP. The request set / flat file generated reflects data from USD 2021 and CAD 2042 for a set of secure Teradata tables and data from Consol 2079 for a set of unsecure Teradata tables. The Teradata tables are accessed by numerous users and support various BI applications. |  |  | Not Required | 10-Not Required-Not Required-Not Required | Not Required | Not Required | Not Required |  | Duplicate of TeraData extracts being discussed in KDD8 |  |  |  |  | Approved | Erica | 2021-05-12 |  |  |  | RTR | RTR-GL | GL | WESCO |  | WES-SUM-5 | [8 empty] | W1 | User Stories - Approval - GL Batch 1
CSTONE-5419 |  |  |  | N/A | REP-RTR-GL-66 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | Legacy Report Name:WES GL Blackline Extract Legacy Report Description:Data extract for Blackline account reconciliation tool |  |  | Not Required | 10-Not Required-Not Required-Not Required | Not Required | Not Required | Not Required |  | Duplicate of Blackline extracts being discussed in KDD8 |  |  |  |  | Approved | Erica | 2021-05-12 |  |  |  | RTR | RTR-GL | GL | WESCO |  | WES-SUM-6 | [8 empty] | W1 | User Stories - Approval - GL Batch 1
CSTONE-5420 |  |  |  | N/A | REP-RTR-GL-68 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | Legacy Report Name:Additons, Disposals by Item & Capital Asset Continuity Report Legacy Report Description:PPE reports to support Tax compliance |  |  | Not Required | 10-Not Required-Not Required-Not Required | Not Required | Not Required | Not Required |  | FA is planned to be continued in EBS. This seems a typical roll-forward report that can be pulled from legacy EBS FA subledger |  |  |  |  | Approved | Erica | 2021-05-12 |  |  |  | RTR | RTR-GL | GL | WESCO |  | WES-SUM-8 | [8 empty] | W1 | User Stories - Approval - GL Batch 1
CSTONE-5421 | CSTONE-1360 | CSTONE-3634 | CSTONE-4414 | CSTONE-4414 | REP-RTR-GL-69 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | Legacy Report Name:Wesco GL Balance Corruption Report Legacy Report Description:Identifies GL table data corruption |  |  | Phase 1A only | 2-Gap-Build-Report | Gap | Build | Report | RPT044 | Build new report to compare GL balances vs GL journals |  |  |  |  | Approved | Erica | 2021-05-12 |  |  |  | RTR | RTR-GL | GL | WESCO |  | WES-SUM-9 | [8 empty] | W1 | User Stories - Approval - GL Batch 1
CSTONE-5422 | CSTONE-1361 | CSTONE-3635 | CSTONE-3656 | CSTONE-3656 | REP-RTR-GL-70 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | Legacy Report Name:WESCO GL Journal Approval Status Report Legacy Report Description:Provides status of journals in approval hierarchy |  |  | Phase 1A only | 2-Gap-Build-Report | Gap | Build | Report | RPT003 | Journal Batch / Journal Header level report. Provides details where the journal is waiting for approval [Different that other Journal report & journal line report. This is more about where is journal in approval currently so that it can be followed up] [As part of lean spec design finalize information that can be pulled from GL tables for reporting] |  |  |  |  | Approved | Erica | 2021-05-12 |  |  |  | RTR | RTR-GL | GL | WESCO |  | WES-SUM-10 | [8 empty] | W1 | User Stories - Approval - GL Batch 1
CSTONE-5423 |  |  |  | N/A | REP-RTR-GL-71 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | Legacy Report Name:WES GL Journal Limits Report Legacy Report Description:Mitigating control for SOD conflict of SuperUser having access to limits table and completing quarterly access review |  |  | Not Required | 10-Not Required-Not Required-Not Required | Not Required | Not Required | Not Required |  | Not required with future state GL approval KDD |  |  |  |  | Approved | Erica | 2021-05-12 |  |  |  | RTR | RTR-GL | GL | WESCO |  | WES-SUM-11 | [8 empty] | W1 | User Stories - Approval - GL Batch 1
CSTONE-5424 |  |  |  | N/A | REP-RTR-GL-72 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | Legacy Report Name:Journal ADI Legacy Report Description:Three versions provided - columns added outside of macro to support user copy/paste |  |  | Not Required | 10-Not Required-Not Required-Not Required | Not Required | Not Required | Not Required |  | This is not a report. Journal ADFDI cannot have custom format in Cloud |  |  |  |  | Approved | Erica | 2021-05-12 |  |  |  | RTR | RTR-GL | GL | WESCO |  | WES-SUM-12 | [8 empty] | W1 | User Stories - Approval - GL Batch 1
CSTONE-5425 |  |  |  | N/A | REP-RTR-GL-73 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | Legacy Report Name:WES GL Income Statement - OnDemand (Standard Cost) Legacy Report Description:Branch income statements to OnDemand |  |  | Not Required | 10-Not Required-Not Required-Not Required | Not Required | Not Required | Not Required |  | Duplicate of OnDemand extracts being discussed in KDD8 |  |  |  |  | Approved | Erica | 2021-05-12 |  |  |  | RTR | RTR-GL | GL | WESCO |  | WES-SUM-13 | [8 empty] | W1 | User Stories - Approval - GL Batch 1
CSTONE-5426 |  |  |  | N/A | REP-RTR-GL-74 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | Legacy Report Name:WES GL Income Statement - OnDemand Legacy Report Description:Branch income statements to OnDemand |  |  | Not Required | 10-Not Required-Not Required-Not Required | Not Required | Not Required | Not Required |  | Duplicate of OnDemand extracts being discussed in KDD8 |  |  |  |  | Approved | Erica | 2021-05-12 |  |  |  | RTR | RTR-GL | GL | WESCO |  | WES-SUM-14 | [8 empty] | W1 | User Stories - Approval - GL Batch 1
CSTONE-5427 |  |  |  | N/A | REP-RTR-GL-75 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | Legacy Report Name:WES GL MFC Report (new) Legacy Report Description:Branch monthly finance charge report OnDemand |  |  | Not Required | 10-Not Required-Not Required-Not Required | Not Required | Not Required | Not Required |  | Duplicate of OnDemand extracts being discussed in KDD8 |  |  |  |  | Approved | Erica | 2021-05-12 |  |  |  | RTR | RTR-GL | GL | WESCO |  | WES-SUM-15 | [8 empty] | W1 | User Stories - Approval - GL Batch 1
CSTONE-5428 |  |  |  | N/A | REP-RTR-GL-76 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | Legacy Report Name:WES GL Create Branch Hierarchy File Legacy Report Description:Branch Header (group, region, district) management rollup |  |  | Not Required | 10-Not Required-Not Required-Not Required | Not Required | Not Required | Not Required |  | Duplicate of TeraData extract being discussed in KDD8 |  |  |  |  | Approved | Erica | 2021-05-12 |  |  |  | RTR | RTR-GL | GL | WESCO |  | WES-SUM-16 | [8 empty] | W1 | User Stories - Approval - GL Batch 1
CSTONE-5429 |  |  |  | N/A | REP-RTR-GL-77 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | Legacy Report Name:WES GL Flash Report (New) Legacy Report Description:Branch flash report |  |  | Not Required | 10-Not Required-Not Required-Not Required | Not Required | Not Required | Not Required |  | Duplicate of OnDemand extracts being discussed in KDD8 |  |  |  |  | Approved | Erica | 2021-05-12 |  |  |  | RTR | RTR-GL | GL | WESCO |  | WES-SUM-17 | [8 empty] | W1 | User Stories - Approval - GL Batch 1
CSTONE-5430 |  |  |  | N/A | REP-RTR-GL-78 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | Legacy Report Name:GL SOD Extract - Value Set History Query Legacy Report Description:Mitigates SOD conflict related to HR / Finance having access to same value sets |  |  | Not Required | 10-Not Required-Not Required-Not Required | Not Required | Not Required | Not Required |  | Erica to add a new user story for security team from SOD perspective to control value set access of HCM vs Fin. As an outcome of security team user story disposition appropriate report (if required) may be built RTR-GL-112 |  |  |  |  | Approved | Erica | 2021-05-12 |  |  |  | RTR | RTR-GL | GL | WESCO |  | WES-SUM-18 | [8 empty] | W1 | User Stories - Approval - GL Batch 1
CSTONE-5431 | CSTONE-1362 | CSTONE-3636 | CSTONE-4415 | CSTONE-4415 | REP-RTR-GL-79 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | Legacy Report Name:GL Period Status Query Legacy Report Description: |  |  | Phase 1A+1B | 2-Gap-Build-Report | Gap | Build | Report | RPT045 | This is period status report showing 1. Who columns 2. Run for entire year 3. Run for ledger Set 4. Shows period status for GL 5. Shows period status for AR & AP [Phase 1B] |  |  |  |  | Approved | Erica | 2021-05-12 |  |  |  | RTR | RTR-GL | GL | WESCO |  | WES-SUM-19 | [8 empty] | W1 | User Stories - Approval - GL Batch 1
CSTONE-5432 | CSTONE-549 |  |  | CSTONE-549 | REP-RTR-GL-80 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | Legacy Report Name:Not a report; Omkar requested to include to not lose sight of the Oracle EBS setup Legacy Report Description:GL data rolled-up using value set parents and template definitions for each ledger |  |  | Phase 1A only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Use Account Groups in Account Monitors. Users to setup Account Groups as required |  |  |  |  | Approved | Erica | 2021-05-12 |  |  |  | RTR | RTR-GL | GL | WESCO |  | WES-SUM-20 | [8 empty] | W1 | User Stories - Approval - GL Batch 1
CSTONE-5433 |  |  |  | N/A | REP-RTR-GL-81 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | Legacy Report Name:WES Journal Detail for Expense Exceptions Legacy Report Description:Supports expense exception tool |  |  | Not Required | 10-Not Required-Not Required-Not Required | Not Required | Not Required | Not Required |  | Duplicate of TeraData extract being discussed in KDD8 |  |  |  |  | Approved | Erica | 2021-05-12 |  |  |  | RTR | RTR-GL | GL | WESCO |  | WES-SUM-21 | [8 empty] | W1 | User Stories - Approval - GL Batch 1
CSTONE-5434 | CSTONE-42 | Not in Jira |  | CSTONE-42 | RTR-AHCS-001 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view transactions by GL journal source system so that data is segregated by source system |  |  | Phase 1A+1B | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Source system visibility in GL, discussed as part of AHCS-003 & AHCS-004 workshops. Subledger determination approach by source system. E.g., EBS AR in AHCS will be represented as EBS AR journal source and journal category in cloud GL. Similarly for Legacy FAH AR in AHCS will be represented as FAH AR journal source and journal category in cloud GL. | Successful reconciliation of EBS to HUB by source and category. | Review transactions to validate account activity based on predefined source systems and categories per business design. |  |  | Approved | Erica | 2021-05-20 |  |  |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  | Ian/Vitaliy | [7 empty] | W3 | User Stories (AHCS Track) - Batch1 GPO Approval
CSTONE-5435 | CSTONE-43 | Not in Jira |  | CSTONE-43 | RTR-AHCS-002 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a Financial Controller, I do not want users with ability to modify subledger journals from Legacy subledger (source system) so that I can ensure data across systems are in sync and can be transactions are auditable |  |  | Phase 1A+1B | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Users will not have the ability to update the AHCS journals. The journal source will be frozen. | User should not access to update any source (Legacy Subledger) transaction in AHCS | Users should only have access to view the transnactions/journals from the source (legacy system) in AHCS. Users should not have the ability to create or modify any transactions or journals in AHCS |  |  | Approved | Erica | 2021-05-20 |  |  |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  | Ian/Vitaliy | [7 empty] | W3 | User Stories (AHCS Track) - Batch1 GPO Approval
CSTONE-5436 |  | CSTONE-550 |  | CSTONE-550 | RTR-AHCS-003 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant, I want the system to reject/error any transactions that are created with accounting date as the prior period so that they are not posted automatically in the current period |  |  | Phase 1A+1B | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Transactions created with accounting date for prior period should fail processing in the current period. | Validate setups with a test transaction. | Review error report to ensure prior period transactions are captured report to capture this. |  |  | Approved |  | 2021-05-25 |  |  |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  | Ian/Vitaliy | [7 empty] | W3 | User Stories (AHCS Track) - Batch1 GPO Approval
CSTONE-5437 | CSTONE-44 | Not in Jira |  | CSTONE-44 | RTR-AHCS-004 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant, I want all the journals to use accounting date attribute as a transaction date so that all transactions are created in the accurate accounting period. |  |  | Phase 1A only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Accounting date from SLA / XLA tables will be utilized for determining the date for AHCS transactions | Confirm accounting dates in legacy subledger and HUB is same | Verify transaction date in AHCS aligns with correct accounting period for subledger journal. |  |  | Approved | Erica | 2021-05-20 |  |  |  | RTR | RTR-AHCS | AHCS | Deloitte | [10 empty] | W3 | User Stories (AHCS Track) - Batch1 GPO Approval
CSTONE-5438 | CSTONE-45 | Not in Jira |  | CSTONE-45 | RTR-AHCS-005 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant, I want all foreign currency transactions from source system imported with the currency exchange rate, entered and accounting amount from the source system so that transaction is properly accounted |  |  | Phase 1A+1B | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Source system should send both entered and accounted currency for all transactions in AHCS | Confirm transaction entered and accounted in legacy and HUB | Verified that entered and accounted amounts if different currencies reflect correct amounts and also rate used in conversion process is captured. |  |  | Approved | Erica | 2021-05-20 |  |  |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  | Ian/Vitaliy | [7 empty] | W3 | User Stories (AHCS Track) - Batch1 GPO Approval
CSTONE-5439 |  | CSTONE-551 |  | CSTONE-551 | RTR-AHCS-006 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL accountant, I want to ensure journals from the source systems are compliant with the cross validation rules and end dated, disabled account strings / segments so that accounting across cloud ERP is consistent. |  |  | Phase 1A+1B | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Legacy EBS and legacy FAH COA should be compliant with cloud COA cross validation rules. COA mapping rules should be defined. | Validate setups with test transactions that agree and violate CVRs / end dates / disabled segments and account strings. | Validate incorrect transactions are carved-out of daily interface and not imported to the HUB. Validate the remaining interface transactions that pass validations are import to the HUB. |  |  | Approved | Erica | 2021-05-20 |  |  |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  | Ian/Vitaliy | [7 empty] | W3 | User Stories (AHCS Track) - Batch1 GPO Approval
CSTONE-5440 | CSTONE-77 | CSTONE-46 | CSTONE-1389 | CSTONE-1389 | RTR-AHCS-007 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the EBS AR source system to extract the transactions with based on the approved data model and AHCS to process the transactions with relevant attributes so that that transactions are accounted with detail information in AHCS |  |  | Phase 1A only | 3-Gap-Build-Interface | Gap | Build | Interface | INT005 | Legacy team to extract legacy EBS AR data and interface into Oracle Cloud Middleware | Build a systematic/automated data completeness check to support the daily imports. Validate / test. | All attributes defined in EBS AR data model are brought in AHCS and detailed inforrmation is available in AHCS |  |  | Approved | Erica | 2021-05-24 |  |  |  | RTR | RTR-AHCS | AHCS | Deloitte | [10 empty] | W3 | User Stories (AHCS Track) - Batch1 GPO Approval
CSTONE-5441 | CSTONE-101 | CSTONE-47 | CSTONE-1390 | CSTONE-1390 | RTR-AHCS-008 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the EBS AP source system to extract the transactions with based on the approved data model and AHCS to process the transactions with relevant attributes so that that transactions are accounted with detail information in AHCS |  |  | Phase 1A only | 3-Gap-Build-Interface | Gap | Build | Interface | INT002 | Legacy team to extract legacy EBS AP data and interface into Oracle Cloud Middleware | Build a systematic/automated data completeness check to support the daily imports. Validate / test. | All attributes defined in EBS AP data model are brought in AHCS and detailed inforrmation is available in AHCS |  |  | Approved | Erica | 2021-05-24 |  |  |  | RTR | RTR-AHCS | AHCS | Deloitte | [10 empty] | W3 | User Stories (AHCS Track) - Batch1 GPO Approval
CSTONE-5442 | CSTONE-102 | CSTONE-48 | CSTONE-1391 | CSTONE-1391 | RTR-AHCS-009 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the EBS FA source system to extract the transactions with based on the approved data model and AHCS to process the transactions with relevant attributes so that that transactions are accounted with detail information in AHCS |  |  | Phase 1A only | 3-Gap-Build-Interface | Gap | Build | Interface | INT004 | Legacy team to extract legacy EBS FA data and interface into Oracle Cloud Middleware | Build a systematic/automated data completeness check to support the daily imports. Validate / test. | All attributes defined in EBS FA data model are brought in AHCS and detailed inforrmation is available in AHCS |  |  | Approved | Erica | 2021-05-24 |  |  |  | RTR | RTR-AHCS | AHCS | Deloitte | [10 empty] | W3 | User Stories (AHCS Track) - Batch1 GPO Approval
CSTONE-5443 | CSTONE-566 | CSTONE-623 | CSTONE-1392 | CSTONE-1392 | RTR-AHCS-010 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the Central source system to extract the transactions with based on the approved data model and AHCS to process the transactions with relevant attributes so that that transactions are accounted with detail information in AHCS |  |  | Phase 1A only | 3-Gap-Build-Interface | Gap | Build | Interface | INT033 | Legacy team to extract legacy Central data and interface into Oracle Cloud Middleware | Build a systematic/automated data completeness check to support the daily imports. Validate / test. | All attributes defined in Central data model are brought in AHCS and detailed inforrmation is available in AHCS |  |  | Approved | Erica | 2021-05-24 |  |  |  | RTR | RTR-AHCS | AHCS | Deloitte | [10 empty] | W3 | User Stories (AHCS Track) - Batch1 GPO Approval
CSTONE-5444 |  |  |  |  | RTR-AHCS-011 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the Legacy FAH AR source system to extract the transactions with based on the approved data model and AHCS to process the transactions with relevant attributes so that that transactions are accounted with detail information in AHCS |  |  | Not Required | 10-Not Required-Not Required-Not Required | Not Required | Not Required | Not Required |  | 5/24: AB-Review complete. Ready for approval | Verify transactions from legacy FAH AR are imported and accounted for in AHCS. Review details in FAH AR subledger ties to source legacy FAH AR data. |  |  |  | Approved | Erica | 2021-05-24 |  |  |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  | Ian/Vitaliy | Ian 11-9-21 | Bhim | Boon | Rhonda | CALA: Beatriz García/Sandra Patiño/Jose Luis Ortiz |  |  | W3 | User Stories (AHCS Track) - Batch1 GPO Approval
CSTONE-5445 |  |  |  |  | RTR-AHCS-012 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the Legacy FAH AP source system to extract the transactions based on the approved data model and AHCS to process the transactions with relevant attributes so that that transactions are accounted with detail information in AHCS |  |  | Not Required | 10-Not Required-Not Required-Not Required | Not Required | Not Required | Not Required |  | 5/24: AB-Review complete. Ready for approval Change the subledger name to MF | Verify transactions from legacy FAH AP are imported and accounted for in AHCS. Review details in FAH AP subledger ties to source legacy FAH AP data. |  |  |  | Approved | Erica | 2021-05-24 |  |  |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  | Ian/Vitaliy | Ian 11-9-21 | Bhim | Boon | Rhonda | CALA: Beatriz García/Sandra Patiño/Jose Luis Ortiz |  |  | W3 | User Stories (AHCS Track) - Batch1 GPO Approval
CSTONE-5446 |  |  |  |  | RTR-AHCS-013 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the Legacy FAH Inventory source system to extract the transactions based on the approved data model and AHCS to process the transactions with relevant attributes so that that transactions are accounted with detail information in AHCS |  |  | Not Required | 10-Not Required-Not Required-Not Required | Not Required | Not Required | Not Required |  | 5/24: AB-Review complete. Ready for approval Change the subledger name to MF | Verify transactions from legacy FAH Inventory are imported and accounted for in AHCS. Review details in FAH Inventory subledger ties to source legacy FAH Inventory data. |  |  |  | Approved | Erica | 2021-05-24 |  |  |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  | Ian/Vitaliy | Ian 11-9-21 | Bhim | Boon | Rhonda | CALA: Beatriz García/Sandra Patiño/Jose Luis Ortiz |  |  | W3 | User Stories (AHCS Track) - Batch1 GPO Approval
CSTONE-5447 |  | CSTONE-5694 |  |  | RTR-AHCS-014 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want AHCS to be configured to process PeopleSoft Fixed Asset application data as per business and accounting rules so that transactions are accounted for correctly and ties to correctly in PS FA Subledger with appropriate line level information , Supporting Reference and other details. | Must Have |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | 5/24: AB-Pending conformation if only journal lines will be brought into AHCS | Verify transactions from PS FA are imported and accounted for in AHCS. Review details in Peoplesoft FA subledger ties to source Peoplesoft FA data. | Review that data in Oracle GL ties to PS FA subledger which ties to source PS FA data |  |  | Approved | Erica | 2021-05-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  | Ian/Vitaliy | Ian 11-9-21 | N/A | N/A | Rhonda | CALA: Beatriz García/Sandra Patiño/Jose Luis Ortiz |  |  | W3 | User Stories (AHCS Track) - Batch1 GPO Approval | 20
CSTONE-5448 | CSTONE-587 | CSTONE-1370 | CSTONE-1393 | CSTONE-1393 | RTR-AHCS-015 |  | Record to Report | Manage General Ledger Accounting | Maintain Chart of Accounts | As a GL accountant Financial Systems Analyst, I want the ability to change the COA mapping rules for legacy EBS to Cloud COA so that accounting in cloud reflects accurately |  |  | Phase 1A only | 5-Gap-Build-Extension | Gap | Build | Extension | EXT007 | COA Mapping rules creation and update for legacy EBS to Cloud | Validate setups with test transactions. Confirm mapping and successful data interface / import / post. |  |  |  | Approved | Erica | 2021-05-24 |  |  |  | RTR | RTR-GL | GL | Deloitte | [10 empty] | W3 | User Stories (AHCS Track) - Batch1 GPO Approval
CSTONE-5449 | CSTONE-588 | CSTONE-1371 | CSTONE-1394 | CSTONE-1394 | RTR-AHCS-016 |  | Record to Report | Manage General Ledger Accounting | Maintain Chart of Accounts | As a GL accountant Financial Systems Analyst, I want the ability to change the COA mapping rules for Central to Cloud COA so that accounting in cloud reflects accurately |  |  | Phase 1A only | 5-Gap-Build-Extension | Gap | Build | Extension | EXT007 | COA Mapping rules creation and update for Central to Cloud | Validate setups with test transactions. Confirm mapping and successful data interface / import / post. |  |  |  | Approved | Erica | 2021-05-24 |  |  |  | RTR | RTR-GL | GL | Deloitte | [10 empty] | W3 | User Stories (AHCS Track) - Batch1 GPO Approval
CSTONE-5450 | CSTONE-589 | CSTONE-1372 | CSTONE-1395 | CSTONE-1395 | RTR-AHCS-017 |  | Record to Report | Manage General Ledger Accounting | Maintain Chart of Accounts | As a GL accountant Financial Systems Analyst, I want the ability to change the COA mapping rules for legacy FAH to Cloud COA so that balances in the cloud reflect accurately |  |  | Phase 1A+1B | 5-Gap-Build-Extension | Gap | Build | Extension | EXT007 | COA Mapping rules creation and update for legacy FAH to Cloud | Validate setups with test transactions. Confirm mapping and successful data interface / import / post. | Validate transactions after they have been mapped to the new COA |  |  | Approved | Erica | 2021-05-24 |  |  |  | RTR | RTR-GL | GL | Deloitte |  |  | Ian/Vitaliy | [7 empty] | W3 | User Stories (AHCS Track) - Batch1 GPO Approval
CSTONE-5451 | CSTONE-590 | CSTONE-1373 | CSTONE-1396 | CSTONE-1396 | RTR-AHCS-018 |  | Record to Report | Manage General Ledger Accounting | Maintain Chart of Accounts | As a Financial System Analyst, I want to create COA mapping (EBS to Cloud) for new COA values added in legacy EBS so that all journals from source systems can be interfaced into AHCS |  |  | Phase 1A only | 5-Gap-Build-Extension | Gap | Build | Extension | EXT007 | COA Mapping updates based on new addition / end-dated chart of account values in legacy EBS application. New mapping to be created between legacy EBS to Cloud | Validate setups with test transactions. Confirm mapping and successful data interface / import / post. |  |  |  | Approved | Erica | 2021-05-24 |  |  |  | RTR | RTR-GL | GL | Deloitte | [10 empty] | W3 | User Stories (AHCS Track) - Batch1 GPO Approval
CSTONE-5452 |  |  |  |  | RTR-AHCS-019 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a Financial System Analyst, I want OIC 'NOT' to default COA segment [ Make it null ] if mapping engine is unable to derive any COA segment due to missing legacy COA value for event based transactions so that all transactions from source systems can be interfaced into AHCS and override with business rule in AHCS | Must Have |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | 02/03 : This will be solutioned as per allignment on COA derivation approach. COA Mapping updates based on new addition / end-dated chart of account values or a default value for blank segment value | OIC should not default COA segment if mapping engine is unable to derive any COA segment due to missing legacy COA value for event based transactions | 1.Validate that legacy segment was missing for that transaction. 2.Validate that transaction does not default COA segment. |  |  | Approved | Manisha | 2022-01-28 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | will there be specific deafult segment for each Source code? And how will this be chosen? |  | Rhonda | CALA: Beatriz García/Sandra Patiño/Jose Luis Ortiz | Clarify the user story. We thought if mapping is not available it would error out. Is this user story related to potential rounding variances or if the mapping is missing? Is this applicable since no more legacy fah? - Ok IP How will that default segment be derived? -IP | MS 11/05 - Yes, this a default COA values is stll required in COA mapping engine for allow engine to derive some default value for event based transactions | W3 | Approved on Tue 2/1/2022 10:02 AM | 29
CSTONE-5453 | CSTONE-591 | CSTONE-1374 | CSTONE-1397 | CSTONE-1397 | RTR-AHCS-020 |  | Record to Report | Manage General Ledger Accounting | Maintain Chart of Accounts | As a Financial System Analyst, I want to create COA mapping (Central to Cloud) for new COA values added in Central so that all journals from source systems can be interfaced into AHCS |  |  | Phase 1A only | 5-Gap-Build-Extension | Gap | Build | Extension | EXT007 | COA Mapping updates based on new addition / end-dated chart of account values in Central application. New mapping to be created between Central to Cloud | Validate setups with test transactions. Confirm mapping and successful data interface / import / post. |  |  |  | Approved | Erica | 2021-05-24 |  |  |  | RTR | RTR-GL | GL | Deloitte | [10 empty] | W3 | User Stories (AHCS Track) - Batch1 GPO Approval
CSTONE-5454 | CSTONE-592 | CSTONE-640 | CSTONE-1398 | CSTONE-1398 | RTR-AHCS-021 |  | Record to Report | Manage General Ledger Accounting | Maintain Chart of Accounts | As a Financial System Analyst, I want to create COA mapping (EBS to Cloud) for new COA values added in Cloud so that all journals from source systems can be interfaced into AHCS |  |  | Phase 1A only | 5-Gap-Build-Extension | Gap | Build | Extension | EXT007 | COA Mapping updates based on new addition / end-dated chart of account values in Cloud GL. New mapping to be created between Cloud to legacy EBS | Validate setups with test transactions. Confirm mapping and successful data interface / import / post. |  |  |  | Approved | Erica | 2021-05-24 |  |  |  | RTR | RTR-GL | GL | Deloitte | [10 empty] | W3 | User Stories (AHCS Track) - Batch1 GPO Approval
CSTONE-5455 |  | CSTONE-6255 |  |  | RTR-AHCS-022 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a Financial System Analyst, I want to create COA mapping (Legacy PS to Cloud) for new COA values added in Cloud so that all journals from source systems can be interfaced into AHCS |  |  | Phase 1B only | 5-Gap-Build-Extension | Gap | Build | Extension | EXT007 | COA Mapping updates based on new addition / end-dated chart of account values in Cloud GL. New mapping to be created between Cloud to legacy FAH On Hold for legacy FAH assessment | All journals from source systems (legacy PS to cloud) should be interfaced into AHCS | Validate transactions after they have been mapped to the new COA |  |  | Approved | Manisha | 2022-01-28 |  | 1-Fit-Configuration-Functional | Sprint Manually overridden - 1A RICE Demo | RTR | RTR-AHCS | AHCS | Deloitte |  |  | Ian/Vitaliy | [5 empty] | Sent to Manisha to review - IP 12-15 | Legacy FAH decision | W3 | Approved on Tue 2/1/2022 10:02 AM
CSTONE-5456 | CSTONE-593 | CSTONE-1376 | CSTONE-1399 | CSTONE-1399 | RTR-AHCS-023 |  | Record to Report | Manage General Ledger Accounting | Maintain Chart of Accounts | As a Financial System Analyst, I want to create COA mapping (Central to Cloud) for new COA values added in Cloud so that all journals from source systems can be interfaced into AHCS |  |  | Phase 1A only | 5-Gap-Build-Extension | Gap | Build | Extension | EXT007 | COA Mapping updates based on new addition / end-dated chart of account values in Cloud GL. New mapping to be created between Cloud to Central | Validate setups with test transactions. Confirm mapping and successful data interface / import / post. |  |  |  | Approved | Erica | 2021-05-24 |  |  |  | RTR | RTR-GL | GL | Deloitte | [10 empty] | W3 | User Stories (AHCS Track) - Batch1 GPO Approval
CSTONE-5457 | CSTONE-594 | CSTONE-3637 | CSTONE-3657 | CSTONE-3657 | RTR-AHCS-024 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report which reconciles legacy and AHCS subledgers so that I can perform period end reconciliations |  |  | Phase 1A+1B | 3-Gap-Build-Interface | Gap | Build | Interface | INT012 | Legacy to AHCS Reconciliation Report - BI:AHCS to provide the feed with all detail transactions to Tera Data for reconciliations | Validate report and compare to legacy subledger to GL reconciliations. | Review AHCS to GL Reconciliation report for variances between legacy, AHCS. Resolve variances as needed. |  |  | Approved | Erica | 2021-05-24 |  |  |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  | Ian/Vitaliy | [7 empty] | W3 | User Stories (AHCS Track) - Batch1 GPO Approval
CSTONE-5458 | CSTONE-1363 | CSTONE-3638 | CSTONE-3658 | CSTONE-3658 | RTR-AHCS-025 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As a GL Accountant, I want a report to reconcile AHCS subldger and Oracle Cloud GL so that I can perform period close reconciliations |  |  | Phase 1A+1B | 2-Gap-Build-Report | Gap | Build | Report | RPT007 | AHCS to GL Reconciliation Report: Shows AHCS and GL code combination balances side by side for reconciliation | Validate report and compare to legacy subledger to GL reconciliations. | Review AHCS to GL Reconciliation report for variances between legacy, AHCS. Resolve variances as needed. |  |  | Approved | Erica | 2021-05-24 |  |  |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  | Ian/Vitaliy | [7 empty] | W3 | User Stories (AHCS Track) - Batch1 GPO Approval
CSTONE-5459 | CSTONE-106 | CSTONE-49 | CSTONE-1400 | CSTONE-1400 | RTR-AHCS-026 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As a GL accountant, I want a report with error details along with error descriptions for all failures (mapping, validations etc.) so that I can review and resolve the errors |  |  | Phase 1A+1B | 2-Gap-Build-Report | Gap | Build | Report | RPT006_R | AHCS Error Report: Errors from Cloud AHCS after processing data by incoming file name and error description. Error / process summary with source chart of accounts and error description | Validate setups and report with test transactions. Confirm invalid data does not interface / import / post. | Validate incorrect transactions are carved-out of daily interface and not imported to the HUB. Validate the remaining interface transactions that pass validations are import to the HUB. | Review AHCS error report for missing coa segments. Verify that transactions did not import to AHCS until COA missing segments were updated. |  | Approved | Erica | 2021-05-24 |  |  |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  | Ian/Vitaliy | [7 empty] | W3 | User Stories (AHCS Track) - Batch1 GPO Approval
CSTONE-5460 | CSTONE-1364 | CSTONE-3639 | CSTONE-3659 | CSTONE-3659 | RTR-AHCS-027 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As a GL Accountant, I want a report that shows exceptions for all AHCS subledgers so that during close I can ensure all transactions are processed from AHCS to GL. |  |  | Phase 1A+1B | 2-Gap-Build-Report | Gap | Build | Report | RPT008 | Subledger Period Close Exception Report: This report provides the exceptions in AHCS that are unprocessed, error or invalid transactions. Report should run across all ledgers and across AHCS subledgers. | Validate setups and report with test transactions. Confirm invalid data does not interface / import / post. | Validate incorrect transactions are carved-out of daily interface and not imported to the HUB. Validate the remaining interface transactions that pass validations are import to the HUB. | Review Subledger Period Close Exception Report for error details. Verify that transactions did not import to AHCS until details have been corrected. |  | Approved | Erica | 2021-05-25 |  |  |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  | Ian/Vitaliy | [7 empty] | W3 | User Stories (AHCS Track) - Batch1 GPO Approval
CSTONE-5461 |  | CSTONE-552 |  | CSTONE-3229 | RTR-AHCS-028 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want all transactions interfaced to AHCS are balanced by balancing segment except Central so that no suspense entries are created and balanced journal is posted in AHCS and GL |  |  | Phase 1A+1B | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Journals booked in legacy system will be balanced by a balancing segment value which will be legal entity/business unit/company. | Validate with an unbalanced test transaction | Validate incorrect transactions are carved-out of daily interface and not imported to the HUB. Validate the remaining interface transactions that pass validations are import to the HUB. | Validate that out of balance journals do not get posted in AHCS (should not be balanced using suspense entries). The balancing error must first be resolved and only balanced journals posted in AHCS |  | Approved | Erica | 2021-05-24 |  |  |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  | Ian/Vitaliy | [7 empty] | W3 | User Stories (AHCS Track) - Batch1 GPO Approval
CSTONE-5462 |  | CSTONE-3230 |  | CSTONE-3230 | RTR-AHCS-029 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant I want to ensure that the subledger journals are created in both primary and secondary ledgers where applicable so that I can record journals in both US GAAP/ Local GAAP as per accounting standards | Must Have |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Journals from source systems will be interfaced to both primary and secondary ledgers based on the extract. | Verify that subledger transactions are reflected in both primary and seconday ledgers for LE's that require local stat data. Ensure correct entries are posted with local gaap accounting rules (per business design). In addition verify that appropriate coa has been populated for local stat where applicable. |  |  |  | Approved | Chris Demko | 2021-07-13 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  | Ian/Vitaliy | Ian 11-9-21 | Bhim | N/A | N/A | N/A |  |  | W3 | User Stories (AHCS Track) - Batch1 GPO Approval | 27
CSTONE-5463 | CSTONE-54 | Not in Jira |  | CSTONE-3231 | RTR-AHCS-030 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant, I want to be able to drilldown from the GL journal to AHCS journal so that I can view supporting reference data |  |  | Phase 1A+1B | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Drill-down capability seeded out of the box functionality from GL to AHCS journals | Validate functionality with sample drilldowns and compare between HUB and legacy | Review data for completeness after drilldown to AHCS subledger from balance on GL journal line |  |  | Approved | Erica | 2021-05-24 |  |  |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  | Ian/Vitaliy | [7 empty] | W3 | User Stories (AHCS Track) - Batch1 GPO Approval
CSTONE-5464 |  | CSTONE-568 |  | CSTONE-568 | RTR-AHCS-031 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL accountant, I want the system to process prior period transactions in the current period with manual intervention so that they can be accounted in AHCS |  |  | Phase 1A+1B | 6-Gap-Work Around-Work Around | Gap | Work Around | Work Around |  | No mechanism to update the date in the transaction object table (TO). As a workaround, IT needs to run the purge the error transnactions using "Accounting Hub Maintainance" program. The source system will resend the transaction with the appropriate corrections required for re-processing. IT to make changes based on offline business approval. | Validate setups with a test transaction. |  |  |  | Approved |  | 2021-05-25 |  |  |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  | Ian/Vitaliy | [7 empty] | W3 | User Stories (AHCS Track) - Batch1 GPO Approval
CSTONE-5465 | CSTONE-55 | Not in Jira |  | CSTONE-55 | RTR-AHCS-032 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant, I want non-balance supporting references enabled to capture reference attributes from the source system so that AHCS journals have detail information |  |  | Phase 1A+1B | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Non-balance enabled supporting references to be enabled by each AHCS subledger based on the data model | Validate HUB supporting references by sampling transactions and compare to legacy subledgers | Review non-balance supporting references and ensure match with source system detail information per business design |  |  | Approved | Erica | 2021-05-24 |  |  |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  | Ian/Vitaliy | [7 empty] | W3 | User Stories (AHCS Track) - Batch1 GPO Approval
CSTONE-5466 | CSTONE-56 | Not in Jira |  | CSTONE-56 | RTR-AHCS-033 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant, I want balance supporting references enabled to capture reference attributes from the source system and capture balances so that provides reporting capailities on non chart of account values |  |  | Phase 1A+1B | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Balance enabled supporting references to be enabled by each AHCS subledger based on the data model | Validate HUB supporting references by sampling transactions and compare to legacy subledgers | Validate balanced enabled supporting references by running reports and confirming totals | Review balance supporting references and ensure match with source system detail information per business design |  | Approved | Erica | 2021-05-24 |  |  |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  | Ian/Vitaliy | [7 empty] | W3 | User Stories (AHCS Track) - Batch1 GPO Approval
CSTONE-5467 |  | CSTONE-6257 |  |  | RTR-AHCS-034 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant, I want system to have the capability to sequence all journals for EMEA both primary and statutory ledgers by legal entity so that the statutory ledgers are compliant with the local regulations and US GAAP. | Must Have |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Accounting and Reporting sequences to be enabled for statutory ledgers in EMEA for statutory compliance | Review sequencing of journals was created accurately as per business design and in compliance with local requirements and US GAAP. Ensure there are no gaps in the sequence of journals. Validate that system was configured for journal sequence to reset in countries that require new sequencing each year as per business design. Ensure sequencing of journals is created in secondary ledgers per business design. |  |  |  | Approved | Chris Demko | 2021-07-13 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  | Ian/Vitaliy | Ian 11-15-21 | Bhim - Confirmed by Patrick. Mentioned that this should be applicable for US GAAP as well. |  | N/A | CALA: Beatriz García/Sandra Patiño/Jose Luis Ortiz | Should highlevel comments be rewritten to incorporate CALA? -Ok IP | MS 11/05 - Updated user story to only consider EMEA Stat ledger as secondary ledgers only applicable for EMEA countries | W3 | User Stories (AHCS Track) - Batch1 GPO Approval | 27
CSTONE-5468 | CSTONE-57 | Not in Jira |  | CSTONE-57 | RTR-AHCS-035 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant, I want the subledger journals to be summarized when transferred to GL so that detail level transaction information is maintained in AHCS whereas the account balances are reflected in GL. |  |  | Phase 1A+1B | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Subledger journals interfaced to GL from AHCS will be summarized by accounting string(code combinations) | Validate summary totals to HUB for a sample of data. Reconcile in total between Cloud GL and HUB. | Review summarized balance in GL ties to detail balance in AHCS |  |  | Approved | Erica | 2021-05-24 |  |  |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  | Ian/Vitaliy | [7 empty] | W3 | User Stories (AHCS Track) - Batch1 GPO Approval
CSTONE-5469 | CSTONE-569 | CSTONE-624 | CSTONE-1401 | CSTONE-1401 | RTR-AHCS-036 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL accountant, I want journals from Central to feed AHCS daily so that the journals are reflected in cloud GL. |  |  | Phase 1A only | 3-Gap-Build-Interface | Gap | Build | Interface | INT033 | Daily inbound interface for Sales and Inventory and COGS entries, Commision Accruals from Central to AHCS | Confirm interface completeness and accuracy |  |  |  | Approved | Erica | 2021-05-24 |  |  |  | RTR | RTR-AHCS | AHCS | Deloitte | [10 empty] | W3 | User Stories (AHCS Track) - Batch1 GPO Approval
CSTONE-5470 | CSTONE-570 | CSTONE-625 | CSTONE-1402 | CSTONE-1402 | RTR-AHCS-037 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL accountant, I want statistical journals from Central to AHCS for stock items so that monthly finance charges can be booked in cloud GL. |  |  | Phase 1A only | 3-Gap-Build-Interface | Gap | Build | Interface | INT034 | Monthly statistical feed for finance charges for stock items from Central to AHCS | Build a systematic/automated data completeness check to support the daily imports. Validate / test. Ensure that statistical entries are not recorded as actuals |  |  |  | Approved |  | 2021-05-26 |  |  |  | RTR | RTR-AHCS | AHCS | Deloitte | [10 empty] | W3 | User Stories (AHCS Track) - Batch1 GPO Approval
CSTONE-5471 | CSTONE-571 | CSTONE-626 | CSTONE-1403 | CSTONE-1403 | RTR-AHCS-038 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL accountant, I want statistical journals from Central to AHCS for SO/DSS items so that mothly finance charges can be booked in cloud GL. |  |  | Phase 1A only | 3-Gap-Build-Interface | Gap | Build | Interface | INT035 | Monthly statistical feed for finance charges of SO/DS items from Central to AHCS | Build a systematic/automated data completeness check to support the daily imports. Validate / test. Ensure that statistical entries are not recorded as actuals |  |  |  | Approved |  | 2021-05-26 |  |  |  | RTR | RTR-AHCS | AHCS | Deloitte | [10 empty] | W3 | User Stories (AHCS Track) - Batch1 GPO Approval
CSTONE-5472 | CSTONE-572 | CSTONE-627 | CSTONE-1404 | CSTONE-1404 | RTR-AHCS-039 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL accountant, I want statistical journals from Central to AHCS for monthly finance charges so that finance charges can be booked in cloud GL. |  |  | Phase 1A only | 3-Gap-Build-Interface | Gap | Build | Interface | INT036 | Monthly statistical feed for finance charges from Central to AHCS | Build a systematic/automated data completeness check to support the daily imports. Validate / test. Ensure that statistical entries are not recorded as actuals |  |  |  | Approved |  | 2021-05-26 |  |  |  | RTR | RTR-AHCS | AHCS | Deloitte | [10 empty] | W3 | User Stories (AHCS Track) - Batch1 GPO Approval
CSTONE-5473 | CSTONE-573 | CSTONE-628 | CSTONE-1405 | CSTONE-1405 | RTR-AHCS-040 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL accountant, I want statistical journals from Central to AHCS for inventory items on an order so that finance charges can be booked in cloud GL. |  |  | Phase 1A only | 3-Gap-Build-Interface | Gap | Build | Interface | INT037 | Monthly feed for inventory items that are on an order from Central to AHCS | Build a systematic/automated data completeness check to support the daily imports. Validate / test. Ensure that statistical entries are not recorded as actuals |  |  |  | Approved |  | 2021-05-26 |  |  |  | RTR | RTR-AHCS | AHCS | Deloitte | [10 empty] | W3 | User Stories (AHCS Track) - Batch1 GPO Approval
CSTONE-5474 | CSTONE-595 | CSTONE-1377 | CSTONE-1406 | CSTONE-1406 | RTR-AHCS-041 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL accountant, I want journals from Central to AHCS for sales commission processing and sales accruals so that commissions and accruals can be booked in cloud GL. |  |  | Phase 1A only | 3-Gap-Build-Interface | Gap | Build | Interface | INT038 | Monthly feed for journal entries from sales commision processing and sales accruals from Central to AHCS | Build a systematic/automated data completeness check to support the daily imports. Validate / test. |  |  |  | Approved |  | 2021-05-26 |  |  |  | RTR | RTR-AHCS | AHCS | Deloitte | [10 empty] | W3 | User Stories (AHCS Track) - Batch1 GPO Approval
CSTONE-5475 | CSTONE-596 | CSTONE-1378 | CSTONE-1407 | CSTONE-1407 | RTR-AHCS-042 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL accountant, I want all cloud GL balances to Central account so that journal entries can be created in Central |  |  | Phase 1A only | 3-Gap-Build-Interface | Gap | Build | Interface | INT040 | Outbound cloud GL balances to Central twice (Last day of Month & through 1- 15th of the month) to prepare journals in Central | Build a systematic/automated data completeness check to support feed to Central from AHCS. Validate / test. |  |  |  | Approved |  | 2021-05-26 |  |  |  | RTR | RTR-AHCS | AHCS | Deloitte | [10 empty] | W3 | User Stories (AHCS Track) - Batch1 GPO Approval
CSTONE-5476 | CSTONE-431 | CSTONE-511 | CSTONE-1090 | CSTONE-1090 | RTR-AHCS-043 |  | Record to Report | Manage General Ledger Accounting | Maintain Chart of Accounts | As a Financial Systems Analyst, I need to confirm COA mapping across all systems identified in AHCS-005 workshop have the appropriate controls and security around COA mapping maintenance (i.e. legacy systems, 3rd party applications, Central, etc.). |  |  | Phase 1A only | 3-Gap-Build-Interface | Gap | Build | Interface | INT120 | Build a report to extract COA mappings from centralized mapping engine. User story RTR-GL-135 covers need to secure Maintainance page to specific users only | Utilize a tool and/or report to validate COA maintenance mapping across systems. |  |  |  | Approved | Erica | 2021-06-04 |  |  |  | RTR | RTR-GL | GL | WESCO | [8 empty] | Erica: Probably need to discuss this user story | Add user stories for security related to COA mapping. Create user stories under GL. | W3 | Cornerstone User Stories (RTR-GL) - GPO Approval (Batch3)
CSTONE-5477 | CSTONE-1365 | CSTONE-3640 | CSTONE-3660 | CSTONE-3660 | RTR-AHCS-044 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant I want all transactions from concur are imported and posted into AHCS concur subledger, so that transactions are accounted with detail transaction information in AHCS |  |  | Phase 1A only | 3-Gap-Build-Interface | Gap | Build | Interface | INT016 | Concur team to extract provide data and interface into Oracle Cloud Middleware | Verify transactions from Concur are imported and accounted for in AHCS. Review details for Concur ties to source AHCS details. |  |  |  | Approved | Erica | 2021-05-25 |  |  |  | RTR | RTR-AHCS | AHCS | ABC Corp |  |  | Ian/Vitaliy | [7 empty] | W3 | User Stories (AHCS Track) - Batch1 GPO Approval
CSTONE-5478 |  | CSTONE-5963 |  |  | RTR-AHCS-046 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want AHCS to be configured to process Lease Interface data as per business and accounting rules so that transactions are accounted correctly in Leases Subledger with appropriate line level information , Supporting Reference and other details. | Must Have |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Legacy team to extract third party lease harbor data and interface into Oracle Cloud Middleware | Verify transactions from 3rd party Lease Harbor are imported and accounted for in AHCS. Review details for from Lease Harbor 3rd party ties to source AHCS details. | Also ensure that AHCS data ties to Oracle GL |  |  | Approved | Chris Demko | 2021-07-13 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  | Ian/Vitaliy | Ian 11-9-21 | Bhim | Boon | Rhonda | CALA: Beatriz García/Sandra Patiño/Jose Luis Ortiz |  |  | W3 | User Stories (AHCS Track) - Batch1 GPO Approval | 24
CSTONE-5479 | CSTONE-58 | Not in Jira |  | CSTONE-557 | RTR-AHCS-048 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a Financial Systems Analyst, I need the ability to add suppoorting references to subledger journals so that they can provide balancing on extended chart of account values |  |  | Phase 1A+1B | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | New supporting references can be added in AHCS at any time. For adding balance enabled supporting reference the driver is to load initial balances before usage. | Validate that new supporting reference was received from source system and added to AHCS |  |  |  | Approved | Erica | 2021-05-25 |  |  |  | RTR | RTR-AHCS | AHCS | WESCO |  |  | Ian/Vitaliy | [7 empty] | W3 | User Stories (AHCS Track) - Batch1 GPO Approval
CSTONE-5480 | CSTONE-59 | Not in Jira |  | CSTONE-59 | RTR-AHCS-049 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a Financial Systems Analyst I need the ability to display user transaction identifiers so that they are visible to user journal screen(UTI) |  |  | Phase 1A+1B | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | New user transaction identifiers can be added for user to view additional information. | Validate that user is able to view and access supporting reference. UTI setup by business design. |  |  |  | Approved | Erica | 2021-05-25 |  |  |  | RTR | RTR-AHCS | AHCS | WESCO |  |  | Ian/Vitaliy | [7 empty] | W3 | User Stories (AHCS Track) - Batch1 GPO Approval
CSTONE-5481 | CSTONE-553 |  |  | CSTONE-553 | RTR-GL-113 |  | Record to Report | Manage General Ledger Accounting | Perform Allocations | As a GL Accountant I need the ability to (1) Batch allocations together to run at the same time. (2) Ability to schedule allocations to run automatically. (3) Allocation sweep / branch-in-branch (ie take balance on one account and move to other accounts (4) need ability to reference both currency value and STAT value accounts to support allocations,(5) Workbench group by batch in sequence or in paralell (6) Ability to grab current and prior period values |  |  | Phase 1A+1B | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Configuration options in Calc Manager noted for each bullet in user sotry: 1. RuleSet 2. Scheduling allocations 3. Allocation Formula 4. Allocation formula and currency 5. RuleSet with option of sequence vs parallel 6. Ruleset with multiple Run Time Variables for periods. Different RTV for accounting periods to be used in source in different rules in a ruleset | Allocations support business requirements, run efficiently, and produce accurate results. |  |  |  | Approved | Erica | 2021-06-10 |  |  |  | RTR | RTR-GL | GL | WESCO | [9 empty] | @Viji - Validate pt.6 | W2 | Cornerstone User Stories (RTR-GL) - GPO Approval (Batch4)
CSTONE-5482 | CSTONE-116 |  |  | CSTONE-116 | RTR-GL-114 |  | Record to Report | Manage General Ledger Accounting | Process Reversing Journal Entries | As a GL Accountant, I want to be able to automatically reverse a multicurrency journal entry in next period to make the journal process more accurate and efficient |  |  | Phase 1A+1B | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Use journal reversal functionality using categories enabled for autoreversal. Journal reversed using system functionality will use same entered and accounted amounts as original journals | Successfully reversed original multicurrency journal entry by selecting auto reversal criteria. Verify that original entry was reversed in following period using same rate from original entry. |  |  |  | Approved |  | 2021-05-27 |  |  |  | RTR | RTR-GL | GL | WESCO |  |  | Ian/Vitaliy | [7 empty] | W1 | Cornerstone User Stories (RTR-GL) - GPO Approval (Batch 2)
CSTONE-5483 |  |  |  | N/A | RTR-GL-115 |  | Record to Report | Manage General Ledger Accounting | Process Reversing Journal Entries | As a GL Accountant, I want to be able to copy multicurrency journal entries and reverse signs, i.e., switch debit/credit to make the journal process more accurate and efficient |  |  | Not Required | 10-Not Required-Not Required-Not Required | Not Required | Not Required | Not Required |  | Use journal reversal functionality manually reverse the journal. Journal reversed using system functionality will use same entered and accounted amounts as original journals Note: When you copy journal you cannot reverse signs unless user goes in and manually reverses journal 5/24: Discussed, not required. Covered in user story RTR-GL-116 | Successfully reversed original multicurrency journal entry using copy/reverse option. Verify that original entry was reversed using same rate from original entry. |  |  |  | Approved |  | 2021-05-27 |  |  |  | RTR | RTR-GL | GL | WESCO |  |  | Ian/Vitaliy | [6 empty] | Incorrect user story. Copy does not update signs | W1 | Cornerstone User Stories (RTR-GL) - GPO Approval (Batch 2)
CSTONE-5484 | CSTONE-117 |  |  | CSTONE-117 | RTR-GL-116 |  | Record to Report | Manage General Ledger Accounting | Process Reversing Journal Entries | As a GL Accountant, I want to be able to manually reverse a multicurrency journal entry to make the journal process more accurate and efficient |  |  | Phase 1A+1B | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Use journal reversal functionality manually reverse the journal. Journal reversed using system functionality will use same entered and accounted amounts as original journals | Successfully reversed original multicurrency journal entry by manually booking entry. Verify that original entry was reversed using same rate from original entry. |  |  |  | Approved |  | 2021-05-27 |  |  |  | RTR | RTR-GL | GL | WESCO |  |  | Ian/Vitaliy | [7 empty] | W1 | Cornerstone User Stories (RTR-GL) - GPO Approval (Batch 2)
CSTONE-5485 | CSTONE-597 | CSTONE-3641 | CSTONE-3661 | CSTONE-3661 | RTR-GL-117 |  | Record to Report | Manage General Ledger Accounting | Maintain Chart of Accounts | As a GL Accountant, I need the capability to enter the old chart string in the application and receive the new COA string [Both Legacy WESCO & Legacy Anixter]. Should support multiple code combinations to be mapped |  |  | Phase 1A+1B | 5-Gap-Build-Extension | Gap | Build | Extension | EXT013 | Need to explore feasibility of UI where user can enter legacy COA string and can retrieve future state COA value. Should support multiple code combinations to be mapped | Review the new chart string results to ensure accurate results |  |  |  | Approved |  | 2021-05-27 |  |  |  | RTR | RTR-GL | GL | WESCO |  |  | Ian/Vitaliy | [8 empty] | Cornerstone User Stories (RTR-GL) - GPO Approval (Batch 2)
CSTONE-5486 | CSTONE-598 | CSTONE-1379 | CSTONE-1408 | CSTONE-1408 | RTR-AHCS-051 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As an IT administrator, I need a dashboard to track the daily exceptions between legacy data feed and AHCS so that there is complete visibility by source, category, count, and Dollar combination (The sample dashboard presented by Manpreet in the Core-group meeting) |  |  | Phase 1A+1B | 5-Gap-Build-Extension | Gap | Build | Extension | EXT010 | The user story needs to be modified as the data is based on what is received in AHCS by source, dollar amount, line count(processed vs. error).Dashboard to be real-time. | Validate the data with subledger period close exceptions. Compare the data with the dashboard and ensure accuracy |  |  |  | Approved |  | 2021-05-26 |  |  |  | RTR | RTR-AHCS | AHCS | WESCO | [10 empty] | W3 | User Stories (AHCS Track) - Batch1 GPO Approval
CSTONE-5487 | N/A | N/A | N/A | TBD | RTR-GL-118 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | As an IT administrator, I want period close automation to systematically close the Subledger periods (Intercompany BU) instead of closing them manually so that In the future Intercompany BU model (Phase 1B), WESCO ends up having 50 + BU’s that must be closed (both AP & AR) manually if we don’t have the systematic solution |  |  | Phase 1B only | 5-Gap-Build-Extension | Gap | Build | Extension | N/A | This is about a state where user has reconciled and cleared up any pending data. Requirement is now ability to automate close having a grouping [E.g. by region] Business case: 60+ ledgers to close for AR and AP every month. Assuming 1 min per ledger close, 1*60*2 = 120 min per close cycle. Also bot will ensure all ledgers for a group are closed and someone doesnt miss lets say one ledger in his/her area of ownership 7/29: Based on input from Satheesh, WESCO IT will take it forward for Bot development etc. Changing sub-track to Legacy 8/4: Confirmed by Satheesh based on conversation with bot team that WESCO IT will take it forward | Validate the open and close of the AR & AP subledgers for all ledgers systematically |  |  | - | Review In Progress | [5 empty] | RTR | LEGACY | IC | WESCO | [9 empty] | Moved subtrack to LEGACY as per input from Satheesh | W3
CSTONE-5488 | CSTONE-554 | Not in Jira |  | CSTONE-554 | RTR-AHCS-052 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a Financial System Analyst, I want the all legacy future segment chart of account values to default to zeros so that the mapping rule can be derived based on only actively used chart of account segments |  |  | Phase 1A only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Legacy COA future segment values will be defaulted to zeros. | Validate that the future segments are not populated in AHCS |  |  |  | Approved | Erica | 2021-05-26 |  |  |  | RTR | RTR-AHCS | AHCS | [12 empty] | User Stories (AHCS Track) - Batch1 GPO Approval
CSTONE-5489 | CSTONE-555 | Not in Jira |  | CSTONE-555 | RTR-AHCS-053 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a Financial System Analyst, I want the derive the complete chart of account string for cloud COA in the mapping tool so that the mapping rules are deriving all future segments |  |  | Phase 1A+1B | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Legacy COA to Cloud COA mapping rules for all segments. | Ensure all the chart of accounts segments are available for mapping including the future segments |  |  |  | Approved | Erica | 2021-05-26 |  |  |  | RTR | RTR-AHCS | AHCS | [12 empty] | User Stories (AHCS Track) - Batch1 GPO Approval
CSTONE-5490 | CSTONE-599 | CSTONE-647 | CSTONE-4416 | CSTONE-4416 | REP-RTR-GL-1 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | Legacy Report Name:GL Activity Legacy Report Description:As an Accountant, I need a report of GL activity by LE, GL Account, trans currency, functional currency, and all other charfield values. Capability to filter by any chartfield value and date ranges. This report is used to analyze GL activity. Reference ID:AXE-GL-1 |  |  | Phase 1A+1B | 2-Gap-Build-Report | Gap | Build | Report | RPT046 | GL Journal Line detail report [Merge AXE-GL-1, AXE-GL-7, , AXE-GL-8, AXE-GL-9, AXE-GL-12, AXE-GL-13]. Ensure there is filter criteria by Period status |  |  |  |  | Approved | Erica | 2021-05-27 |  |  |  | RTR | RTR-GL | GL | WESCO |  | AXE-GL-1 |  | Ian/Vitaliy | [7 empty] | Cornerstone User Stories (RTR-GL) - GPO Approval (Batch 2)
CSTONE-5491 | CSTONE-600 | CSTONE-4396 | CSTONE-4417 | CSTONE-4417 | REP-RTR-GL-2 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | Legacy Report Name:GL Balances Legacy Report Description:As an Accountant, I need a report of GL balances by LE, GL Account, trans currency, functional currency, and all other charfield values. Capability to filter by any chartfield value and date ranges. This report is used to analyze GL activity. Reference ID:AXE-GL-2 |  |  | Phase 1A+1B | 2-Gap-Build-Report | Gap | Build | Report | RPT047 | New balance report by entered and accounted Note: Why SmartView is not useful - Many people will use it |  |  |  |  | Approved | Erica | 2021-05-27 |  |  |  | RTR | RTR-GL | GL | WESCO |  | AXE-GL-2 |  | Ian/Vitaliy | [7 empty] | Cornerstone User Stories (RTR-GL) - GPO Approval (Batch 2)
CSTONE-5492 | CSTONE-6842 | Not in Jira | Not in Jira | Sprint 11 | REP-RTR-GL-3 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | Legacy Report Name:GL I/C Balances Legacy Report Description:As an Accountant, I need a report of I/C Payables and Receivables balances by LE, account, affiliate (or GL cloud equivalent), cost center, and other chartfield values. Capability to filter by LE, Affliate, account, and other chartfield values. This report is used to analyze I/C balances Reference ID:AXE-GL-3 |  |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report | RPT048 | IC Balance Matrix: IC Balance report by GL balances [based on IC segment and specific natural accounts] Note: Why SmartView is not useful - Many people will use it 6/22: Changed release to 1B only as per email confirmation from Erica with subject "GL Reports Prioritization" |  |  |  | Sprint 11 | Approved | Erica | 2021-05-27 |  | #REF! |  | RTR | RTR-GL | GL | WESCO |  | AXE-GL-3 |  | Ian/Vitaliy | [7 empty] | Cornerstone User Stories (RTR-GL) - GPO Approval (Batch 2)
CSTONE-5493 | CSTONE-601 | CSTONE-3642 | CSTONE-3662 | CSTONE-3662 | REP-RTR-GL-4 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | Legacy Report Name:GL I/C Activity Legacy Report Description:As an Accountant, I need a report of I/C Payables and Receivables activity by LE, account, affiliate (or GL cloud equivalent), cost center, and other chartfield values. Capability to filter by LE, Affliate, account, and other chartfield values. This report is used to analyze I/C activity. Reference ID:AXE-GL-4 |  |  | Phase 1A+1B | 2-Gap-Build-Report | Gap | Build | Report | RPT009 | Merge with GL Drill down report - User story RTR-GL-077 |  |  |  |  | Approved | Erica | 2021-05-27 |  |  |  | RTR | RTR-GL | GL | WESCO |  | AXE-GL-4 |  | Ian/Vitaliy | [7 empty] | Cornerstone User Stories (RTR-GL) - GPO Approval (Batch 2)
CSTONE-5494 | CSTONE-9208 | CSTONE-9209 | CSTONE-9210 | Sprint 12 | REP-RTR-GL-5 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | Legacy Report Name:GL Revaluation Legacy Report Description:As an Accountant, I need a report of FX revaluation (using month-end rate) by account, LE, location and other chartfield values. This report is used to analyze current period FX exposure (currently GL 36) Reference ID:AXE-GL-5 |  |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report | RPT049 | Revaluation summary at COA level [all COA segments]. Run report after reval is executed in system |  |  |  | Sprint 12 | Approved | Erica | 2021-05-27 |  | #REF! |  | RTR | RTR-GL | GL | WESCO |  | AXE-GL-5 |  | Ian/Vitaliy | [7 empty] | Cornerstone User Stories (RTR-GL) - GPO Approval (Batch 2)
CSTONE-5495 | CSTONE-9211 | CSTONE-9212 | CSTONE-9213 | Sprint 12 | REP-RTR-GL-6 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | Legacy Report Name:GL Revaluation by account Legacy Report Description:As an accountant, I need a report which shows the monthly revaluation amount for each account for a particular LE. This report is used for FX analysis Reference ID:AXE-GL-6 |  |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report | RPT050 | Revaluation summary at COA level [only LE & Account]. Run report after reval is executed in system |  |  |  | Sprint 12 | Approved | Erica | 2021-05-27 |  | #REF! |  | RTR | RTR-GL | GL | WESCO |  | AXE-GL-6 |  | Ian/Vitaliy | [7 empty] | Cornerstone User Stories (RTR-GL) - GPO Approval (Batch 2)
CSTONE-5496 | CSTONE-602 | CSTONE-650 | CSTONE-4418 | CSTONE-4418 | REP-RTR-GL-7 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | Legacy Report Name:GL Activity by journal enter and post date Legacy Report Description:As an Accountant, I need a report of GL activity by LE, GL Account, trans currency, functional currency, and all other charfield values. Capability to filter by any chartfield value, Journal entered date, journal posted data or date ranges. This report is used to analyze GL activity by posted date. Reference ID:AXE-GL-7 |  |  | Phase 1A+1B | 2-Gap-Build-Report | Gap | Build | Report | RPT046 | GL Journal Line detail report [Merge AXE-GL-1, AXE-GL-7, , AXE-GL-8, AXE-GL-9, AXE-GL-12, AXE-GL-13]. Ensure there is filter criteria by Period status |  |  |  |  | Approved | Erica | 2021-05-27 |  |  |  | RTR | RTR-GL | GL | WESCO |  | AXE-GL-7 |  | Ian/Vitaliy | [7 empty] | Cornerstone User Stories (RTR-GL) - GPO Approval (Batch 2)
CSTONE-5497 | CSTONE-603 | CSTONE-651 | CSTONE-4419 | CSTONE-4419 | REP-RTR-GL-8 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | Legacy Report Name:GL Journal detail Legacy Report Description:As an accountant, I need a report which shows all journal lines for the specific JE (JE ID and period is the input data). Currently in PS GL 28 Reference ID:AXE-GL-8 |  |  | Phase 1A+1B | 2-Gap-Build-Report | Gap | Build | Report | RPT046 | GL Journal Line detail report [Merge AXE-GL-1, AXE-GL-7, , AXE-GL-8, AXE-GL-9, AXE-GL-12, AXE-GL-13]. Ensure there is filter criteria by Period status |  |  |  |  | Approved | Erica | 2021-05-27 |  |  |  | RTR | RTR-GL | GL | WESCO |  | AXE-GL-8 |  | Ian/Vitaliy | [7 empty] | Cornerstone User Stories (RTR-GL) - GPO Approval (Batch 2)
CSTONE-5498 | CSTONE-604 | CSTONE-652 | CSTONE-4420 | CSTONE-4420 | REP-RTR-GL-9 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | Legacy Report Name:Journal activity by status Legacy Report Description:As an accountant, I need a report of all journals processed by status foe example: posted, entered, validated, deleted…. (JE status and period is the input data). Currently in PS GL 08 Reference ID:AXE-GL-9 |  |  | Phase 1A+1B | 2-Gap-Build-Report | Gap | Build | Report | RPT046 | GL Journal Line detail report [Merge AXE-GL-1, AXE-GL-7, , AXE-GL-8, AXE-GL-9, AXE-GL-12, AXE-GL-13]. Ensure there is filter criteria by Period status |  |  |  |  | Approved |  | 2021-05-27 |  |  |  | RTR | RTR-GL | GL | WESCO |  | AXE-GL-9 |  | Ian/Vitaliy | [7 empty] | Cornerstone User Stories (RTR-GL) - GPO Approval (Batch 2)
CSTONE-5499 | CSTONE-605 | CSTONE-1380 | CSTONE-1409 | CSTONE-1409 | REP-RTR-GL-10 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | Legacy Report Name:Current month FX rates Legacy Report Description:As an accountant, I need a report of all current FX rates loaded in GL by currency and rate type (budget, month end, average, daily). Currently in PS GL 35 Reference ID:AXE-GL-10 |  |  | Phase 1A+1B | 2-Gap-Build-Report | Gap | Build | Report | RPT051 | FX Rates loaded in ERP to be pulled out for reporting [Create date range and period as parameters]. Created separate EPM line for budget rates |  |  |  |  | Approved |  | 2021-05-27 |  |  |  | RTR | RTR-GL | GL | WESCO |  | AXE-GL-10 |  | Ian/Vitaliy | [7 empty] | Cornerstone User Stories (RTR-GL) - GPO Approval (Batch 2)
CSTONE-5500 | CSTONE-606 | CSTONE-1381 | CSTONE-1410 | CSTONE-1410 | REP-RTR-GL-12 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | Legacy Report Name:Historical FX rates by date Legacy Report Description:As an accountant, I need a report of all historical FX rates loaded in GL by date, currency and rate type (budget, month end, average, daily). Ability to filter by date and currency and geography (if loaded multiple times per day). Currently in PS GL 60 Reference ID:AXE-GL-11 |  |  | Phase 1A+1B | 2-Gap-Build-Report | Gap | Build | Report | RPT051 | FX Rates loaded in ERP to be pulled out for reporting [Create date range and period as parameters]. Created separate EPM line for budget rates |  |  |  |  | Approved |  | 2021-05-27 |  |  |  | RTR | RTR-GL | GL | WESCO |  | AXE-GL-11 |  | Ian/Vitaliy | [7 empty] | Cornerstone User Stories (RTR-GL) - GPO Approval (Batch 2)
CSTONE-5501 | CSTONE-607 | CSTONE-655 | CSTONE-4421 | CSTONE-4421 | REP-RTR-GL-14 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | Legacy Report Name:Report of journals which failed CVR Legacy Report Description:I need a report that Lists all accounting events and journal entries that fail period close validation. Groups report by ledger, period, journal source, journal category, and event class at submission. Reference ID:AXE-GL-12 |  |  | Phase 1A+1B | 2-Gap-Build-Report | Gap | Build | Report | RPT046 | GL Journal Line detail report [Merge AXE-GL-1, AXE-GL-7, , AXE-GL-8, AXE-GL-9, AXE-GL-12, AXE-GL-13]. Ensure there is filter criteria by Period status |  |  |  |  | Approved |  | 2021-05-27 |  |  |  | RTR | RTR-GL | GL | WESCO |  | AXE-GL-12 |  | Ian/Vitaliy | [7 empty] | Cornerstone User Stories (RTR-GL) - GPO Approval (Batch 2)
CSTONE-5502 | CSTONE-608 | CSTONE-656 | CSTONE-4422 | CSTONE-4422 | REP-RTR-GL-15 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | Legacy Report Name:Journals entered not posted Legacy Report Description:I need a report that Lists journal entries that have been entered not posted. Reference ID:AXE-GL-13 |  |  | Phase 1A+1B | 2-Gap-Build-Report | Gap | Build | Report | RPT046 | GL Journal Line detail report [Merge AXE-GL-1, AXE-GL-7, , AXE-GL-8, AXE-GL-9, AXE-GL-12, AXE-GL-13]. Ensure there is filter criteria by Period status |  |  |  |  | Approved |  | 2021-05-27 |  |  |  | RTR | RTR-GL | GL | WESCO |  | AXE-GL-13 |  | Ian/Vitaliy | [7 empty] | Cornerstone User Stories (RTR-GL) - GPO Approval (Batch 2)
CSTONE-5503 | CSTONE-609 | CSTONE-657 | CSTONE-4423 | CSTONE-4423 | REP-RTR-GL-67-A |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | Legacy Report Name:IT extracts GL data for Tax compliance work Legacy Report Description: |  |  | Phase 1A only | 2-Gap-Build-Report | Gap | Build | Report | RPT046 | This Tax reporting requirement needs to bring subledger and GL details together. Sample of subledger fields would be Tax Code on Invoice level, payment term etc. In future state for Phase 1 this is expected to driven out of multiple systems: 1. Legacy EBS to provide subledger details similar to today 2. Using COA mapping extension users would take old COA values from report, use the COA engine to map to new COA values & add back new COA values to report from EBS. This would give subledger details in future state COA 2. For on-system entities GL journal line detail reports with filter on journal source [manual/spreadsheet] can be used to layer in manual journals 3. As need FCCS can be used to pull additional TB level details Note: This investigation process may start with pt.3 i.e. from FCCS and then go to GL and subledger i.e. in inverse order of noted above as well. This user story is used to track GL Journal line detail report |  |  |  |  | Approved | Erica | 2021-06-10 |  |  |  | RTR | RTR-GL | GL | WESCO |  | WES-SUM-7 | [7 empty] | Awaiting input from Satheesh |  | Cornerstone User Stories (RTR-GL) - GPO Approval (Batch4)
CSTONE-5504 | CSTONE-610 | CSTONE-3643 | CSTONE-3663 | CSTONE-3663 | REP-RTR-GL-67-B |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | Legacy Report Name:IT extracts GL data for Tax compliance work Legacy Report Description: |  |  | Phase 1A only | 5-Gap-Build-Extension | Gap | Build | Extension | EXT013 | This Tax reporting requirement needs to bring subledger and GL details together. Sample of subledger fields would be Tax Code on Invoice level, payment term etc. In future state for Phase 1 this is expected to driven out of multiple systems: 1. Legacy EBS to provide subledger details similar to today 2. Using COA mapping extension users would take old COA values from report, use the COA engine to map to new COA values & add back new COA values to report from EBS. This would give subledger details in future state COA 2. For on-system entities GL journal line detail reports with filter on journal source [manual/spreadsheet] can be used to layer in manual journals 3. As need FCCS can be used to pull additional TB level details Note: This investigation process may start with pt.3 i.e. from FCCS and then go to GL and subledger i.e. in inverse order of noted above as well. This user story is used to track COA mapping extension that user can trigger where user provides multiple old/legacy COA values & utility returns new COA values |  |  |  |  | Approved | Erica | 2021-06-10 |  |  |  | RTR | RTR-GL | GL | WESCO |  | WES-SUM-7 | [7 empty] | Awaiting input from Satheesh |  | Cornerstone User Stories (RTR-GL) - GPO Approval (Batch4)
CSTONE-5505 | Not in Jira | Not in Jira |  |  | RTR-AHCS-054 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a Financial Controller, I want a user role that will provide the access to only EBS AR subledger so that the user is restricted to a specific AHCS subledger |  |  | Phase 1A+1B | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Enabling EBS AR subledger security by user roles | Ensure all the chart of accounts segments are available for mapping including the future segments |  |  |  | Approved | Erica | 2021-05-26 |  |  |  | RTR | SECURITY | AHCS | [12 empty] | User Stories (AHCS Track) - Batch1 GPO Approval
CSTONE-5506 |  |  |  |  | RTR-AHCS-055 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As an IT administrator, I want the capability to modify the source transaction information for any exceptions post business approval so that the transactions completd in error can be re-porcessed with corrections |  |  | Phase 1A+1B | [5 empty] | IT administrator should able to make modifications to the data except accoutning attributes in error post business approval to reprocess data in AHCS |  |  |  |  | Initial Fit/Gap Complete | [5 empty] | RTR | SECURITY | AHCS
CSTONE-5507 |  |  |  |  | RTR-AHCS-056 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant I want all transactions from concur to be sent in new COA and no COA mapping required in cloud before posting in Concur subledger, so that transactions are accounted using source segment values | Must Have |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Concur will be providing the data in the new cloud COA and no mapping transformation will take place 02/02 : As per conversation from 0201 Concur will send data in old COA and we will map this to new COA. | Ensure concur transactions accurately posted into AHCS. Validate AHCS contains all supporting references as per business design. Ensure transactions are posted in both primary and secondary ledger. |  |  |  | Approved | Chris Demko | 2021-07-13 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  | Ian/Vitaliy | Ian 11-9-21 | Bhim | N/A | Rhonda | Betty | What is the difference between -056 and 061? - Ok IP We haven't fully discussed concur as yet. Ok per Manpreet comments 11-9-21 | MS 11/05 - This story is to ensure and verify that CONCUR is sending data in new COA. MS 11/09 - This have been program guidance and agreed with Concur project |  | User Stories (AHCS Track) - Batch1 GPO Approval | 26.1
CSTONE-5508 |  | Not in Jira |  |  | RTR-AHCS-057 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As an IT administrator, I want the ability to make changes to AHCS configuration so that meet business requirments |  |  | Phase 1A+1B | 1-Fit-Configuration-Functional | Fit | Configuration | Functional | [6 empty] | Initial Fit/Gap Complete | [5 empty] | RTR | SECURITY | AHCS
CSTONE-5509 |  |  |  |  | RTR-AHCS-058 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a Financial controller,I want to users to have access only specific ledger/ledger set so that data security by ledger/ledger set is enabled |  |  | Phase 1A+1B | [10 empty] | Initial Fit/Gap Complete | [5 empty] | RTR | SECURITY | AHCS
CSTONE-5510 |  | Not in Jira |  |  | RTR-AHCS-059 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL accountant, I want the ability to run create accounting on demand so that any errors/exceptions can be reprocessed during period close |  |  | Phase 1A+1B | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Create Accounting job execution on-demand for un-accounted transnactions by user |  |  |  |  | Initial Fit/Gap Complete | [5 empty] | RTR | SECURITY | AHCS
CSTONE-5511 | CSTONE-107 | CSTONE-50 | CSTONE-1411 | CSTONE-1411 | RTR-GL-119 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | GL Open Balances (YTD plus Current Fiscal Year period balances) - WESCO Primary Ledgers |  |  | Phase 1A only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV001 | GL Conversion for Legacy WESCO Primary ledgers | Validate / reconcile data loads from legacy to cloud |  |  |  | Approved | Erica | 2021-06-02 |  |  |  | RTR | RTR-GL | GL | WESCO | [11 empty] | Cornerstone User Stories (RTR-GL) - GPO Approval (Batch3)
CSTONE-5512 | N/A | N/A | N/A | N/A | RTR-GL-120 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | Currency Rates required to support reporting ledgers with translation [for beginnging balances] |  |  | Phase 1B only | 10-Not Required-Not Required-Not Required | Not Required | Not Required | Not Required | CNV002 (DESCOPED) | Exchange rates needed to support month end TB translation for reporting ledgers For acceptance criteria 1: Balance validation is covered in usr story RTR-GL-123 | Validate rates were acurately loaded in the system. Ensure the beginning balances for reporting ledger matches legacy balances. |  |  | - | Approved | Erica | 2021-07-14 |  | #REF! |  | RTR | RTR-GL | GL | WESCO |  |  | Ian/Vitaliy | [8 empty] | User Stories - GL Batch 6 GPO Approval
CSTONE-5513 | CSTONE-5739 | CSTONE-6258 | CSTONE-6301 | CSTONE-5513 | RTR-GL-121 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | GL Open Balances (YTD plus Current Fiscal Year period balances) - Anixter Secondary Ledger |  |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV003 | GL Conversion for Legacy Anixter Secondary ledgers |  |  |  | Sprint 8 | Approved | Erica | 2021-06-04 |  | #REF! |  | RTR | RTR-GL | GL | WESCO | [11 empty] | Cornerstone User Stories (RTR-GL) - GPO Approval (Batch3)
CSTONE-5514 | CSTONE-5740 | CSTONE-6668 | CSTONE-6302 | CSTONE-5514 | RTR-GL-122 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | GL Open Balances (YTD plus Current Fiscal Year period balances) - Anixter Primary Ledger |  |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV004 | GL Conversion for Legacy Anixter Primary ledgers |  |  |  | Sprint 8 | Approved | Erica | 2021-06-04 |  | #REF! |  | RTR | RTR-GL | GL | WESCO | [11 empty] | Cornerstone User Stories (RTR-GL) - GPO Approval (Batch3)
CSTONE-5515 | CSTONE-5741 | CSTONE-6259 | CSTONE-6303 | CSTONE-5515 | RTR-GL-123 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | GL Open Balances (YTD plus Current Fiscal Year period balances) - Anixter Reporting Ledgers. As a GL Accountant, I want the ability to load beginning balances for reporting ledgers. |  |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV010 | GL Conversion for Legacy Anixter Reporting ledgers E.g. Reporting ledgers for Russia, Turkey and Indonesia Note: This user story is not applicable to reporting ledgers with month end translation. For month end translations there will be no extract from legacy. Rates as per RTR-GL-120 will be loaded & source ledger data will be translated. Any differences in translation as compared to legacy offline computations cannot be adjusted | Validate the beginning balances for all reporting ledgers have been loaded correctly. Reconciled loaded balances to source data. Validate the configuration of reporting ledgers as per business design. |  |  | Sprint 8 | Approved | Erica | 2021-07-11 |  | #REF! |  | RTR | RTR-GL | GL | WESCO |  |  | Ian/Vitaliy | [8 empty] | User Stories - GL Batch 6 GPO Approval
CSTONE-5516 | CSTONE-115 | CSTONE-60 | CSTONE-1091 | CSTONE-1091 | RTR-GL-124 |  | Record to Report | Manage General Ledger Accounting | Maintain Chart of Accounts | COA Mapping - COA Mapping Service |  |  | Phase 1A+1B | 5-Gap-Build-Extension | Gap | Build | Extension | EXT001 | Use case: Ability to build a Centralized COA Mapping Engine to support COA transformation to future state for multiple legacy COA scenarios |  |  |  |  | Approved | Erica | 2021-06-04 |  |  |  | RTR | RTR-GL | GL | WESCO | [11 empty] | Cornerstone User Stories (RTR-GL) - GPO Approval (Batch3)
CSTONE-5517 | CSTONE-118 | CSTONE-61 | CSTONE-1092 | CSTONE-1092 | RTR-GL-125 |  | Record to Report | Manage General Ledger Accounting | Maintain Chart of Accounts | COA Mapping - Mapping Engine |  |  | Phase 1A+1B | 5-Gap-Build-Extension | Gap | Build | Extension | EXT002 | Use case: Ability to build a Centralized COA Mapping Engine to support COA transformation to future state for multiple legacy COA scenarios |  |  |  |  | Approved | Erica | 2021-06-04 |  |  |  | RTR | RTR-GL | GL | WESCO | [11 empty] | Cornerstone User Stories (RTR-GL) - GPO Approval (Batch3)
CSTONE-5518 | CSTONE-119 | CSTONE-65 | N/A | CSTONE-119 | RTR-GL-126 |  | Record to Report | Manage General Ledger Accounting | Maintain Chart of Accounts | COA Mapping - Validation Engine - France Local COA |  |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | EXT003 | Use case: Ability to build a Centralized COA Mapping Engine to support COA transformation to future state for multiple legacy COA scenarios |  |  |  |  | Approved | Erica | 2021-06-04 |  | #REF! |  | RTR | RTR-GL | GL | WESCO | [11 empty] | Cornerstone User Stories (RTR-GL) - GPO Approval (Batch3)
CSTONE-5519 | CSTONE-120 | CSTONE-66 | CSTONE-1093 | CSTONE-1093 | RTR-GL-127 |  | Record to Report | Manage General Ledger Accounting | Maintain Chart of Accounts | COA Mapping - Mapping Report |  |  | Phase 1A+1B | 5-Gap-Build-Extension | Gap | Build | Extension | INT120 | Use case: Ability to pull report of current state code block mapping values |  |  |  |  | Approved | Erica | 2021-06-04 |  |  |  | RTR | RTR-GL | GL | WESCO | [11 empty] | Cornerstone User Stories (RTR-GL) - GPO Approval (Batch3)
CSTONE-5520 | CSTONE-121 | CSTONE-69 | CSTONE-1094 | CSTONE-1094 | RTR-GL-128 |  | Record to Report | Manage General Ledger Accounting | Maintain Chart of Accounts | COA Mapping - Oracle COA value import for validations |  |  | Phase 1A+1B | 5-Gap-Build-Extension | Gap | Build | Extension | INT121 (DESCOPED) | Use case: Ability to build a Centralized COA Mapping Engine to support COA transformation to future state for multiple legacy COA scenarios |  |  |  |  | Approved | Erica | 2021-06-04 |  |  |  | RTR | RTR-GL | GL | WESCO | [11 empty] | Cornerstone User Stories (RTR-GL) - GPO Approval (Batch3)
CSTONE-5521 | CSTONE-122 | CSTONE-70 | CSTONE-1095 | CSTONE-1095 | RTR-GL-129 |  | Record to Report | Manage General Ledger Accounting | Maintain Chart of Accounts | COA Mapping - Validation Engine - Global COA |  |  | Phase 1A+1B | 5-Gap-Build-Extension | Gap | Build | Extension | EXT004 (DESCOPED) | Use case: Ability to build a Centralized COA Mapping Engine to support COA transformation to future state for multiple legacy COA scenarios |  |  |  |  | Approved | Erica | 2021-06-04 |  |  |  | RTR | RTR-GL | GL | WESCO | [11 empty] | Cornerstone User Stories (RTR-GL) - GPO Approval (Batch3)
CSTONE-5522 |  |  |  | N/A | RTR-GL-130 |  | Record to Report | Manage General Ledger Accounting | Maintain Chart of Accounts | COA Mapping - UI - Chart structure definition in COA engine [Configuration screen] |  |  | Not Required | 10-Not Required-Not Required-Not Required | Not Required | Not Required | Not Required | EXT005 (DESCOPED) | Use case: Ability to use COA Mapping engine & mapping rules maintenance for Off-systems 7/7: No longer required based on approved KDD23A. Approved Lean spec document "EXT001- EXT002- EXT014-COA Mapping Engine" documents that engine configs will be loaded as installation scripts and not through UI build |  |  |  |  | Approved | Erica | 2021-07-11 |  |  |  | RTR | RTR-GL | GL | WESCO |  |  | Erica: Off-Systems TBD | [6 empty] | KDD23A approved, comments section updated & set to not required. Ready for approval |  | User Stories - GL Batch 6 GPO Approval
CSTONE-5523 |  |  |  | N/A | RTR-GL-131 |  | Record to Report | Manage General Ledger Accounting | Maintain Chart of Accounts | COA Mapping - UI - Mapping rule definition for pair of charts. |  |  | Not Required | 10-Not Required-Not Required-Not Required | Not Required | Not Required | Not Required | EXT006 (DESCOPED) | Use case: Ability to use COA Mapping engine & mapping rules maintenance for Off-systems 7/7: No longer required based on approved KDD23A. Approved Lean spec document "EXT001- EXT002- EXT014-COA Mapping Engine" documents that engine configs will be loaded as installation scripts and not through UI build |  |  |  |  | Approved | Erica | 2021-07-11 |  |  |  | RTR | RTR-GL | GL | WESCO |  |  | Erica: Off-Systems TBD | [6 empty] | KDD23A approved, comments section updated & set to not required. Ready for approval |  | User Stories - GL Batch 6 GPO Approval
CSTONE-5524 |  |  |  | N/A | RTR-GL-132 |  | Record to Report | Manage General Ledger Accounting | Maintain Chart of Accounts | COA Mapping - UI - Mapping values for a rule [group of segments to group of segments mapping] |  |  | Not Required | 10-Not Required-Not Required-Not Required | Not Required | Not Required | Not Required |  | Duplicate of multiple user stories E.g. RTR-AHCS-015 RTR-AHCS-016 RTR-AHCS-017 |  |  |  |  | Approved | Erica | 2021-06-04 |  |  |  | RTR | RTR-GL | GL | WESCO | [11 empty] | Cornerstone User Stories (RTR-GL) - GPO Approval (Batch3)
CSTONE-5525 | CSTONE-611 | CSTONE-1382 | CSTONE-1412 | CSTONE-1412 | RTR-GL-133 |  | Record to Report | Manage General Ledger Accounting | Maintain Chart of Accounts | COA Mapping - UI - Code combination to code combination mapping for a chart structure pair |  |  | Phase 1A+1B | 5-Gap-Build-Extension | Gap | Build | Extension | EXT008 | Use case: Ability to support COA mapping updates using UI (including Bulk upload) |  |  |  |  | Approved | Erica | 2021-06-04 |  |  |  | RTR | RTR-GL | GL | WESCO | [11 empty] | Cornerstone User Stories (RTR-GL) - GPO Approval (Batch3)
CSTONE-5526 | CSTONE-612 | CSTONE-1383 | CSTONE-1413 | CSTONE-1413 | RTR-GL-134 |  | Record to Report | Manage General Ledger Accounting | Maintain Chart of Accounts | COA Mapping - UI - Bulk upload support |  |  | Phase 1A+1B | 5-Gap-Build-Extension | Gap | Build | Extension | EXT009 | Use case: Ability to support COA mapping updates using UI (including Bulk upload) |  |  |  |  | Approved | Erica | 2021-06-04 |  |  |  | RTR | RTR-GL | GL | WESCO | [11 empty] | Cornerstone User Stories (RTR-GL) - GPO Approval (Batch3)
CSTONE-5527 | CSTONE-613 | CSTONE-3644 | CSTONE-3664 | CSTONE-3664 | RTR-GL-135 |  | Record to Report | Manage General Ledger Accounting | Maintain Chart of Accounts | COA Mapping - Enable Page / application level security to COA Mapper custom application |  |  | Phase 1A+1B | 5-Gap-Build-Extension | Gap | Build | Extension | EXT012 | Use case: Ability to support COA mapping updates using UI (including Bulk upload) |  |  |  |  | Approved | Erica | 2021-06-04 |  |  |  | RTR | RTR-GL | GL | WESCO | [11 empty] | Cornerstone User Stories (RTR-GL) - GPO Approval (Batch3)
CSTONE-5528 |  |  |  | N/A | RTR-GL-136 |  | Record to Report | Manage General Ledger Accounting | Maintain Chart of Accounts | COA Mapping - Derive user initiated bulk Old COA to new COA mapping |  |  | Not Required | 10-Not Required-Not Required-Not Required | Not Required | Not Required | Not Required |  | Duplicate of RTR-GL-117 |  |  |  |  | Approved | Erica | 2021-06-04 |  |  |  | RTR | RTR-GL | GL | WESCO | [11 empty] | Cornerstone User Stories (RTR-GL) - GPO Approval (Batch3)
CSTONE-5529 | CSTONE-123 | CSTONE-74 | CSTONE-1096 | CSTONE-2644 | RTR-GL-137 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | Outbound to:Teradata Outbound from:Cloud GL Feed Type:GL Balance [Functional currency, Actuals] Feed#:Tera Data Feed 2 |  |  | Phase 1A+1B | 3-Gap-Build-Interface | Gap | Build | Interface | INT010 | Interface to BI tool as per KDD8 | Validate / reconcile data loads from Cloud GL to Teradata |  |  |  | Approved | Erica | 2021-06-02 |  |  |  | RTR | RTR-GL | GL | WESCO | [11 empty] | Cornerstone User Stories (RTR-GL) - GPO Approval (Batch3)
CSTONE-5530 | CSTONE-5742 | CSTONE-6260 | CSTONE-6304 | CSTONE-5530 | RTR-GL-138 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | Outbound to:IAP Outbound from:Cloud GL Feed Type:GL Balances Feed#:IAP Feed 3 |  |  | Phase 1B Only | 3-Gap-Build-Interface | Gap | Build | Interface | INT042 | Interface to BI tool as per KDD8 |  |  |  | Sprint 8 | Approved | Erica | 2021-06-04 |  | #REF! |  | RTR | RTR-GL | GL | WESCO | [11 empty] | Cornerstone User Stories (RTR-GL) - GPO Approval (Batch3)
CSTONE-5531 | CSTONE-124 | CSTONE-75 | CSTONE-1097 | CSTONE-2646 | RTR-GL-139 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | Outbound to:Teradata Outbound from:Cloud GL Feed Type:GL Journals Feed#:Tera Data Feed 1 |  |  | Phase 1A+1B | 3-Gap-Build-Interface | Gap | Build | Interface | INT011 | Interface to BI tool as per KDD8 | Validate / reconcile data loads from Cloud GL to Teradata | Confirm expense exceptions tool queries and reports Cloud GL journals stored in Teradata correctly |  |  | Approved | Erica | 2021-06-02 |  |  |  | RTR | RTR-GL | GL | WESCO | [11 empty] | Cornerstone User Stories (RTR-GL) - GPO Approval (Batch3)
CSTONE-5532 | CSTONE-5743 | CSTONE-6261 | CSTONE-6305 | CSTONE-5532 | RTR-GL-140 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | Outbound to:IAP Outbound from:Cloud GL Feed Type:GL Journals Feed#:IAP Feed 1 |  |  | Phase 1B Only | 3-Gap-Build-Interface | Gap | Build | Interface | INT021 | Interface to BI tool as per KDD8 |  |  |  | Sprint 8 | Approved | Erica | 2021-06-04 |  | #REF! |  | RTR | RTR-GL | GL | WESCO | [11 empty] | Cornerstone User Stories (RTR-GL) - GPO Approval (Batch3)
CSTONE-5533 | CSTONE-614 | CSTONE-3645 | CSTONE-3665 | CSTONE-3665 | RTR-GL-141 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | Outbound to:TeraData Outbound from:Cloud AHCS Feed Type:AHCS Details Feed#:Tera Data Feed 4 |  |  | Phase 1A Only | 3-Gap-Build-Interface | Gap | Build | Interface | INT012 | Interface to BI tool as per KDD8 | Validate / reconcile data loads from Cloud HUB to Teradata |  |  |  | Approved | Erica | 2021-06-02 |  |  |  | RTR | RTR-AHCS | AHCS | WESCO | [11 empty] | Cornerstone User Stories (RTR-GL) - GPO Approval (Batch3)
CSTONE-5534 |  |  |  |  | RTR-GL-142 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | Outbound to:IAP [or Auditable BI tool] Outbound from:Cloud AHCS Feed Type:AHCS Details Feed#:IAP Feed 2 |  |  | Phase 1B Only | 3-Gap-Build-Interface | Gap | Build | Interface | INT043 | Interface to BI tool as per KDD8 |  |  |  |  | Approved | Erica | 2021-06-04 |  | #REF! |  | RTR | RTR-GL | GL | ABC Corp | [11 empty] | Approved On Thu 1/20/2022 9:17 PM
CSTONE-5535 | CSTONE-615 | CSTONE-3646 | CSTONE-3666 | CSTONE-3666 | RTR-GL-143 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | Outbound to:TeraData Outbound from:Cloud AHCS Feed Type:AHCS Reconciliation Balances Feed#:Tera Data Feed 3 |  |  | Phase 1A Only | 3-Gap-Build-Interface | Gap | Build | Interface | INT041 | Interface to BI tool as per KDD8 | Validate / reconcile data loads from Cloud HUB to Teradata |  |  |  | Approved | Erica | 2021-06-02 |  |  |  | RTR | RTR-AHCS | AHCS | WESCO | [11 empty] | Cornerstone User Stories (RTR-GL) - GPO Approval (Batch3)
CSTONE-5536 |  |  |  |  | RTR-GL-144 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | Outbound to:IAP [or Auditable BI tool] Outbound from:Cloud AHCS Feed Type:AHCS Reconciliation Balances Feed#:IAP Feed 4 |  |  | Phase 1B Only | 3-Gap-Build-Interface | Gap | Build | Interface | INT044 | Interface to BI tool as per KDD8 |  |  |  |  | Approved | Erica | 2021-06-04 |  | #REF! |  | RTR | RTR-GL | GL | ABC Corp | [11 empty] | Approved On Thu 1/20/2022 9:17 PM
CSTONE-5537 | CSTONE-616 | CSTONE-1384 | CSTONE-1414 | CSTONE-1414 | RTR-GL-145 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | Outbound to:OnDemand Outbound from:Cloud GL Feed Type:GL Balances & Daily Journal summary [specific accounts] Feed#:On Demand Feed 1 |  |  | Phase 1A only | 3-Gap-Build-Interface | Gap | Build | Interface | INT007 (DESCOPED) | Interface to BI tool as per KDD8 | Validate daily Flash report |  |  |  | Approved | Erica | 2021-06-02 |  |  |  | RTR | RTR-GL | GL | WESCO | [11 empty] | Cornerstone User Stories (RTR-GL) - GPO Approval (Batch3)
CSTONE-5538 | CSTONE-617 | CSTONE-1385 | CSTONE-1415 | CSTONE-1415 | RTR-GL-146 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | Outbound to:Central Outbound from:Cloud GL Feed Type:GL Balances - Certain accounts Feed#:Central Feed 1 |  |  | Phase 1A Only | 3-Gap-Build-Interface | Gap | Build | Interface | INT040 | GL Interface to Central as per KDD25 | Validate Cloud GL data extracts and load to Central |  |  |  | Approved | Erica | 2021-06-02 |  |  |  | RTR | RTR-GL | GL | WESCO | [11 empty] | Cornerstone User Stories (RTR-GL) - GPO Approval (Batch3)
CSTONE-5539 | CSTONE-125 | CSTONE-76 | CSTONE-1416 | CSTONE-1416 | RTR-GL-147 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | COA Mapping - BI / Analytics tool bulk invoke support |  |  | Phase 1A+1B | 5-Gap-Build-Extension | Gap | Build | Extension | EXT014 | Use case: Ability for BI tools to use Centralized COA mapping engine to map legacy COA to Cloud COA |  |  |  |  | Approved | Erica | 2021-06-04 |  |  |  | RTR | RTR-GL | GL | [12 empty] | Cornerstone User Stories (RTR-GL) - GPO Approval (Batch3)
CSTONE-5540 | CSTONE-8807 | CSTONE-11749 | CSTONE-11750 | Sprint 12 | RTR-GL-148 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | As an accountant, I will need a Gl trial balance by LE which shows the Debit and Credit in separate columns. Balances should be accumulated separately by debit and credit column. |  |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report | RPT047 | Required for International reporting. Accounting would not want planned TB report to show Dr/Cr & hence a new custom report 5/10 - RPT018 is descoped and RPT047 wwill meet the tax requirement. Hence, updated Build ID to RPT047 | Reviewed TB for completeness and accuracy. Valid balances in Debit and Credit columns. |  |  |  | Approved | Erica | 2021-07-11 |  | #REF! |  | RTR | RTR-GL | GL | WESCO |  |  | Ian/Vitaliy | [8 empty] | User Stories - GL Batch 6 GPO Approval
CSTONE-5541 | CSTONE-5115 |  |  | CSTONE-5115 | RTR-GL-149 |  | Record to Report | Manage General Ledger Accounting | Maintain Chart of Accounts | As an accountant, I need the ability to assign alternate account values as part of my COA in the secondary ledger (as a supporting reference), the alternate values are linked to the USGAAP GL accounts. The alternate values will be used for statutory reporting. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Assumption: 1 to 1 between USGAAP and local GAAP account. Alternate account number to be stored in translated language description [if language translations enabled and language available in patch applied] OR if all required alternate languages are not available, alternate account numbers to be stored in DFF Acceptance criteria 1 & user story: Not sure what supporting reference is referring to here. As part of this soln we will not be storing alternate accounts in AHCS, but rather will be at COA natural account level as either as DFF or in language translations | Validated alternate accounts as part of supporting reference ties back to USGAAP GL accounts. |  |  | - | Approved | Erica | 2021-07-11 |  | #REF! |  | RTR | RTR-GL | GL | WESCO |  |  | Ian/Vitaliy | [8 empty] | User Stories - GL Batch 6 GPO Approval
CSTONE-5542 | CSTONE-556 |  |  | CSTONE-556 | RTR-GL-150 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | As a GL accountant, I want the exchange rates for foreign currency transnactions imported from FXLoader into Cloud ERP so that I can perform transactions in foreign currencies |  |  | Phase 1A only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | As per KDD3B1 FXLoader will be utilized to import rates. All required computations as per KDD3A would be performed in FXLoader including cross reciprocation. No additional development is required in Cloud ERP. FXLoader will also manage import in Cloud ERP. FXLoader setup and management will be by WESCO team | Validate the Exchange Rates Import from FXLoader into OracleCloud GL |  |  |  | Approved | Erica | 2021-06-22 |  |  |  | RTR | RTR-GL | GL | WESCO | [11 empty] | RTR-GL Batch 5 - GPO Approval
CSTONE-5543 | CSTONE-622 | CSTONE-1388 | CSTONE-1419 | CSTONE-1419 | RTR-GL-151 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | As a GL accountant, I want the exchange rates for foreign currency transnactions transferred from Cloud ERP to Oracle EBS so that I can perform transactions in foreign currencies |  |  | Phase 1A only | 3-Gap-Build-Interface | Gap | Build | Interface | INT047 | Outbound to be built to SFTP Server as per KDD3B to send a snapshot of rates as per frequency to SFTP server. Various systems would then consume same file as required by the systems as per KDD3B architecture Cross reciprocation will be done in FXLoader load to Cloud ERP. This interface will only extract rates from Cloud ERP. No transactions will be interfaced as part of this interface | Validate the Exchange Rates Import from OracleCloudGL into EBS |  |  |  | Approved | Erica | 2021-06-22 |  |  |  | RTR | RTR-GL | GL | WESCO | [11 empty] | RTR-GL Batch 5 - GPO Approval
CSTONE-5544 | CSTONE-5107 |  |  | CSTONE-5107 | RTR-GL-152 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | As a GL accountant, I want the Central Bank exchange rates for foreign currency transnactions imported from FXLoader into Cloud ERP so that I can perform transactions in foreign currencies |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | As per KDD3B2 FXLoader will be utilized to import rates. All required computations as per KDD3A would be performed in FXLoader including cross reciprocation & Central Bank Rates. No additional development is required in Cloud ERP. FXLoader will also manage import in Cloud ERP. FXLoader setup and management will be by WESCO team | Validate the Exchange Rates Import along with the Central Bank Rates into OracleCloud GL |  |  | Sprint 7 | Approved | Erica | 2021-07-11 |  | #REF! |  | RTR | RTR-GL | GL | WESCO |  |  | Ian/Vitaliy | [8 empty] | User Stories - GL Batch 6 GPO Approval
CSTONE-5545 | Not in Jira | CSTONE-6262 | Not in Jira | CSTONE-6262 | RTR-GL-153 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | As a GL accountant, I want the exchange rates for foreign currency transnactions transferred from Cloud ERP to Main Frame so that I can perform transactions in foreign currencies |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT047 | Outbound to be built to SFTP Server as per KDD3B to send a snapshot of rates as per frequency to SFTP server. Various systems would then consume same file as required by the systems as per KDD3B architecture Cross reciprocation will be done in FXLoader load to Cloud ERP. This interface will only extract rates from Cloud ERP | Validate the Exchange Rate feed into MainFrame System with Cross reciprocation |  |  | Sprint 10 | Approved | Erica | 2021-07-11 |  | 1-Fit-Configuration-Functional | Sprint Manually overridden - 1A RICE Demo | RTR | RTR-GL | GL | WESCO |  |  | Ian/Vitaliy | [8 empty] | User Stories - GL Batch 6 GPO Approval
CSTONE-5546 | CSTONE-1366 | CSTONE-4403 | CSTONE-4424 | CSTONE-4424 | REP-FSG-RTR-GL-001 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | Current Type: FSG PROD NAME: GA_BS (GAAP)_TRENDED_YTD PROD Report Title: BALANCE SHEET TRENDED (GAAP) |  |  | Phase 1A+1B | 2-Gap-Build-Report | Gap | Build | Report | RPT052 | Build GL ERP balance based report based on LE actuals only [does not include consolidated/eliminated/budget/forecast etc.] |  |  |  |  | Approved | Erica | 2021-06-04 |  |  |  | RTR | RTR-GL | GL | WESCO | [11 empty] | Cornerstone User Stories (RTR-GL) - GPO Approval (Batch3)
CSTONE-5547 | CSTONE-618 | CSTONE-4404 | CSTONE-4425 | CSTONE-4425 | REP-FSG-RTR-GL-002 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | Current Type: FSG PROD NAME: GA_TB (ACCOUNT)_LE_YTD PROD Report Title: TRIAL BALANCE BY LEGAL ENTITY (ACCOUNT) |  |  | Phase 1A+1B | 2-Gap-Build-Report | Gap | Build | Report | RPT053 | Build GL ERP balance based report based on LE actuals only [does not include consolidated/eliminated/budget/forecast etc.] |  |  |  |  | Approved | Erica | 2021-06-04 |  |  |  | RTR | RTR-GL | GL | WESCO | [11 empty] | Cornerstone User Stories (RTR-GL) - GPO Approval (Batch3)
CSTONE-5548 | CSTONE-1367 | CSTONE-4405 | CSTONE-4426 | CSTONE-4426 | REP-FSG-RTR-GL-003 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | Current Type: FSG PROD NAME: GA_IS (GAAP)_MONTHLY_PTD PROD Report Title: INCOME STATEMENT TRAILING BY MONTH (GAAP) |  |  | Phase 1A+1B | 2-Gap-Build-Report | Gap | Build | Report | RPT054 | Build GL ERP balance based report based on LE actuals only [does not include consolidated/eliminated/budget/forecast etc.] |  |  |  |  | Approved | Erica | 2021-06-04 |  |  |  | RTR | RTR-GL | GL | WESCO | [11 empty] | Cornerstone User Stories (RTR-GL) - GPO Approval (Batch3)
CSTONE-5549 |  |  |  | CSTONE-4390 | REP-FSG-RTR-GL-004 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | Current Type: FSG PROD NAME: GA_BS (GAAP)_COUNTRY_YTD PROD Report Title: BALANCE SHEET BY COUNTRY (GAAP) |  |  | Future Phase | 2-Gap-Build-Report | Gap | Build | Report | RPT055 (DESCOPED) | Build GL ERP balance based report based on LE actuals only [does not include consolidated/eliminated/budget/forecast etc.] 7/16: Phase changed to future phase as per meeting of 7/16 |  |  |  |  | Approved | Erica | 2021-06-04 |  |  |  | RTR | RTR-GL | GL | WESCO | [11 empty] | Cornerstone User Stories (RTR-GL) - GPO Approval (Batch3)
CSTONE-5550 |  |  |  | CSTONE-4391 | REP-FSG-RTR-GL-005 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | Current Type: FSG PROD NAME: GA_IS (GAAP)_COUNTRY_YTD PROD Report Title: INCOME STATEMENT BY COUNTRY (GAAP) |  |  | Future Phase | 2-Gap-Build-Report | Gap | Build | Report | RPT056 (DESCOPED) | Build GL ERP balance based report based on LE actuals only [does not include consolidated/eliminated/budget/forecast etc.] 7/16: Phase changed to future phase as per meeting of 7/16 |  |  |  |  | Approved | Erica | 2021-06-04 |  |  |  | RTR | RTR-GL | GL | WESCO | [11 empty] | Cornerstone User Stories (RTR-GL) - GPO Approval (Batch3)
CSTONE-5551 |  |  |  | CSTONE-4392 | REP-FSG-RTR-GL-006 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | Current Type: FSG PROD NAME: GA_IS (OPER)_TRAILING_QTD PROD Report Title: Income Statement Trailing by Quarter (Operating) with % |  |  | Future Phase | 2-Gap-Build-Report | Gap | Build | Report | RPT057 (DESCOPED) | Build GL ERP balance based report based on LE actuals only [does not include consolidated/eliminated/budget/forecast etc.] 7/16: Phase changed to future phase as per meeting of 7/16 |  |  |  |  | Approved | Erica | 2021-06-04 |  |  |  | RTR | RTR-GL | GL | WESCO | [11 empty] | Cornerstone User Stories (RTR-GL) - GPO Approval (Batch3)
CSTONE-5552 | CSTONE-1368 | CSTONE-4406 | CSTONE-4427 | CSTONE-4427 | REP-FSG-RTR-GL-007 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | Current Type: FSG PROD NAME: GA_TB_BRANCH_ACTUAL PROD Report Title: Trial Balance by Branch - Actual |  |  | Phase 1A+1B | 2-Gap-Build-Report | Gap | Build | Report | RPT058 (DESCOPED) | Build GL ERP balance based report based on LE actuals only [does not include consolidated/eliminated/budget/forecast etc.] |  |  |  |  | Approved | Erica | 2021-06-04 |  |  |  | RTR | RTR-GL | GL | WESCO | [11 empty] | Cornerstone User Stories (RTR-GL) - GPO Approval (Batch3)
CSTONE-5553 | CSTONE-4683 | CSTONE-4684 |  | CSTONE-4684 | REP-FSG-RTR-GL-008 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | Current Type: FSG PROD NAME: GA_TB_BRANCH_STAT PROD Report Title: Trial Balance by Branch - STAT |  |  | Phase 1A+1B | 2-Gap-Build-Report | Gap | Build | Report | RPT059 (DESCOPED) RPT058 (DESCOPED) | Build GL ERP balance based report based on LE actuals only [does not include consolidated/eliminated/budget/forecast etc.] 7/20: Descoped RPT059 and merged with RPT058. We will tag RPT058 and RPT059 as to be merged for now. Once in build we might have to revisit on whether these two can be delivered in single report or discuss with PMO if they cannot be delivered in single report. Summarily we will update RPT 059 as not required for Release 1. |  |  |  |  | Approved | Erica | 2021-06-04 |  |  |  | RTR | RTR-GL | GL | WESCO | [11 empty] | Cornerstone User Stories (RTR-GL) - GPO Approval (Batch3)
CSTONE-5554 | CSTONE-2642 | CSTONE-4407 | CSTONE-4677 | CSTONE-4677 | REP-FSG-RTR-GL-009 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | Current Type: FSG PROD NAME: GA_TB_BRANCH_TRAILING_YTD_ACTUAL PROD Report Title: Trial Balance by Branch Trailing YTD - Actual |  |  | Phase 1A+1B | 2-Gap-Build-Report | Gap | Build | Report | RPT060 | Build GL ERP balance based report based on LE actuals only [does not include consolidated/eliminated/budget/forecast etc.] 7/16: Phase changed to future phase as per meeting of 7/16 10/01: As per subsequent discussions RPT060 was brought in and RPT063 was moved to out of scope |  |  |  |  | Approved | Erica | 2021-06-04 |  |  |  | RTR | RTR-GL | GL | WESCO | [11 empty] | Cornerstone User Stories (RTR-GL) - GPO Approval (Batch3)
CSTONE-5555 |  |  |  | CSTONE-4408 | REP-FSG-RTR-GL-010 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | Current Type: FSG PROD NAME: GA_TB_BRANCH_TRAILING_PTD_ACTUAL PROD Report Title: Trial Balance by Branch Trailing PTD - Actual |  |  | Future Phase | 2-Gap-Build-Report | Gap | Build | Report | RPT061 (DESCOPED) | Build GL ERP balance based report based on LE actuals only [does not include consolidated/eliminated/budget/forecast etc.] 7/16: Phase changed to future phase as per meeting of 7/16 |  |  |  |  | Approved | Erica | 2021-06-04 |  |  |  | RTR | RTR-GL | GL | WESCO | [11 empty] | Cornerstone User Stories (RTR-GL) - GPO Approval (Batch3)
CSTONE-5556 |  |  |  | CSTONE-4409 | REP-FSG-RTR-GL-011 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | Current Type: FSG PROD NAME: GA_TB_BRANCH_TRAILING_PTD_STAT PROD Report Title: Trial Balance by Branch Trailing PTD - STAT |  |  | Future Phase | 2-Gap-Build-Report | Gap | Build | Report | RPT062 (DESCOPED) | Build GL ERP balance based report based on LE actuals only [does not include consolidated/eliminated/budget/forecast etc.] 7/16: Phase changed to future phase as per meeting of 7/16 |  |  |  |  | Approved | Erica | 2021-06-04 |  |  |  | RTR | RTR-GL | GL | WESCO | [11 empty] | Cornerstone User Stories (RTR-GL) - GPO Approval (Batch3)
CSTONE-5557 | CSTONE-1369 | CSTONE-4410 | CSTONE-4428 | CSTONE-4428 | REP-FSG-RTR-GL-012 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | Current Type: FSG PROD NAME: GA_IS(STDCST)_MONTHLY_PTD PROD Report Title: Income Statement Trailing by Month (Standard Cost Operating) |  |  | Not Required | 2-Gap-Build-Report | Gap | Build | Report | RPT063 (DESCOPED) | Build GL ERP balance based report based on LE actuals only [does not include consolidated/eliminated/budget/forecast etc.] 10/1: Based on decision that internal and external statements will be same, this report is no longer required. Marked user story as not required |  |  |  |  | Approved | Erica | 2021-06-04 |  |  |  | RTR | RTR-GL | GL | WESCO | [11 empty] | Cornerstone User Stories (RTR-GL) - GPO Approval (Batch3)
CSTONE-5558 | CSTONE-619 | CSTONE-1386 | CSTONE-1417 | CSTONE-1417 | RTR-AHCS-060 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As an IT administrator, I need a dashboard to track the daily exceptions for Create Accounting Jobs in AHCS so that there is complete visibility of job completion status by source system |  |  | Phase 1A+1B | 5-Gap-Build-Extension | Gap | Build | Extension | EXT011 | Use case: Interface Monitoring Dashboard Extension to derive the status of the Create Accounting jobs for each source system and update them in the AHCS dashboard | Validate the data with subledger period close exceptions. Compare the data with the dashboard and ensure accuracy |  |  |  | Approved | Erica | 2021-06-04 |  |  |  | RTR | RTR-AHCS | AHCS | WESCO | [11 empty] | Cornerstone User Stories (AHCS Track) - GPO Approval (Batch3)
CSTONE-5559 |  |  |  |  | RTR-AHCS-061 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant I want all transactions from concur for ABC Corp and ABC Corp employees imported and posted into AHCS concur subledger, so that transactions are accounted with detail transaction information in AHCS | Must Have |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Concur team to extract provide data and interface into Oracle Cloud Middleware | Verify transactions from Concur are imported and accounted for in AHCS from ABC Corp and ABC Corp. Review details for Concur ties to source AHCS details. | Also ensure that AHCS data ties to Oracle GL |  |  | Approved | Erica | 2021-06-04 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  | Ian 11-9-21 | Bhim | N/A | Rhonda | CALA: Beatriz García/Sandra Patiño/Jose Luis Ortiz | What is the difference between -056 and 061? - Ok IP | MS 11/05 - This story is to verify that CONCUR sends data for both ABC Corp and ABC Corp Business | W1 | User Stories (AHCS Track) - Batch1 GPO Approval | 26.1
CSTONE-5560 | CSTONE-620 | CSTONE-3647 | CSTONE-3667 | CSTONE-3667 | RTR-AHCS-062 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report which reconciles legacy and AHCS balance so that I can perform period end reconciliations |  |  | Phase 1A+1B | 3-Gap-Build-Interface | Gap | Build | Interface | INT041 | Legacy to AHCS Account Balances Reconciliation- BI: Shows legacy code combination and AHCS code combination side by side with AHCS balances. | Validate report and compare to legacy subledger to GL reconciliations. | Review AHCS to GL Reconciliation report for variances between legacy, AHCS. Resolve variances as needed. |  |  | Approved | Erica | 2021-06-04 |  |  |  | RTR | RTR-AHCS | AHCS | Deloitte | [11 empty] | Cornerstone User Stories (AHCS Track) - GPO Approval (Batch3)
CSTONE-5561 |  |  |  |  | RTR-AHCS-063 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report for the spend by employee based on the Concur feed in AHCS so that I can ensure reconciliation of expenses between Concur and AHCS |  |  | Not Required | 10-Not Required-Not Required-Not Required | Not Required | Not Required | Not Required |  | 6/3: To be built in BI. Hence marked as Not Required Spend Analysis by Employee:The report displays the employee expense data for a particular month for reconciliation | Not Required |  |  |  | Approved | Erica | 2021-06-04 |  |  |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  | Ian 11-9-21 | Bhim | N/A | Rhonda | CALA: Beatriz García/Sandra Patiño/Jose Luis Ortiz | CALA: Is this the same situation that was discussed on Oct 28th on session AHCS-30 related to CONCUR -- last minute--? Or the discussion was focused if it is needed the balancing support from Concur by employee? If this user storie is a report from concur to cross the expenses vs what is in books, this is valid to have it |  |  | Cornerstone User Stories (AHCS Track) - GPO Approval (Batch3)
CSTONE-5562 | CSTONE-621 | CSTONE-3648 | CSTONE-3668 | CSTONE-3668 | RTR-AHCS-064 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report with the subledger transaction details so that I can perform ad-hoc analysis on subledger data in AHCS |  |  | Phase 1A+1B | 2-Gap-Build-Report | Gap | Build | Report | RPT009 | Subledger Account Analysis Report: The report to provide the details of the subledger for ad-hoc analysis | Validate report and compare to legacy subledger for reconciliations. |  |  |  | Approved | Erica | 2021-06-08 |  |  |  | RTR | RTR-AHCS | AHCS | Deloitte | [11 empty] | AHCS user story review and approval[Batch 4] - Phase 1A
CSTONE-5563 | CSTONE-434 | CSTONE-671 | CSTONE-1418 | CSTONE-1418 | RTR-AHCS-065 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the EBS POC source system to extract the transactions with based on the approved data model and AHCS to process the transactions with relevant attributes so that that transactions are accounted with detail information in AHCS |  |  | Phase 1A only | 3-Gap-Build-Interface | Gap | Build | Interface | INT122 | Legacy data extract from EBS POC and interface into Oracle Cloud Middleware | Build a systematic/automated data completeness check to support the daily imports. Validate / test. | All attributes defined in EBS POC data model are brought in AHCS and detailed inforrmation is available in AHCS |  |  | Approved | Erica | 2021-06-10 |  |  |  | RTR | RTR-AHCS | AHCS | Deloitte | [11 empty] | User story (AHCS Track) review and approval _Batch 5_ - Phase 1A _KDD23B for POC_
CSTONE-5564 |  |  |  |  | RTR-AHCS-066 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ADP source system to extract the transactions based on the approved data model and AHCS to process the transactions with relevant attributes so that the transactions are accounted with detail information in AHCS |  |  | Not Required | 10-Not Required-Not Required-Not Required | Not Required | Not Required | Not Required |  | Legacy team to extract legacy ADP data and interface into Oracle Cloud Middleware | Build a systematic/automated data completeness check to support the daily imports. Validate / test. | All attributes defined in ADP data model are brought in AHCS and detailed information is available in AHCS |  |  | Approved | Chris Demko | 2021-07-13 |  |  |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  | Ian/Vitaliy | Ian 11-9-21 | N/A | N/A | Rhonda | CALA: Beatriz García/Sandra Patiño/Jose Luis Ortiz | Need to clarify why this is not required. Haven't had meeting to discuss as yet.. Meeting on 11-9-21. Going in assumption is that ADP will be vendor as of right now. | 10/25 - Not required as ADP will be a manual journal process in Cloud GL | W3
CSTONE-5565 | CSTONE-6235 |  |  |  | RTR-AHCS-067 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As IT Administrator, I want Cloud Pay (UK) Source system to extract the transactions from Legacy system, send to Oracle Cloud, OIC to perform validation and transform the data in AHCS approved data model so that AHCS can process the transaction | Must Have |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT018 | Legacy team to extract legacy Cloud Pay (UK) data and interface into Oracle Cloud Middleware | Build a systematic/automated data completeness check to support the daily imports. Validate / test. | All attributes defined in Cloud Pay (UK) data model are brought in AHCS and detailed information is available in AHCS |  |  | Approved | Sijo John Ian Plummer | 11/28/2021 12-23-21 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  | Ian/Vitaliy | Ian |  |  |  | CALA: Beatriz García/Sandra Patiño/Jose Luis Ortiz | Haven't had meeting to discuss as yet. Love to set up meeting |  |  | User Stories (AHCS Track) - Batch2 GPO Approval | 26
CSTONE-5566 |  |  |  |  | RTR-AHCS-068 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the Concur source system to extract the transactions based on the approved data model and AHCS to process the transactions with relevant attributes so that the transactions are accounted with detail information in AHCS |  |  | Not Required | 10-Not Required-Not Required-Not Required | Not Required | Not Required | Not Required |  | This is for Wesco post Phase 1B go-live, Concur will send the data in Future state COA and no COA transformation is required. | Build a systematic/automated data completeness check to support the daily imports. Validate / test. | All attributes defined in Concur data model are brought in AHCS and detailed information is available in AHCS |  |  | Approved | Chris Demko | 2021-07-13 |  |  |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  | Ian/Vitaliy | Ian 11-9-21 | Bhim | N/A | Rhonda | CALA: Beatriz García/Sandra Patiño/Jose Luis Ortiz | Not sure this relates to 1B Please provide further details - Ok IP | 10/25 - Not required as this is duplicate | W3
CSTONE-5567 |  | CSTONE-6263 |  |  | RTR-AHCS-070 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want AHCS to be configured to process Treasury workstation(Power Solutions) Interface data as per business and accounting rules so that transactions are accounted correctly in Treasury Subledger with appropriate line level information , Supporting Reference and other details. | Must Have |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Legacy team to extract legacy Treasury Workstation (Power Solutions) data and interface into Oracle Cloud Middleware | Build a systematic/automated data completeness check to support the daily imports. Validate / test. | All attributes defined in Treasury Workstation data model are brought in AHCS and detailed information is available in AHCS. Also ensure that AHCS data ties to Oracle GL |  |  | Approved | Chris Demko | 2021-07-13 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  | Ian/Vitaliy | Ian 11-9-21 | N/A | N/A | Rhonda | CALA: Beatriz García/Sandra Patiño/Jose Luis Ortiz | Can this be identified that relates to only Power solutions? - Ok IP | MS 11/05 - Userstory updated to relate only for Power Solutions |  | User Stories (AHCS Track) - Batch1 GPO Approval | 23
CSTONE-5568 |  | CSTONE-6185 |  |  | RTR-AHCS-071 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want AHCS to be configured to process SXE(US) Interface data as per business and accounting rules so that transactions are accounted correctly in SXE Subledger with appropriate line level information , Supporting Reference and other details. | Must Have |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Legacy team to extract legacy SXE data and interface into Oracle Cloud Middleware | Build a systematic/automated data completeness check to support the daily imports. Validate / test. | All attributes defined in SXE data model are brought in AHCS and detailed information is available in AHCS. Also ensure that AHCS data ties to Oracle GL |  |  | Approved | Chris Demko | 2021-07-13 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  | Ian/Vitaliy | Ian 11-9-21 | N/A | N/A | N/A | Rhonda |  |  | W1 | User Stories (AHCS Track) - Batch1 GPO Approval | 21
CSTONE-5569 | CSTONE-6186 | Not in Jira |  |  | RTR-AHCS-072 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want AHCS to be configured to process Eclipse Interface data as per business and accounting rules so that transactions are accounted correctly in Eclipse Subledger with appropriate line level information , Supporting Reference and other details. | Must Have |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Legacy team to extract legacy Eclipse data and interface into Oracle Cloud Middleware | Build a systematic/automated data completeness check to support the daily imports. Validate / test. | All attributes defined in Eclipse data model are brought in AHCS and detailed information is available in AHCS. Also ensure that AHCS data ties to Oracle GL |  |  | Approved | Chris Demko | 2021-07-13 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  | Ian/Vitaliy | Ian 11-9-21 | N/A | N/A | N/A | Rhonda |  |  | W1 | User Stories (AHCS Track) - Batch1 GPO Approval | 22
CSTONE-5570 |  |  |  |  | RTR-AHCS-073 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the IAP source system to extract the transactions based on the approved data model and AHCS to process the transactions with relevant attributes so that the transactions are accounted with detail information in AHCS |  |  | Not Required | 10-Not Required-Not Required-Not Required | Not Required | Not Required | Not Required |  | Legacy team to extract IAP data and interface into Oracle Cloud Middleware | Build a systematic/automated data completeness check to support the daily imports. Validate / test. |  |  |  | Approved | Chris Demko | 2021-07-13 |  |  |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  | Ian/Vitaliy | Ian 11-9-21 | Bhim | Boon Hui | Rhonda | CALA: Beatriz García/Sandra Patiño/Jose Luis Ortiz | I don't understand the acceptance criteria as relates to user story | MS 11/05 - Acceptance criteria updated. During revised workshops/ KDD session no one confirmed on IAP to Cloud Feed. Please crosscheck MS 11/08 - Marked it as NOT REQUIRED | W3
CSTONE-5571 |  |  |  |  | RTR-AHCS-074 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the PeopleSoft FA source system to extract the transactions based on the approved data model and AHCS to process the transactions with relevant attributes so that the transactions are accounted with detail information in AHCS |  |  | Not Required | 10-Not Required-Not Required-Not Required | Not Required | Not Required | Not Required |  | Legacy team to extract PeopleSoft Fixed asset data and interface into Oracle Cloud Middleware | Build a systematic/automated data completeness check to support the daily imports. Validate / test. |  |  |  | Approved | Chris Demko | 2021-07-13 |  |  |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  | Ian/Vitaliy | Ian 11-9-21 | N/A | N/A | Rhonda | CALA: Beatriz García/Sandra Patiño/Jose Luis Ortiz | acceptance criteria not making sense and isn't this a duplicate? - Ok IP | MS 10/25 - Not Required, duplicate | W3
CSTONE-5572 |  | CSTONE-6264 |  |  | RTR-AHCS-075 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant, I want all transactions for Treasury Workstation (Power Solutions) to be recorded in the correct accounting period. | Must Have |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Accounting date from SLA / XLA tables will be utilized for determining the date for AHCS transactions | Confirm accounting dates in legacy subledger and AHCS is same | Verify accounting date in AHCS aligns with correct accounting period for subledger journal. |  |  | Approved | Ian | 2022-01-18 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  | Ian/Vitaliy | Ian 11-9-21 | Bhim | N/A | Rhonda | NA for CALA | How should Cresus be accounted for? Also are we including IAP? Thought we were not. Now updated to exclude IAP and include Cresus | MS 11/08 - Updated | W3 | User Stories (AHCS Track) - Batch1 GPO Approval | 23
CSTONE-5573 |  |  |  |  | RTR-AHCS-077 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant, I want all the transactions from Concur to use Report Payment Processing date attribute as a accounting date so that all transactions are created in the accurate accounting period. to be recorded in the correct accounting period. | Must Have |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Accounting date from SLA / XLA tables will be utilized for determining the date for AHCS transactions | Confirm accounting dates in legacy subledger and HUB is same | Verify transaction date in AHCS aligns with correct accounting period for subledger journal. | Verified accounting date in AHCS ties to date from source application through reporting. |  | Approved | Ian | 2021-12-07 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  | Ian/Vitaliy | Ian 11-9-21 | Bhim | N/A | Rhonda | CALA: Beatriz García/Sandra Patiño/Jose Luis Ortiz | Why not combine with 075? - ok IP | MS 11/05 - Except Concur and MF, all other systems send Accounting date. |  | User Stories (AHCS Track) - Batch1 GPO Approval | 26.1
CSTONE-5574 |  |  |  |  | RTR-AHCS-087 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As a GL accountant, I want a report which needs to be extracted based on the File Name on an Ad hoc basis in order to capture all the details associated with a specific transaction | Must Have |  | Not Required | 10-Not Required-Not Required-Not Required | Not Required | Not Required | Not Required |  | Legacy Report Name: AHCS File Extract Report. Similar to this legacy report a new report needs to be created which captures all the details associated to a specific transaction. This report is to be extracted based on the File Name on an Ad hoc basis | Validate the report with test transactions. |  |  |  | Approved | Chris Demko | 2021-07-13 |  |  |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  | Ian/Vitaliy | Ian 11-9-21 | Bhim | Boon Hui | Rhonda | CALA: Beatriz García/Sandra Patiño/Jose Luis Ortiz | Is this same as interface extract report? Would this be replaced with RPT009? - Ok IP What are the specifics of the report? If unique to today vs tomorrow useful to run a particular transaction to identify any differences. Sent follow up email to Manpreet 11-9-21. Created new user story - IP | MS 11/05 - This story has been marked as NOT REQUIRED. Please reconfirm if this a requirement | W3
CSTONE-5575 | CSTONE-4708 | CSTONE-6265 |  |  | RTR-AHCS-088 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As IT Administrator, I want SII (Sales) Source system to extract the transactions from Legacy system, send to Oracle Cloud, OIC to perform validation and transform the data in AHCS approved data model so that AHCS can processed the transaction | Must Have |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT216, INT217, EXT118 | Legacy team to extract legacy SII(Sales) data and interface into Oracle Cloud Middleware | Build a systematic/automated data completeness check to support the daily imports. Validate / test. | All attributes defined in SII (MF AR) data model are brought in AHCS and detailed inforrmation is available in AHCS |  |  | Approved | Sijo John Ian Plummer | 2021-11-28 |  | Interface | Sprint Manually overridden | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | Boon Hui | Rhonda | CALA: Beatriz García/Sandra Patiño/Jose Luis Ortiz | Sent to Manisha and Sijo to review - IP 11-11 |  | W2 | User Stories (AHCS Track) - Batch2 GPO Approval | 12
CSTONE-5576 | CSTONE-4709 | CSTONE-6266 |  |  | RTR-AHCS-089 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As IT Administrator, I want CAI (Contra) Source system to extract the transactions from Legacy system, send to Oracle Cloud, OIC to perform validation and transform the data in AHCS approved data model so that AHCS can processed the transaction | Must Have |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT218, INT219, EXT119 | Legacy team to extract legacy CAI(Contra) data and interface into Oracle Cloud Middleware | Build a systematic/automated data completeness check to support the daily imports. Validate / test. | All attributes defined in CAI (MF AP) data model are brought in AHCS and detailed inforrmation is available in AHCS |  |  | Approved | Sijo John Ian Plummer | 2021-11-28 |  | Interface | Sprint Manually overridden | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | Boon Hui | Rhonda | CALA: Beatriz García/Sandra Patiño/Jose Luis Ortiz | Sent to Manisha and Sijo to review - IP 11-11 |  | W2 | User Stories (AHCS Track) - Batch2 GPO Approval | 15
CSTONE-5577 | CSTONE-5949 | CSTONE-6267 |  |  | RTR-AHCS-090 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As IT Administrator, I want DAI (Dropped Accruals) Source system to extract the transactions from Legacy system, send to Oracle Cloud, OIC to perform validation and transform the data in AHCS approved data model so that AHCS can processed the transaction | Must Have |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT222, INT223, EXT121 | Legacy team to extract legacy DAI(Dropped Accrual Invoices) data and interface into Oracle Cloud Middleware | Build a systematic/automated data completeness check to support the daily imports. Validate / test. | All attributes defined in DAI (MF Inventory) data model are brought in AHCS and detailed inforrmation is available in AHCS |  |  | Approved | Sijo John Ian Plummer | 2021-11-28 |  | Interface | Sprint Manually overridden | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | Boon Hui | Rhonda | CALA: Beatriz García/Sandra Patiño/Jose Luis Ortiz | Sent to Manisha and Sijo to review - IP 11-11 |  | W2 | User Stories (AHCS Track) - Batch2 GPO Approval | 16
CSTONE-5578 | CSTONE-4710 | CSTONE-6268 |  |  | RTR-AHCS-091 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As IT Administrator, I want API (Trade Invoices) Source system to extract the transactions from Legacy system, send to Oracle Cloud, OIC to perform validation and transform the data in AHCS approved data model so that AHCS can processed the transaction | Must Have |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT218, INT219, EXT119 | Legacy team to extract legacy API(Trade Invoices) data and interface into Oracle Cloud Middleware | Build a systematic/automated data completeness check to support the daily imports. Validate / test. | All attributes defined in API (MF AP) data model are brought in AHCS and detailed inforrmation is available in AHCS |  |  | Approved | Sijo John Ian Plummer | 2021-11-28 |  | Interface | Sprint Manually overridden | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | Boon Hui | Rhonda | CALA: Beatriz García/Sandra Patiño/Jose Luis Ortiz | Sent to Manisha and Sijo to review - IP 11-11 |  | W2 | User Stories (AHCS Track) - Batch2 GPO Approval | 17
CSTONE-5579 | CSTONE-4711 | CSTONE-6269 |  |  | RTR-AHCS-092 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As IT Administrator, I want ADI (Payments) Source system to extract the transactions from Legacy system, send to Oracle Cloud, OIC to perform validation and transform the data in AHCS approved data model so that AHCS can processed the transaction | Must Have |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT218, INT219, EXT119 | Legacy team to extract legacy ADI(Trade Invoices) data and interface into Oracle Cloud Middleware | Build a systematic/automated data completeness check to support the daily imports. Validate / test. | All attributes defined in ADI (MF AP) data model are brought in AHCS and detailed inforrmation is available in AHCS |  |  | Approved | Sijo John Ian Plummer | 2021-11-28 |  | Interface | Sprint Manually overridden | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | Boon Hui | Rhonda | CALA: Beatriz García/Sandra Patiño/Jose Luis Ortiz | Sent to Manisha and Sijo to review - IP 11-11 |  | W2 | User Stories (AHCS Track) - Batch2 GPO Approval | 18
CSTONE-5580 | CSTONE-4712 | CSTONE-6270 |  |  | RTR-AHCS-093 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As IT Administrator, I want LSI (Liability Switch) Source system to extract the transactions from Legacy system, send two seperate file LSIP and LSIR to Oracle Cloud for posting to respective MF AP and MR Subledger, OIC to perform validation and transform the data in AHCS approved data model so that AHCS can processed the transaction | Must Have |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT216, INT217, EXT118, INT218, INT219, EXT119 | Legacy team to extract legacy LSI(Liability Switch) data and interface into Oracle Cloud Middleware | Build a systematic/automated data completeness check to support the daily imports. Validate / test. | All attributes defined in LSIP (MF AP) data model are brought in AHCS and detailed inforrmation is available in AHCS All attributes defined in LSIR (MF AR) data model are brought in AHCS and detailed inforrmation is available in AHCS |  |  | Approved | Sijo John Ian Plummer | 2021-11-28 |  | Interface | Sprint Manually overridden | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | Boon Hui | Rhonda | CALA: Beatriz García/Sandra Patiño/Jose Luis Ortiz | Sent to Manisha and Sijo to review - IP 11-11 |  | W2 | User Stories (AHCS Track) - Batch2 GPO Approval | 8
CSTONE-5581 | Not in Jira | CSTONE-6271 |  |  | RTR-AHCS-094 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want AHCS to be configured to process LSI(Liability Switch) Interface data as per business and accounting rules so that transactions are accounted correctly in MF AP Subledger and MF AR Subledger with appropriate line level information , Supporting Reference and other details. | Must Have |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT216 INT217 INT218 INT219 EXT118 EXT119 | Legacy team to extract legacy LSI(Liability Switch) data and interface into Oracle Cloud Middleware | Build a systematic/automated data completeness check to support the daily imports. Validate / test. | Verified that total amount entered and accounted in AHCS is denoted with status of final through review subledger journal panel. Validate that total amounts in AHCS ties to total from source application through reporting for. Verify that LSI AR and LSI AP are broken out separately. Validate that items were reflected correctly in AHCS based on business and accounting rules. Verified that able to review detail transactions at line level through supporting refernces a per business design. |  |  | Approved | Ian | 2021-12-07 |  | Interface | Sprint Manually overridden | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | Boon Hui | Rhonda | CALA: Beatriz García/Sandra Patiño/Jose Luis Ortiz | Sent to Manisha and Sijo to review - IP 11-11 |  |  | Approved as Batch 3 | 8
CSTONE-5582 | CSTONE-5950 | CSTONE-6272 |  |  | RTR-AHCS-095 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As IT Administrator, I want SSI (Spec Customer) Source system to extract the transactions from Legacy system, send to Oracle Cloud, OIC to perform validation and transform the data in AHCS approved data model so that AHCS can processed the transaction | Must Have |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT222, INT223, EXT121 | Legacy team to extract legacy SSI(Special Customers) data and interface into Oracle Cloud Middleware | Build a systematic/automated data completeness check to support the daily imports. Validate / test. | All attributes defined in SSI (MF Inventory) data model are brought in AHCS and detailed inforrmation is available in AHCS |  |  | Approved | Sijo John Ian Plummer | 2021-11-28 |  | Interface | Sprint Manually overridden | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | Boon Hui | Rhonda | CALA: Beatriz García/Sandra Patiño/Jose Luis Ortiz | Sent to Manisha and Sijo to review - IP 11-11 |  | W2 | User Stories (AHCS Track) - Batch2 GPO Approval | 19
CSTONE-5583 | CSTONE-4713 | CSTONE-6273 |  |  | RTR-AHCS-096 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As IT Administrator, I want AQI (Intercompany) Source system to extract the transactions from Legacy system, send to Oracle Cloud, OIC to perform validation and transform the data in AHCS approved data model so that AHCS can processed the transaction | Must Have |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT218, INT219, EXT119 | Legacy team to extract legacy AQI(Intercompany Invoices) data and interface into Oracle Cloud Middleware | Build a systematic/automated data completeness check to support the daily imports. Validate / test. | All attributes defined in AQI (MF AP) data model are brought in AHCS and detailed inforrmation is available in AHCS |  |  | Approved | Sijo John Ian Plummer | 2021-11-28 |  | Interface | Sprint Manually overridden | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | Boon Hui | Rhonda | CALA: Beatriz García/Sandra Patiño/Jose Luis Ortiz | Sent to Manisha and Sijo to review - IP 11-11 |  | W2 | User Stories (AHCS Track) - Batch2 GPO Approval | 3
CSTONE-5584 | CSTONE-5951 | CSTONE-6274 |  |  | RTR-AHCS-097 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As IT Administrator, I want ICI (Intransit) Source system to extract the transactions from Legacy system, send to Oracle Cloud, OIC to perform validation and transform the data in AHCS approved data model so that AHCS can processed the transaction | Must Have |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT222, INT223, EXT121 | Legacy team to extract legacy ICI(Intransit) data and interface into Oracle Cloud Middleware | Build a systematic/automated data completeness check to support the daily imports. Validate / test. | All attributes defined in ICI (MF Inventory) data model are brought in AHCS and detailed inforrmation is available in AHCS |  |  | Approved | Sijo John Ian Plummer | 2021-11-28 |  | Interface | Sprint Manually overridden | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | Boon Hui | Rhonda | CALA: Beatriz García/Sandra Patiño/Jose Luis Ortiz | Sent to Manisha and Sijo to review - IP 11-11 |  | W2 | User Stories (AHCS Track) - Batch2 GPO Approval | 4
CSTONE-5585 | CSTONE-5952 | CSTONE-6275 |  |  | RTR-AHCS-098 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As IT Administrator, I want AII (Intransit Backout) Source system to extract the transactions from Legacy system, send to Oracle Cloud, OIC to perform validation and transform the data in AHCS approved data model so that AHCS can processed the transaction | Must Have |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT222, INT223, EXT121 | Legacy team to extract legacy AII(Intransit backout) data and interface into Oracle Cloud Middleware | Build a systematic/automated data completeness check to support the daily imports. Validate / test. | All attributes defined in AII (MF Inventory) data model are brought in AHCS and detailed inforrmation is available in AHCS |  |  | Approved | Sijo John Ian Plummer | 2021-11-28 |  | Interface | Sprint Manually overridden | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | Boon Hui | Rhonda | CALA: Beatriz García/Sandra Patiño/Jose Luis Ortiz | Sent to Manisha and Sijo to review - IP 11-11 |  | W2 | User Stories (AHCS Track) - Batch2 GPO Approval | 2
CSTONE-5586 | CSTONE-5953 | CSTONE-6276 |  |  | RTR-AHCS-099 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As IT Administrator, I want FII (Input Output Freight Invoices) Source system to extract the transactions from Legacy system, send to Oracle Cloud, OIC to perform validation and transform the data in AHCS approved data model so that AHCS can processed the transaction | Must Have |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT222, INT223, EXT120 | Legacy team to extract legacy FII(Input output Freight Invoices) data and interface into Oracle Cloud Middleware | Build a systematic/automated data completeness check to support the daily imports. Validate / test. | All attributes defined in FII (MF Inventory) data model are brought in AHCS and detailed inforrmation is available in AHCS |  |  | Approved | Sijo John Ian Plummer | 2021-11-28 |  | Interface | Sprint Manually overridden | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | APAC do not have this interface currently, can we have more information / setup on this interface | Rhonda | CALA: Beatriz García/Sandra Patiño/Jose Luis Ortiz | Sent to Manisha and Sijo to review - IP 11-11 |  | W2 | User Stories (AHCS Track) - Batch2 GPO Approval | 14
CSTONE-5587 | CSTONE-5954 | CSTONE-6277 |  |  | RTR-AHCS-100 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As IT Administrator, I want FTI (Freight Accrual Invoices) Source system to extract the transactions from Legacy system, send to Oracle Cloud, OIC to perform validation and transform the data in AHCS approved data model so that AHCS can processed the transaction | Must Have |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT222, INT223, EXT120 | Legacy team to extract legacy FTI(Freight Accrual Invoices) data and interface into Oracle Cloud Middleware | Build a systematic/automated data completeness check to support the daily imports. Validate / test. | All attributes defined in FTI (MF Inventory) data model are brought in AHCS and detailed inforrmation is available in AHCS |  |  | Approved | Sijo John Ian Plummer | 2021-11-28 |  | Interface | Sprint Manually overridden | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | Boon Hui | Rhonda | CALA: Beatriz García/Sandra Patiño/Jose Luis Ortiz | Sent to Manisha and Sijo to review - IP 11-11 |  | W2 | User Stories (AHCS Track) - Batch2 GPO Approval | 13
CSTONE-5588 | CSTONE-4714 | CSTONE-6278 |  |  | RTR-AHCS-101 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As IT Administrator, I want ARI (Adjustment) Source system to extract the transactions from Legacy system, send to Oracle Cloud, OIC to perform validation and transform the data in AHCS approved data model so that AHCS can processed the transaction | Must Have |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT216, INT217, EXT118 | Legacy team to extract legacy ARI(Adjustments) data and interface into Oracle Cloud Middleware | Build a systematic/automated data completeness check to support the daily imports. Validate / test. | All attributes defined in ARI (MF AR) data model are brought in AHCS and detailed inforrmation is available in AHCS |  |  | Approved | Sijo John Ian Plummer | 2021-11-28 |  | Interface | Sprint Manually overridden | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | Boon Hui | Rhonda | CALA: Beatriz García/Sandra Patiño/Jose Luis Ortiz | Sent to Manisha and Sijo to review - IP 11-11 |  | W2 | User Stories (AHCS Track) - Batch2 GPO Approval | 11
CSTONE-5589 | CSTONE-5955 | CSTONE-6279 |  |  | RTR-AHCS-102 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As IT Administrator, I want ISI (Inventory Sales) Source system to extract the transactions from Legacy system, send to Oracle Cloud, OIC to perform validation and transform the data in AHCS approved data model so that AHCS can processed the transaction | Must Have |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT222, INT223, EXT121 | Legacy team to extract legacy ISI(Inventory Sales) data and interface into Oracle Cloud Middleware | Build a systematic/automated data completeness check to support the daily imports. Validate / test. | All attributes defined in ISI (MF Inventory) data model are brought in AHCS and detailed inforrmation is available in AHCS |  |  | Approved | Sijo John Ian Plummer | 2021-11-28 |  | Interface | Sprint Manually overridden | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | Boon Hui | Rhonda | CALA: Beatriz García/Sandra Patiño/Jose Luis Ortiz | Sent to Manisha and Sijo to review - IP 11-11 |  | W2 | User Stories (AHCS Track) - Batch2 GPO Approval | 1
CSTONE-5590 | CSTONE-4715 | CSTONE-6280 |  |  | RTR-AHCS-103 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As IT Administrator, I want CRI (Cash) Source system to extract the transactions from Legacy system, send to Oracle Cloud, OIC to perform validation and transform the data in AHCS approved data model so that AHCS can processed the transaction | Must Have |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT216, INT217, EXT118 | Legacy team to extract legacy CRI(Cash) data and interface into Oracle Cloud Middleware | Build a systematic/automated data completeness check to support the daily imports. Validate / test. | All attributes defined in CRI (MF AR) data model are brought in AHCS and detailed inforrmation is available in AHCS |  |  | Approved | Sijo John Ian Plummer | 2021-11-28 |  | Interface | Sprint Manually overridden | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | Boon Hui | Rhonda | CALA: Beatriz García/Sandra Patiño/Jose Luis Ortiz | Sent to Manisha and Sijo to review - IP 11-11 |  | W2 | User Stories (AHCS Track) - Batch2 GPO Approval | 10
CSTONE-5591 | CSTONE-5956 | CSTONE-6281 |  |  | RTR-AHCS-104 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As IT Administrator, I want IRI (Inventory Receipt) Source system to extract the transactions from Legacy system, send to Oracle Cloud, OIC to perform validation and transform the data in AHCS approved data model so that AHCS can processed the transaction | Must Have |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT222, INT223, EXT121 | Legacy team to extract legacy IRI(Inventory receipts) data and interface into Oracle Cloud Middleware | Build a systematic/automated data completeness check to support the daily imports. Validate / test. | All attributes defined in IRI (MF Inventory) data model are brought in AHCS and detailed inforrmation is available in AHCS |  |  | Approved | Sijo John Ian Plummer | 2021-11-28 |  | Interface | Sprint Manually overridden | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | Boon Hui | Rhonda | CALA: Beatriz García/Sandra Patiño/Jose Luis Ortiz | Sent to Manisha and Sijo to review - IP 11-11 |  | W2 | User Stories (AHCS Track) - Batch2 GPO Approval | 5
CSTONE-5592 | CSTONE-5957 | CSTONE-6282 |  |  | RTR-AHCS-105 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As IT Administrator, I want IBI (Cost Adjustment) Source system to extract the transactions from Legacy system, send to Oracle Cloud, OIC to perform validation and transform the data in AHCS approved data model so that AHCS can processed the transaction | Must Have |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT222, INT223, EXT121 | Legacy team to extract legacy IBI(Cost Adjustments) data and interface into Oracle Cloud Middleware | Build a systematic/automated data completeness check to support the daily imports. Validate / test. | All attributes defined in IBI (MF Inventory) data model are brought in AHCS and detailed inforrmation is available in AHCS |  |  | Approved | Sijo John Ian Plummer | 2021-11-28 |  | Interface | Sprint Manually overridden | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | Boon Hui | Rhonda | CALA: Beatriz García/Sandra Patiño/Jose Luis Ortiz | Sent to Manisha and Sijo to review - IP 11-11 |  | W2 | User Stories (AHCS Track) - Batch2 GPO Approval | 6
CSTONE-5593 | CSTONE-5958 | CSTONE-6283 |  |  | RTR-AHCS-106 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As IT Administrator, I want CQI (Cost & Quantity Adjustment) Source system to extract the transactions from Legacy system, send to Oracle Cloud, OIC to perform validation and transform the data in AHCS approved data model so that AHCS can processed the transaction | Must Have |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT222, INT223, EXT121 | Legacy team to extract legacy CQI(Cost Quantity Adjustment) data and interface into Oracle Cloud Middleware | Build a systematic/automated data completeness check to support the daily imports. Validate / test. | All attributes defined in CQI (MF Inventory) data model are brought in AHCS and detailed inforrmation is available in AHCS |  |  | Approved | Sijo John Ian Plummer | 2021-11-28 |  | Interface | Sprint Manually overridden | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | Boon Hui | Rhonda | CALA: Beatriz García/Sandra Patiño/Jose Luis Ortiz | Sent to Manisha and Sijo to review - IP 11-11 |  | W2 | User Stories (AHCS Track) - Batch2 GPO Approval | 7
#N/A |  |  |  |  | RTR-AHCS-107 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant I want to ensure that the subledger journals are created in both primary and secondary ledgers where applicable so that transaction are posted in both USGAAP /STAT accounting convention for Austria and Secondary Ledger description fields use Local language |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | The Subledger level conversion process will be used during the Secondary ledger creation which will be assigned with a different Subledger Accounting Method. When the create accounting process is executed Subledger journal entries will be created both in Primary as well as secondary transactions | Verify that subledger transactions are reflected in both primary and seconday ledgers for LE's that require local stat data. Ensure correct entries are posted with local gaap accounting rules (per business design). | Verify that subledger transactions are reflected in both primary and seconday ledgers for LE's that require local stat data. Ensure correct entries are posted with local gaap accounting rules (per business design). In addition verify that appropriate coa has been populated for local stat where applicable. Also validate Secondary Ledger description fields are populated in local language per Business design. |  |  | Approved | Ian | 2021-12-03 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  | Ian 12-3-21 | Bhim | N/A | N/A | N/A |  |  |  | Approved as Batch 3 | 27
#N/A |  |  |  |  | RTR-AHCS-108 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant I want to ensure that the subledger journals are created in both primary and secondary ledgers where applicable so that I can record journals in both GAAP/STAT accounting convention for Germany and Secondary Ledger description fields use Local language |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | The Subledger level conversion process will be used during the Secondary ledger creation which will be assigned with a different Subledger Accounting Method (DEGAAP). When the create accounting process is executed Subledger journal entries will be created both in Primary as well as secondary transactions | Verify that subledger transactions are reflected in both primary and seconday ledgers for LE's that require local stat data. Ensure correct entries are posted with local gaap accounting rules (per business design). | Verify that subledger transactions are reflected in both primary and seconday ledgers for LE's that require local stat data. Ensure correct entries are posted with local gaap accounting rules (per business design). In addition verify that appropriate coa has been populated for local stat where applicable. Also validate Secondary Ledger description fields are populated in local language per Business design. |  |  | Approved | Ian | 2021-12-03 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  | Ian 12-3-21 | Bhim | N/A | N/A | N/A |  |  |  | Approved as Batch 3 | 27
#N/A |  |  |  |  | RTR-AHCS-109 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant I want to ensure that the subledger journals are created in both primary and secondary ledgers where applicable so that I can record journals in both GAAP/STAT accounting convention & Global COA/Local COA respectively for Norway and Secondary Ledger description fields use Local language |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | The Subledger level conversion process will be used during the Secondary ledger creation which will be assigned with a different Subledger Accounting Method (NOGAAP) & Norway Local COA. When the create accounting process is executed Subledger journal entries will be created both in Primary as well as secondary transactions | Verify that subledger transactions are reflected in both primary and seconday ledgers for LE's that require local stat data. Ensure correct entries are posted with local gaap accounting rules (per business design). In addition verify that Norway Local coa has been populated for local stat where applicable. | Verify that subledger transactions are reflected in both primary and seconday ledgers for LE's that require local stat data. Ensure correct entries are posted with local gaap accounting rules (per business design). In addition verify that appropriate coa has been populated for local stat where applicable. Also validate Secondary Ledger description fields are populated in local language per Business design. |  |  | Approved | Ian | 2021-12-03 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  | Ian 12-3-21 | Bhim | N/A | N/A | N/A |  |  |  | Approved as Batch 3 | 27
#N/A |  |  |  |  | RTR-AHCS-110 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant I want to ensure that the subledger journals are created in both primary and secondary ledgers where applicable so that I can record journals in both GAAP/STAT accounting convention & Global COA/Local COA respectively for Spain |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | The Subledger level conversion process will be used during the Secondary ledger creation which will be assigned with a different Subledger Accounting Method (ESGAAP) & Spain Local COA. When the create accounting process is executed Subledger journal entries will be created both in Primary as well as secondary transactions | Verify that subledger transactions are reflected in both primary and seconday ledgers for LE's that require local stat data. Ensure correct entries are posted with local gaap accounting rules (per business design). In addition verify that Spain Local coa has been populated for local stat where applicable. | Verify that subledger transactions are reflected in both primary and seconday ledgers for LE's that require local stat data. Ensure correct entries are posted with local gaap accounting rules (per business design). In addition verify that appropriate coa has been populated for local stat where applicable. Also validate Secondary Ledger description fields are populated in local language per Business design. |  |  | Approved | Ian | 2021-12-03 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  | Ian 12-3-21 | Bhim | N/A | N/A | N/A |  |  |  | Approved as Batch 3 | 27
#N/A |  |  |  |  | RTR-AHCS-111 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant I want to ensure that the subledger journals are created in both primary and secondary ledgers where applicable so that I can record journals in both GAAP/STAT accounting convention & Global COA/Local COA respectively for Poland and Secondary Ledger description fields use Local language |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | The Subledger level conversion process will be used during the Secondary ledger creation which will be assigned with a different Subledger Accounting Method (PLGAAP) & Poland Local COA. When the create accounting process is executed Subledger journal entries will be created both in Primary as well as secondary transactions | Verify that subledger transactions are reflected in both primary and seconday ledgers for LE's that require local stat data. Ensure correct entries are posted with local gaap accounting rules (per business design). In addition verify that Poland Local coa has been populated for local stat where applicable. | Verify that subledger transactions are reflected in both primary and seconday ledgers for LE's that require local stat data. Ensure correct entries are posted with local gaap accounting rules (per business design). In addition verify that appropriate coa has been populated for local stat where applicable. Also validate Secondary Ledger description fields are populated in local language per Business design. |  |  | Approved | Ian | 2021-12-03 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  | Ian 12-3-21 | Bhim | N/A | N/A | N/A |  |  |  | Approved as Batch 3 | 27
#N/A |  |  |  |  | RTR-AHCS-112 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant I want to ensure that the subledger journals are created in both primary and secondary ledgers where applicable so that I can record journals in both GAAP/STAT accounting convention for Saudi Arabia and Secondary Ledger description fields use Local language |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | The Subledger level conversion process will be used during the Secondary ledger creation which will be assigned with a different Subledger Accounting Method. When the create accounting process is executed Subledger journal entries will be created both in Primary as well as secondary transactions | Verify that subledger transactions are reflected in both primary and seconday ledgers for LE's that require local stat data. Ensure correct entries are posted with local gaap accounting rules (per business design). | Verify that subledger transactions are reflected in both primary and seconday ledgers for LE's that require local stat data. Ensure correct entries are posted with local gaap accounting rules (per business design). In addition verify that appropriate coa has been populated for local stat where applicable. Also validate Secondary Ledger description fields are populated in local language per Business design. |  |  | Approved | Ian | 2021-12-03 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  | Ian 12-3-21 | Bhim | N/A | N/A | N/A |  |  |  | Approved as Batch 3 | 27
#N/A |  |  |  |  | RTR-AHCS-113 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want all Concur transactions interfacing to AHCS to be balanced by generating a offset i.e. Liability lines so that transaction is posted successfully in AHCS | Must Have |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Concur only send Expense side of the entry (unbalanced journal), to process in AHCS it should be balanced using AHCS Configurations to create offset line | Validate if Concur transactions are balanced and posted successfully in AHCS | Verified that total lines received from concur per transaction in AHCS offset liability line based on business design. |  |  | Approved | Ian | 2022-01-18 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  | Is this related to the default balancing segment question? Where default bal seg will be used? If so we still haven't discussed and solved for. IP -11/18 |  | Bhim | N/A | Rhonda | Betty | Please clarify this story. Is this related to the spefied default segment? IP 11-16 | MS 11/18 _ Updated |  | Approved On Thu 1/20/2022 9:17 PM | 26.1
#N/A |  |  |  |  | RTR-AHCS-114 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want all transactions interfaced to AHCS are balanced by balancing segment except Concur and Payroll systems so that balanced journal is posted in AHCS and GL | Must Have |  | Not Required | 10-Not Required-Not Required-Not Required | Not Required | Not Required | Not Required |  | Journals booked in legacy system will be balanced by a balancing segment value which will be legal entity/business unit/company. Suspense not enabled in Oracle for unbalanced journal | Validate if all the transactions are balanced when sent to OIC and successfully accounted in AHCS | Also ensure that AHCS data ties to Oracle GL | [8 empty] | RTR | RTR-AHCS | AHCS |  |  |  | Is this related to the default balancing segment question? Where default bal seg will be used? If so we still haven't discussed and solved for. IP -11/18 |  | Bhim | Boon Hui | Rhonda | Betty | Please clarify this story. Is this related to the spefied default segment? IP 11-16 12-15 | MS 11/18 - Updated |  |  | 26.1
#N/A |  |  |  |  | RTR-AHCS-115 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As a GL accountant, I want a report to see the AP Trial Balance so that I can review AP opening and closing balances | Won't Have |  | Phase 1B only | 10-Not Required-Not Required-Not Required | Not Required | Not Required | Not Required |  | 02/03 : Per latest discussion this is not required, removing old reference of user story from comment. Reason this is not required is because we are using the detailed AP trial balance report instead | Review results of report to ensure AP Subledger balances and period activity is correct |  |  |  | Approved | Ian | 2022-02-03 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  | Not required as will use AP Detail TB report. See user stories RTR-AHCS-202, RTR-AHCS-279, RTR-AHCS-280, RTR-AHCS-281, RTR-AHCS-282, RTR-AHCS-283 - IP 2-3-22 | [8 empty] | Approved on Mon 2/7/2022 7:10 PM | 28
#N/A |  |  |  |  | RTR-AHCS-116 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As a GL accountant, I want a report to see the AR Trial Balance so that I can review AR opening and closing balances | Won't Have |  | Phase 1B only | 10-Not Required-Not Required-Not Required | Not Required | Not Required | Not Required |  | 02/03 : Per latest discussion this is not required, removing old reference of user story from comment. Reason this is not required is because we are using the detailed AR trial balance report instead. | Review results of report to ensure AP Subledger balances and period activity is correct |  |  |  | Approved | Ian | 2022-02-03 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  | Not required as will use AR Detail TB report. See user stories RTR-AHCS-203, RTR-AHCS-299, RTR-AHCS-301, RTR-AHCS-300, RTR-AHCS-302, RTR-AHCS-303 - IP 2-3-22 | [8 empty] | Approved on Mon 2/7/2022 7:10 PM | 28
#N/A |  |  |  |  | RTR-AHCS-117 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As a GL accountant, I want a report to search and extract transaction required for Close Out so that I can review the open transaction and submit for closure | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT129 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' Refined version of Subledger Account Analysis Report with only relevant subledger fields: The report to provide the details of the subledger for ad-hoc analysis | User should be allowed to search by different transaction number (like Invoice#, PO# etc.) Transaction to be displayed with required field values | Generate report through entering specific parameters like PO#, Inv#, part#. Reviewed results and confirmed that output is as expected. Through expected results, complete close out process. |  |  | Approved | Ian | 2022-01-18 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim |  |  | Betty |  |  |  | Approved On Thu 1/20/2022 9:17 PM | 28
#N/A |  | Not in Jira |  |  | RTR-AHCS-118 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant, I want all the journals to use MF derived accounting date attribute as Oracle Accounting date so that all transactions are created in the accurate accounting period for MF(all interfaces) | Must Have |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Accounting date from Legacy will be the Accounting Date in SLA / XLA tables and will be utilized for determining the date for AHCS transactions | Confirm accounting dates in legacy subledger and HUB is same | Verify accounting date in AHCS aligns with correct accounting period for subledger journal. | Validate that date from extract file from source system ties to Accounting date in AHCS through reporting. Verify that able to query summarized related JE in Oracle GL in correct specified period. |  | Approved | Ian | 44533 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  | Ian 12-3-21 | Consult with ian on cresus and get understanding, understand that some of the Cresus ME transaction are backdated? Discussion with stakeholder lead to thinking that the Transaction date should be the accounting date? | Boon Hui | Rhonda | Betty | Need further clarification. NB: Cresus is by Trans date. Eg last day of month related items are back dated during close week so lands in correct period. Should trans date for all be used as accounting date? | MS 11/11 - Split this story and create separate story for Cresus to use transaction date (RTR-AHCS-120) |  | Approved as Batch 3 | 31
#N/A |  | CSTONE-6284 |  |  | RTR-AHCS-119 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant, I want all the transactions from Cloud Pay to use File DateStamp attribute as accounting date so that all transactions are created in the accurate accounting period for Cloud Pay (UK). to be recorded in the correct accounting period. | Must Have |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | File Date timestamp will be used as Accounting date for AHCS processing and determine the appropriate period | Cloud Pay transaction is using File Data Timestamap as the accounting date and posted transaction to appropriate period | Verify accounting date in AHCS aligns with correct accounting period for subledger journal. | Verified accounting date in AHCS ties to date from source application through reporting. |  | Approved | Ian | 2021-12-07 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | N/A | N/A | N/A |  |  |  | Approved as Batch 3 | 26
#N/A |  | Not in Jira |  |  | RTR-AHCS-120 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant, I want all the journals to use Transaction date as Accounting date for BKI (Cresus) so that all transactions are created in the accurate accounting period |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Transaction date from Cresus will be used as Accounting Date and period determined accrordingly in AHCS | Verify Transaction date in Cresus is used as accounting date and data posted to correct period | Validate that date from extract file from source system ties to Accounting date in AHCS through reporting. Verify that able to query summarized related JE in Oracle GL in correct specified period. |  |  | Approved | Ian | 44533 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  | Ian 12-3-21 | Bhim | N/A | N/A | N/A |  |  |  | Approved as Batch 3 | 9
#N/A |  | CSTONE-6285 |  |  | RTR-AHCS-121 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As IT Adminstrator, I want to see the details of all Integrations (Inbound and Outbound) which occurred in OIC middleware and AHCS/Cloud GL during the processing of data for all Subledgers |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional | Digital Pulse | Leverage the existing digital pulse platform to see the details of all Integrations (Inbound and Outbound) which occurred during the processing of data for all Subledgers in OIC Middleware and AHCS/Cloud GL | Validate all the inbound & outbound processing status in Digital pulse | All OIC inbound and outbound processing status with timestamp are available in Digital Pulse |  |  | Approved | Sijo John Ian Plummer | 2021-11-28 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | Boon Hui | Rhonda | Betty |  | MS 11/11 - Updated | W2 | User Stories (AHCS Track) - Batch2 GPO Approval | 30
#N/A |  | CSTONE-6286 |  |  | RTR-AHCS-122 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant, I want balance enabled supporting references to capture reference attributes from the source system and capture balances so that provides reporting capabilities on non chart of account values |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Balance enabled supporting references to be enabled by each AHCS subledger based on the data model. Balance enabled supporting references is to be defined at the Subledger level and assigned at the Event Type level. For Phase1B MF AP,MF AR,MF INVENTORY,LEASES,PS FA,Sxe, Eclipse, treasury (powersolutions) has balanced supporting reference | Validate HUB supporting references by sampling transactions and compare to legacy subledgers | Validate through reporting that for each subledger able to run required detailed information based on the business design associated with the specific BSRs for that subledger. In addition verify that report amounts ties to total entered and accounting in AHCS and then to Oracle GL. |  |  | Approved | Ian | 2021-12-07 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | Boon Hui | Rhonda | Betty |  | MS 11/19 - Pending confirmation from Ian to split this into multiple stories by SR |  | Approved as Batch 3 | 28
#N/A | cstone-6236 |  |  |  | RTR-AHCS-123 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As IT Administrator, I want BKI (Cresus) Source system to extract the transactions from Legacy system, send to Oracle Cloud, OIC to perform validation and transform the data in AHCS approved data model so that AHCS can processed the transaction |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT216, INT217, EXT118, INT218, INT219, EXT119 INT240 | Legacy team to extract legacy Cresus data and interface into Oracle Cloud Middleware | Build a systematic/automated data completeness check to support the daily imports. Validate / test. | All attributes defined in MF AP and MF AR data model (for BKI Cresus) are brought in AHCS and detailed information is available in AHCS |  |  | Approved | Sijo John Ian Plummer 12-23-21 |  |  | Interface | Sprint Manually overridden | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | N/A | N/A | N/A |  |  |  | Approved as Batch 3 | 9
#N/A | CSTONE-6237 |  |  |  | RTR-AHCS-124 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As IT Administrator, I want the BKI (Cresus) source system transactions split between MF AP and MF AR Subledger based on Transaction Type to process the transactions with relevant attributes so that transaction is accounted in appropriate subledger. |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT216, INT217, EXT118, INT218, INT219, EXT119 INT240 | Legacy team to extract legacy Cresus data and interface into Oracle Cloud Middleware | Build a systematic/automated data completeness check to support the daily imports. Validate / test. | The Cresus BKI file is split between MF AP and MF AR based on the below logic: WHEN TRANSACTION_TYPE = ''0'' THEN ''AXE_BKIP_CHARGES'' WHEN TRANSACTION_TYPE = ''2'' THEN ''AXE_BKIP_PAYMENTS'' WHEN TRANSACTION_TYPE = ''B'' THEN ''AXE_BKIR_BALANCES'' WHEN TRANSACTION_TYPE = ''1'' THEN ''AXE_BKIR_COLLECTIONS'' |  |  | Approved | Sijo John Ian Plummer 12-23-21 |  |  | Interface | Sprint Manually overridden | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | N/A | N/A | N/A |  |  |  | Approved as Batch 3 | 9
CSTONE-5594 |  | CSTONE-6217 |  |  | RTR-AHCS-125 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want AHCS to be configured to process SII (Sales) Interface data as per business and accounting rules so that transactions are accounted correctly in MF AR Subledger with appropriate line level information , Supporting Reference and other details. | Must Have |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | AHCS Configuration | Verify transactions are accounted correctly in relevant subledger with appropriate attributes | Verified that total amount entered and accounted in AHCS is denoted with status of final through review subledger journal panel. Validate that total amounts in AHCS ties to total from source application through reporting. Validate that items were reflected correctly in AHCS based on business and accounting rules. Verified that able to review detail transactions at line level through supporting references a per business design. |  |  | Approved | Ian | 2021-12-03 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  | Ian 12-3-21 | Bhim | Boon Hui | Rhonda | Betty |  |  |  | Approved as Batch 3 | 12
CSTONE-5595 |  | CSTONE-4717 |  |  | RTR-AHCS-126 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want AHCS to be configured to process CAI (Contra Invoice) Interface data as per business and accounting rules so that transactions are accounted correctly in MF AP Subledger with appropriate line level information , Supporting Reference and other details. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | AHCS Configuration | Verify transactions are accounted correctly in relevant subledger with appropriate attributes | Verified that total amount entered and accounted in AHCS is denoted with status of final through review subledger journal panel. Validate that total amounts in AHCS ties to total from source application through reporting. Validate that items were reflected correctly in AHCS based on business and accounting rules. Verified that able to review detail transactions at line level through supporting references a per business design. |  |  | Approved | Ian | 2021-12-07 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | Boon Hui | Rhonda | Betty |  |  |  | Approved as Batch 3 | 15
CSTONE-5596 |  | Not in Jira |  |  | RTR-AHCS-127 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want AHCS to be configured to process DAI (Dropped Accrual) Interface data as per business and accounting rules so that transactions are accounted correctly in MF Inventory Subledger with appropriate line level information , Supporting Reference and other details. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | AHCS Configuration | Verify transactions are accounted correctly in relevant subledger with appropriate attributes | Verified that total amount entered and accounted in AHCS is denoted with status of final through review subledger journal panel. Validate that total amounts in AHCS ties to total from source application through reporting. Validate that items were reflected correctly in AHCS based on business and accounting rules. Verified that able to review detail transactions at line level through supporting references a per business design. |  |  | Approved | Ian | 2021-12-07 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | Boon Hui | Rhonda | Betty |  |  |  | Approved as Batch 3 | 16
CSTONE-5597 |  | CSTONE-4718 |  |  | RTR-AHCS-128 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want AHCS to be configured to process API (Trade Invoices) Interface data as per business and accounting rules so that transactions are accounted correctly in MF AP Subledger with appropriate line level information , Supporting Reference and other details. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | AHCS Configuration | Verify transactions are accounted correctly in relevant subledger with appropriate attributes | Verified that total amount entered and accounted in AHCS is denoted with status of final through review subledger journal panel. Validate that total amounts in AHCS ties to total from source application through reporting. Validate that items were reflected correctly in AHCS based on business and accounting rules. Verified that able to review detail transactions at line level through supporting references a per business design. |  |  | Approved | Ian | 2021-12-07 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | Boon Hui | Rhonda | Betty |  |  |  | Approved as Batch 3 | 17
CSTONE-5598 |  | CSTONE-4719 |  |  | RTR-AHCS-129 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want AHCS to be configured to process ADI (Payments) Interface data as per business and accounting rules so that transactions are accounted correctly in MF AP Subledger with appropriate line level information , Supporting Reference and other details. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | AHCS Configuration | Verify transactions are accounted correctly in relevant subledger with appropriate attributes | Verified that total amount entered and accounted in AHCS is denoted with status of final through review subledger journal panel. Validate that total amounts in AHCS ties to total from source application through reporting. Validate that items were reflected correctly in AHCS based on business and accounting rules. Verified that able to review detail transactions at line level through supporting references a per business design. |  |  | Approved | Ian | 2021-12-07 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | Boon Hui | Rhonda | Betty |  |  |  | Approved as Batch 3 | 18
CSTONE-5599 |  |  |  |  | RTR-AHCS-130 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want AHCS to be configured to process LSI(Liability Switch) Interface data as per business and accounting rules so that transactions are accounted correctly in MF AP Subledger with appropriate line level information , Supporting Reference and other details. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | AHCS Configuration | Verify transactions are accounted correctly in relevant subledger with appropriate attributes | Verified that total amount entered and accounted in AHCS is denoted with status of final through review subledger journal panel. Validate that total amounts in AHCS ties to total from source application through reporting. Validate that items were reflected correctly in AHCS based on business and accounting rules. Verified that able to review detail transactions at line level through supporting references a per business design. |  |  | Approved | Ian | 2021-12-07 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | Boon Hui | Rhonda | N/A |  |  | W3 | Approved as Batch 3 | 8
CSTONE-5600 |  |  |  |  | RTR-AHCS-131 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want AHCS to be configured to process LSI(Liability Switch) Interface data as per business and accounting rules so that transactions are accounted correctly in MF AR Subledger with appropriate line level information , Supporting Reference and other details. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | AHCS Configuration | Verify transactions are accounted correctly in relevant subledger with appropriate attributes | Verified that total amount entered and accounted in AHCS is denoted with status of final through review subledger journal panel. Validate that total amounts in AHCS ties to total from source application through reporting. Validate that items were reflected correctly in AHCS based on business and accounting rules. Verified that able to review detail transactions at line level through supporting references a per business design. |  |  | Approved | Ian | 2021-12-07 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | Boon Hui | Rhonda | N/A |  |  |  | Approved as Batch 3 | 8
CSTONE-5601 |  | CSTONE-6287 |  |  | RTR-AHCS-132 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want AHCS to be configured to process SSI(Special Customers) Interface data as per business and accounting rules so that transactions are accounted correctly in MF Inventory Subledger with appropriate line level information , Supporting Reference and other details. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | AHCS Configuration | Verify transactions are accounted correctly in relevant subledger with appropriate attributes | Verified that total amount entered and accounted in AHCS is denoted with status of final through review subledger journal panel. Validate that total amounts in AHCS ties to total from source application through reporting. Validate that items were reflected correctly in AHCS based on business and accounting rules. Verified that able to review detail transactions at line level through supporting references a per business design. |  |  | Approved | Ian | 2021-12-07 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | Boon Hui | Rhonda | Betty |  |  |  | Approved as Batch 3 | 19
CSTONE-5602 |  | CSTONE-6288 |  |  | RTR-AHCS-133 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want AHCS to be configured to process AQI(Intercompany Invoices) Interface data as per business and accounting rules so that transactions are accounted correctly in MF AP Subledger with appropriate line level information , Supporting Reference and other details. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | AHCS Configuration | Verify transactions are accounted correctly in relevant subledger with appropriate attributes | Verified that total amount entered and accounted in AHCS is denoted with status of final through review subledger journal panel. Validate that total amounts in AHCS ties to total from source application through reporting. Validate that items were reflected correctly in AHCS based on business and accounting rules. Verified that able to review detail transactions at line level through supporting references a per business design. |  |  | Approved | Ian | 2021-12-07 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | Boon Hui | Rhonda | Betty |  |  |  | Approved as Batch 3 | 3
CSTONE-5603 |  | CSTONE-6289 |  |  | RTR-AHCS-134 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want AHCS to be configured to process ICI(Intransit) Interface data as per business and accounting rules so that transactions are accounted correctly in MF Inventory Subledger with appropriate line level information , Supporting Reference and other details. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | AHCS Configuration | Verify transactions are accounted correctly in relevant subledger with appropriate attributes | Verified that total amount entered and accounted in AHCS is denoted with status of final through review subledger journal panel. Validate that total amounts in AHCS ties to total from source application through reporting. Validate that items were reflected correctly in AHCS based on business and accounting rules. Verified that able to review detail transactions at line level through supporting references a per business design. |  |  | Approved | Ian | 2021-12-07 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | Boon Hui | Rhonda | Betty |  |  |  | Approved as Batch 3 | 4
CSTONE-5604 |  | CSTONE-6290 |  |  | RTR-AHCS-135 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want AHCS to be configured to process AII(Intransit Backout) Interface data as per business and accounting rules so that transactions are accounted correctly in MF Inventory Subledger with appropriate line level information , Supporting Reference and other details. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | AHCS Configuration | Verify transactions are accounted correctly in relevant subledger with appropriate attributes | Verified that total amount entered and accounted in AHCS is denoted with status of final through review subledger journal panel. Validate that total amounts in AHCS ties to total from source application through reporting. Validate that items were reflected correctly in AHCS based on business and accounting rules. Verified that able to review detail transactions at line level through supporting references a per business design. |  |  | Approved | Ian | 2021-12-07 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | Boon Hui | Rhonda | Betty |  |  |  | Approved as Batch 3 | 2
CSTONE-5605 |  | CSTONE-6291 |  |  | RTR-AHCS-136 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want AHCS to be configured to process FII(Input Output Freight Invoices) Interface data as per business and accounting rules so that transactions are accounted correctly in MF Inventory Subledger with appropriate line level information , Supporting Reference and other details. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | AHCS Configuration | Verify transactions are accounted correctly in relevant subledger with appropriate attributes | Verified that total amount entered and accounted in AHCS is denoted with status of final through review subledger journal panel. Validate that total amounts in AHCS ties to total from source application through reporting. Validate that items were reflected correctly in AHCS based on business and accounting rules. Verified that able to review detail transactions at line level through supporting references a per business design. |  |  | Approved | Ian | 2021-12-07 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | APAC do not have FII currently | Rhonda | Betty (CALA did not have transactions in 2021 for this, but eventually could have in the future) so please considerate that it is applicable for CALA too |  |  |  | Approved as Batch 3 | 14
CSTONE-5606 |  | Not in Jira |  |  | RTR-AHCS-137 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want AHCS to be configured to process FTI( Freight Accrual Invoices) Interface data as per business and accounting rules so that transactions are accounted correctly in MF Inventory Subledger with appropriate line level information , Supporting Reference and other details. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | AHCS Configuration | Verify transactions are accounted correctly in relevant subledger with appropriate attributes | Verified that total amount entered and accounted in AHCS is denoted with status of final through review subledger journal panel. Validate that total amounts in AHCS ties to total from source application through reporting. Validate that items were reflected correctly in AHCS based on business and accounting rules. Verified that able to review detail transactions at line level through supporting references a per business design. |  |  | Approved | Ian | 2021-12-07 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | Boon Hui | Rhonda | Betty |  |  |  | Approved as Batch 3 | 13
CSTONE-5607 |  | CSTONE-6218 |  |  | RTR-AHCS-138 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want AHCS to be configured to process ARI( Adjustments) Interface data as per business and accounting rules so that transactions are accounted correctly in MF AR Subledger with appropriate line level information , Supporting Reference and other details. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | AHCS Configuration | Verify transactions are accounted correctly in relevant subledger with appropriate attributes | Verified that total amount entered and accounted in AHCS is denoted with status of final through review subledger journal panel. Validate that total amounts in AHCS ties to total from source application through reporting. Validate that items were reflected correctly in AHCS based on business and accounting rules. Verified that able to review detail transactions at line level through supporting references a per business design. |  |  | Approved | Ian | 2021-12-07 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | Boon Hui | Rhonda | Betty |  |  |  | Approved as Batch 3 | 11
CSTONE-5608 |  | Not in Jira |  |  | RTR-AHCS-139 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want AHCS to be configured to process ISI( Inventory Sales) Interface data as per business and accounting rules so that transactions are accounted correctly in MF Inventory Subledger with appropriate line level information , Supporting Reference and other details. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | AHCS Configuration | Verify transactions are accounted correctly in relevant subledger with appropriate attributes | Verified that total amount entered and accounted in AHCS is denoted with status of final through review subledger journal panel. Validate that total amounts in AHCS ties to total from source application through reporting. Validate that items were reflected correctly in AHCS based on business and accounting rules. Verified that able to review detail transactions at line level through supporting references a per business design. |  |  | Approved | Ian | 2021-12-07 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | Boon Hui | Rhonda | Betty |  |  |  | Approved as Batch 3 | 1
CSTONE-5609 |  | CSTONE-6219 |  |  | RTR-AHCS-140 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want AHCS to be configured to process CRI( Cash) Interface data as per business and accounting rules so that transactions are accounted correctly in MF AR Subledger with appropriate line level information , Supporting Reference and other details. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | AHCS Configuration | Verify transactions are accounted correctly in relevant subledger with appropriate attributes | Verified that total amount entered and accounted in AHCS is denoted with status of final through review subledger journal panel. Validate that total amounts in AHCS ties to total from source application through reporting. Validate that items were reflected correctly in AHCS based on business and accounting rules. Verified that able to review detail transactions at line level through supporting references a per business design. |  |  | Approved | Ian | 2021-12-07 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | Boon Hui | Rhonda | Betty |  |  |  | Approved as Batch 3 | 10
CSTONE-5610 |  | Not in Jira |  |  | RTR-AHCS-141 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want AHCS to be configured to process IRI( Inventory Receipts) Interface data as per business and accounting rules so that transactions are accounted correctly in MF Inventory Subledger with appropriate line level information , Supporting Reference and other details. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | AHCS Configuration | Verify transactions are accounted correctly in relevant subledger with appropriate attributes | Verified that total amount entered and accounted in AHCS is denoted with status of final through review subledger journal panel. Validate that total amounts in AHCS ties to total from source application through reporting. Validate that items were reflected correctly in AHCS based on business and accounting rules. Verified that able to review detail transactions at line level through supporting references a per business design. |  |  | Approved | Ian | 2021-12-07 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | Boon Hui | Rhonda | Betty |  |  |  | Approved as Batch 3 | 5
CSTONE-5611 |  | Not in Jira |  |  | RTR-AHCS-142 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want AHCS to be configured to process IBI( Cost Adjustments) Interface data as per business and accounting rules so that transactions are accounted correctly in MF Inventory Subledger with appropriate line level information , Supporting Reference and other details. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | AHCS Configuration | Verify transactions are accounted correctly in relevant subledger with appropriate attributes | Verified that total amount entered and accounted in AHCS is denoted with status of final through review subledger journal panel. Validate that total amounts in AHCS ties to total from source application through reporting. Validate that items were reflected correctly in AHCS based on business and accounting rules. Verified that able to review detail transactions at line level through supporting references a per business design. |  |  | Approved | Ian | 2021-12-07 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | Boon Hui | Rhonda | Betty |  |  |  | Approved as Batch 3 | 6
CSTONE-5612 |  | Not in Jira |  |  | RTR-AHCS-143 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want AHCS to be configured to process CQI( Cost quantity Adjustment) Interface data as per business and accounting rules so that transactions are accounted correctly in MF Inventory Subledger with appropriate line level information , Supporting Reference and other details. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | AHCS Configuration | Verify transactions are accounted correctly in relevant subledger with appropriate attributes | Verified that total amount entered and accounted in AHCS is denoted with status of final through review subledger journal panel. Validate that total amounts in AHCS ties to total from source application through reporting. Validate that items were reflected correctly in AHCS based on business and accounting rules. Verified that able to review detail transactions at line level through supporting references a per business design. |  |  | Approved | Ian | 2021-12-07 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | Boon Hui | Rhonda | Betty |  |  |  | Approved as Batch 3 | 7
CSTONE-5613 |  |  |  |  | RTR-AHCS-144 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want AHCS to be configured to process Concur Interface data as per business and accounting rules so that transactions are accounted correctly in Concur Subledger with appropriate line level information , Supporting Reference and other details. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | AHCS Configuration | Verify transactions are accounted correctly in relevant subledger with appropriate attributes | Verified that total amount entered and accounted in AHCS is denoted with status of final through review subledger journal panel. Validate that total amounts in AHCS ties to total from source application through reporting. Validate that items were reflected correctly in AHCS based on business and accounting rules. Verified that able to review detail transactions at line level through supporting references a per business design. |  |  | Approved | Ian | 2022-01-18 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | N/A | Rhonda | Betty |  |  | W3 | Approved On Thu 1/20/2022 9:17 PM | 26.1
CSTONE-5614 |  |  |  |  | RTR-AHCS-145 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As IT Administrator, I want Cloud Pay (UK) Source system to extract the transactions from Legacy system, send to Oracle Cloud, OIC to perform validation and transform the data in AHCS approved data model so that AHCS can process the transaction |  |  | Not Required | 10-Not Required-Not Required-Not Required | Not Required | Not Required | Not Required |  | Duplicate of RTR-AHCS-067 | [10 empty] | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | N/A | Rhonda | N/A |  | Duplicate |  |  | 26
CSTONE-5615 |  | CSTONE-6292 |  |  | RTR-AHCS-146 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want AHCS to be configured to process Cloud pay(UK) Interface data so that transactions are accounted correctly in Payroll Subledger with appropriate line level information , Supporting Reference and other details. | Must Have |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | AHCS Configuration | Verify transactions are accounted correctly in relevant subledger with appropriate attributes | Verified that total amount entered and accounted in AHCS is denoted with status of final through review subledger journal panel. Validate that total amounts in AHCS ties to total from source application through reporting. Validate that items were reflected correctly in AHCS based on business and accounting rules. Verified that able to review detail transactions at line level through supporting references a per business design. |  |  | Approved | Ian | 2022-01-18 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | N/A | N/A | N/A |  |  |  | Approved On Thu 1/20/2022 9:17 PM | 26
CSTONE-5616 |  | CSTONE-5964 |  |  | RTR-AHCS-147 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want AHCS to be setup to process Lease Harbor data using ABC Corp and ABC Corp Legacy COA structure so that transactions are accounted correctly in Leases Subledger with appropriate line level information , Supporting Reference and other details. | Must Have |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | AHCS Configuration | Verify transactions are accounted correctly in relevant subledger with appropriate attributes | Verified that total amount entered and accounted in AHCS is denoted with status of final through review subledger journal panel. Validate that total amounts in AHCS ties to total from source application through reporting. Validate that items were reflected correctly in AHCS based on business and accounting rules. Verified that able to review detail transactions at line level through supporting references a per business design(legacy COA for both legacy ABC Corp/ABC Corp for example). |  |  | Approved | Ian | 2022-01-18 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | Boon Hui | Rhonda | Betty |  |  | W3 | Approved On Thu 1/20/2022 9:17 PM | 24
CSTONE-5617 | CSTONE-5960 | CSTONE-6293 |  |  | RTR-AHCS-148 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As IT Administrator, I want SxE - US Source system to extract the transactions from Legacy system, send to Oracle Cloud, OIC to perform validation and transform the data in AHCS approved data model so that AHCS can processed the transaction | Must Have |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT123 | AHCS Configuration | Verify transactions are accounted correctly in relevant subledger with appropriate attributes | All attributes defined in SXE data model are brought in AHCS and detailed information is available in AHCS |  |  | Approved | Sijo John Ian Plummer | 2021-11-28 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | N/A | Rhonda | N/A |  |  | W2 | User Stories (AHCS Track) - Batch2 GPO Approval | 21
CSTONE-5618 | CSTONE-5961 | CSTONE-6294 |  |  | RTR-AHCS-149 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As IT Administrator, I want Eclipse Source system to extract the summary journals from Legacy system, send to Oracle Cloud, OIC to perform validation and transform the data in AHCS approved data model so that AHCS can processed the transaction |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT124 | AHCS Configuration | Verify transactions are accounted correctly in relevant subledger with appropriate attributes | All attributes defined in Eclipse data model are brought in AHCS and detailed information is available in AHCS |  |  | Approved | Sijo John Ian Plummer | 2021-11-28 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | N/A | Rhonda | N/A |  |  | W2 | User Stories (AHCS Track) - Batch2 GPO Approval | 22
CSTONE-5619 | CSTONE-5962 | CSTONE-6295 |  |  | RTR-AHCS-150 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As IT Administrator, I want PeopleSoft Fixed Asset to extract detailed transactions from FA module, send to Oracle Cloud, OIC to perform validation and transform the data in AHCS approved data model so that AHCS can processed the transaction | Must Have |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT184 | AHCS Configuration | Verify transactions are accounted correctly in relevant subledger with appropriate attributes | All attributes defined in Peoplesoft FA data model are brought in AHCS and detailed information is available in AHCS |  |  | Approved | Sijo John Ian Plummer | 2021-11-28 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | N/A | Rhonda | Betty (Applicable only in Puerto Rico) |  |  | W2 | User Stories (AHCS Track) - Batch2 GPO Approval | 20
CSTONE-5620 |  | Not in Jira |  |  | RTR-AHCS-151 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As IT Admistrator, I want AHCS to be configured to process Cresus Interface data so that transactions are accounted correctly in MF AP,MF AR Subledger with appropriate line level information , Supporting Reference and other details. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | AHCS Configuration | Verify if configurations are correct and review | Cresus data is interfaced to AHCS MF AP and MF AR sub ledgers with appropriate line level information , Supporting Reference and other details. |  |  | Approved | Sijo John |  |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | N/A | N/A | N/A |  |  | 2/1/2022 Sijo | Approved on Thu 2/3/2022 2:33 AM | 25
#N/A |  | CSTONE-6296 |  |  | RTR-AHCS-152 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view transactions by GL journal source system (i.e. same as AHCS subledger) so that data is segregated by AHCS subledger |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Existing Phase 1A Functionality Subledger determination approach by source system. E.g., SII, ARI in AHCS will be represented as MF AR journal source and journal category in cloud GL. | User has ability to search GL Journals by Journal Source or Journal category (i.e AHCS subledger) | Verify that Journal Source matches with AHCS subleger. Validated that selected source only relates to subledger data. |  |  | Approved | Ian | 2021-12-03 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  | Ian 12-3-21 | Bhim | Boon Hui | Rhonda | Betty |  |  | W2 | Approved On Thu 1/20/2022 9:17 PM | 31
#N/A |  |  |  |  | RTR-AHCS-153 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a Financial Controller, I do not want users with ability to modify Legacy subledger transaction(source system) flowing in AHCS so that I can ensure data across systems are in sync and can be transactions are auditable | Must Have |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Enable security so that users do not have ability to update AHCS journals interfaced from source applications | User should not access to update any source (Legacy Subledger) transaction in AHCS | Verify that users don't have security to modify Legacy subledger transactions. |  |  | Approved | Manisha | 2022-01-28 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  | manisha? |  | Bhim | Boon Hui | Rhonda | Betty | sent to manisha to review - ip 12-15 |  |  | Approved on Tue 2/1/2022 10:02 AM | 29
#N/A |  |  |  |  | RTR-AHCS-154 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant, I want the system to reject/error any transactions that are created with closed period accounting date so that they are not posted automatically in the current period |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Existing Phase 1A Functionality Transactions created with accounting date for prior period should fail processing when prior period is closed | Validate setups with a test transaction. Confirm that transaction was rejected/errored out through reporting. |  |  |  | Approved | Ian | 2021-12-03 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  | Ian 12-3-21 | Bhim | Boon Hui | Rhonda | Betty |  |  |  | Approved as Batch 3 | 31
#N/A |  |  |  |  | RTR-AHCS-155 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant, I want all foreign currency transactions from source system imported with the currency exchange rate, entered and accounted amount from the source system so that transaction is properly entered and accounted |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Existing Phase 1A Functionality Source system should send both entered and accounted currency along with FX Rate for all transactions in AHCS | Confirm transaction entered and accounted amount in legacy and HUB match | Verify that entered and accounted amount ties to source system based on specified currency exchange rate from source system. In addition verified that entered and accounted amount also posted and matches in oracle GL. |  |  | Approved | Ian | 2021-12-03 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  | Ian 12-3-21 | Bhim | Boon Hui | Rhonda | Betty |  |  |  | Approved as Batch 3 | 31
#N/A |  |  |  |  | RTR-AHCS-156 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report which reconciles legacy and AHCS subledgers so that I can perform period end reconciliations |  |  | Phase 1B only | 10-Not Required-Not Required-Not Required | Not Required | Not Required | Not Required |  | 01/31 : Do not see this in Report rationalisation tracker as of 01/31, hence marking as ' Not required' and routing for approval. Enhance Phase 1A Functionality Legacy to AHCS Reconciliation Report - BI:AHCS to provide the feed with all detail transactions to Tera Data for reconciliations | Validate report and compare to legacy subledger to GL reconciliations. | Reviewed results of the report. Validate that legacy amount ties with AHCS amount for each subledger. Document any differences and research to identify where difference is coming from. |  |  | Approved | Ian | 2022-02-01 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | Boon Hui | Rhonda | Betty |  |  | 2022-02-01 | Approved on Thu 2/3/2022 2:33 AM | 28
#N/A |  |  |  |  | RTR-AHCS-157 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As a GL Accountant, I want a report to reconcile AHCS subldger and Oracle Cloud GL so that I can perform period close reconciliations | Must Have |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report | RPT007_R | Existing Phase 1A Report AHCS to GL Reconciliation Report: Shows AHCS and GL code balances side by side for reconciliation | Validate report and compare to legacy subledger to GL reconciliations. | Reviewed results of report RPT007. Validate that AHCS amount ties with Oracle Cloud GL amount for each subledger. Document any differences and research to identify where difference is coming from. |  |  | Approved | Ian | 2022-01-18 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | Boon Hui | Rhonda | Betty |  |  |  | Approved On Thu 1/20/2022 9:17 PM | 28
#N/A |  | CSTONE-6297 |  |  | RTR-AHCS-158 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As a GL accountant, I want a report with error details along with error descriptions for all failures (mapping, validations etc.) so that I can review and resolve the errors | Must Have |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report | RPT006_R | Existing Phase 1A Report AHCS Error Report: Errors from Cloud AHCS after processing data by incoming file name and error description. Error / process summary with source chart of accounts and error description | Validate setups and report with test transactions. Confirm invalid data does not interface / import / post. | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs. |  |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | Boon Hui | Rhonda | Betty |  |  |  | Approved on Tuesday, January 18, 2022 7:15 PM | 28
#N/A |  |  |  |  | RTR-AHCS-159 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As a GL Accountant, I want a report that shows exceptions for all AHCS subledgers so that during close I can ensure all transactions are processed from AHCS to GL. | Must Have |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional | RPT008 | Existing Phase 1A Report Subledger Period Close Exception Report: This report provides the exceptions in AHCS that are unprocessed, error or invalid transactions. Report should run across all ledgers and across AHCS subledgers. | Validate setups and report with test transactions. Confirm invalid data does not interface / import / post. | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs. |  |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | Boon Hui | is this report available for the business to see as well as IT? Rhonda | Betty |  |  |  | Approved on Tuesday, January 18, 2022 7:15 PM | 28
#N/A |  |  |  |  | RTR-AHCS-160 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant, I want to be able to drilldown from the GL journal to AHCS journal so that I can view supporting reference data |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Drill-down capability seeded out of the box functionality from GL to AHCS journals | Validate functionality with sample drilldowns and compare between HUB and legacy | Verify the ability to drilldown from GL to AHCS subledger details. Verify supporting references are correct based on business design. |  |  | Approved | Ian | 2021-12-03 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  | Ian 12-3-21 | Bhim | Boon Hui | Rhonda | Betty |  |  |  | Approved as Batch 3 | 31
#N/A |  |  |  |  | RTR-AHCS-161 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL accountant, I want the system to automatically process any unaccounted prior period transactions in next period when period is closed so that they can be accounted in AHCS | Must Have |  | Phase 1B only | 6-Gap-Work Around-Work Around | Gap | Work Around | Work Around |  | No mechanism to update the date in the transaction object table (TO). As a workaround, IT needs to run the purge the error transnactions using "Accounting Hub Maintainance" program. The source system will resend the transaction with the appropriate corrections required for re-processing. IT to make changes based on offline business approval. | Validate setups with a test transaction. | Verified that that prior period transaction was posted through Create Accounting in current open period. Ensure that transaction did not post in prior period. Reviewed Accounting date in AHCS. |  |  | Approved | Ian | 2022-01-18 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim, but again there should be a report that should be available to the Accountants so that they are aware of such errors | Boon Hui - agreed that there should be a report for Accoutant to review especially if the next period is cross the year end | Rhonda - agree with Bhim's statement | Betty | Is there a separate report that just identifies scenarios like these? IP 12-15 | MS 11/18 - AHCS Error Report will show such errors |  | Approved On Thu 1/20/2022 9:17 PM | 31
#N/A |  |  |  |  | RTR-AHCS-162 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant, I want non-balance supporting references enabled to capture reference attributes from the source system so that AHCS journals have detail information |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Existing Phase 1A Functionality Non-balance enabled supporting references to be enabled by each AHCS subledger based on the data model. Non-balance enabled supporting references is to be defined at the Subledger level and assigned at the Event Type level. | Validate HUB supporting references by sampling transactions and compare to legacy subledgers | Verified that able to drill down from GL to AHCS by subledger. Review subledger line details have appropriate non balance enabled supporting references per business design. Validate through reporting that source attributes ties to defined non balance supporting references in AHCS. |  |  | Approved | Ian | 2021-12-03 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  | Ian 12-3-21 | Bhim | Boon Hui | Rhonda | Betty |  |  |  | Approved as Batch 3 | 31
#N/A |  |  |  |  | RTR-AHCS-163 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant, I want the subledger journals to be summarized by date when posting to GL so that detail level transaction information is maintained in AHCS and GL journals is summarized |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Subledger journals interfaced to GL from AHCS will be summarized by accounting string(code combinations) and GL date | Validate summary totals to HUB for a sample of data. Reconcile in total between Cloud GL and HUB. | Verified total amount in GL is summarized based on Subledger and GL source based on posted date. In addition verified summarized GL amount ties back to details in AHCS for that specific date through drilling down into the details. |  |  | Approved | Ian | 2021-12-03 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  | Ian 12-3-21 | Bhim, agree with the approach. | Boon Hui | Rhonda | Betty |  |  |  | Approved as Batch 3 | 31
#N/A |  |  |  |  | RTR-AHCS-164 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a IT Manager, I need the ability to add supporting references to AHCS journals so that they can provide balancing on extended chart of account values | Must Have |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | New supporting references can be added in AHCS at any time. For adding balance enabled supporting reference the driver is to load initial balances before usage. | Validate that new supporting reference was received from source system and added to AHCS |  |  |  | Approved | Sijo John |  |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | Boon Hui | Rhonda | Betty |  |  |  | Approved On Thu 1/20/2022 9:17 PM | 30
#N/A |  |  |  |  | RTR-AHCS-165 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a Financial Controller, I want ability to restrict access to subledger so that only restricted users can see detailed information | Must Have |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Existing Phase 1A Functionality Enabling MF AR subledger security by user roles | Ensure all the chart of accounts segments are available for mapping including the future segments | validate users without security access do not have access to detailed information |  |  | Approved | Ian | 2022-01-18 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | Boon Hui | Rhonda | Betty | Ned more clarification on this story. What would be restricted items? IP 12-15 |  |  | Approved On Thu 1/20/2022 9:17 PM | 29
#N/A |  |  |  |  | RTR-AHCS-166 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As an IT administrator, I need a dashboard to track the daily exceptions for Create Accounting Jobs in AHCS so that there is complete visibility of job completion status by source system |  |  | Phase 1B only | 5-Gap-Build-Extension | Gap | Build | Extension | EXT123 | Existing Phase 1A Dashboard needs enhancement Use case: Interface Monitoring Dashboard Extension to derive the status of the Create Accounting jobs for each source system and update them in the AHCS dashboard | Validate the data with subledger period close exceptions. Compare the data with the dashboard and ensure accuracy | The enhanced Dashboard should help to track daily exceptions to create accounting jobs and validate the data with subledger period close exceptions using additional attributes like MF Interface (SII, API etc.) |  |  | Approved | Sijo john Ian Plummer 12-23-21 |  |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | Boon Hui | Rhonda | Betty |  |  |  | Approved as Batch 3 | 30
#N/A |  |  |  |  | RTR-AHCS-167 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report which reconciles legacy and AHCS balance so that I can perform period end reconciliations |  |  | Phase 1B only | 10-Not Required-Not Required-Not Required | Not Required | Not Required | Not Required |  | 01/31 : Do not see this in Report rationalisation tracker as of 01/31, hence marking as ' Not required' and routing for approval. Legacy to AHCS Account Balances Reconciliation- BI: Shows legacy code combination and AHCS code combination side by side with AHCS balances. | Validate report and compare to legacy subledger to GL reconciliations. | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs. |  |  | Approved | Ian | 2022-02-01 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | Boon Hui | Rhonda | Betty |  |  | 2022-02-01 | Approved on Thu 2/3/2022 2:33 AM | 28
CSTONE-5621 | CSTONE-6843 | Not in Jira | CSTONE-9728 | Sprint 11 | RTR-IC-015A |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As a GL Accountant, I need the ability to generate IC invoices in the IC module. The invoice format must comply with local requirements based on the business design. |  |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report | RPT102 | In intercompany module user will create IC batch & select a transaction type that is tagged for invoicing or journals. When submitted, IC transaction would go through approval. Once approved & if invoicing is required: Next run of Transfer to AR would transfer IC transaction to AR. This scheduled run will be followed by another scheduled run to transfer invoice to AP. Create Accounting on AR & AP invoices will create journals in GL. Once approved & if invoicing is not required: Next run of Transfer to GL would create journals 2 invoice templates in AR need to be planned based on approval of assumptions on invoice templates by Patrick/Vitaliy/Jess. Note around data elements: As mentioned on call, tax computation and related field population is currently not in scope for IC currently in 1B – [both Tax engine OR & Oracle tax module config are not in scope]. Invoice template assumes that data required for template is there on invoice data in Oracle tables – It is either static [E.g. LE Name], user entered [E.g. Amount ] OR tax related [E.g Tax Code] which is derived either by Tax engine OR Tax configs OR user entered. [both Tax engine and Tax module config are currently not in scope for Release 1] No AP Invoice print is planned | Validate that IC invoice was created with the correct format per business design. Must validate every invoice template created to ensure compliance across all the countries. |  |  | Sprint 11 | Approved | Erica | 2021-08-05 |  | #REF! |  | RTR | RTR-GL | IC | WESCO |  |  | Ian/Vitaliy | [6 empty] | Invoice print |  | WESCO -User Stories - GL - Batch7 - GPO Approval
CSTONE-5621 | CSTONE-6844 | Not in Jira | CSTONE-9729 | Sprint 11 | RTR-IC-015B |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As a GL Accountant, I need the ability to generate IC invoices in the IC module. The invoice format must comply with local requirements based on the business design. |  |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report | RPT103 | In intercompany module user will create IC batch & select a transaction type that is tagged for invoicing or journals. When submitted, IC transaction would go through approval. Once approved & if invoicing is required: Next run of Transfer to AR would transfer IC transaction to AR. This scheduled run will be followed by another scheduled run to transfer invoice to AP. Create Accounting on AR & AP invoices will create journals in GL. Once approved & if invoicing is not required: Next run of Transfer to GL would create journals 2 invoice templates in AR need to be planned based on approval of assumptions on invoice templates by Patrick/Vitaliy/Jess. Note around data elements: As mentioned on call, tax computation and related field population is currently not in scope for IC currently in 1B – [both Tax engine OR & Oracle tax module config are not in scope]. Invoice template assumes that data required for template is there on invoice data in Oracle tables – It is either static [E.g. LE Name], user entered [E.g. Amount ] OR tax related [E.g Tax Code] which is derived either by Tax engine OR Tax configs OR user entered. [both Tax engine and Tax module config are currently not in scope for Release 1] No AP Invoice print is planned | Validate that IC invoice was created with the correct format per business design. Must validate every invoice template created to ensure compliance across all the countries. |  |  | Sprint 11 | Approved | Erica | 2021-08-05 |  | #REF! |  | RTR | RTR-GL | IC | WESCO |  |  | Ian/Vitaliy | [6 empty] | Invoice print |  | WESCO -User Stories - GL - Batch7 - GPO Approval
CSTONE-5622 | CSTONE-5744 |  |  | CSTONE-5744 | RTR-IC-016 |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As a Intercompany GL Accountant, I need the ability to create intercompany journal entries using a spreadsheet for the Intercompany Accounting Module |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Using IC Module: IC batch can be created as required. Whether it creates invoices or journals based on approved batch will be dependent on IC Transaction type. IC batch can be created using front end or using ADFDI spreadsheet Using GL: 1. For US & CA journal entries within a single ledger can span legal entities. Auto-Balancing rules will be used if entry is unbalanced 2. For other International ledgers: Journal entry will be restricted to one LE. Users can choose to create separate journal entries in each LE Note: In IC batch you cannot use "user" rate type | Validate IC journal was correctly entered and posted in GL without generating an IC invoice. Validate journal was entered correctly and posted in GL and generated IC invoice. Validate all values including entered and accounted currencies. |  |  | Sprint 8 | Approved | Erica | 2021-07-11 |  | #REF! |  | RTR | RTR-GL | IC | WESCO |  |  | Ian/Vitaliy | [8 empty] | User Stories - GL Batch 6 GPO Approval
CSTONE-5623 | CSTONE-5745 |  |  | CSTONE-5745 | RTR-IC-017 |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As a GL Manager I want the ability to reject IC journals if they don't meet business requirements |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Approvers can reject IC batches For acceptance criteria 1: Submitted by can be configured to receive rejection notifications. Format of notification is planned standard format. If custom format is required please log a separate user story describing format 7/16: Another user story is already there to customize IC approval format. For IC rejection format, Vitaliy has reviewed seeded notification & has no changes required. Hence marking as fit | Validate the ability to reject IC journals. Ensure that rejected journals do not get posted. Also ensure preparer is notified once journal has been rejected. Review notification format matches business design. |  |  | Sprint 8 | Approved | Erica | 2021-07-18 |  | #REF! |  | RTR | RTR-GL | IC | WESCO |  |  | Ian/Vitaliy | [8 empty] | User Stories - GL Batch 6 GPO Approval
CSTONE-5624 | CSTONE-5746 |  |  | CSTONE-5746 | RTR-IC-018 |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As a GL Accountant I want the ability to resubmit IC journals which was previously rejected. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Rejected transactions cannot be re-routed for approval. Users can copy rejected IC transactions and then route them for approval again after making any edits as required | Review the submission of previously rejected journal. Validated journal has posted correctly in the ledger after approval. Review IC AR and AP invoices to ensure accuracy. |  |  | Sprint 8 | Approved | Erica | 2021-07-11 |  | #REF! |  | RTR | RTR-GL | IC | WESCO |  |  | Ian/Vitaliy | [8 empty] | User Stories - GL Batch 6 GPO Approval
CSTONE-5625 | CSTONE-5747 |  |  | CSTONE-5747 | RTR-IC-019 |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As a GL Accountant I want the ability to enter IC journals transferring charges from one entity to many entities. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Create one IC batch with singe provider IC Org and multiple receiver IC org i.e. one batch with multiple transactions. Approval will be at transaction level | Review IC journal and validate IC balance for each entity. Validate AR and AP invoices for each entity. Ensure journal only had one provider (AR) and multiple debtors (AP). Validate both entered and accounted currencies. Ensure transactions posted in both primary and secondary ledger. |  |  | Sprint 8 | Approved | Erica | 2021-07-11 |  | #REF! |  | RTR | RTR-GL | IC | WESCO |  |  | Ian/Vitaliy | [8 empty] | User Stories - GL Batch 6 GPO Approval
CSTONE-5626 |  |  |  | CSTONE-5748 | RTR-IC-020 |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As a GL Accountant I want the ability to enter IC journals transferring charges from many entities to many entities. |  |  | Phase 1B only | 10-Not Required-Not Required-Not Required | Not Required | Not Required | Not Required |  | Discussed with Vitaliy. Duplicate of RTR-IC-034. Marking as not required | Review IC journal and validate IC balance for each entity. Validate AR and AP invoices for each entity. Ensure journal only had multiple providers (AR) and multiple debtors (AP). Validate both entered and accounted currencies. Ensure transactions posted in both primary and secondary ledger. |  |  |  | Approved | Erica | 2021-07-15 |  | #REF! |  | RTR | RTR-GL | IC | WESCO |  |  | Ian/Vitaliy | [8 empty] | User Stories - GL Batch 6 GPO Approval
CSTONE-5627 | CSTONE-5748 |  |  | CSTONE-5749 | RTR-IC-021 |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As a GL Accountant I want the capability to generate IC invoice credits. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | IC batch will generate negative amount AR invoice and credit memo if signs are inversed or dr/cr are flipped Discussed verbiage of acceptance criteria with Vitaliy in light of commments noted, he is okay with comments. Acceptance criteria is more of business terminology | Validate that IC transaction created credit note in AR and a debit note in AP. Validate AR and AP is recorded for the correct provider and debtor. Validate both entered and accounted currecies. |  |  | Sprint 8 | Approved | Erica | 2021-07-11 |  | #REF! |  | RTR | RTR-GL | IC | WESCO |  |  | Ian/Vitaliy | [8 empty] | User Stories - GL Batch 6 GPO Approval
CSTONE-5628 | CSTONE-5749 |  |  | CSTONE-5750 | RTR-IC-022 |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As a GL Accountant I should not have the capability to book a reversing journal which generates an invoice. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | IC batches with Trx Type requiring invoicing will create AR and AP invoices. These invoices when accounted will create GL journals. Soruces for AR and AP will be frozen i.e. these journals cannot be reversed Note: Above comments were updated after discussing with Vitaliy | Ensure transactions cannot be marked for auto reversal if they are generating an IC invoice. |  |  | Sprint 8 | Approved | Erica | 2021-07-11 |  | #REF! |  | RTR | RTR-GL | IC | WESCO |  |  | Ian/Vitaliy | [8 empty] | User Stories - GL Batch 6 GPO Approval
CSTONE-5629 | CSTONE-5750 |  |  | CSTONE-5750 | RTR-IC-023 |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As a GL Accountant I should not have the capability to book a reversing journal which generates an invoice. But I should have ability to create reversing invoices/credit/debit memos |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | 1. For IC batches that had originally generated invoices: You can reverse at IC batch or transaction level. If reversing at batch level, all transactions must have invoices created [both AR & AP] i.e. batch must be in complete status. If reversing at transaction level, transaction must have both AR & AP invoices created i.e. transaction must be in complete status. While reversing select batch date = original batch date, this would create reversal AR and AP invoices with invoice date & exchange date of original invoices. When reversing if AR invoice was positive, reversal invoice will be negative and vice versa. When reversing if AP invoice was standard invoice, reversal invoice will be credit memo and vice versa 2. For IC batches that had originally created journals: Pass reversing journals in GL. If you use standard IC reversal fucntonality across period, system will create exchange rate differences | Validate that journal and reversal posted correctly in the ledger. Ensure transactions posted in both primary and secondary ledger. |  |  | Sprint 8 | Approved | Erica | 2021-07-11 |  | #REF! |  | RTR | RTR-GL | IC | WESCO |  |  | Ian/Vitaliy | [8 empty] | User Stories - GL Batch 6 GPO Approval
CSTONE-5630 | CSTONE-6845 | Not in Jira | Not in Jira | Sprint 11 | RTR-IC-024A |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As an I/C GL accountant, I will need a report of I/C AR invoices that have been settled by period and legal entity |  |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report | RPT029 | Split user story into A & B. RTR-IC-024A: New report to pull IC related AR invoices based on receipts created & invoice open amount. RTR-IC-024B: New report to pull IC related AP invoices based on payments created & invoice open amount | Validate accuracy of the report. Ensure all settled AR invoices are captured. Ensure format of report matches business design |  |  | Sprint 11 | Approved | Erica | 2021-07-15 |  | #REF! |  | RTR | RTR-GL | IC | WESCO |  |  | Ian/Vitaliy | [8 empty] | User Stories - GL Batch 6 GPO Approval
CSTONE-5631 | CSTONE-6846 | Not in Jira | Not in Jira | Sprint 11 | RTR-IC-024B |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As a I/C GL accountant, I will need a report of I/C AP invoices that have been settled by period and legal entity |  |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report | RPT030 | Split user story into A & B. RTR-IC-024A: New report to pull IC related AR invoices based on receipts created & invoice open amount. RTR-IC-024B: New report to pull IC related AP invoices based on payments created & invoice open amount | Validate accuracy of the report. Ensure all settled AP invoices are captured. Ensure format of report matches business design. |  |  | Sprint 11 | Approved | Erica | 2021-07-15 |  | #REF! |  | RTR | RTR-GL | IC | WESCO |  |  | Ian/Vitaliy | [8 empty] | User Stories - GL Batch 6 GPO Approval
CSTONE-5632 | CSTONE-5751 |  |  | CSTONE-5751 | RTR-IC-025 |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As an intercompany Accountant, I need to be able to process netting of Payables and Receivables transactions for related intercompany organizations |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Systematic Customer Supplier netting to be configured twice for each relationship as per KDD22. Netting process would create dummy receipts and payments in subledgers which would create realized gain/loss if applicable | Validate the netting process accurately closed the required AP and AR invoices and posted to the GL. Ensure the netting agreements are set up in the module per business design. Ensure netting was performed for the correct entities as per business design. Ensure all clearing accounts used for netting zeroes out. Validate proper FX gain/loss was recognized. |  |  | Sprint 8 | Approved | Erica | 2021-07-15 |  | #REF! |  | RTR | RTR-GL | IC | WESCO |  |  | Ian/Vitaliy | [8 empty] | User Stories - GL Batch 6 GPO Approval
CSTONE-5633 | CSTONE-5752 |  |  | CSTONE-5752 | RTR-IC-026 |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As a I/C GL Accountant, I need the ability to reverse IC settlements which may have been processed in error. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Use Oracle standard subledger functionality to cancel AP Payments and reverse AR receipt | Validate IC settlement has been reversed. Ensure both AR and AP invoices are marked as open in the subledger. Ensure reversal accurately recorded in the GL. Ensure transactions are recorded in both primary and secondary ledger |  |  | Sprint 8 | Approved | Erica | 2021-07-15 |  | #REF! |  | RTR | RTR-GL | IC | WESCO |  |  | Ian/Vitaliy | [8 empty] | User Stories - GL Batch 6 GPO Approval
CSTONE-5634 | CSTONE-5753 |  |  | CSTONE-5753 | RTR-IC-027 |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As a I/C GL Accountant, I need the ability to reverse IC netting that may have been processed in error. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Use Oracle standard Netting functionality's feature to reverse netting if issue is identified after dummy receipts and payments were created. If issue is identified in review stage use standard fucntionality to delete netting batch | Validate IC netting has been reversed. Ensure both AR and AP invoices are marked as open in the subledger. Ensure reversal accurately recorded in the GL. Ensure transactions are recorded in both primary and secondary ledger |  |  | Sprint 8 | Approved | Erica | 2021-07-15 |  | #REF! |  | RTR | RTR-GL | IC | WESCO |  |  | Ian/Vitaliy | [8 empty] | User Stories - GL Batch 6 GPO Approval
CSTONE-5635 | CSTONE-6847 | Not in Jira | Not in Jira | Sprint 11 | RTR-IC-028 |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As a I/C GL Accountant, I will need a report of I/C AP invoices that have been selected (not yet settled) for settlement. Report should show I/C AR and AP invoices side by side. This report will be used to approve the settlement of I/C invoices. |  |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report | RPT031 | Create new custom report that pulls AP invoices that are selected for payment, but not yet paid. Report would then show side by side corresponding AR invoice details | Review format of report to ensure matches business design. Ensure AP invoices selected for settlement from the report have not been settled in the subledger. Validate that invoices selected for settlement cannot be settled on another batch. |  |  | Sprint 11 | Approved | Erica | 2021-07-15 |  | #REF! |  | RTR | RTR-GL | IC | WESCO |  |  | Ian/Vitaliy | [8 empty] | User Stories - GL Batch 6 GPO Approval
CSTONE-5636 | CSTONE-5754 |  |  | CSTONE-5754 | RTR-IC-029 |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As an I/C accountant, when creating journals in I/C modules the FX rate should default to daily rate of when journal is entered or ME rate if entered in the following period. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Rate type is a field that user can update on each IC batch. Default will be "Actual" rate type as per workshop alignment. If user wants to use Month End rate user would change rate type How is rate date derived for IC module initiated transactions: Transfer to GL : Exchange rate date = GL date of AGIS batch Transfer to AP/AR : Exchange rate date = Batch date on AGIS batch How is rate date used when a Direct GL Journal entry is created [not through IC module]: Rate date field on journal drives rate usage. Default of Rate Date is accounting date but user can override | Validate the FX rate on the journal meets business requirements. Validate both entered and accounted amounts and ensure journal accurately posted in the ledger in both primary and secondary ledgers. If invoice was generated validate format and values on the invoice. |  |  | Sprint 8 | Approved | Erica | 2021-07-18 |  | #REF! |  | RTR | RTR-GL | IC | WESCO |  |  | Ian/Vitaliy | [8 empty] | User Stories - GL Batch 6 GPO Approval
CSTONE-5637 | CSTONE-5755 |  |  | CSTONE-5755 | RTR-IC-030 |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As an I/C accountant, when I/C transaction is created in primary ledger, it should also be recorded in secondary ledger (if enabled). |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | When IC batch is approved, it will be transferred to GL or AR/AP. If GL: When GL batch is posted it will be copied to secondary If AR/AP: When accounting for AR and AP invoices in subledger happen, it will be generated to secondary ledger as well as level of secondary ledger as per KDD2 is subledger | Ensure transactions are accurately posted in both primary and secondary ledger. |  |  | Sprint 8 | Approved | Erica | 2021-07-15 |  | #REF! |  | RTR | RTR-GL | IC | WESCO |  |  | Ian/Vitaliy | [8 empty] | User Stories - GL Batch 6 GPO Approval
CSTONE-5638 | CSTONE-5756 |  |  | CSTONE-5756 | RTR-IC-031 |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As an I/C accountant, when AR/AP invoices are settled in primary ledger, it should also be recorded in the secondary ledger. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | When subledger transactions are acounted, accounting will be generated to secondary ledger as well as level of secondary ledger as per KDD2 is subledger | Ensure transactions are accurately posted in both primary and secondary ledger. |  |  | Sprint 8 | Approved | Erica | 2021-07-15 |  | #REF! |  | RTR | RTR-GL | IC | WESCO |  |  | Ian/Vitaliy | [8 empty] | User Stories - GL Batch 6 GPO Approval
CSTONE-5639 | CSTONE-5757 |  |  | CSTONE-5757 | RTR-IC-032 |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As an I/C accountant, when AR/AP invoices are netted in primary ledger, it should also be recorded in the secondary ledger. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | When subledger transactions are acounted, accounting will be generated to secondary ledger as well as level of secondary ledger as per KDD2 is subledger | Ensure transactions are accurately posted in both primary and secondary ledger. |  |  | Sprint 8 | Approved | Erica | 2021-07-15 |  | #REF! |  | RTR | RTR-GL | IC | WESCO |  |  | Ian/Vitaliy | [8 empty] | User Stories - GL Batch 6 GPO Approval
CSTONE-5640 | CSTONE-6049 | CSTONE-6852 | CSTONE-8118 | CSTONE-6049 | RTR-IC-033A |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As an I/C accountant, when AR/AP invoices are switched (LSI) in primary ledger, it should also be recorded in the secondary ledger. FX impact may be different in primary vs secondary ledger. |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT195 | Need to build LSI extensions as per requirement. To be discussed as part of detailed design | Ensure transactions are accurately posted in both primary and secondary ledger. |  |  | Sprint 9 | Approved | Erica | 2021-07-15 |  | #REF! |  | RTR | RTR-GL | IC | WESCO |  |  | Ian/Vitaliy | [8 empty] | User Stories - GL Batch 6 GPO Approval
CSTONE-5641 | CSTONE-6050 | CSTONE-6853 | CSTONE-8119 | CSTONE-6050 | RTR-IC-033B |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As an I/C accountant, when AR/AP invoices are switched (LSI) in primary ledger, it should also be recorded in the secondary ledger. FX impact may be different in primary vs secondary ledger. |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT196 | Need to build LSI extensions as per requirement. To be discussed as part of detailed design | Ensure transactions are accurately posted in both primary and secondary ledger. |  |  | Sprint 9 | Approved | Erica | 2021-07-15 |  | #REF! |  | RTR | RTR-GL | IC | WESCO |  |  | Ian/Vitaliy | [8 empty] | User Stories - GL Batch 6 GPO Approval
CSTONE-5642 | CSTONE-6051 | CSTONE-6854 | CSTONE-8120 | CSTONE-6051 | RTR-IC-033C |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As an I/C accountant, when AR/AP invoices are switched (LSI) in primary ledger, it should also be recorded in the secondary ledger. FX impact may be different in primary vs secondary ledger. |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT197 | Need to build LSI extensions as per requirement. To be discussed as part of detailed design | Ensure transactions are accurately posted in both primary and secondary ledger. |  |  | Sprint 9 | Approved | Erica | 2021-07-15 |  | #REF! |  | RTR | RTR-GL | IC | WESCO |  |  | Ian/Vitaliy | [8 empty] | User Stories - GL Batch 6 GPO Approval
CSTONE-5643 | CSTONE-6052 | CSTONE-6855 | CSTONE-8121 | CSTONE-6052 | RTR-IC-033D |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As an I/C accountant, when AR/AP invoices are switched (LSI) in primary ledger, it should also be recorded in the secondary ledger. FX impact may be different in primary vs secondary ledger. |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT198 | Need to build LSI extensions as per requirement. To be discussed as part of detailed design | Ensure transactions are accurately posted in both primary and secondary ledger. |  |  | Sprint 9 | Approved | Erica | 2021-07-15 |  | #REF! |  | RTR | RTR-GL | IC | WESCO |  |  | Ian/Vitaliy | [8 empty] | User Stories - GL Batch 6 GPO Approval
CSTONE-5644 | CSTONE-6053 | CSTONE-6856 | CSTONE-8122 | CSTONE-6053 | RTR-IC-033E |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As an I/C accountant, when AR/AP invoices are switched (LSI) in primary ledger, it should also be recorded in the secondary ledger. FX impact may be different in primary vs secondary ledger. |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT199 | Need to build LSI extensions as per requirement. To be discussed as part of detailed design | Ensure transactions are accurately posted in both primary and secondary ledger. |  |  | Sprint 9 | Approved | Erica | 2021-07-15 |  | #REF! |  | RTR | RTR-GL | IC | WESCO |  |  | Ian/Vitaliy | [8 empty] | User Stories - GL Batch 6 GPO Approval
CSTONE-5645 | CSTONE-6054 | CSTONE-6857 | CSTONE-8123 | CSTONE-6054 | RTR-IC-033F |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As an I/C accountant, when AR/AP invoices are switched (LSI) in primary ledger, it should also be recorded in the secondary ledger. FX impact may be different in primary vs secondary ledger. |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT200 | Need to build LSI extensions as per requirement. To be discussed as part of detailed design | Ensure transactions are accurately posted in both primary and secondary ledger. |  |  | Sprint 9 | Approved | Erica | 2021-07-15 |  | #REF! |  | RTR | RTR-GL | IC | WESCO |  |  | Ian/Vitaliy | [8 empty] | User Stories - GL Batch 6 GPO Approval
CSTONE-5646 | CSTONE-6055 | CSTONE-6858 | CSTONE-6914 | CSTONE-6055 | RTR-IC-033G |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As an I/C accountant, when AR/AP invoices are switched (LSI) in primary ledger, it should also be recorded in the secondary ledger. FX impact may be different in primary vs secondary ledger. |  |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report | RPT100 | Need to build LSI extensions as per requirement. To be discussed as part of detailed design | Ensure transactions are accurately posted in both primary and secondary ledger. |  |  | Sprint 9 | Approved | Erica | 2021-07-15 |  | #REF! |  | RTR | RTR-GL | IC | WESCO |  |  | Ian/Vitaliy | [8 empty] | User Stories - GL Batch 6 GPO Approval
CSTONE-5647 | CSTONE-6056 | CSTONE-6859 | CSTONE-8124 | CSTONE-6056 | RTR-IC-033H |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As an I/C accountant, when AR/AP invoices are switched (LSI) in primary ledger, it should also be recorded in the secondary ledger. FX impact may be different in primary vs secondary ledger. |  |  | Phase 1B only | 5-Gap-Build-Extension | Gap | Build | Extension | EXT042 | Need to build LSI extensions as per requirement. To be discussed as part of detailed design | Ensure transactions are accurately posted in both primary and secondary ledger. |  |  | Sprint 9 | Approved | Erica | 2021-07-15 |  | #REF! |  | RTR | RTR-GL | IC | WESCO |  |  | Ian/Vitaliy | [8 empty] | User Stories - GL Batch 6 GPO Approval
CSTONE-5648 | CSTONE-6057 | CSTONE-6860 | CSTONE-8125 | CSTONE-6057 | RTR-IC-034A |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As a GL Accountant I want the ability to enter IC journals transferring charges from one entity to many entities. Also journal will contain charges transferred between departments within an entity. |  |  | Phase 1B only | 5-Gap-Build-Extension | Gap | Build | Extension | EXT036 | Extensions to be built to tackle below 3 scenarios. May need revisit of verbiage of user story/acceptance criteria, but scenarios noted as part of discussion with Vitaliy 1. One to many – only Intercompany [Sample: example sheet]: 1.1. Base Data doesn’t balance by LE 1.2. Algorithm: 1.2.1. Find provider by looking for lines where IC segment is non zero. Those lines become provider revenue lines [if same receiver may have to summarize lines] 1.2.2. Find corresponding receiver lines with receiver as LE, no IC segment. These become receiver AP lines 1.2.3. Create IC batches. Oracle will add IC balancing lines 1.2.4. If provider was found as per pt.X.2.1, rest of lines identified for LE as provider should have IC as 000. These would become GL lines & should be already balanced. May be in different ledgers --- This will not yield any results in this scenario 1.2.5. Assumption that was validated: There will be no data such that there is more than one provider identified as per pt.X.2.1 above 2. One to many with intra-company [Sample: Both IC and Intra sheet – see rows 7-15] : 2.1. Base Data doesn’t balance by LE 2.2. Algorithm: 2.2.1. Find provider by looking for lines where IC segment is non zero. Those lines become provider revenue lines [if same receiver may have to summarize lines] 2.2.2. Find corresponding receiver lines with receiver as LE, no IC segment. These become receiver AP lines 2.2.3. Create IC batches. Oracle will add IC balancing lines 2.2.4. If provider was found as per pt.X.2.1, rest of lines identified for LE as provider should have IC as 000. These would become GL lines & should be already balanced. May be in different ledgers 2.2.5. Assumption that was validated: There will be no data such that there is more than one provider identified as per pt.X.2.1 above 3. Pure intra-company [Sample: Intra only with many LEs]: 3.1. Base data balances by LE 3.2. Algorithm: 3.2.1. Find provider by looking for lines where IC segment is non zero. Those lines become provider revenue lines [if same receiver may have to summarize lines] --- This will not yield any results in this scenario 3.2.2. Find corresponding receiver lines with receiver as LE, no IC segment. These become receiver AP lines --- This will not yield any results in this scenario 3.2.3. Create IC batches. Oracle will add IC balancing lines --- This will not yield any results in this scenario 3.2.4. If provider was found as per pt.X.2.1, rest of lines identified for LE as provider should have IC as 000. These would become GL lines & should be already balanced. May be in different ledgers 3.2.5. Assumption that was validated: There will be no data such that there is more than one provider identified as per pt.X.2.1 above | Review IC journal and validate IC balance for each entity. Validate AR and AP invoices for each entity. Ensure journal only had single provider (AR) and multiple debtors (AP). Ensure transactions that balance within the entity do not create IC. Validate both entered and accounted currencies. Ensure transactions posted in both primary and secondary ledger. |  |  | Sprint 9 | Approved | Erica | 2021-07-15 |  | #REF! |  | RTR | RTR-GL | IC | WESCO |  |  | Ian/Vitaliy | [8 empty] | User Stories - GL Batch 6 GPO Approval
CSTONE-5649 | CSTONE-6058 | CSTONE-6861 | CSTONE-8126 | CSTONE-6058 | RTR-IC-034B |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As a GL Accountant I want the ability to enter IC journals transferring charges from one entity to many entities. Also journal will contain charges transferred between departments within an entity. |  |  | Phase 1B only | 5-Gap-Build-Extension | Gap | Build | Extension | EXT037 | Extensions to be built to tackle below 3 scenarios. May need revisit of verbiage of user story/acceptance criteria, but scenarios noted as part of discussion with Vitaliy 1. One to many – only Intercompany [Sample: example sheet]: 1.1. Base Data doesn’t balance by LE 1.2. Algorithm: 1.2.1. Find provider by looking for lines where IC segment is non zero. Those lines become provider revenue lines [if same receiver may have to summarize lines] 1.2.2. Find corresponding receiver lines with receiver as LE, no IC segment. These become receiver AP lines 1.2.3. Create IC batches. Oracle will add IC balancing lines 1.2.4. If provider was found as per pt.X.2.1, rest of lines identified for LE as provider should have IC as 000. These would become GL lines & should be already balanced. May be in different ledgers --- This will not yield any results in this scenario 1.2.5. Assumption that was validated: There will be no data such that there is more than one provider identified as per pt.X.2.1 above 2. One to many with intra-company [Sample: Both IC and Intra sheet – see rows 7-15] : 2.1. Base Data doesn’t balance by LE 2.2. Algorithm: 2.2.1. Find provider by looking for lines where IC segment is non zero. Those lines become provider revenue lines [if same receiver may have to summarize lines] 2.2.2. Find corresponding receiver lines with receiver as LE, no IC segment. These become receiver AP lines 2.2.3. Create IC batches. Oracle will add IC balancing lines 2.2.4. If provider was found as per pt.X.2.1, rest of lines identified for LE as provider should have IC as 000. These would become GL lines & should be already balanced. May be in different ledgers 2.2.5. Assumption that was validated: There will be no data such that there is more than one provider identified as per pt.X.2.1 above 3. Pure intra-company [Sample: Intra only with many LEs]: 3.1. Base data balances by LE 3.2. Algorithm: 3.2.1. Find provider by looking for lines where IC segment is non zero. Those lines become provider revenue lines [if same receiver may have to summarize lines] --- This will not yield any results in this scenario 3.2.2. Find corresponding receiver lines with receiver as LE, no IC segment. These become receiver AP lines --- This will not yield any results in this scenario 3.2.3. Create IC batches. Oracle will add IC balancing lines --- This will not yield any results in this scenario 3.2.4. If provider was found as per pt.X.2.1, rest of lines identified for LE as provider should have IC as 000. These would become GL lines & should be already balanced. May be in different ledgers 3.2.5. Assumption that was validated: There will be no data such that there is more than one provider identified as per pt.X.2.1 above | Review IC journal and validate IC balance for each entity. Validate AR and AP invoices for each entity. Ensure journal only had single provider (AR) and multiple debtors (AP). Ensure transactions that balance within the entity do not create IC. Validate both entered and accounted currencies. Ensure transactions posted in both primary and secondary ledger. |  |  | Sprint 9 | Approved | Erica | 2021-07-15 |  | #REF! |  | RTR | RTR-GL | IC | WESCO |  |  | Ian/Vitaliy | [8 empty] | User Stories - GL Batch 6 GPO Approval
CSTONE-5650 | CSTONE-6059 | CSTONE-6861 | CSTONE-8127 | CSTONE-6059 | RTR-IC-034C |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As a GL Accountant I want the ability to enter IC journals transferring charges from one entity to many entities. Also journal will contain charges transferred between departments within an entity. |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT193 | Extensions to be built to tackle below 3 scenarios. May need revisit of verbiage of user story/acceptance criteria, but scenarios noted as part of discussion with Vitaliy 1. One to many – only Intercompany [Sample: example sheet]: 1.1. Base Data doesn’t balance by LE 1.2. Algorithm: 1.2.1. Find provider by looking for lines where IC segment is non zero. Those lines become provider revenue lines [if same receiver may have to summarize lines] 1.2.2. Find corresponding receiver lines with receiver as LE, no IC segment. These become receiver AP lines 1.2.3. Create IC batches. Oracle will add IC balancing lines 1.2.4. If provider was found as per pt.X.2.1, rest of lines identified for LE as provider should have IC as 000. These would become GL lines & should be already balanced. May be in different ledgers --- This will not yield any results in this scenario 1.2.5. Assumption that was validated: There will be no data such that there is more than one provider identified as per pt.X.2.1 above 2. One to many with intra-company [Sample: Both IC and Intra sheet – see rows 7-15] : 2.1. Base Data doesn’t balance by LE 2.2. Algorithm: 2.2.1. Find provider by looking for lines where IC segment is non zero. Those lines become provider revenue lines [if same receiver may have to summarize lines] 2.2.2. Find corresponding receiver lines with receiver as LE, no IC segment. These become receiver AP lines 2.2.3. Create IC batches. Oracle will add IC balancing lines 2.2.4. If provider was found as per pt.X.2.1, rest of lines identified for LE as provider should have IC as 000. These would become GL lines & should be already balanced. May be in different ledgers 2.2.5. Assumption that was validated: There will be no data such that there is more than one provider identified as per pt.X.2.1 above 3. Pure intra-company [Sample: Intra only with many LEs]: 3.1. Base data balances by LE 3.2. Algorithm: 3.2.1. Find provider by looking for lines where IC segment is non zero. Those lines become provider revenue lines [if same receiver may have to summarize lines] --- This will not yield any results in this scenario 3.2.2. Find corresponding receiver lines with receiver as LE, no IC segment. These become receiver AP lines --- This will not yield any results in this scenario 3.2.3. Create IC batches. Oracle will add IC balancing lines --- This will not yield any results in this scenario 3.2.4. If provider was found as per pt.X.2.1, rest of lines identified for LE as provider should have IC as 000. These would become GL lines & should be already balanced. May be in different ledgers 3.2.5. Assumption that was validated: There will be no data such that there is more than one provider identified as per pt.X.2.1 above | Review IC journal and validate IC balance for each entity. Validate AR and AP invoices for each entity. Ensure journal only had single provider (AR) and multiple debtors (AP). Ensure transactions that balance within the entity do not create IC. Validate both entered and accounted currencies. Ensure transactions posted in both primary and secondary ledger. |  |  | Sprint 9 | Approved | Erica | 2021-07-15 |  | #REF! |  | RTR | RTR-GL | IC | WESCO |  |  | Ian/Vitaliy | [8 empty] | User Stories - GL Batch 6 GPO Approval
CSTONE-5651 | CSTONE-6060 | CSTONE-6863 | CSTONE-8128 | CSTONE-6060 | RTR-IC-034D |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As a GL Accountant I want the ability to enter IC journals transferring charges from one entity to many entities. Also journal will contain charges transferred between departments within an entity. |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT194 | Extensions to be built to tackle below 3 scenarios. May need revisit of verbiage of user story/acceptance criteria, but scenarios noted as part of discussion with Vitaliy 1. One to many – only Intercompany [Sample: example sheet]: 1.1. Base Data doesn’t balance by LE 1.2. Algorithm: 1.2.1. Find provider by looking for lines where IC segment is non zero. Those lines become provider revenue lines [if same receiver may have to summarize lines] 1.2.2. Find corresponding receiver lines with receiver as LE, no IC segment. These become receiver AP lines 1.2.3. Create IC batches. Oracle will add IC balancing lines 1.2.4. If provider was found as per pt.X.2.1, rest of lines identified for LE as provider should have IC as 000. These would become GL lines & should be already balanced. May be in different ledgers --- This will not yield any results in this scenario 1.2.5. Assumption that was validated: There will be no data such that there is more than one provider identified as per pt.X.2.1 above 2. One to many with intra-company [Sample: Both IC and Intra sheet – see rows 7-15] : 2.1. Base Data doesn’t balance by LE 2.2. Algorithm: 2.2.1. Find provider by looking for lines where IC segment is non zero. Those lines become provider revenue lines [if same receiver may have to summarize lines] 2.2.2. Find corresponding receiver lines with receiver as LE, no IC segment. These become receiver AP lines 2.2.3. Create IC batches. Oracle will add IC balancing lines 2.2.4. If provider was found as per pt.X.2.1, rest of lines identified for LE as provider should have IC as 000. These would become GL lines & should be already balanced. May be in different ledgers 2.2.5. Assumption that was validated: There will be no data such that there is more than one provider identified as per pt.X.2.1 above 3. Pure intra-company [Sample: Intra only with many LEs]: 3.1. Base data balances by LE 3.2. Algorithm: 3.2.1. Find provider by looking for lines where IC segment is non zero. Those lines become provider revenue lines [if same receiver may have to summarize lines] --- This will not yield any results in this scenario 3.2.2. Find corresponding receiver lines with receiver as LE, no IC segment. These become receiver AP lines --- This will not yield any results in this scenario 3.2.3. Create IC batches. Oracle will add IC balancing lines --- This will not yield any results in this scenario 3.2.4. If provider was found as per pt.X.2.1, rest of lines identified for LE as provider should have IC as 000. These would become GL lines & should be already balanced. May be in different ledgers 3.2.5. Assumption that was validated: There will be no data such that there is more than one provider identified as per pt.X.2.1 above | Review IC journal and validate IC balance for each entity. Validate AR and AP invoices for each entity. Ensure journal only had single provider (AR) and multiple debtors (AP). Ensure transactions that balance within the entity do not create IC. Validate both entered and accounted currencies. Ensure transactions posted in both primary and secondary ledger. |  |  | Sprint 9 | Approved | Erica | 2021-07-15 |  | #REF! |  | RTR | RTR-GL | IC | WESCO |  |  | Ian/Vitaliy | [8 empty] | User Stories - GL Batch 6 GPO Approval
CSTONE-5652 | CSTONE-6061 | CSTONE-6864 | CSTONE-8129 | CSTONE-6061 | RTR-IC-034E |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As a GL Accountant I want the ability to enter IC journals transferring charges from one entity to many entities. Also journal will contain charges transferred between departments within an entity. |  |  | Phase 1B only | 5-Gap-Build-Extension | Gap | Build | Extension | EXT038 | Extensions to be built to tackle below 3 scenarios. May need revisit of verbiage of user story/acceptance criteria, but scenarios noted as part of discussion with Vitaliy 1. One to many – only Intercompany [Sample: example sheet]: 1.1. Base Data doesn’t balance by LE 1.2. Algorithm: 1.2.1. Find provider by looking for lines where IC segment is non zero. Those lines become provider revenue lines [if same receiver may have to summarize lines] 1.2.2. Find corresponding receiver lines with receiver as LE, no IC segment. These become receiver AP lines 1.2.3. Create IC batches. Oracle will add IC balancing lines 1.2.4. If provider was found as per pt.X.2.1, rest of lines identified for LE as provider should have IC as 000. These would become GL lines & should be already balanced. May be in different ledgers --- This will not yield any results in this scenario 1.2.5. Assumption that was validated: There will be no data such that there is more than one provider identified as per pt.X.2.1 above 2. One to many with intra-company [Sample: Both IC and Intra sheet – see rows 7-15] : 2.1. Base Data doesn’t balance by LE 2.2. Algorithm: 2.2.1. Find provider by looking for lines where IC segment is non zero. Those lines become provider revenue lines [if same receiver may have to summarize lines] 2.2.2. Find corresponding receiver lines with receiver as LE, no IC segment. These become receiver AP lines 2.2.3. Create IC batches. Oracle will add IC balancing lines 2.2.4. If provider was found as per pt.X.2.1, rest of lines identified for LE as provider should have IC as 000. These would become GL lines & should be already balanced. May be in different ledgers 2.2.5. Assumption that was validated: There will be no data such that there is more than one provider identified as per pt.X.2.1 above 3. Pure intra-company [Sample: Intra only with many LEs]: 3.1. Base data balances by LE 3.2. Algorithm: 3.2.1. Find provider by looking for lines where IC segment is non zero. Those lines become provider revenue lines [if same receiver may have to summarize lines] --- This will not yield any results in this scenario 3.2.2. Find corresponding receiver lines with receiver as LE, no IC segment. These become receiver AP lines --- This will not yield any results in this scenario 3.2.3. Create IC batches. Oracle will add IC balancing lines --- This will not yield any results in this scenario 3.2.4. If provider was found as per pt.X.2.1, rest of lines identified for LE as provider should have IC as 000. These would become GL lines & should be already balanced. May be in different ledgers 3.2.5. Assumption that was validated: There will be no data such that there is more than one provider identified as per pt.X.2.1 above | Review IC journal and validate IC balance for each entity. Validate AR and AP invoices for each entity. Ensure journal only had single provider (AR) and multiple debtors (AP). Ensure transactions that balance within the entity do not create IC. Validate both entered and accounted currencies. Ensure transactions posted in both primary and secondary ledger. |  |  | Sprint 9 | Approved | Erica | 2021-07-15 |  | #REF! |  | RTR | RTR-GL | IC | WESCO |  |  | Ian/Vitaliy | [8 empty] | User Stories - GL Batch 6 GPO Approval
CSTONE-5653 | CSTONE-6062 | CSTONE-6865 | CSTONE-8130 | CSTONE-6062 | RTR-IC-034F |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As a GL Accountant I want the ability to enter IC journals transferring charges from one entity to many entities. Also journal will contain charges transferred between departments within an entity. |  |  | Phase 1B only | 5-Gap-Build-Extension | Gap | Build | Extension | EXT039 | Extensions to be built to tackle below 3 scenarios. May need revisit of verbiage of user story/acceptance criteria, but scenarios noted as part of discussion with Vitaliy 1. One to many – only Intercompany [Sample: example sheet]: 1.1. Base Data doesn’t balance by LE 1.2. Algorithm: 1.2.1. Find provider by looking for lines where IC segment is non zero. Those lines become provider revenue lines [if same receiver may have to summarize lines] 1.2.2. Find corresponding receiver lines with receiver as LE, no IC segment. These become receiver AP lines 1.2.3. Create IC batches. Oracle will add IC balancing lines 1.2.4. If provider was found as per pt.X.2.1, rest of lines identified for LE as provider should have IC as 000. These would become GL lines & should be already balanced. May be in different ledgers --- This will not yield any results in this scenario 1.2.5. Assumption that was validated: There will be no data such that there is more than one provider identified as per pt.X.2.1 above 2. One to many with intra-company [Sample: Both IC and Intra sheet – see rows 7-15] : 2.1. Base Data doesn’t balance by LE 2.2. Algorithm: 2.2.1. Find provider by looking for lines where IC segment is non zero. Those lines become provider revenue lines [if same receiver may have to summarize lines] 2.2.2. Find corresponding receiver lines with receiver as LE, no IC segment. These become receiver AP lines 2.2.3. Create IC batches. Oracle will add IC balancing lines 2.2.4. If provider was found as per pt.X.2.1, rest of lines identified for LE as provider should have IC as 000. These would become GL lines & should be already balanced. May be in different ledgers 2.2.5. Assumption that was validated: There will be no data such that there is more than one provider identified as per pt.X.2.1 above 3. Pure intra-company [Sample: Intra only with many LEs]: 3.1. Base data balances by LE 3.2. Algorithm: 3.2.1. Find provider by looking for lines where IC segment is non zero. Those lines become provider revenue lines [if same receiver may have to summarize lines] --- This will not yield any results in this scenario 3.2.2. Find corresponding receiver lines with receiver as LE, no IC segment. These become receiver AP lines --- This will not yield any results in this scenario 3.2.3. Create IC batches. Oracle will add IC balancing lines --- This will not yield any results in this scenario 3.2.4. If provider was found as per pt.X.2.1, rest of lines identified for LE as provider should have IC as 000. These would become GL lines & should be already balanced. May be in different ledgers 3.2.5. Assumption that was validated: There will be no data such that there is more than one provider identified as per pt.X.2.1 above | Review IC journal and validate IC balance for each entity. Validate AR and AP invoices for each entity. Ensure journal only had single provider (AR) and multiple debtors (AP). Ensure transactions that balance within the entity do not create IC. Validate both entered and accounted currencies. Ensure transactions posted in both primary and secondary ledger. |  |  | Sprint 9 | Approved | Erica | 2021-07-15 |  | #REF! |  | RTR | RTR-GL | IC | WESCO |  |  | Ian/Vitaliy | [8 empty] | User Stories - GL Batch 6 GPO Approval
CSTONE-5654 | CSTONE-6063 | N/A | N/A | N/A | RTR-IC-034G |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As a GL Accountant I want the ability to enter IC journals transferring charges from one entity to many entities. Also journal will contain charges transferred between departments within an entity. |  |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | EXT040 | Extensions to be built to tackle below 3 scenarios. May need revisit of verbiage of user story/acceptance criteria, but scenarios noted as part of discussion with Vitaliy 1. One to many – only Intercompany [Sample: example sheet]: 1.1. Base Data doesn’t balance by LE 1.2. Algorithm: 1.2.1. Find provider by looking for lines where IC segment is non zero. Those lines become provider revenue lines [if same receiver may have to summarize lines] 1.2.2. Find corresponding receiver lines with receiver as LE, no IC segment. These become receiver AP lines 1.2.3. Create IC batches. Oracle will add IC balancing lines 1.2.4. If provider was found as per pt.X.2.1, rest of lines identified for LE as provider should have IC as 000. These would become GL lines & should be already balanced. May be in different ledgers --- This will not yield any results in this scenario 1.2.5. Assumption that was validated: There will be no data such that there is more than one provider identified as per pt.X.2.1 above 2. One to many with intra-company [Sample: Both IC and Intra sheet – see rows 7-15] : 2.1. Base Data doesn’t balance by LE 2.2. Algorithm: 2.2.1. Find provider by looking for lines where IC segment is non zero. Those lines become provider revenue lines [if same receiver may have to summarize lines] 2.2.2. Find corresponding receiver lines with receiver as LE, no IC segment. These become receiver AP lines 2.2.3. Create IC batches. Oracle will add IC balancing lines 2.2.4. If provider was found as per pt.X.2.1, rest of lines identified for LE as provider should have IC as 000. These would become GL lines & should be already balanced. May be in different ledgers 2.2.5. Assumption that was validated: There will be no data such that there is more than one provider identified as per pt.X.2.1 above 3. Pure intra-company [Sample: Intra only with many LEs]: 3.1. Base data balances by LE 3.2. Algorithm: 3.2.1. Find provider by looking for lines where IC segment is non zero. Those lines become provider revenue lines [if same receiver may have to summarize lines] --- This will not yield any results in this scenario 3.2.2. Find corresponding receiver lines with receiver as LE, no IC segment. These become receiver AP lines --- This will not yield any results in this scenario 3.2.3. Create IC batches. Oracle will add IC balancing lines --- This will not yield any results in this scenario 3.2.4. If provider was found as per pt.X.2.1, rest of lines identified for LE as provider should have IC as 000. These would become GL lines & should be already balanced. May be in different ledgers 3.2.5. Assumption that was validated: There will be no data such that there is more than one provider identified as per pt.X.2.1 above | Review IC journal and validate IC balance for each entity. Validate AR and AP invoices for each entity. Ensure journal only had single provider (AR) and multiple debtors (AP). Ensure transactions that balance within the entity do not create IC. Validate both entered and accounted currencies. Ensure transactions posted in both primary and secondary ledger. |  |  | Sprint 9 | Approved | Erica | 2021-07-15 |  | #REF! |  | RTR | RTR-GL | IC | WESCO |  |  | Ian/Vitaliy | [8 empty] | User Stories - GL Batch 6 GPO Approval
CSTONE-5655 | CSTONE-6064 | CSTONE-6866 | CSTONE-6913 | CSTONE-6064 | RTR-IC-034H |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As a GL Accountant I want the ability to enter IC journals transferring charges from one entity to many entities. Also journal will contain charges transferred between departments within an entity. |  |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report | RPT099 | Extensions to be built to tackle below 3 scenarios. May need revisit of verbiage of user story/acceptance criteria, but scenarios noted as part of discussion with Vitaliy 1. One to many – only Intercompany [Sample: example sheet]: 1.1. Base Data doesn’t balance by LE 1.2. Algorithm: 1.2.1. Find provider by looking for lines where IC segment is non zero. Those lines become provider revenue lines [if same receiver may have to summarize lines] 1.2.2. Find corresponding receiver lines with receiver as LE, no IC segment. These become receiver AP lines 1.2.3. Create IC batches. Oracle will add IC balancing lines 1.2.4. If provider was found as per pt.X.2.1, rest of lines identified for LE as provider should have IC as 000. These would become GL lines & should be already balanced. May be in different ledgers --- This will not yield any results in this scenario 1.2.5. Assumption that was validated: There will be no data such that there is more than one provider identified as per pt.X.2.1 above 2. One to many with intra-company [Sample: Both IC and Intra sheet – see rows 7-15] : 2.1. Base Data doesn’t balance by LE 2.2. Algorithm: 2.2.1. Find provider by looking for lines where IC segment is non zero. Those lines become provider revenue lines [if same receiver may have to summarize lines] 2.2.2. Find corresponding receiver lines with receiver as LE, no IC segment. These become receiver AP lines 2.2.3. Create IC batches. Oracle will add IC balancing lines 2.2.4. If provider was found as per pt.X.2.1, rest of lines identified for LE as provider should have IC as 000. These would become GL lines & should be already balanced. May be in different ledgers 2.2.5. Assumption that was validated: There will be no data such that there is more than one provider identified as per pt.X.2.1 above 3. Pure intra-company [Sample: Intra only with many LEs]: 3.1. Base data balances by LE 3.2. Algorithm: 3.2.1. Find provider by looking for lines where IC segment is non zero. Those lines become provider revenue lines [if same receiver may have to summarize lines] --- This will not yield any results in this scenario 3.2.2. Find corresponding receiver lines with receiver as LE, no IC segment. These become receiver AP lines --- This will not yield any results in this scenario 3.2.3. Create IC batches. Oracle will add IC balancing lines --- This will not yield any results in this scenario 3.2.4. If provider was found as per pt.X.2.1, rest of lines identified for LE as provider should have IC as 000. These would become GL lines & should be already balanced. May be in different ledgers 3.2.5. Assumption that was validated: There will be no data such that there is more than one provider identified as per pt.X.2.1 above | Review IC journal and validate IC balance for each entity. Validate AR and AP invoices for each entity. Ensure journal only had single provider (AR) and multiple debtors (AP). Ensure transactions that balance within the entity do not create IC. Validate both entered and accounted currencies. Ensure transactions posted in both primary and secondary ledger. |  |  | Sprint 9 | Approved | Erica | 2021-07-15 |  | #REF! |  | RTR | RTR-GL | IC | WESCO |  |  | Ian/Vitaliy | [8 empty] | User Stories - GL Batch 6 GPO Approval
CSTONE-5656 | CSTONE-9220 | CSTONE-9221 | CSTONE-9222 | Sprint 12 | RTR-IC-035A |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As a GL accountant, I need a non-material I/C AR Aging report by legal entity. Report should provide a detail at invoice level. |  |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report | RPT032 | User story split into A & B. RTR-IC-035A is AR Aging at invoice level. RTR-IC-035B is AP Aging at Invoice level | Validate completeness and accuracy of the report. Ensure the report contains all the required data per business design. Validate that fields are available for data selection as per business design. |  |  | Sprint 12 | Approved | Erica | 2021-07-18 |  | #REF! |  | RTR | RTR-GL | IC | WESCO |  |  | Ian/Vitaliy | [8 empty] | User Stories - GL Batch 6 GPO Approval
CSTONE-5657 | CSTONE-9223 | CSTONE-9224 | CSTONE-9225 | Sprint 12 | RTR-IC-035B |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As a GL accountant, I need a non-material I/C AP Aging report by legal entity. Report should provide a detail at invoice level. |  |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report | RPT033 | User story split into A & B. RTR-IC-035A is AR Aging at invoice level. RTR-IC-035B is AP Aging at Invoice level | Validate completeness and accuracy of the report. Ensure the report contains all the required data per business design. Validate that fields are available for data selection as per business design. |  |  | Sprint 12 | Approved | Erica | 2021-07-18 |  | #REF! |  | RTR | RTR-GL | IC | WESCO |  |  | Ian/Vitaliy | [8 empty] | User Stories - GL Batch 6 GPO Approval
CSTONE-5658 | CSTONE-9226 | CSTONE-9227 | CSTONE-9228 | Sprint 12 | RTR-IC-036A |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As a GL accountant, I need a non-material I/C AR Aging report by legal entity. Report should provide a summary at account level. |  |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report | RPT034 | User story split into A & B. RTR-IC-036A is AR Aging at account level. RTR-IC-036B is AP Aging at account level | Validate completeness and accuracy of the report. Ensure the report contains all the required data per business design. Validate that fields are available for data selection as per business design. |  |  | Sprint 12 | Approved | Erica | 2021-07-18 |  | #REF! |  | RTR | RTR-GL | IC | WESCO |  |  | Ian/Vitaliy | [8 empty] | User Stories - GL Batch 6 GPO Approval
CSTONE-5659 | CSTONE-9229 | CSTONE-9230 | CSTONE-9231 | Sprint 12 | RTR-IC-036B |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As a GL accountant, I need a non-material I/C AP Aging report by legal entity. Report should provide a summary at account level. |  |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report | RPT035 | User story split into A & B. RTR-IC-036A is AR Aging at account level. RTR-IC-036B is AP Aging at account level | Validate completeness and accuracy of the report. Ensure the report contains all the required data per business design. Validate that fields are available for data selection as per business design. |  |  | Sprint 12 | Approved | Erica | 2021-07-18 |  | #REF! |  | RTR | RTR-GL | IC | WESCO |  |  | Ian/Vitaliy | [8 empty] | User Stories - GL Batch 6 GPO Approval
CSTONE-5660 | CSTONE-6848 | Not in Jira | CSTONE-6734 | Sprint 11 | RTR-IC-037 |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As a GL accountant, I need a report of all IC transactions entered but not approved. |  |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report | RPT036 | IC Transaction Detail report to be built - similar to workshop layout | Validate completeness and accuracy of the report. Ensure the report contains all the required data per business design. |  |  | Sprint 11 | Approved | Erica | 2021-07-18 |  | #REF! |  | RTR | RTR-GL | IC | WESCO |  |  | Ian/Vitaliy | [8 empty] | User Stories - GL Batch 6 GPO Approval
CSTONE-5661 |  |  |  | N/A | RTR-IC-038 |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As a GL accountant, I need a report of all IC transactions that are in error (part of the subledger close process). |  |  | Phase 1B only | 10-Not Required-Not Required-Not Required | Not Required | Not Required | Not Required |  | Duplicate of reports and steps added under AR and AP close L2 |  |  |  |  | Approved | Erica | 2021-07-15 |  | #REF! |  | RTR | RTR-GL | IC | WESCO |  |  | Ian/Vitaliy | [8 empty] | User Stories - GL Batch 6 GPO Approval
CSTONE-5662 | CSTONE-6849 | Not in Jira | CSTONE-6735 | Sprint 11 | RTR-IC-039 |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As a GL accountant, I need a report of all IC AR invoices recorded but not yet transferred to AP. |  |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report | RPT036 | IC Transaction Detail report to be built - similar to workshop layout | Validate completeness and accuracy of the report. Ensure the report contains all the required data per business design. |  |  | Sprint 11 | Approved | Erica | 2021-07-18 |  | #REF! |  | RTR | RTR-GL | IC | WESCO |  |  | Ian/Vitaliy | [8 empty] | User Stories - GL Batch 6 GPO Approval
CSTONE-5663 | CSTONE-5758 |  |  | CSTONE-5758 | RTR-IC-040 |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As a Financial Systems Analyst, I need the ability to close IC AR and AP subledger. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Oracle standard subledger process to be used to close/open/re-open period. Role security would determine users who have access to close / open AR/AP periods. Note: AR & AP close is at ledger level. Once third party AR / AP is deployed in future release, need to align on who will own close [IC vs Third party team] | Validate that AP and AR subledgers closed correctly. Ensure no transactions can be posted in the subledger after it is closed. |  |  | Sprint 8 | Approved | Erica | 2021-07-18 |  | #REF! |  | RTR | RTR-GL | IC | WESCO |  |  | Ian/Vitaliy | [8 empty] | User Stories - GL Batch 6 GPO Approval
CSTONE-5664 | CSTONE-5759 |  |  | CSTONE-5759 | RTR-IC-041 |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As a Financial Systems Analyst, I need the ability to open IC AR and AP subledger for the next period. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Oracle standard subledger process to be used to close/open/re-open period. Role security would determine users who have access to close / open AR/AP periods. Note: AR & AP close is at ledger level. Once third party AR / AP is deployed in future release, need to align on who will own close [IC vs Third party team] | Validate that AP and AR subledgers opened correctly. Ensure transactions can be posted in the subledger after it is opened. |  |  | Sprint 8 | Approved | Erica | 2021-07-18 |  | #REF! |  | RTR | RTR-GL | IC | WESCO |  |  | Ian/Vitaliy | [8 empty] | User Stories - GL Batch 6 GPO Approval
CSTONE-5665 | CSTONE-5760 |  |  | CSTONE-5760 | RTR-IC-042 |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As a Financial Systems Analyst, I need the ability to reopen IC AR and AP subledger for the period previously closed. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Oracle standard subledger process to be used to close/open/re-open period. Role security would determine users who have access to close / open AR/AP periods. Note: AR & AP close is at ledger level. Once third party AR / AP is deployed in future release, need to align on who will own close [IC vs Third party team] | Validate that AP and AR subledgers reopened correctly. Ensure transactions can be posted in the subledger after it is opened. |  |  | Sprint 8 | Approved | Erica | 2021-07-18 |  | #REF! |  | RTR | RTR-GL | IC | WESCO |  |  | Ian/Vitaliy | [8 empty] | User Stories - GL Batch 6 GPO Approval
CSTONE-5666 | CSTONE-5111 |  |  | CSTONE-5111 | RTR-IC-043 |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As an Intercompany Accountant, I want the ability to create many to many IC journals directly in GL and the system to auto balance the journal (for US and Canadian entities). |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | GL Journal autobalancing enabled for US and Canada ledgers. Many to Many to be setup using "default clearing balancing account" option | Validate that balancing lines were correctly created for each IC journal [directly entered in GL]. Validate both entered and accounted currencies. Validate balancing is only enabled for US and Canadian entities. |  |  | Sprint 7 | Approved | Erica | 2021-07-15 |  | #REF! |  | RTR | RTR-GL | IC | WESCO |  |  | Ian/Vitaliy | [8 empty] | User Stories - GL Batch 6 GPO Approval
CSTONE-5667 |  |  |  | N/A | RTR-IC-044 |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As a I/C GL accountant, I need a report of all non-material I/C AP invoices created by LE and period. |  |  | Phase 1B only | 10-Not Required-Not Required-Not Required | Not Required | Not Required | Not Required |  | Duplicate of RTR-IC-014B | Reviewed non-material I/C AP invoices report. Ensure all AP invoices generated by period is captured in the report. Ensure format of report matches business design. |  |  |  | Approved | Erica | 2021-07-15 |  | #REF! |  | RTR | RTR-GL | IC | WESCO |  |  | Ian/Vitaliy | [8 empty] | User Stories - GL Batch 6 GPO Approval
CSTONE-5668 | CSTONE-5761 |  |  | CSTONE-5761 | RTR-IC-045 |  | Record to Report | Manage Intercompany Accounting | Perform AR Period Close | As an Intercompany accountant, I need the ability to run Receivables to GL Reconciliation Report so that I can carry out reconciliation at Month-end [IC AR] |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Seeeded AR to GL Recon report [Security]. Two step process, run a process & then view results in another screen | Validate AR reconciliation report. Ensure subledger reconciles with GL. Ensure reconciliaion can be ran for prior periods. Validate the GL balance on the report matches GL balance in ERP. Validates balance on report matches subledger. |  |  | Sprint 8 | Approved | Erica | 2021-07-18 |  | #REF! |  | RTR | RTR-GL | IC | Deloitte |  |  | Ian/Vitaliy | [8 empty] | User Stories - GL Batch 6 GPO Approval
CSTONE-5669 | CSTONE-5762 |  |  | CSTONE-5762 | RTR-IC-046 |  | Record to Report | Manage Intercompany Accounting | Perform AR Period Close | As an Intercompany Accountant, I need the ability to run Subledger Period Close Exception Report so that I can validate the invalid transactions and close the period [IC AR] |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Seeded Subledger period close exception report OR custom subledger period close exception report being developed in 1A Exception report will show exception till it is resolved. Once report it re-run after resolution, exception will not appear in report output | Validate exception report. Ensure all errors are captured on the report. Once errors are resolved, ensure they no longer appear in the report. Ensure exception reports from prior can be generated or are archived. |  |  | Sprint 8 | Approved | Erica | 2021-07-18 |  | #REF! |  | RTR | RTR-GL | IC | Deloitte |  |  | Ian/Vitaliy | [8 empty] | User Stories - GL Batch 6 GPO Approval
CSTONE-5670 | CSTONE-5763 |  |  | CSTONE-5763 | RTR-IC-047 |  | Record to Report | Manage Intercompany Accounting | Perform AR Period Close | As a Intercompany Accountant, Financial Analyst I need the ability to run create accounting at month-end to post all transactions in GL [IC AR] |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Standard Create Accounting process [Security] | Validate that create accounting can be ran at month end. Ensure all transactions posted in the GL. |  |  | Sprint 8 | Approved | Erica | 2021-07-18 |  | #REF! |  | RTR | RTR-GL | IC | Deloitte |  |  | Ian/Vitaliy | [8 empty] | User Stories - GL Batch 6 GPO Approval
CSTONE-5671 | CSTONE-5764 |  |  | CSTONE-5764 | RTR-IC-048 |  | Record to Report | Manage Intercompany Accounting | Perform AR Period Close | As an Intercompany Accountant, I need the ability to access the period close dashboard to close the current period and open the next [IC AR]. Should also support ability to re-open period |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Standard period close screen [Security] | Review period close dashboard. Ensure all open subledgers are marked. Also ensure all closed subledgers are marked on the dash board. |  |  | Sprint 8 | Approved | Erica | 2021-07-18 |  | #REF! |  | RTR | RTR-GL | IC | Deloitte |  |  | Ian/Vitaliy | [8 empty] | User Stories - GL Batch 6 GPO Approval
CSTONE-5672 | CSTONE-5765 |  |  | CSTONE-5765 | RTR-IC-049 |  | Record to Report | Manage Intercompany Accounting | Perform AP Period Close | As an Intercompany accountant, I need the ability to run Payables to GL Reconciliation Report so that I can carry out reconciliation at Month-end [IC AP] |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Seeeded AP to GL Recon report [Security]. Two step process, run a process & then view results in another screen | Validate AP reconciliation report. Ensure subledger reconciles with GL. Ensure reconciliaion can be ran for prior periods. Validate the GL balance on the report matches GL balance in ERP. Validates balance on report matches subledger. |  |  | Sprint 8 | Approved | Erica | 2021-07-18 |  | #REF! |  | RTR | RTR-GL | IC | Deloitte |  |  | Ian/Vitaliy | [8 empty] | User Stories - GL Batch 6 GPO Approval
CSTONE-5673 | CSTONE-5766 |  |  | CSTONE-5766 | RTR-IC-050 |  | Record to Report | Manage Intercompany Accounting | Perform AP Period Close | As a Financial Analyst, I need the ability to run Invoice Validation process so that I can validate the transactions as preparation to close the period [IC AP] |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Standard Invoice validation process [Security] | Verify validation ran correctly. Ensure transactions are included as part of the validation. |  |  | Sprint 8 | Approved | Erica | 2021-07-18 |  | #REF! |  | RTR | RTR-GL | IC | Deloitte |  |  | Ian/Vitaliy | [8 empty] | User Stories - GL Batch 6 GPO Approval
CSTONE-5674 | CSTONE-5767 |  |  | CSTONE-5767 | RTR-IC-051 |  | Record to Report | Manage Intercompany Accounting | Perform AP Period Close | As a Financial Analyst, I need the ability to run the approval process so that system can mark AP invoices are auto=approved in preparation to close the period [IC AP] |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Standard Approval process [Security] | Ensure auto approval ran automatically. Validate all AP invoices have been approved by the process. |  |  | Sprint 8 | Approved | Erica | 2021-07-18 |  | #REF! |  | RTR | RTR-GL | IC | Deloitte |  |  | Ian/Vitaliy | [8 empty] | User Stories - GL Batch 6 GPO Approval
CSTONE-5675 | CSTONE-5768 |  |  | CSTONE-5768 | RTR-IC-052 |  | Record to Report | Manage Intercompany Accounting | Perform AP Period Close | As an Intercompany Accountant, I need the ability to run Subledger Period Close Exception Report so that I can validate the invalid transactions and close the period [IC AP] |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Seeded Subledger period close exception report OR custom subledger period close exception report being developed in 1A Exception report will show exception till it is resolved. Once report it re-run after resolution, exception will not appear in report output | Validate exception report. Ensure all errors are captured on the report. Once errors are resolved, ensure they no longer appear in the report. Ensure exception reports from prior can be generated or are archived. |  |  | Sprint 8 | Approved | Erica | 2021-07-18 |  | #REF! |  | RTR | RTR-GL | IC | Deloitte |  |  | Ian/Vitaliy | [8 empty] | User Stories - GL Batch 6 GPO Approval
CSTONE-5676 | CSTONE-5769 |  |  | CSTONE-5769 | RTR-IC-053 |  | Record to Report | Manage Intercompany Accounting | Perform AP Period Close | As a Financial Analyst, I need the ability to run create accounting at month-end to post all transactions in GL [IC AP] |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Standard Create Accounting process [Security] | Validate that create accounting can be ran at month end. Ensure all transactions posted in the GL. |  |  | Sprint 8 | Approved | Erica | 2021-07-18 |  | #REF! |  | RTR | RTR-GL | IC | Deloitte |  |  | Ian/Vitaliy | [8 empty] | User Stories - GL Batch 6 GPO Approval
CSTONE-5677 | CSTONE-5770 |  |  | CSTONE-5770 | RTR-IC-054 |  | Record to Report | Manage Intercompany Accounting | Perform AP Period Close | As an Intercompany Accountant, I need the ability to access the period close dashboard to close the current period and open the next [IC AP]. Should also support ability to re-open period |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Standard period close screen [Security] | Review period close dashboard. Ensure all open subledgers are marked. Also ensure all closed subledgers are marked on the dash board. |  |  | Sprint 8 | Approved | Erica | 2021-07-18 |  | #REF! |  | RTR | RTR-GL | IC | Deloitte |  |  | Ian/Vitaliy | [8 empty] | User Stories - GL Batch 6 GPO Approval
CSTONE-5678 |  |  |  |  | RTR-AHCS-168 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant , I want the ability to generate a report with the subledger transaction details for Mexican entities so that I can meet local electronic reporting requirements | Must Have | MX | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Use existing Subledger Account Analysis Report: The report to provide the details of the subledger for monthly detail reporting | Validate report and compare to legacy subledger reporting used for Mexican electronic reporting | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs for CALA LE's. |  |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | N/a |  | N/A |  |  |  |  | Approved on Tuesday, January 18, 2022 7:15 PM | 28
CSTONE-5679 | CSTONE-7623 | CSTONE-9904 | CSTONE-9964 | N/A | RTR-IC-055 |  | Record to Report | Manage Intercompany Accounting | Perform AP Period Close | Currency Rates (For Monthly translation rate for countries such as FINLAND) |  |  | Phase 1B only | 10-Not Required-Not Required-Not Required | Not Required | Not Required | Not Required | CNV012 (DESCOPED) |  |  |  |  | Sprint 8 | Approved |  |  |  | #REF! |  | RTR | RTR-GL | IC | Deloitte |  |  | Ian/Vitaliy | [8 empty] | Update to 1B User Stories
CSTONE-5680 | CSTONE-6238 | CSTONE-6867 | CSTONE-8131 | CSTONE-6238 | RTR-IC-056 |  | Record to Report | Manage Intercompany Accounting | Perform AP Period Close | Intercompany AR Invoices Conversion - North America |  |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV015 |  |  |  |  | Sprint 10 | Approved |  |  |  | #REF! |  | RTR | RTR-GL | IC | Deloitte |  |  | Ian/Vitaliy | [8 empty] | Update to 1B User Stories
CSTONE-5681 | CSTONE-6239 | CSTONE-6868 | CSTONE-8132 | CSTONE-6239 | RTR-IC-057 |  | Record to Report | Manage Intercompany Accounting | Perform AP Period Close | Intercompany AP Invoices Conversion (non-material) - North America |  |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV016 |  |  |  |  | Sprint 10 | Approved |  |  |  | #REF! |  | RTR | RTR-GL | IC | Deloitte |  |  | Ian/Vitaliy | [8 empty] | Update to 1B User Stories
CSTONE-5682 | CSTONE-6240 | CSTONE-6869 | CSTONE-8133 | CSTONE-6240 | RTR-IC-058 |  | Record to Report | Manage Intercompany Accounting | Perform AP Period Close | Intercompany AR Invoices Conversion (non-material) - EMEA |  |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV017 |  |  |  |  | Sprint 10 | Approved |  |  |  | #REF! |  | RTR | RTR-GL | IC | Deloitte |  |  | Ian/Vitaliy | [8 empty] | Update to 1B User Stories
CSTONE-5683 | CSTONE-6241 | CSTONE-6870 | CSTONE-8134 | CSTONE-6241 | RTR-IC-059 |  | Record to Report | Manage Intercompany Accounting | Perform AP Period Close | Intercompany AP Invoices Conversion (non-material) - EMEA |  |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV018 |  |  |  |  | Sprint 10 | Approved |  |  |  | #REF! |  | RTR | RTR-GL | IC | Deloitte |  |  | Ian/Vitaliy | [8 empty] | Update to 1B User Stories
CSTONE-5684 | CSTONE-6242 | CSTONE-6871 | CSTONE-8135 | CSTONE-6242 | RTR-IC-060 |  | Record to Report | Manage Intercompany Accounting | Perform AP Period Close | Intercompany AR Invoices Conversion (non-material) - APAC |  |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV019 |  |  |  |  | Sprint 10 | Approved |  |  |  | #REF! |  | RTR | RTR-GL | IC | Deloitte |  |  | Ian/Vitaliy | [8 empty] | Update to 1B User Stories
CSTONE-5685 | CSTONE-6243 | CSTONE-6872 | CSTONE-8136 | CSTONE-6243 | RTR-IC-061 |  | Record to Report | Manage Intercompany Accounting | Perform AP Period Close | Intercompany AP Invoices Conversion (non-material) - APAC |  |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV020 |  |  |  |  | Sprint 10 | Approved |  |  |  | #REF! |  | RTR | RTR-GL | IC | Deloitte |  |  | Ian/Vitaliy | [8 empty] | Update to 1B User Stories
CSTONE-5686 | CSTONE-6244 | CSTONE-6873 | CSTONE-8137 | CSTONE-6244 | RTR-IC-062 |  | Record to Report | Manage Intercompany Accounting | Perform AP Period Close | Intercompany AR Invoices Conversion (non-material) - CALA |  |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV021 |  |  |  |  | Sprint 10 | Approved |  |  |  | #REF! |  | RTR | RTR-GL | IC | Deloitte |  |  | Ian/Vitaliy | [8 empty] | Update to 1B User Stories
CSTONE-5687 | CSTONE-6245 | CSTONE-6874 | CSTONE-8138 | CSTONE-6245 | RTR-IC-063 |  | Record to Report | Manage Intercompany Accounting | Perform AP Period Close | Intercompany AP Invoices Conversion (non-material) - CALA |  |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV022 |  |  |  |  | Sprint 10 | Approved |  |  |  | #REF! |  | RTR | RTR-GL | IC | Deloitte |  |  | Ian/Vitaliy | [8 empty] | Update to 1B User Stories
CSTONE-5688 | CSTONE-6246 | CSTONE-6672 | CSTONE-8139 | CSTONE-6672 | RTR-IC-064 |  | Record to Report | Manage Intercompany Accounting | Perform AP Period Close | Intercompany AP Invoice Feed to Teradata |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT186 |  |  |  |  | Sprint 10 | Approved |  |  |  | #REF! |  | RTR | RTR-GL | IC | Deloitte |  |  | Ian/Vitaliy | [8 empty] | Update to 1B User Stories
CSTONE-5689 | CSTONE-6247 | Not in Jira | CSTONE-8140 | CSTONE-6676 | RTR-IC-065 |  | Record to Report | Manage Intercompany Accounting | Perform AP Period Close | Intercompany AP Payment Feed to Teradata (Netting, Settlement, LSI) |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT188 |  |  |  |  | Sprint 10 | Approved |  |  |  | #REF! |  | RTR | RTR-GL | IC | Deloitte |  |  | Ian/Vitaliy | [8 empty] | Update to 1B User Stories
CSTONE-5690 | CSTONE-6248 | CSTONE-6875 | CSTONE-8141 | CSTONE-6248 | RTR-IC-066 |  | Record to Report | Manage Intercompany Accounting | Perform AP Period Close | Intercompany AR invoice feed to Teradata |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT190 |  |  |  |  | Sprint 10 | Approved |  |  |  | #REF! |  | RTR | RTR-GL | IC | Deloitte |  |  | Ian/Vitaliy | [8 empty] | Update to 1B User Stories
CSTONE-5691 | CSTONE-6249 | CSTONE-6676 | CSTONE-8142 | CSTONE-6249 | RTR-IC-067 |  | Record to Report | Manage Intercompany Accounting | Perform AP Period Close | Intercompany AR Receipt Feed to Teradata (Netting, Settlement, LSI) |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT192 |  |  |  |  | Sprint 10 | Approved |  |  |  | #REF! |  | RTR | RTR-GL | IC | Deloitte |  |  | Ian/Vitaliy | [8 empty] | Update to 1B User Stories
#N/A |  |  |  |  | RTR-AHCS-169 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As a GL accountant, I want a report which needs to be extracted based on the Event Type (SII, ISI,CQI, etc) from Mainframe on an Ad hoc basis in order to search by a specific transaction and all the details associated with it. | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT129 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' Merge with RTR-AHCS-197 , create Close out search report | Report should extract data based on the Event Type (SII, ISI,CQI, etc) from Mainframe on an Ad hoc basis | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs. |  |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte | [11 empty] | Approved on Tuesday, January 18, 2022 7:15 PM | 28
#N/A |  |  |  |  | RTR-AHCS-170 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As a GL Accountant, I need a process to identify and open Accrual balances versus closed accrual balances between various accrual accounts, Trade Unvouchered, IC Unvouchered, Kava Unvouchered, Intra Intransit, Returns Unvouchered, WO Unvouchered, Freight Duty Unvouchered, Freight Accrual. | Won't Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope |  | 04/22 NG : Based on KDD approval marking this as ‘Out of Scope’ sent for approval. 02/04 : JIRA ID # CTPFS-3876 This is associated with Accrual Discussion To be finalised after Report Disposition | The report should identify pen Accrual balances versus closed accrual balances between various accrual accounts, Trade Unvouchered, IC Unvouchered, Kava Unvouchered, Intra Intransit, Returns Unvouchered, WO Unvouchered, Freight Duty Unvouchered, Freight Accrual. |  |  |  | TBD | ian plummer | 2022-04-24 |  |  |  | RTR | RTR-AHCS | AHCS | Deloitte | [12 empty] | 31
#N/A |  |  |  |  | RTR-AHCS-171 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As a GL Accountant, I need a process to Close out balances in each subledger due to system limitations from the legacy system where items cannot easily be matched and closed out in the system (Close out tool). | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT129 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' Based on Closeout tool meeting decision business is inclined to option1 "Retrofit current Close out tool" as part of which new report needs to be created for closeout. | Report should provide the Close out balances in each subledger due to system limitations from the legacy system where items cannot easily be matched and closed out in the system (Close out tool). | Confirm through reconciliation process variance to be moved using the close out tool. Ensure able to to input required data to move variance as per business design. Verify variance have been moved after close out tool process has been ran through reporting. |  |  | Approved | Ian | 2022-02-03 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte | [11 empty] | Approved on Mon 2/7/2022 7:10 PM | 31
#N/A |  |  |  |  | RTR-AHCS-172 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As a GL Accountant, I need a report that captures legacy source codes by transaction detail so that I can tie these back to GL data. For example SII, ARI and CRI, etc. Reference existing report RPT009 needs enhancement. | Must Have |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report | RPT009_R | 01/31 : Do not see this in Report rationalisation tracker as of 01/31, hence marking as ' Not required' and routing for approval. Enhance existing Subledger account analysis report to display legacy source code and other supporting reference attributes | Verify source code is displayed on correct AHCS transactions | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs. |  |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | Boon Hui | Rhonda | Betty |  |  |  | Approved on Tuesday, January 18, 2022 7:15 PM | 28
#N/A |  |  |  |  | RTR-AHCS-173 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report with the subledger transaction details so that I can perform ad-hoc analysis on subledger data in AHCS | Must Have |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report | RPT009_R | Existing 1A Report Subledger Account Analysis Report: The report to provide the details of the subledger for ad-hoc analysis | Validate report and compare to legacy subledger for reconciliations. | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs. |  |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | Boon Hui | Rhonda | Betty - what is RPT009? | Sent Betty reponse on RPT009 - IP 11/15 |  |  | Approved on Tuesday, January 18, 2022 7:15 PM | 28
#N/A | Not in Jira |  |  |  | RTR-AHCS-174 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a IT Manager, i want to ensure that all Legacy transactions that are in error and successfully posted are communcicated back to Legacy system as BAD file | Must Have |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report | RPT006_R, EXT010, EXT011 INT237 | Use existing OIC Dashboard, AHCS Dashboard, AHCS Error Report and AHCS to GL Recon to identify issues in system and solution | All trasnactions that are in error are comunicated to IT in a timely manner | All transactions that are in error are sent back to Legacy IT. Bad records file will be sent back to IT for Mainframe transactions. |  |  | Approved | Sijo John |  |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  | Acceptance criteria 1 doesn't make sense. What would be the process for IT to communicate to business? How would we test this? IP 12-15 |  | Bhim | Boon Hui | Rhonda | Betty. What would be the "timely manner?" I mean how often or specific day (s) on the calendar? |  |  |  | Approved On Thu 1/20/2022 9:17 PM | 31
CSTONE-5692 |  |  |  |  | RTR-AHCS-175 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As IT Administrator, I want Concur Source system to extract the transactions from Legacy system for both ABC Corp and ABC Corp, send to Oracle Cloud, OIC to perform validation and transform the data in AHCS approved data model so that AHCS can processed the transaction | Must Have |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT125 | Interface to process Concur data in Oracle Cloud | Verify transactions are accounted correctly in relevant subledger with appropriate attributes | All attributes defined in Concur data model are brought in AHCS and detailed information is available in AHCS |  |  | Approved | Sijo John Ian Plummer | 2021-11-28 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | GL accountant don’t have ability to process Concur transactions? Change the user? We need to check each source code as well. AP AR etc need to be confirmed as well. Specifically AP as i am lead to believe MF only gives one side of the transaction offsetting balance to trade ap is created in FAH? | N/A | Rhonda | CALA: Beatriz García/Sandra Patiño/Jose Luis Ortiz | Should this user story be related to IT as opposed to GL accountant? - IP | MS 11/11 - AHCS need balanced journals for processing, Concur only provides expense side of the entry, we need information from Business on the offset lines to create a balanced journal in AHCS. |  | User Stories (AHCS Track) - Batch2 GPO Approval | 26.1
#N/A |  |  |  |  | RTR-AHCS-176 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant I want to ensure that the subledger journals are created in both primary and secondary ledgers where applicable so that I can record journals in both GAAP/STAT accounting convention & Global COA/Local COA respectively for France and Secondary Ledger description fields use Local language | Must Have |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | The Subledger level conversion process will be used during the Secondary ledger creation which will be assigned with a different Subledger Accounting Method. When the create accounting process is executed Subledger journal entries will be created both in Primary as well as secondary transactions | Verify that subledger transactions are reflected in both primary and seconday ledgers for LE's that require local stat data. Ensure correct entries are posted with local gaap accounting rules (per business design). | Verify that subledger transactions are reflected in both primary and seconday ledgers for LE's that require local stat data. Ensure correct entries are posted with local gaap accounting rules (per business design). In addition verify that appropriate coa has been populated for local stat where applicable. Also validate Secondary Ledger description fields are populated in local language per Business design. |  |  | Approved | Ian | 2021-12-03 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  | Ian 12-3-21 | Bhim | N/A | N/A | N/A |  |  |  | Approved as Batch 3 | 27
#N/A |  |  |  |  | RTR-AHCS-177 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As an IT administrator, I need a dashboard to compare source system, validate and transformed transaction counts any error by different Legacy source system so that IT team can perform completeness check and take appropriate action if required | Must Have |  | Phase 1B only | 5-Gap-Build-Extension | Gap | Build | Extension | EXT010 (R), EXT011 (R) | Enhance existing OIC dashboard, to reconcile transaction count by legacy source systems | Dashboard should be near real time, displaying the count of transaction received and processed across different source system | The enhanced Dashboard should display the count of transaction received and processed across different source system and interfaces (SII, API etc.) |  |  | Approved | Sijo john Ian Plummer 12-23-21 |  |  | 1-Fit-Configuration-Functional | Sprint Manually overridden - 1A RICE Demo | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | Boon Hui | Rhonda |  |  |  |  | Approved as Batch 3 | 26.2
#N/A |  |  |  |  | RTR-AHCS-178 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant I want to ensure that the AHCS detailed transactions are send to IAP so that accounting details along with reference data can be used for reporting | Must Have |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT043 | AHCS Detailed Info (Header and Line info along with Net Period activity details) will be sent to IAP for reconciliation | Review AHCS detailed transactions along with reference data is available in IAP for reporting. Verified through testing that transactions in AHCS along with supporting references can be extracted in IAP. | Validate detailed transactions tie to IAP tables |  |  | Approved | Ian | 2022-01-18 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | Boon Hui | Rhonda | Betty | Disagree with acceptance criteria #1. Isn't this an IT function? iP 12-15 Also should story be rewritten that I want to be able to access data in IAP related to AHCS? | MS 12/16 - Requirement of sending posted AHCS data to IAP is business requirement. This story is about AHCS sending transaction and not accesing / presenting in AHCS |  | Approved On Thu 1/20/2022 9:17 PM | 28
#N/A |  |  |  |  | RTR-AHCS-179 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant I want to ensure that the AHCS balances are send to IAP so that data can be used for reporting | Must Have |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT044 | AHCS Balances (alomg with Balance enabled SR) will be sent to IAP for reconciliation of Balances | Review AHCS detailed transactions balances along with reference data is available in IAP for reporting. Verified through testing that balances in AHCS along with supporting references can be extracted in IAP. | validate AHCS balances tie to IAP |  |  | Approved | Ian | 2022-01-18 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | Boon Hui | Rhonda | Betty | Disagree with acceptance criteria #1. Isn't this an IT function? iP 12-15 Also should story be rewritten that I want to be able to access data in IAP related to AHCS? | MS 12/16 - Requirement of sending posted AHCS data to IAP is business requirement. This story is about AHCS sending transaction and not accesing / presenting in AHCS |  | Approved On Thu 1/20/2022 9:17 PM | 28
#N/A |  |  |  |  | RTR-AHCS-181 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As IT Administrator, I want SxE - US Source system to transform the Legacy ERP COA segment to PeopleSoft COA segment so that Oracle can transform from PeopleSoft COA to Cloud COA using centralized mapping engine |  |  | Not Required | 7-Out of Scope-Out of Scope-Out of Scope |  |  |  |  | This requirement is for Legacy application and out of Oracle scope | [10 empty] | RTR | RTR-AHCS | AHCS | [13 empty] | 21
#N/A |  |  |  |  | RTR-AHCS-182 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As IT Administrator, I want Eclipse Source system to transform the Journals from ERP COA segment to PeopleSoft COA segment so that Oracle can use centralized PS COA to Cloud COA mapping |  |  | Not Required | 7-Out of Scope-Out of Scope-Out of Scope |  |  |  |  | This requirement is for Legacy application and out of Oracle scope |  |  |  |  | Initial Fit/Gap Complete | [5 empty] | RTR | RTR-AHCS | AHCS | [13 empty] | 22
#N/A | CSTONE-5700 |  |  |  | RTR-AHCS-183 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As IT Administrator, I want Lease Harbor Source system to extract the transactions from Legacy system, send to Oracle Cloud, OIC to perform validation and transform the data in AHCS approved data model so that AHCS can processed the transaction | Must Have |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT020 | Interface to process Lease Harbor data for both ABC Corp and ABC Corp in Oracle Cloud | Interface should be able to pick up Lease Harbor transactions and process it in OIC Middleware and AHCS successfully | All attributes defined in Lease Harbor data model are brought in AHCS and detailed information is available in AHCS |  |  | Approved | Sijo John |  |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim |  | Rhonda |  |  |  |  | Approved On Thu 1/20/2022 9:17 PM | 24
#N/A |  |  |  |  | RTR-AHCS-184 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant I want to ensure that the GL summary journals are send to IAP so that accounting details along with reference data can be used for reporting |  |  | Not Required | 10-Not Required-Not Required-Not Required | Not Required | Not Required | Not Required |  | Duplicate | [10 empty] | RTR | RTR-AHCS | AHCS | [13 empty] | 28
#N/A |  |  |  |  | RTR-AHCS-185 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant I want to ensure that the GL balances are send to IAP so that accounting details along with reference data can be used for reporting |  |  | Not Required | 10-Not Required-Not Required-Not Required | Not Required | Not Required | Not Required |  | Duplicate | [10 empty] | RTR | RTR-AHCS | AHCS | [13 empty] | 28
#N/A |  |  |  |  | RTR-AHCS-186 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As IT Administrator, I want US Payrolll Source system to extract the transactions from Legacy system, send to Oracle Cloud in new COA, OIC to perform validation and transform the data in AHCS approved data model so that AHCS can processed the transaction | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Gap | Build | Interface |  | 04/22 NG : Based on KDD approval marking this as ‘Out of Scope’ sent for approval. 02/04 : JIRA ID # CTPFS-3877 01/31 : Marked as 'TBD' remove RICE ID and in future will visit again. Payroll system will be finalised in apr 2023, Vendor slection is not yet done. Legacy team to extract US Payroll data and interface into Oracle Cloud Middleware | Build a systematic/automated data completeness check to support the daily imports. Validate / test | All attributes defined in US Payroll data model are brought in AHCS and detailed information is available in AHCS |  |  | TBD | Sijo John Ian Plummer | 2022-04-24 |  |  |  | RTR | RTR-AHCS | AHCS | Deloitte | [12 empty] | 26.2
#N/A |  |  |  |  | RTR-AHCS-187 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As IT Administrator, I want Canada Payroll Source system to extract the transactions from Legacy system, send to Oracle Cloud in new COA, OIC to perform validation and transfL462orm the data in AHCS approved data model so that AHCS can processed the transaction | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Gap | Build | Interface |  | 04/22 NG : Based on KDD approval marking this as ‘Out of Scope’ sent for approval. 02/04 : JIRA ID # CTPFS-3877 01/31 : Marked as 'TBD' remove RICE ID and in future will visit again. Payroll system will be finalised in apr 2023, Vendor slection is not yet done. Legacy team to extract US Payroll data and interface into Oracle Cloud Middleware | Build a systematic/automated data completeness check to support the daily imports. Validate / test | All attributes defined in Canada Payroll data model are brought in AHCS and detailed information is available in AHCS |  |  | TBD | Sijo John Ian Plummer | 2022-04-24 |  |  |  | RTR | RTR-AHCS | AHCS | Deloitte | [12 empty] | 26.2
#N/A |  |  |  |  | RTR-AHCS-188 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want AHCS to be configured for US and Canada payroll Interface data as per business and accounting rules so that transactions are accounted correctly in Payroll Subledger with appropriate line level information , Supporting Reference and other details. | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope |  | 04/22 NG : Based on KDD approval marking this as ‘Out of Scope’ sent for approval. 02/04 : JIRA ID # CTPFS-3877 01/31 : Marked as 'TBD' remove RICE ID and in future will visit again. Payroll system will be finalised in apr 2023, Vendor slection is not yet done. Legacy team to extract US Payroll data and interface into Oracle Cloud Middleware | Verify transactions are accounted correctly in relevant subledger with appropriate attributes | Verified that total amount entered and accounted in AHCS is denoted with status of final through review subledger journal panel. Validate that total amounts in AHCS ties to total from source application through reporting. Validate that items were reflected correctly in AHCS. Verified that able to review detail transactions at line level through supporting references as per business design. |  |  | TBD | Ian Ian Plummer | 1/18/2022 4/24/22 |  |  |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | n/a | N/A | Rhonda | N/A |  |  |  |  | 26.2
#N/A |  |  |  |  | RTR-AHCS-189 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As a GL Accountant I need a systematic process that records Unvouchered for various process such as Workorders, Freight Accrual, Material Trade/Direct Shipment/ KAVA/Intra Intransit/Returns/IC/Freight and Duty. | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope |  | 04/22 NG : Based on KDD approval marking this as ‘Out of Scope’ sent for approval. 02/04 : JIRA ID # CTPFS-3876 Will be finalised in future Accrual Process. |  |  |  |  | TBD | ian plummer | 2022-04-24 |  |  |  | RTR | RTR-AHCS | AHCS | Deloitte | [12 empty] | 31
#N/A |  |  |  |  | RTR-AHCS-190 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As a GL Accountant I need a systematic process that identifies closed unvouchered balances and open unvouchered balances. | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope |  | 04/22 NG : Based on KDD approval marking this as ‘Out of Scope’ sent for approval. 02/04 : JIRA ID # CTPFS-3876 Will be finalised in future Accrual Process. |  |  |  |  | TBD | ian plummer | 2022-04-24 |  |  |  | RTR | RTR-AHCS | AHCS | Deloitte | [12 empty] | 31
#N/A |  |  |  |  | RTR-AHCS-191 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As a GL Accountant I need a process that automates any close out of balances in AHCS (Close out tool) that should be closed or netted off. | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope |  | 04/22 NG : Based on KDD approval marking this as ‘Out of Scope’ sent for approval. 02/04 : JIRA ID # CTPFS-3876 Will be finalised in future Accrual Process. |  |  |  |  | TBD | ian plummer | 2022-04-24 |  |  |  | RTR | RTR-AHCS | AHCS | Deloitte | [12 empty] | 31
#N/A |  |  |  |  | RTR-AHCS-192 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As a GL Accountant I need a systematic process that identifies any variances between Inventory in MF and AHCS and true up the balance based on specific threshold. | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope |  | 04/22 NG : Based on KDD approval marking this as ‘Out of Scope’ sent for approval. 02/04 : JIRA ID # CTPFS-3876 Will be finalised in future Accrual Process. |  |  |  |  | TBD | ian plummer | 2022-04-24 |  |  |  | RTR | RTR-AHCS | AHCS | Deloitte | [12 empty] | 31
#N/A |  | CSTONE-6187 |  |  | RTR-AHCS-193 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant, I want all the transactions for SXE US to be recorded in the correct accounting period. | Must Have |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Accounting date from SLA / XLA tables will be utilized for determining the date for AHCS transactions | Confirm accounting dates in legacy subledger and HUB is same | Verify accounting date in AHCS aligns with correct accounting period for subledger journal. | Validate that date from source system ties to Accounting date in AHCS through reporting. |  | Approved | Ian | 2022-01-18 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | n/a | N/A | Rhonda | N/A |  |  |  | Approved On Thu 1/20/2022 9:17 PM | 21
#N/A |  | CSTONE-6188 |  |  | RTR-AHCS-194 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant, I want all the transactions for Eclipse to be recorded in the correct accounting period. | Must Have |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Accounting date from SLA / XLA tables will be utilized for determining the date for AHCS transactions | Confirm accounting dates in legacy subledger and HUB is same | Verify accounting date in AHCS aligns with correct accounting period for subledger journal. | Validate that date from source system ties to Accounting date in AHCS through reporting. |  | Approved | Ian | 2022-01-18 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | n/a | N/A | Rhonda | N/A |  |  |  | Approved On Thu 1/20/2022 9:17 PM | 22
#N/A |  | CSTONE-5695 |  |  | RTR-AHCS-195 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant, I want all the journals for Peoplesoft Fixed Assets (PS FA) to use accounting date attribute as an accounting date so that all transactions are created in the accurate accounting period | Must Have |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Accounting date from SLA / XLA tables will be utilized for determining the date for AHCS transactions | Confirm accounting dates in legacy subledger and HUB is same | Verify accounting date in AHCS aligns with correct accounting period for subledger journal. | Validate that date from source system ties to Accounting date in AHCS through reporting. |  | Approved | Ian | 2022-01-18 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | n/a | N/A | Rhonda | Betty. Only applicable for PR |  |  |  | Approved On Thu 1/20/2022 9:17 PM | 20
#N/A |  | CSTONE-5698 |  |  | RTR-AHCS-196 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant, I want all the transactions for Lease Harbor to be recorded in the correct accounting period. | Must Have |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Apply date from SLA / XLA tables will be utilized for determining the date for AHCS transactions | Confirm accounting dates in legacy subledger and HUB is same | Verify accounting date in AHCS aligns with correct accounting period for subledger journal. | Validate that date from source system ties to Accounting date in AHCS through reporting. |  | Approved | Ian | 2022-01-18 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | Boon Hui | Rhonda | Betty |  |  |  | Approved On Thu 1/20/2022 9:17 PM | 24
#N/A |  |  |  |  | RTR-AHCS-197 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report with the subledger transaction details so that I have the option to search by Receipt Purchase order or Vendor or customer Invoices. | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT129 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope'' Current Report Name in Legacy FAH -'Close Out Search'- Subledger Account Analysis Report with Extended Search Functionality: The report to provide the details of the subledger for monthly detail reporting with additional option to search by Receipt Purchase order or Vendor or customer Invoices. This is required for research purposes in order to close out any incorrect Invoices / PO across all Interfaces. Merge with RTR-AHCS-169 | User should be able to search by Invoice#, PO# etc. and get specific set of data in the report in the required format | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs. |  |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte | [11 empty] | Approved on Tue 2/1/2022 10:02 AM | 28
#N/A |  |  |  |  | RTR-AHCS-198 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a reportshowing the differences of Intercompany AP amount versus Intercompany AR amount with Accounting Period and Legal Entity as the Parameters |  |  | Not Required | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope |  | 12/23 NG: Removed as per latest report rationalization master document Current Report Name in Legacy FAH- 'Intercompany Exception' This report will show dat only if there is a difference between Intercompany AP and AR amounts for that particularLE- High Volume AUDIT Report. Would need to check the performance issues- For Comparing IC AP and AR amount for a Accounting Period and Legal Entity | User should be able to compare the AP and AR IC Amounts and should be able to see the data with difference for that particular Period and LE. |  |  |  | Approved | [5 empty] | RTR | RTR-AHCS | AHCS | [5 empty] | Bhim | Boon Hui | Rhonda | Betty |  |  |  |  | 28
#N/A |  |  |  |  | RTR-AHCS-199 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report showing the open AP items by their aging buckets with invoice details as well in English (US) Language | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT131 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' Current Report Name in Legacy FAH- 'AP Aging With Invoices' - Report to show the open AP items by their aging buckets with invoice details as well (INV_I & INV_D & INV_DUE_D) in English (US) Language It should be able to run by the selected month.-APAC | User should be able to generate a report showing the open AP items by their aging buckets with invoice details in English (US) Language | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs in English language. |  |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | Boon Hui | Rhonda | Betty |  |  |  | Approved on Tuesday, January 18, 2022 7:15 PM | 28
#N/A |  |  |  |  | RTR-AHCS-200 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report which shows a detailed report break down the of open transactions in account 310010009 in English (US) Language | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT132 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' Current Report Name in Legacy FAH- 'AP Cash Clearing Aging Details' - report breaksdown the open transactions in account 310010009 by BU, Loc, Vendor, Source code type, Statement ID and aging amongst others in English (US) Language | User should be able to generate a report which shows detailed report break down the open transactions in account 310010009 in English (US) Language | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs in English language. |  |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | Boon Hui | Rhonda | Betty |  |  |  | Approved on Tuesday, January 18, 2022 7:15 PM | 28
#N/A |  |  |  |  | RTR-AHCS-201 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report which shows the movement by AP Intercompany invoices details within said month in English (US) Language | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT133 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' 02/04 - Based on accounting hub data only.Current Report Name in Legacy FAH- 'AP Detailed Intercompany Trial Balance' - Detailed report that shows the movement by invoice details (INV_I, INV_D, JRNL_I, PAY_TERM, FRT_BILL_I) within said month in English (US) Language | User should be able to generate a report which shows the movement by AP Intercompany invoice details within said month in English (US) Language | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs in English language. |  |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | Boon Hui | Rhonda | Betty |  |  |  | Approved on Tuesday, January 18, 2022 7:15 PM | 28
#N/A |  |  |  |  | RTR-AHCS-202 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report which shows the movement by AP invoice details within said month in English (US) Language | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT134 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' Current Report Name in Legacy FAH- 'AP Detailed Trial Balance' - Detailed report that shows the movement by invoice details (INV_I & INV_D & INV_DUE_D) within said month. It should be able to run by the selected month. Information such as vendor name, vendor invoice, invoice amounts, etc will be required in English | User should be able to generate a report which shows the movement by AP invoice details within said month in English (US) Language | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs in English language. |  |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | Boon Hui | Rhonda | Betty |  |  |  | Approved on Tuesday, January 18, 2022 7:15 PM | 28
#N/A |  |  |  |  | RTR-AHCS-203 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report showing the open AR items by their aging buckets with invoice details as well in English (US) Language | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT135 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' Current Report Name in Legacy FAH- 'AR Aging With Invoices' - Report to show the open AP items by their aging buckets with invoice details as well (INV_I & INV_D & INV_DUE_D) in English (US) Language It should be able to run by the selected month | User should be able to generate a report showing the open AR items by their aging buckets with invoice details in English (US) Language | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs in English language. |  |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | Boon Hui | Rhonda | Betty |  |  |  | Approved on Tuesday, January 18, 2022 7:15 PM | 28
#N/A |  |  |  |  | RTR-AHCS-204 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report which shows a detailed report break down the of open transactions in account 121100009 in English (US) Language | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT136 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' Current Report Name in Legacy FAH- 'AR Cash Clearing Aging Details' - report breaksdown the open transactions in account 121100009 by Loc, Customer, Source code type, Statement ID and aging amongst other in English (US) Language | User should be able to generate a report which shows detailed report break down the open transactions in account 121100009 in English (US) Language | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs in English language. |  |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | Boon Hui | N/A | Betty |  |  |  | Approved on Tuesday, January 18, 2022 7:15 PM | 28
#N/A |  |  |  |  | RTR-AHCS-205 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report which shows the movement by Intercompany AR invoices details within said month in English (US) Language | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT137 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' 02/04 - Based on accounting hub data only.Current Report Name in Legacy FAH- 'AR Detailed Intercompany Trial Balance' - Detailed report that the movement by invoice details (INV_I, INV_D, JRNL_I, PAY_TERM, FRT_BILL_I) within said month. Non Detailed version of this report is not needed if this is provided. Account 127000000 in English (US) Language High volume report, performance may be impacted - but parked for AHCS as this is AUDIT report | User should be able to generate a report which shows the movement by AR Intercompany invoice details within said month in English (US) Language | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs in English language. |  |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | Boon Hui | N/A | Betty |  |  |  | Approved on Tuesday, January 18, 2022 7:15 PM | 28
#N/A |  |  |  |  | RTR-AHCS-206 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report which breaksdown the open transactions for different Cash Clearing Accounts in English (US) Language | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT138 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' Current Report Name in Legacy FAH- 'Bank Cash Clearing' - This detailed report breaksdown the open transactions in accounts 351100009, 328361009, 101400001, 101499999 and 379990009 by BU, Loc, Customer, Source code type, Statement ID amongst other in English (US) Language High volume report, performance may be impacted - but parked for AHCS as this is AUDIT report | User should be able to generate a report which shows the open transactions for different Cash Clearing Accounts in English (US) Language | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs in English language. |  |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | can we have 310099999 - AP Offsets & 121200001 - Unapplied Cash - A/R Offset in this report as well? Atm we're doing a closeout search to get all transactions in this account to reconcile. | N/A | N/A | N/A |  |  |  | Approved on Tuesday, January 18, 2022 7:15 PM | 28
#N/A |  |  |  |  | RTR-AHCS-207 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report which shows the movement by AR invoice details within said month in English (US) Language | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT139 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' Current Report Name in Legacy FAH- 'AR Detailed Trial Balance' - Detailed report that shows the movement by invoice details (INV_I & INV_D & INV_DUE_D) within said month. It should be able to run by the selected month. Information such as customer name, invoice number, invoice amounts, etc will be required in English (US) Language | User should be able to generate a report which shows the movement by AR invoice details within said month in English (US) Language | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs in English language. |  |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | Boon Hui | Rhonda | Betty |  |  |  | Approved on Tuesday, January 18, 2022 7:15 PM | 28
#N/A |  |  |  |  | RTR-AHCS-208 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report that shows the movement by transaction within all the bank accounts by Legal Entity in English (US) Language | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT140 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' Current Report Name in Legacy FAH- 'Bank Roll Forward detail'- Should show the movement by transaction within all the bank accounts grouped by LE in English (US) Language | User should be able to generate a report that shows the movement by transaction within all the bank accounts by Legal Entity in English (US) Language | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs in English language. |  |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | Boon Hui | N/A | Betty |  |  |  | Approved on Tue 2/1/2022 10:02 AM | 28
#N/A |  |  |  |  | RTR-AHCS-209 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report that shows the WIP, RTV, Warranty Replacement, Freight Claims aging which ties back to GL in English Language | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT141 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' Current Report Name in Legacy FAH- 'Special Sales Aging'- Should be able to tie back to GL in English (US) Language This report show special sales aging by customer/invoice number/date | User should be able to generate a report that he WIP, RTV, Warrenty, Freight Claims and can be tied back to GL in English (US) Language | Validate WIP, RTV, Warranty, Freight Claims are broken out by category | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs in English language. |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | Boon Hui | Rhonda | Betty |  |  |  | Approved on Tuesday, January 18, 2022 7:15 PM | 28
#N/A |  |  |  |  | RTR-AHCS-210 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report that shows the Intercompany AP Aging (material & non material) process in English Language | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT142 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' 02/03 - Based on accouting hub data only. Current Report Name in Legacy FAH- 'Intercompany AP Aging (material & non material)'- Nees this in English Language | User should be able to generate a report that shows the Intercompany Aging (material & non material) process in English Language | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs in English language. |  |  | Approved | Ian | 2022-01-18 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | Boon Hui | N/A | Betty | Sent email to Nilakanth 1-13 to revise story. IP |  |  | Approved on Tue 2/1/2022 10:02 AM | 28
#N/A |  |  |  |  | RTR-AHCS-211 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report that shows the Intercompany AP Trail balance (material & no material) details in English Language | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT143 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' 02/04 - Based on accounting hub data only.Current Report Name in Legacy FAH- 'Intercompany AP Trail balance (material & no material)'. This is in in English Language | User should be able to generate a report that shows the Intercompany Trail balance (material & no material) details in English (US) Language | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs in English language. |  |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim, How is this different to the AP & AR IC reports mentioned above? is this Material and non-material while the above is only material? | Boon Hui | N/A | Betty | Sent email to Nilakanth 1-13 to revise story. IP |  |  | Approved on Tue 2/1/2022 10:02 AM | 28
#N/A |  |  |  |  | RTR-AHCS-212 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report that shows the aging of open Invoices hitting Trade Payables and Intercompany Payables | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT144 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' 02/04 - Based on accounting hub data only.Current Report Name in Legacy FAH- 'AP Aging Without Invoices' Invoices hitting intercompany are flaged as Intercompany (Yes) in the report. Does not have invoice numbers. | User should be able to generate a report shows the aging of open Invoices hitting Trade Payables and Intercompany Payables | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs. |  |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim, FAH- 'AP Aging Without Invoices' - This should be AP Aging with invoice? | Boon Hui | Rhonda | Betty |  |  |  | Approved on Tuesday, January 18, 2022 7:15 PM | 28
#N/A |  |  |  |  | RTR-AHCS-213 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report that shows payments which have not yet been matched in AHCS based on Invoice# or Statement ID | Must Have |  | Not Required | 10-Not Required-Not Required-Not Required | Not Required | Not Required | Not Required |  | 12/23 NG: Removed as per latest report rationalization master document Current Report Name in Legacy FAH- 'AP Cash Clearing Aging'. If base and foreign AMT add to zero and records match on Inv_I, Vndr_I, Invoice_date, Loc_I, GL_dept, GL_Account then record should not appear on this report | User should be able to generate a report which shows payments which have not yet been matched in FAH based on Invoice# or Statement ID |  |  |  | Approved | [5 empty] | RTR | RTR-AHCS | AHCS | [5 empty] | Bhim, How is this different to RTR-AHCS-200? | Statement ID means bank statement ID? | Rhonda | Betty |  |  |  |  | 28
#N/A |  |  |  |  | RTR-AHCS-214 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report that shows inventory in transit by location and invoices. | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT146 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' Current Report Name in Legacy FAH- 'Goods In Intransit - Intercompany'. The report should consist of invoice date, material amount, freight, duty and brokerage, IC mark up, tax & etc in both local and vendor amount. | User should be able to generate a report which shows inventory in transit by location and invoices. | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs. |  |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | Boon Hui | N/A | Betty |  |  |  | Approved on Tuesday, January 18, 2022 7:15 PM | 28
#N/A |  |  |  |  | RTR-AHCS-215 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report that displays month ending balances by BU, Loc and Item# for transactions impacting Inventory Accounts in English (US) Language | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT147 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' Current Report Name in Legacy FAH- 'Inventory Detailed Trial Balance'. PS Journals hitting Material Inventory or Direct Shipment accounts are not considered for this report. To include item quantity, unit cost, item description, product class, UOM, UOM Conversion.-APAC req in English (US) Language | User should be able to generate a report which has the ability to generate a report that displays month ending balances by BU, Loc and Item# for transactions impacting Inventory Accounts in English (US) Language | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs in English language. |  |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | Boon Hui | Rhonda | Betty |  |  |  | Approved On Thu 1/20/2022 9:17 PM | 28
#N/A |  |  |  |  | RTR-AHCS-217 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report that shows breakdown the revenue by BU | Must Have |  | Not Required | 10-Not Required-Not Required-Not Required | Not Required | Not Required | Not Required |  | 12/23 NG: Removed as per latest report rationalization master document Current Report Name in Legacy FAH- 'Revenue Breakdown by BU'. This is an Audit Report. | User should be able to generate a report that shows Report to breakdown the revenue by BU |  |  |  | Initial Fit/Gap Complete | [5 empty] | RTR | RTR-AHCS | AHCS | [5 empty] | Bhim | Boon Hui | N/A | Betty |  |  |  |  | 28
#N/A |  |  |  |  | RTR-AHCS-218 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report that shows high level month to date and year to date sales, payments, and adj for MF AR transactions | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT149 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' Current Report Name in Legacy FAH- 'A/R Rollforward'. This is a Report for audit with Manual GL Journals | User should be able to generate a report that shows high level month to date and year to date sales, payments, and adj for MF AR transactions | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs. |  |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | Boon Hui | Rhonda | Betty |  |  |  | Approved On Thu 1/20/2022 9:17 PM | 28
#N/A |  |  |  |  | RTR-AHCS-219 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report that shows high level month to date and year to date payments, and adj for MF AP transactions | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT150 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' Current Report Name in Legacy FAH- 'A/P Rollforward'. This is a Report for audit with Manual GL Journals | User should be able to generate a report that shows high level month to date and year to date payments, and adj for MF AP transactions | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs. |  |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | Boon Hui | Rhonda - should this say month to date and year to date invoices instead of sales? | Betty |  |  |  | Approved on Tue 2/1/2022 10:02 AM | 28
#N/A |  |  |  |  | RTR-AHCS-220 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report that shows high level month to date and year to date receipts, shipments, adj, and returns split between trade and I/C for MF INV transactions | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT151 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' Current Report Name in Legacy FAH- 'Inv Rollforward'. This is a Report for audit with Manual GL Journals (Only Amount) | User should be able to generate a report that shows high level month to date and year to date receipts, shipments, adj, and returns split between trade and I/C for MF INV transactions | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs. |  |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | Boon Hui | Rhonda | Betty |  |  |  | Approved On Tuesday, January 18, 2022 7:15 PM | 28
#N/A |  |  |  |  | RTR-AHCS-221 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report that shows beginning balance, ytd activity, and ending balance of assets by category for cost and depreciation in AHCS to tie to Asset Management balances | Must Have |  | Not Required | 10-Not Required-Not Required-Not Required | Not Required | Not Required | Not Required |  | 12/23 NG: Removed as per latest report rationalization master document Current Report Name in Legacy FAH- 'Fixed Asset Rollforward'. Audit Report, as all FA data will be posted to single future account, use different event type / transaction type to create Asset Roll Forward | User should be able to generate a report that shows beginning balance, ytd activity, and ending balance of assets by category for cost and depreciation in AHCS to tie to Asset Management balances |  |  |  | Approved | [5 empty] | RTR | RTR-AHCS | AHCS | [5 empty] | n/a | N/A | N/A - AHCS will not contain beg balances for FA. | N/A for CALA, only PR but same comment as Rhonda or that is my understanding |  |  |  |  | 28
#N/A |  |  |  |  | RTR-AHCS-222 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report to tie out g/l balances to Accounting Hub and Asset Mgmt by category | Must Have |  | Not Required | 10-Not Required-Not Required-Not Required | Not Required | Not Required | Not Required |  | 12/23 NG: Removed as per latest report rationalization master document Current Report Name in Legacy FAH- 'Fixed Asset Tie Out'. This is a Report to tie out g/l balances to Accounting Hub and Asset Mgmt by category | User should be able to generate a report to tie out g/l balances to Accounting Hub and Asset Mgmt by category |  |  |  | Approved | [5 empty] | RTR | RTR-AHCS | AHCS | [5 empty] | n/a | N/A | N/A - AHCS will not contain beg balances for FA. | N/A for CALA, only PR but same comment as Rhonda or that is my understanding |  |  |  |  | 28
#N/A |  |  |  |  | RTR-AHCS-223 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report for G/L Account for an individual location or range of locations by date or period range based on Source | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT154 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' Current Report Name in Legacy FAH- 'SXE/Eclipse Interface Extract Report'. | User should be able to generate a report for G/L Account for an individual location or range of locations by date or period range based on Source | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs. |  |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | Boon Hui | Rhonda | Betty |  |  |  | Approved on Tuesday, January 18, 2022 7:15 PM | 28
CSTONE-5540 | CSTONE-6850 | Not in Jira | CSTONE-9741 | Sprint 11 | RTR-GL-164 |  | Record to Report | Manage General Ledger Accounting | Process Intercompany Journal Entries | As GL Accountant, I want the ability to generate a report for reconciling differences per LE-Intercompany combination between Intercompany AP and AR transactions with Accounting Period, Legal Entity and Intercompany Segments as the Parameters | Must Have |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report | RPT036 | Current Report Name- 'Intercompany Matching' - Matching by LE and Intercompany segment for AP and AR I/C Accounts - Current applicable for EMEA 2/8: IC Transaction Detail Report. Will use open balance columsn in the report | User should be able to compare the AP and AR IC Amounts and should be able to see the data with difference for that particular Period , LE - Intercompany segment combinations |  |  | Sprint 11 | Approved | Rita | 2022-02-08 |  | #REF! |  | RTR | RTR-GL | IC
CSTONE-5541 | CSTONE-8810 | CSTONE-11754 | CSTONE-11755 | Sprint 11 | RTR-GL-165 |  | Record to Report | Manage General Ledger Accounting | Process Manual Journal Entries | As GL Accountant, I want the ability to generate a report for showing Opening Balance (in debit & Credit Format), Credit , Debit, and Closing Balance (in debit & Credit Format). | Must Have |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report | RPT047 | Current Report Name- 'Trial balance in a true debit and credit format' 2/8: Existing RPT018 report 5/10 - RPT018 is descoped and RPT047 wwill meet the tax requirement. Hence, updated Build ID to RPT047 | User should be able to geenrate a report for showing Opening Balance (in debit & Credit Format), Credit , Debit, and Closing Balance (in debit & Credit Format). |  |  | Sprint 11 | Approved | Rita | 2022-02-08 |  | #REF! |  | RTR | RTR-GL | GL
#N/A | [6 empty] | EPM | Master Data Management | Maintain Chart of Accounts | As a GL Accountant I want to ensure that AR, AP, Inv, Bank Accounts, IC (127* & 3127*) are locked accounts. | Must Have |  | Phase 1B only | [24 empty] | Bhim
#N/A |  |  |  |  | RTR-AHCS-224 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to Import Material Intercompany Opening Balances into AHCS MF AR Subledger and mechanism to differentaite opening balances from daily transactions | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV042 | Beginning Balances will be brought to AHCS through a different AP Beg Bal Event Type Specifically for Trade payable Invoices & AP Cash Clearing Accounts | Opening balances are posted in AHCS MF AP Subledger and AP Beg Bal event type, AHCS Opening balance should match Legacy systems ending balance | Validate Legacy System ending balance ties to AHCS MF AP Beginning Balance through reporting from FAH onprem. Verify that there are no differences. |  |  | Approved | Ian | 2022-01-18 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | Boon Hui | Rhonda | Betty |  |  |  | Approved On Thu 1/20/2022 9:17 PM
#N/A |  | Not in Jira |  |  | RTR-AHCS-225 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As Financial Systems Analyst, I want the ability to restrict the Subledger Data related to MF AP Beginning Balance Event Type not to be transferred and posted to GL | Must Have |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Beginning Balances will be brought to AHCS through a different AP Beg Bal Event Type Specifically for Trade payable Invoices & AP Cash Clearing and will be finally accounted in AHCS and Not transferred to GL. This can be managed through Accounting Attribute - GL_TRANSFER_CODE | Subledger Data related to MF AP Beginning Balance should not to be transferred and posted to GL | Validate AHCS AP Beg Bal event type does not get transferred and posted to G/L |  |  | Approved | Manisha Ian | 1/31/2022 2/1/2022 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  | Need further discussion. How would we test to ensure doesn't post to GL? Also not listing all the beg bal loads IP 1-13 |  | Bhim | Boon Hui | Rhonda | Betty | Do beginning Balances go through create accounting? IP 12-15 | 12/16- Yes, Beginning balance follow-ssame process for exisi ting. | 2022-02-01 | Approved on Wed 2/2/2022 4:45 AM
#N/A |  |  |  |  | RTR-AHCS-226 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to Import Trade Receivables Opening Balances into AHCS MF AR Subledger and mechanism to differentaite opening balances from daily transactions | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV042 | Beginning Balances will be brought to AHCS through a different AR Beg Bal Event Type Specifically for Trade receivable. | Opening balances are posted in AHCS MF AR Subledger and AR Beg Bal event type, AHCS Opening balance should match Legacy systems ending balance | Validate Legacy System ending balance ties to AHCS MF AR Beginning Balance through reporting from FAH onprem. Verify that there are no differences. |  |  | Approved | Ian | 2022-01-18 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | Boon Hui | Rhonda | Betty |  |  |  | Approved On Thu 1/20/2022 9:17 PM
#N/A |  | Not in Jira |  |  | RTR-AHCS-227 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As Financial Systems Analyst, I want the ability to restrict the Subledger Data related to MF AR Beginning Balance Event Type not to be transferred and posted to GL | Must Have |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Beginning Balances will be brought to AHCS through a different AR Beg Bal Event Type Specifically for Trade payable Invoices and will be finally accounted in AHCS and Not transferred to GL. This can be managed through Accounting Attribute - GL_TRANSFER_CODE | Subledger Data related to MF AR Beginning Balance should not to be transferred and posted to GL | Validate AHCS AR Beg Bal event type does not get transferred and posted to G/L |  |  | Approved | Manisha Ian | 1/31/2022 2/1/2022 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  | Need further discussion. How would we test to ensure doesn't post to GL? Also not listing all the beg bal loads IP 1-13 |  | Bhim | Boon Hui | Rhonda | Betty | Do beginning Balances go through create accounting? IP 12-15 | 12/16-As per approved KDD, all beginning AP504balance follow-ssame process for exisi ting. | 2022-02-01 | Approved on Wed 2/2/2022 4:45 AM
#N/A |  |  |  |  | RTR-AHCS-228 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to Import Inventory Opening Balances into AHCS MF Inventory Subledger and mechanism to differentaite opening balances from daily transactions | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV043 | Beginning Balances will be brought to AHCS through a different MF INV Beg Bal Event Type Applicable for Trade Inventory & Others(Intangible,Reels,Intransit Stock, Intra Intrasit,RTV,Warranty,Freight & Claims) | Opening balances are posted in AHCS MF Inventory Subledger and Inv Beg Bal event type, AHCS Opening balance should match Legacy systems ending balance | Validate Legacy System ending balance ties to AHCS MF INV Beginning Balance through reporting from FAH onprem. Verify that there are no differences. |  |  | Approved | Ian | 2022-01-18 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | Boon Hui | Rhonda | Betty |  |  |  | Approved On Thu 1/20/2022 9:17 PM
#N/A |  | Not in Jira |  |  | RTR-AHCS-229 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As Financial Systems Analyst, I want the ability to restrict the Subledger Data related to MF INV Beginning Balance Event Type not to be transferred and posted to GL | Must Have |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Beginning Balances will be brought to AHCS through a different MF INV Beg Bal Event Type Specifically for Trade payable Invoices and will be finally accounted in AHCS and Not transferred to GL. This can be managed through Accounting Attribute - GL_TRANSFER_CODE | Subledger Data related to MF Inventory Beginning Balance should not to be transferred and posted to GL | Validate AHCS Inv Beg Bal event type does not get transferred and posted to G/L |  |  | Approved | Manisha Ian | 1/31/2022 2/1/2022 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  | Need further discussion. How would we test to ensure doesn't post to GL? Also not listing all the beg bal loads IP 1-13 |  | Bhim | Boon Hui | Rhonda | Betty | Do beginning Balances go through create accounting? IP 12-15 | Yes, it goes through create accounting process but AHCS has configuration functionality to restrict certain transaction from going to GL | 2022-02-01 | Approved on Wed 2/2/2022 4:45 AM
#N/A |  |  |  |  | RTR-AHCS-230 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to Import Unvouchered Opening Balances into AHCS MF AP Subledger and mechanism to differentaite opening balances from daily transactions | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV041 | Beginning Balances will be brought to AHCS through a different Unvouch Beg Bal Event Type Applicable for Unvouchered (Work Orders,Intercompany,Freight & Duty,Trade,Direct Ship & Return) | Unvouchered Opening balances are posted in AHCS AP Subledger and Unvouch Beg Bal event type, AHCS Opening balance should match Legacy systems ending balance | Validate Legacy System ending balance ties to AHCS Unvouchered WO, Interco, Freight&Duty, Trade, Direct Ship, Return Beginning Balance through reporting from FAH onprem. Verify that there are no differences. |  |  | Approved | Ian | 2022-01-18 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | Boon Hui | Rhonda | Betty |  |  |  | Approved On Thu 1/20/2022 9:17 PM
#N/A |  | Not in Jira |  |  | RTR-AHCS-231 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As Financial Systems Analyst, I want the ability to restrict the Subledger Data related to MF AP Unvouchered Beginning Balance Event Type not to be transferred and posted to GL | Must Have |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Beginning Balances will be brought to AHCS through a different Unvouch Beg Bal Event Type Specifically for Trade payable Invoices and will be finally accounted in AHCS and Not transferred to GL. This can be managed through Accounting Attribute - GL_TRANSFER_CODE | The Subledger Data related to MF AP (Unvouchered) Beginning Balance should not to be transferred and posted to GL | Validate AHCS AP Unvouch Beg Bal event type does not get transferred and posted to G/L |  |  | Approved | Manisha Ian | 1/31/2022 2/1/2022 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  | Need further discussion. How would we test to ensure doesn't post to GL? Also not listing all the beg bal loads IP 1-13 |  | Bhim | Boon Hui | Rhonda | Betty | Do beginning Balances go through create accounting? IP 12-15 | Yes, it goes through create accounting process but AHCS has configuration functionality to restrict certain transaction from going to GL | 2022-02-01 | Approved on Wed 2/2/2022 4:45 AM
#N/A |  |  |  |  | RTR-AHCS-232 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to Import Unvouchered Opening Balances into AHCS MF Inventory Subledger and mechanism to differentaite opening balances from daily transactions | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV043 | Beginning Balances will be brought to AHCS through a different AR Beg Bal Event Type Applicable for Unvouchered (Work Orders,Intercompany,Freight & Duty,Trade,Direct Ship,PPV/AP Variance & Other Material) | Unvouchered Opening balances are posted in AHCS Inventory Subledger and Unvouch Beg Bal event type, AHCS Opening balance should match Legacy systems ending balance | Validate Legacy System ending balance ties to AHCS Inv Unvouchered WO, Interco, Freight&Duty, Trade, Direct Ship, Return Beginning Balance through reporting from FAH onprem. Verify that there are no differences. In addition verify that Unvouchered PPV/AP Variance and other material ties to manual file loaded. |  |  | Approved | Ian | 2022-01-18 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | Boon Hui | Rhonda | Betty |  |  |  | Approved On Thu 1/20/2022 9:17 PM
#N/A |  | Not in Jira |  |  | RTR-AHCS-233 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As Financial Systems Analyst, I want the ability to restrict the Subledger Data related to MF INV Unvouchered Beginning Balance Event Type not to be transferred and posted to GL | Must Have |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Beginning Balances will be brought to AHCS through a different MF INV Unvouchered Beg Bal Event Type Applicable for Applicable for Unvouchered (Work Orders,Intercompany,Freight & Duty,Trade,Direct Ship,PPV/AP Variance & Other Material) and will be finally accounted in AHCS and Not transferred to GL. This can be managed through Accounting Attribute - GL_TRANSFER_CODE | The Subledger Data related to MF INV (Unvouchered) Beginning Balance should not to be transferred and posted to GL | Validate AHCS Inv Unvouch Beg Bal event type does not get transferred and posted to G/L |  |  | Approved | Manisha Ian | 1/31/2022 2/1/2022 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  | Need further discussion. How would we test to ensure doesn't post to GL? Also not listing all the beg bal loads IP 1-13 |  | Bhim | Boon Hui | Rhonda | Betty | Do beginning Balances go through create accounting? IP 12-15 | Yes, it goes through create accounting process but AHCS has configuration functionality to restrict certain transaction from going to GL | 2022-02-01 | Approved on Wed 2/2/2022 4:45 AM
#N/A |  |  |  |  | RTR-AHCS-234 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to Import Material Intercompany Opening Balances into AHCS MF AP Subledger and mechanism to differentaite opening balances from daily transactions | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV041 | Beginning Balances will be brought to AHCS through a different AP Beg Bal Event Type Applicable for Applicable for Intercompany(Invoice Related) | User should be able to Conversion of initial balances using event type for MF AP Subledger | Validate Legacy System ending balance ties to AHCS AP I/C subledger Beginning Balance through reporting from FAH onprem for EMEA. For other regions verify based on source file loaded. Verify that there are no differences. |  |  | Approved | Ian | 2022-01-18 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim, Should the acceptance criterias say AP IC Subledger? | Boon Hui | Rhonda | Betty |  |  |  | Approved On Thu 1/20/2022 9:17 PM
#N/A |  | Not in Jira |  |  | RTR-AHCS-235 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As Financial Systems Analyst, I want the ability to restrict the Subledger Data related to MF AP IC Beginning Balance Event Type not to be transferred and posted to GL | Must Have |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Beginning Balances will be brought to AHCS through a different MF AP Beg Bal Event Type applicable for Intercompany(Invoice Related)and will be finally accounted in AHCS and Not transferred to GL. This can be managed through Accounting Attribute - GL_TRANSFER_CODE | The Subledger Data related to MF AP (IC) Beginning Balance should not to be transferred and posted to GL | Validate AHCS AP I/C Beg Bal event type does not get transferred and posted to G/L |  |  | Approved | Manisha Ian | 1/31/2022 2/1/2022 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  | Need further discussion. How would we test to ensure doesn't post to GL? Also not listing all the beg bal loads IP 1-13 |  | Bhim | Boon Hui | Rhonda | Betty | Do beginning Balances go through create accounting? IP 12-15 | Yes, it goes through create accounting process but AHCS has configuration functionality to restrict certain transaction from going to GL | 2022-02-01 | Approved on Wed 2/2/2022 4:45 AM
#N/A |  |  |  |  | RTR-AHCS-236 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to Import Material Intercompany Opening Balances into AHCS MF AR Subledger and mechanism to differentaite opening balances from daily transactions | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV042 | Beginning Balances will be brought to AHCS through a different AR Beg Bal Event Type Applicable for Applicable for Intercompany(Invoice Related) | User should be able to Conversion of initial balances using event type for MF AR Subledger | Validate Legacy System ending balance ties to AHCS AR I/C subledger Beginning Balance through reporting from FAH onprem for EMEA. For other regions verify based on source file loaded. Verify that there are no differences. |  |  | Approved | Ian | 2022-01-18 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim, Should the acceptance criterias say AR IC Subledger? | Boon Hui | Rhonda | Betty |  |  |  | Approved On Thu 1/20/2022 9:17 PM
#N/A |  | Not in Jira |  |  | RTR-AHCS-237 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As Financial Systems Analyst, I want the ability to restrict the Subledger Data related to MF AR IC Beginning Balance Event Type not to be transferred and posted to GL | Must Have |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Beginning Balances will be brought to AHCS through a different MF AR Beg Bal Event Type applicable for Intercompany(Invoice Related)and will be finally accounted in AHCS and Not transferred to GL. This can be managed through Accounting Attribute - GL_TRANSFER_CODE | The Subledger Data related to MF AR (IC) Beginning Balance should not to be transferred and posted to GL | Validate AHCS AR I/C Beg Bal event type does not get transferred and posted to G/L |  |  | Approved | Manisha Ian | 1/31/2022 2/1/2022 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  | Need further discussion. How would we test to ensure doesn't post to GL? Also not listing all the beg bal loads IP 1-13 |  | Bhim | Boon Hui | Rhonda | Betty | Do beginning Balances go through create accounting? IP 12-15 | Yes, it goes through create accounting process but AHCS has configuration functionality to restrict certain transaction from going to GL | 2022-02-01 | Approved on Wed 2/2/2022 4:45 AM
#N/A |  |  |  |  | RTR-AHCS-238 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to Import Cresus (BKI) Beginning Balances from Cresus source into AHCS MF AP Subledger and mechanism to differentiate Bank Beg Bal (MF AP) transactions |  |  | Not Required | 10-Not Required-Not Required-Not Required | Not Required | Not Required | Not Required |  | Bank Beginning balance will not be loaded in AHCS, rather reports should refer to GL level balances for BKI transactions | User should be review opening balances under Bank Beg Bal under MF AP Subledger. Cresus and AHCS amount should reconcile | [9 empty] | RTR | RTR-AHCS | AHCS | [5 empty] | Bhim | N/A | N/A | N/A | Are these stories correct? Are we truly loading bank beg bal per kdd30? IP 12-16 | MS 12/16 - Agreed, changed the story status to NOT REQUIRED
#N/A |  |  |  |  | RTR-AHCS-239 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to restrict the Subledger Data related to MF AP Bank( for Cresus) Beg Balance Event Type not to be transferred and posted to GL |  |  | Not Required | 10-Not Required-Not Required-Not Required | Not Required | Not Required | Not Required |  | Beginning Balances will be brought to AHCS through a different MF AP Beg Bal Event Type Applicable for Cash clearing Account & Bank Opening Balance and will be finally accounted in AHCS and Not transferred to GL. This can be managed through Accounting Attribute - GL_TRANSFER_CODE | The Subledger Data related to MF AP Bank( for Cresus) Beginning Balance Event Type should not to be transferred and posted to GL | [9 empty] | RTR | RTR-AHCS | AHCS | [5 empty] | Bhim | N/A | N/A | N/A | Are these stories correct? Are we truly loading bank beg bal per kdd30? IP 12-16 | MS 12/16 - Agreed, changed the story status to NOT REQUIRED
#N/A |  |  |  |  | RTR-AHCS-240 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to Import Cresus (BKI) Beginning Balances from Cresus source into AHCS MF AR Subledger and mechanism to differentiate Bank Beg Bal (MF AR) transactions |  |  | Not Required | 10-Not Required-Not Required-Not Required | Not Required | Not Required | Not Required |  | Beginning Balances will be brought to AHCS through a Bank Beg Bal Event Type applicable for Cash clearing Account & Bank Opening Balance - EMEA only | User should be review opening balances under Bank Beg Bal under MF AR Subledger. Cresus and AHCS amount should reconcile | [9 empty] | RTR | RTR-AHCS | AHCS | [5 empty] | Bhim | N/A | N/A | N/A | Are these stories correct? Are we truly loading bank beg bal per kdd30? IP 12-16 | MS 12/16 - Agreed, changed the story status to NOT REQUIRED
#N/A |  |  |  |  | RTR-AHCS-241 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to restrict the Subledger Data related to MF AR Bank( for Cresus) Beg Balance Event Type not to be transferred and posted to GL |  |  | Not Required | 10-Not Required-Not Required-Not Required | Not Required | Not Required | Not Required |  | Beginning Balances will be brought to AHCS through a different MF AR Beg Bal Event Type Applicable for Cash clearing Account & Bank Opening Balance and will be finally accounted in AHCS and Not transferred to GL. This can be managed through Accounting Attribute - GL_TRANSFER_CODE | The Subledger Data related to MF AR Bank( for Cresus) Beginning Balance Event Type should not to be transferred and posted to GL | [9 empty] | RTR | RTR-AHCS | AHCS | [5 empty] | Bhim | N/A | N/A | N/A | Are these stories correct? Are we truly loading bank beg bal per kdd30? IP 12-16 | MS 12/16 - Agreed, changed the story status to NOT REQUIRED
#N/A |  |  |  |  | RTR-AHCS-242 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to Import PS Fixed Asset Opening Balances into AHCS PS FA Subledger and mechanism to differentaite opening balances from daily transactions |  |  | Not Required | 10-Not Required-Not Required-Not Required | Not Required | Not Required | Not Required |  | Beginning Balances will be brought to AHCS through a different event type - Beg Bal, balanced loaded by Asset ID (NA Only) | User should be review opening balances under FA Beg Bal event type and reconcile againt FA balances | [9 empty] | RTR | RTR-AHCS | AHCS | [5 empty] | n/a | N/A | Rhonda - Removed need for beginning balances in AHCS for Fixed Assets - this should be N/A now | N/A | N/A - IP 12-16 | MS 12/16 - Agreed, changed the story status to NOT REQUIRED
#N/A |  |  |  |  | RTR-AHCS-243 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to restrict the Subledger Data related to PS FA beg balance Beginning Balance Event Type not to be transferred and posted to GL |  |  | Not Required | 10-Not Required-Not Required-Not Required | Not Required | Not Required | Not Required |  | Beginning Balances will be brought to AHCS through a different PSFA beg balance and will be finally accounted in AHCS and Not transferred to GL. This can be managed through Accounting Attribute - GL_TRANSFER_CODE | The Subledger data related to PSFA Beginning Balance Event Type should not to be transferred or posted to GL | [9 empty] | RTR | RTR-AHCS | AHCS | [5 empty] | n/a | N/A | Rhonda - Removed need for beginning balances in AHCS for Fixed Assets - this should be N/A now | N/A | N/A - IP 12-16 | MS 12/16 - Agreed, changed the story status to NOT REQUIRED
#N/A |  |  |  |  | RTR-AHCS-244 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to Import Trade Payable Invoices & AP Cash Clearing Opening Balances into AHCS MF AP Subledger for 2nd term. and mechanism to differentiate opening balances from daily transactions\ | Must Have |  | Phase 1B only | 10-Not Required-Not Required-Not Required | Not Required | Not Required | Not Required |  | AHCS Conversion to load AP, AR, Inventory subledger opening balance for Austria secondary ledger These users stories are marked as 'Not required' and 'Approved' under Subtype and added new User stories from RTR-AHCS-344 to 469 and added as "Initial Fit/Gap Complete" , Kindly review and have Acceptance Criteria Documented for these. | User should be review opening balances under MF AP, MF AR and MF Eventory subledger, respective Beg Bal event type. |  |  |  | Approved | ian | 2022-01-21 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  | Need further discussion. Don't under story fully. Ip 1-13 | [8 empty] | Approved on Wed 2/2/2022 4:45 AM
#N/A |  |  |  |  | RTR-AHCS-245 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to load AP, AR, Inventory subledger opening balance for Germany secondary ledger | Must Have |  | Phase 1B only | 10-Not Required-Not Required-Not Required | Not Required | Not Required | Not Required |  | AHCS Conversion to load AP, AR, Inventory subledger opening balance for Germany secondary ledger These users stories are marked as 'Not required' and 'Approved' under Subtype and added new User stories from RTR-AHCS-344 to 469 and added as "Initial Fit/Gap Complete" , Kindly review and have Acceptance Criteria Documented for these. | User should be review opening balances under MF AP, MF AR and MF Eventory subledger, respective Beg Bal event type. |  |  |  | Approved | ian | 2022-01-21 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  | Are these being generalized or are we listing out all beg loads? Ip 1-13 | [8 empty] | Approved on Wed 2/2/2022 4:45 AM
#N/A |  |  |  |  | RTR-AHCS-246 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to load AP, AR, Inventory subledger opening balance for Norway secondary ledger | Must Have |  | Phase 1B only | 10-Not Required-Not Required-Not Required | Not Required | Not Required | Not Required |  | AHCS Conversion to load AP, AR, Inventory subledger opening balance for Norway secondary ledger These users stories are marked as 'Not required' and 'Approved' under Subtype and added new User stories from RTR-AHCS-344 to 469 and added as "Initial Fit/Gap Complete" , Kindly review and have Acceptance Criteria Documented for these. | User should be review opening balances under MF AP, MF AR and MF Eventory subledger, respective Beg Bal event type. |  |  |  | Approved | ian | 2022-01-21 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  | Are these being generalized or are we listing out all beg loads? Ip 1-13 | [8 empty] | Approved on Wed 2/2/2022 4:45 AM
#N/A |  |  |  |  | RTR-AHCS-247 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to load AP, AR, Inventory subledger opening balance for Spain secondary ledger | Must Have |  | Phase 1B only | 10-Not Required-Not Required-Not Required | Not Required | Not Required | Not Required |  | AHCS Conversion to load AP, AR, Inventory subledger opening balance for Spain secondary ledger These users stories are marked as 'Not required' and 'Approved' under Subtype and added new User stories from RTR-AHCS-344 to 469 and added as "Initial Fit/Gap Complete" , Kindly review and have Acceptance Criteria Documented for these. | User should be review opening balances under MF AP, MF AR and MF Eventory subledger, respective Beg Bal event type. |  |  |  | Approved | ian | 2022-01-21 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  | Are these being generalized or are we listing out all beg loads? Ip 1-13 | [8 empty] | Approved on Wed 2/2/2022 4:45 AM
#N/A |  |  |  |  | RTR-AHCS-248 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to load AP, AR, Inventory subledger opening balance for Poland secondary ledger | Must Have |  | Phase 1B only | 10-Not Required-Not Required-Not Required | Not Required | Not Required | Not Required |  | AHCS Conversion to load AP, AR, Inventory subledger opening balance for Poland secondary ledger These users stories are marked as 'Not required' and 'Approved' under Subtype and added new User stories from RTR-AHCS-344 to 469 and added as "Initial Fit/Gap Complete" , Kindly review and have Acceptance Criteria Documented for these. | User should be review opening balances under MF AP, MF AR and MF Eventory subledger, respective Beg Bal event type. |  |  |  | Approved | ian | 2022-01-21 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  | Are these being generalized or are we listing out all beg loads? Ip 1-13 | [8 empty] | Approved on Wed 2/2/2022 4:45 AM
#N/A |  |  |  |  | RTR-AHCS-249 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to load AP, AR, Inventory subledger opening balance for Arabia secondary ledger | Must Have |  | Phase 1B only | 10-Not Required-Not Required-Not Required | Not Required | Not Required | Not Required |  | AHCS Conversion to load AP, AR, Inventory subledger opening balance for Arabia secondary ledger These users stories are marked as 'Not required' and 'Approved' under Subtype and added new User stories from RTR-AHCS-344 to 469 and added as "Initial Fit/Gap Complete" , Kindly review and have Acceptance Criteria Documented for these. | User should be review opening balances under MF AP, MF AR and MF Eventory subledger, respective Beg Bal event type. |  |  |  | Approved | ian | 2022-01-21 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  | Are these being generalized or are we listing out all beg loads? Ip 1-13 | [8 empty] | Approved on Wed 2/2/2022 4:45 AM
#N/A | CSTONE-6250 |  |  |  | RTR-AHCS-250 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As IT Manager, I want the Treasury Workstation (Power Solutions) source system to extract the transactions based on the approved data model and AHCS to process the transactions with relevant attributes so that the transactions are accounted with detail information in AHCS’ | Must Have |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT045 | Legacy team to extract legacy Treasury Workstation (Power Solutions) data and interface into Oracle Cloud Middleware | Legacy treasury data should be successfully interfaced to AHCS via OIC Middleware | All attributes defined in Treasury Workstation data model are brought in AHCS and detailed information is available in AHCS. Also ensure that AHCS data ties to Oracle GL |  |  | Approved | Sijo John |  |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | n/a | N/A | Rhonda - how is this different from RTR-AHCS-070? | N/A | Rhonda - how is this different from RTR-AHCS-070? - IP 12-16 |  |  | Approved On Thu 1/20/2022 9:17 PM
#N/A | CSTONE-2612 | CSTONE-2635 |  | CSTONE-4652 | RTR-GL-137A |  | Record to Report | Manage General Ledger Accounting | Maintain Chart of Accounts | As a member of the BI team creating Oracle GL reporting, I will require a Teradata table DSS_TABLES.ORACLE_CLD_GL_JE containing the GL journal details from INT011 |  |  | 1a | 2-Gap-Build-Report | Gap | Build | Report |  | Dependency:INT011 | Succesfully Validated |  |  | 2021-08-08 | IN PROGRESS | Jeremy Hornbuckle | 2021-08-13 | M |  |  | RTR | RTR-BI | NA | Deloitte
#N/A | CSTONE-2613 | CSTONE-2636 |  | CSTONE-4655 | RTR-GL-137B |  | Record to Report | Manage General Ledger Accounting | Maintain Chart of Accounts | As a member of the BI team creating Oracle GL reporting, I will require a Teradata table DSS_TABLES.ORACLE_CLD_GL_BAL containing the GL balances from INT010 |  |  | 1a | 2-Gap-Build-Report | Gap | Build | Report |  | Dependency:INT010 | Succesfully Validated |  |  | 2021-08-08 | IN PROGRESS | Jeremy Hornbuckle | 2021-08-13 | M |  |  | RTR | RTR-BI | NA | Deloitte
CSTONE-5535 | CSTONE-615 | CSTONE-3646 | CSTONE-3666 | CSTONE-3227 | RTR-GL-143 | BI-RTR-GL-143 | Record to Report | Manage General Ledger Accounting | Maintain Chart of Accounts | As an accountant, I require Outbound to:TeraData (AHCS Data to TeraData - AHCS Reconciliation Balances) Outbound from:Cloud AHCS Feed Type:AHCS Reconciliation Balances Feed#:Tera Data Feed 3 |  |  | 1a | 2-Gap-Build-Report | Gap | Build | Report |  | KDD8 requirements RICE ID INT041 | Succesfully Validated | [6 empty] | M |  |  | RTR | RTR-BI | NA | Deloitte
CSTONE-5533 | CSTONE-614 | CSTONE-3645 | CSTONE-3665 | CSTONE-3228 | RTR-GL-141 | BI-RTR-GL-141 | Record to Report | Manage General Ledger Accounting | Maintain Chart of Accounts | As an accountant, I require Outbound to:TeraData (AHCS Data to TeraData - AHCS Details) Outbound from:Cloud AHCS Feed Type:AHCS Details Feed#:Tera Data Feed 4 |  |  | 1a | 2-Gap-Build-Report | Gap | Build | Report |  | KDD8 requirements RICE ID INT044 | Succesfully Validated | [6 empty] | M |  |  | RTR | RTR-BI | NA | Deloitte
CSTONE-5552 |  |  |  | N/A | REP-FSG-RTR-GL-007 | BI-REP-FSG-RTR-GL-007A | Record to Report | Manage General Ledger Accounting | Maintain Chart of Accounts | AS an Accountant I want to be able to generate a Trial Balance by ODS (oper grp/dept/site) report with filters allowing to pull data by actuals or stat accounts. |  |  | 1a | 2-Gap-Build-Report | Gap | Build | Report | DESCOPED | Replaces Oracle FSG GA_TB_BRANCH_ACTUAL & GA_TB_BRANCH_STAT. Replaces REP | FSG | RTR | GL | 1900-01-07 |  |  |  | M |  |  | RTR | RTR-BI | NA | Deloitte
CSTONE-5552 |  |  |  | N/A | REP-FSG-RTR-GL-007 | BI-REP-FSG-RTR-GL-007B | Record to Report | Manage General Ledger Accounting | Maintain Chart of Accounts | AS an Accountant I want to be able to generate a Trial Balance by ODS (oper grp/dept/site) report with filters allowing to pull data by actuals or stat accounts. |  |  | 1a | 2-Gap-Build-Report | Gap | Build | Report | DESCOPED | Replaces Oracle FSG GA_TB_BRANCH_ACTUAL & GA_TB_BRANCH_STAT. Replaces REP | FSG | RTR | GL | 1900-01-07 |  |  |  | M |  |  | RTR | RTR-BI | NA | Deloitte
CSTONE-5554 |  | CSTONE-4407 | CSTONE-4677 | CSTONE-4677 | REP-FSG-RTR-GL-009 | BI-REP-FSG-RTR-GL-009A | Record to Report | Manage General Ledger Accounting | Maintain Chart of Accounts | AS an Accountant I want to be able to generate a Trial Balance by ODS (oper grp/dept/site) Trailing report with filters allowing to pull data YTD or PTD by actuals or stat accounts. |  |  | 1a | 2-Gap-Build-Report | Gap | Build | Report |  | Replaces Oracle FSG GA_TB_BRANCH_TRAILING_YTD_ACTUAL, GA_TB_BRANCH_TRAILING_PTD_ACTUAL & GA_TB_BRANCH_TRAILING_PTD_STAT. replaces REP | FSG | RTR | GL | 010 & REP | FSG | RTR | GL | M |  |  | RTR | RTR-BI | NA | Deloitte
CSTONE-5554 |  | CSTONE-4407 | CSTONE-4677 | CSTONE-4677 | REP-FSG-RTR-GL-009 | BI-REP-FSG-RTR-GL-009B | Record to Report | Manage General Ledger Accounting | Maintain Chart of Accounts | AS an Accountant I want to be able to generate a Trial Balance by ODS (oper grp/dept/site) Trailing report with filters allowing to pull data YTD or PTD by actuals or stat accounts. |  |  | 1a | 2-Gap-Build-Report | Gap | Build | Report |  | Replaces Oracle FSG GA_TB_BRANCH_TRAILING_YTD_ACTUAL, GA_TB_BRANCH_TRAILING_PTD_ACTUAL & GA_TB_BRANCH_TRAILING_PTD_STAT. replaces REP | FSG | RTR | GL | 010 & REP | FSG | RTR | GL | M |  |  | RTR | RTR-BI | NA | Deloitte
CSTONE-5554 |  | CSTONE-4407 | CSTONE-4677 | CSTONE-4677 | REP-FSG-RTR-GL-009 | BI-REP-FSG-RTR-GL-009C | Record to Report | Manage General Ledger Accounting | Maintain Chart of Accounts | AS an Accountant I want to be able to generate a Trial Balance by ODS (oper grp/dept/site) Trailing report with filters allowing to pull data YTD or PTD by actuals or stat accounts. |  |  | 1a | 2-Gap-Build-Report | Gap | Build | Report |  | Replaces Oracle FSG GA_TB_BRANCH_TRAILING_YTD_ACTUAL, GA_TB_BRANCH_TRAILING_PTD_ACTUAL & GA_TB_BRANCH_TRAILING_PTD_STAT. replaces REP | FSG | RTR | GL | 010 & REP | FSG | RTR | GL | M |  |  | RTR | RTR-BI | NA | Deloitte
CSTONE-5461 | CSTONE-552 |  |  | CSTONE-3229 | RTR-AHCS-028 | BI-RTR-AHCS-028 | Record to Report | Manage Subledger Accounting | Maintain Chart of Accounts | As a GL Accountant, I want a report to reconcile AHCS subldger and EBS AP so that I can perform period close reconciliations |  |  | 1a | 2-Gap-Build-Report | Gap | Build | Report |  | KDD6A requirements | Succesfully Validated | [6 empty] | M |  |  | RTR | RTR-BI | NA | Deloitte
CSTONE-5462 | CSTONE-6256 |  |  | CSTONE-3230 | RTR-AHCS-029 | BI-RTR-AHCS-029 | Record to Report | Manage Subledger Accounting | Maintain Chart of Accounts | As a GL Accountant, I want a report to reconcile AHCS subldger and EBS AR so that I can perform period close reconciliations |  |  | 1a | 2-Gap-Build-Report | Gap | Build | Report |  | KDD6A requirements | Succesfully Validated | [6 empty] | M |  |  | RTR | RTR-BI | NA | Deloitte
CSTONE-5463 | CSTONE-54 |  |  | CSTONE-3231 | RTR-AHCS-030 | BI-RTR-AHCS-030 | Record to Report | Manage Subledger Accounting | Maintain Chart of Accounts | As a GL Accountant, I want a report to reconcile AHCS subldger and EBS FA so that I can perform period close reconciliations |  |  | 1a | 2-Gap-Build-Report | Gap | Build | Report |  | KDD6A requirements | Succesfully Validated | [6 empty] | M |  |  | RTR | RTR-BI | NA | Deloitte
CSTONE-5529 | CSTONE-74 | CSTONE-123 | CSTONE-1096 | CSTONE-1096 | RTR-GL-137 | BI-RTR-GL-137A | Record to Report | Manage General Ledger Accounting | Maintain Chart of Accounts | As an accountant, I require the finance team secured Teradata/P3 database tables to be updated for the ability to query the IS and BS. |  |  | 1a | 2-Gap-Build-Report | Gap | Build | Report |  | Replacing current 15 IS/BS files with KDD8 Teradata file feeds 1 & 2 RICE IDs INT010 & INT011 (GL Data to TeraData for reporting - GL Balances & GL Data to TeraData for reporting - GL Journals) | Succesfully Validated | [6 empty] | M |  |  | RTR | RTR-BI | NA | Deloitte
CSTONE-5529 | CSTONE-74 | CSTONE-123 | CSTONE-1096 | CSTONE-1096 | RTR-GL-137 | BI-RTR-GL-137B | Record to Report | Manage General Ledger Accounting | Maintain Chart of Accounts | As an accountant, I require the finance team secured Teradata/P3 database tables to be updated for the ability to query the IS and BS. |  |  | 1a | 2-Gap-Build-Report | Gap | Build | Report |  | Replacing current 15 IS/BS files with KDD8 Teradata file feeds 1 & 2 RICE IDs INT010 & INT011 (GL Data to TeraData for reporting - GL Balances & GL Data to TeraData for reporting - GL Journals) | Succesfully Validated | [6 empty] | M |  |  | RTR | RTR-BI | NA | Deloitte
CSTONE-5531 | CSTONE-75 | CSTONE-124 | CSTONE-1097 | CSTONE-1097 | RTR-GL-139 | BI-RTR-GL-139A | Record to Report | Manage General Ledger Accounting | Maintain Chart of Accounts | As an accountant, I require the finance team unsecured Tereadata/P3 database tables to be updated for the ability to query the IS and BS. |  |  | 1a | 2-Gap-Build-Report | Gap | Build | Report |  | Replacing current 15 IS/BS files with KDD8 Teradata file feeds 1 & 2 RICE IDs INT010 & INT011 (GL Data to TeraData for reporting - GL Balances & GL Data to TeraData for reporting - GL Journals) | Succesfully Validated | [6 empty] | M |  |  | RTR | RTR-BI | NA | Deloitte
CSTONE-5531 | CSTONE-75 | CSTONE-124 | CSTONE-1097 | CSTONE-1097 | RTR-GL-139 | BI-RTR-GL-139B | Record to Report | Manage General Ledger Accounting | Maintain Chart of Accounts | As an accountant, I require the finance team unsecured Tereadata/P3 database tables to be updated for the ability to query the IS and BS. |  |  | 1a | 2-Gap-Build-Report | Gap | Build | Report |  | Replacing current 15 IS/BS files with KDD8 Teradata file feeds 1 & 2 RICE IDs INT010 & INT011 (GL Data to TeraData for reporting - GL Balances & GL Data to TeraData for reporting - GL Journals) | Succesfully Validated | [6 empty] | M |  |  | RTR | RTR-BI | NA | Deloitte
#N/A | CSTONE-2614 | CSTONE-2637 |  | CSTONE-4654 | RTR-GL-137E |  | Record to Report | Manage General Ledger Accounting | Maintain Chart of Accounts | As a member of the BI team maintaining Teradata table DSS_TABLES.ORACLE_EXPENSE_CURRENT_NEW for the Expense Exception Application, an update to the table with the file from INT011 is required. |  |  | 1a | 2-Gap-Build-Report | Gap | Build | Report |  | Dependency:INT011 | Succesfully Validated |  |  | 2021-08-08 | IN PROGRESS | Jeremy Hornbuckle | 2021-08-13 | M |  |  | RTR | RTR-BI | NA | Deloitte
#N/A |  |  |  | CSTONE-3232 | REP-RTR-AHCS-35 |  | Record to Report | Manage General Ledger Accounting | Maintain Chart of Accounts | As an accoutant, I require Legacy Report Name:Spending Per Employee Legacy Report Description:This report identifies all employee expenses processed for the month via the ERI (Concur) Interface BU becomes legal entity. |  |  | 1a | 2-Gap-Build-Report | Gap | Build | Report |  | Ad Hoc from FAH (covers WES user story RTR-AHCS-063) | Succesfully Validated | [6 empty] | M |  |  | RTR | RTR-BI | NA | Deloitte
#N/A |  |  |  |  | REP-FSG-RTR-GL-013 | BI-REP-FSG-RTR-GL-013A | Record to Report | Manage General Ledger Accounting | Maintain Chart of Accounts | As a BI developer, downstream Tables/views for operational reporting need to be updated. (No reports seemed to required right now but we will need to build these tables for GL reporting with the cloud data) |  |  | 1a | 2-Gap-Build-Report | Gap | Build | Report |  | User story requested by BI team | Succesfully Validated | [6 empty] | M |  |  | RTR | RTR-BI | NA | Deloitte
#N/A |  |  |  |  | REP-FSG-RTR-GL-013 | BI-REP-FSG-RTR-GL-013B | Record to Report | Manage General Ledger Accounting | Maintain Chart of Accounts | As a BI developer, downstream Tables/views for operational reporting need to be updated. (No reports seemed to required right now but we will need to build these tables for GL reporting with the cloud data) |  |  | 1a | 2-Gap-Build-Report | Gap | Build | Report |  | User story requested by BI team | Succesfully Validated | [6 empty] | M |  |  | RTR | RTR-BI | NA | Deloitte
#N/A |  |  |  |  | REP-FSG-RTR-GL-013 | BI-REP-FSG-RTR-GL-013C | Record to Report | Manage General Ledger Accounting | Maintain Chart of Accounts | As a BI developer, downstream Tables/views for operational reporting need to be updated. (No reports seemed to required right now but we will need to build these tables for GL reporting with the cloud data) |  |  | 1a | 2-Gap-Build-Report | Gap | Build | Report |  | User story requested by BI team | Succesfully Validated | [6 empty] | M |  |  | RTR | RTR-BI | NA | Deloitte
#N/A |  |  |  |  | REP-FSG-RTR-GL-013 | BI-REP-FSG-RTR-GL-013D | Record to Report | Manage General Ledger Accounting | Maintain Chart of Accounts | As a BI developer, downstream Tables/views for operational reporting need to be updated. (No reports seemed to required right now but we will need to build these tables for GL reporting with the cloud data) |  |  | 1a | 2-Gap-Build-Report | Gap | Build | Report |  | User story requested by BI team | Succesfully Validated | [6 empty] | M |  |  | RTR | RTR-BI | NA | Deloitte
#N/A |  |  |  |  | REP-FSG-RTR-GL-013 | BI-REP-FSG-RTR-GL-013E | Record to Report | Manage General Ledger Accounting | Maintain Chart of Accounts | As a BI developer, downstream Tables/views for operational reporting need to be updated. (No reports seemed to required right now but we will need to build these tables for GL reporting with the cloud data) |  |  | 1a | 2-Gap-Build-Report | Gap | Build | Report |  | User story requested by BI team | Succesfully Validated | [6 empty] | M |  |  | RTR | RTR-BI | NA | Deloitte
#N/A |  |  |  |  | REP-FSG-RTR-GL-013 | BI-REP-FSG-RTR-GL-013F | Record to Report | Manage General Ledger Accounting | Maintain Chart of Accounts | As a BI developer, downstream Tables/views for operational reporting need to be updated. (No reports seemed to required right now but we will need to build these tables for GL reporting with the cloud data) |  |  | 1a | 2-Gap-Build-Report | Gap | Build | Report |  | User story requested by BI team | Succesfully Validated | [6 empty] | M |  |  | RTR | RTR-BI | NA | Deloitte
#N/A |  |  |  | CSTONE-3233 | REP-FSG-RTR-GL-013 | BI-REP-FSG-RTR-GL-013G | Record to Report | Manage General Ledger Accounting | Maintain Chart of Accounts | As a BI developer, downstream Tables/views for operational reporting need to be updated. (No reports seemed to required right now but we will need to build these tables for GL reporting with the cloud data) |  |  | 1a | 2-Gap-Build-Report | Gap | Build | Report |  | User story requested by BI team | Succesfully Validated | [6 empty] | M |  |  | RTR | RTR-BI | NA | Deloitte
#N/A |  |  |  | CSTONE-3234 | REP-FSG-RTR-GL-013 | BI-REP-FSG-RTR-GL-013H | Record to Report | Manage General Ledger Accounting | Maintain Chart of Accounts | As a BI developer, downstream Tables/views for operational reporting need to be updated. (No reports seemed to required right now but we will need to build these tables for GL reporting with the cloud data) |  |  | 1a | 2-Gap-Build-Report | Gap | Build | Report |  | User story requested by BI team | Succesfully Validated | [6 empty] | M |  |  | RTR | RTR-BI | NA | Deloitte
#N/A |  |  |  | CSTONE-3235 | REP-FSG-RTR-GL-013 | BI-REP-FSG-RTR-GL-013I | Record to Report | Manage General Ledger Accounting | Maintain Chart of Accounts | As a BI developer, downstream Tables/views for operational reporting need to be updated. (No reports seemed to required right now but we will need to build these tables for GL reporting with the cloud data) |  |  | 1a | 2-Gap-Build-Report | Gap | Build | Report |  | User story requested by BI team | Succesfully Validated | [6 empty] | M |  |  | RTR | RTR-BI | NA | Deloitte
#N/A |  |  |  |  | REP-FSG-RTR-GL-013 | BI-REP-FSG-RTR-GL-013J | Record to Report | Manage General Ledger Accounting | Maintain Chart of Accounts | As a BI developer, downstream Tables/views for operational reporting need to be updated. (No reports seemed to required right now but we will need to build these tables for GL reporting with the cloud data) |  |  | 1a | 2-Gap-Build-Report | Gap | Build | Report |  | User story requested by BI team | Succesfully Validated | [6 empty] | M |  |  | RTR | RTR-BI | NA | Deloitte
#N/A |  |  |  |  | REP-FSG-RTR-GL-013 | BI-REP-FSG-RTR-GL-013K | Record to Report | Manage General Ledger Accounting | Maintain Chart of Accounts | As a BI developer, downstream Tables/views for operational reporting need to be updated. (No reports seemed to required right now but we will need to build these tables for GL reporting with the cloud data) |  |  | 1a | 2-Gap-Build-Report | Gap | Build | Report |  | User story requested by BI team | Succesfully Validated | [6 empty] | M |  |  | RTR | RTR-BI | NA | Deloitte
#N/A |  |  |  |  | REP-FSG-RTR-GL-013 | BI-REP-FSG-RTR-GL-013L | Record to Report | Manage General Ledger Accounting | Maintain Chart of Accounts | As a BI developer, downstream Tables/views for operational reporting need to be updated. (No reports seemed to required right now but we will need to build these tables for GL reporting with the cloud data) |  |  | 1a | 2-Gap-Build-Report | Gap | Build | Report |  | User story requested by BI team | Succesfully Validated | [6 empty] | M |  |  | RTR | RTR-BI | NA | Deloitte
#N/A |  |  |  |  | REP-FSG-RTR-GL-013 | BI-REP-FSG-RTR-GL-013M | Record to Report | Manage General Ledger Accounting | Maintain Chart of Accounts | As a BI developer, downstream Tables/views for operational reporting need to be updated. (No reports seemed to required right now but we will need to build these tables for GL reporting with the cloud data) |  |  | 1a | 2-Gap-Build-Report | Gap | Build | Report |  | User story requested by BI team | Succesfully Validated | [6 empty] | M |  |  | RTR | RTR-BI | NA | Deloitte
#N/A |  |  |  |  | REP-FSG-RTR-GL-013 | BI-REP-FSG-RTR-GL-013N | Record to Report | Manage General Ledger Accounting | Maintain Chart of Accounts | As a BI developer, downstream Tables/views for operational reporting need to be updated. (No reports seemed to required right now but we will need to build these tables for GL reporting with the cloud data) |  |  | 1a | 2-Gap-Build-Report | Gap | Build | Report |  | User story requested by BI team | Succesfully Validated | [6 empty] | M |  |  | RTR | RTR-BI | NA | Deloitte
#N/A | CSTONE-2846 | CSTONE-2866 |  | CSTONE-4656 | RTR-GL-137C |  | Record to Report | Manage General Ledger Accounting | Maintain Chart of Accounts | As a member of the BI team creating Oracle GL reporting, I will require Teradata table(s) containing the GL hierarchy feed from EDMCS |  |  | 1a | 2-Gap-Build-Report | Gap | Build | Report |  | Dependency:GL Hierarchy Feed from EDMCS | Succesfully Validated |  |  | 2021-08-08 | IN PROGRESS | Jeremy Hornbuckle | 2021-08-13 | M |  |  | RTR | RTR-BI | NA | Deloitte
#N/A | CSTONE-2847 | CSTONE-2867 |  | CSTONE-2867 | RTR-GL-137D |  | Record to Report | Manage General Ledger Accounting | Maintain Chart of Accounts | As a member of the BI team creating Oracle GL reporting, I will require a Teradata table containing the COA mapping file |  |  | 1a | 2-Gap-Build-Report | Gap | Build | Report |  | Dependency:COA mapping file | Succesfully Validated |  |  | 2021-08-08 | NOT STARTED | Jeremy Hornbuckle | 2021-08-13 | M |  |  | RTR | RTR-BI | NA | Deloitte
#N/A | CSTONE-2848 | CSTONE-2868 |  |  | REP-FSG-RTR-GL-013A |  | Record to Report | Manage General Ledger Accounting | Maintain Chart of Accounts | As the Accounting owner of the Teradata report Income Statement Detail (Legacy), I will need to review report results with the updated COA. |  |  | 1a | 2-Gap-Build-Report | Gap | Build | Report |  | Dependency:BI-RICE-20 | Succesfully Validated |  |  | 2021-08-08 | NOT STARTED | Jeremy Hornbuckle | 2021-08-13 | M |  |  | RTR | RTR-BI | NA | Deloitte
#N/A | CSTONE-2849 | CSTONE-2869 |  | CSTONE-4653 | REP-FSG-RTR-GL-013B |  | Record to Report | Manage General Ledger Accounting | Maintain Chart of Accounts | As the Accounting owner of the Teradata report Income Statement Summary (Legacy), I will need to review report results with the updated COA. |  |  | 1a | 2-Gap-Build-Report | Gap | Build | Report |  | Dependency:BI-RICE-20 | Succesfully Validated |  |  | 2021-08-08 | NOT STARTED | Jeremy Hornbuckle | 2021-08-13 | M |  |  | RTR | RTR-BI | NA | Deloitte
#N/A | CSTONE-2850 | CSTONE-2870 |  |  | REP-FSG-RTR-GL-013C |  | Record to Report | Manage General Ledger Accounting | Maintain Chart of Accounts | As the Accounting owner of the Teradata report Income Statement Drilldown 1 (Legacy), I will need to review report results with the updated COA. |  |  | 1a | 2-Gap-Build-Report | Gap | Build | Report |  | Dependency:BI-RICE-20 | Succesfully Validated |  |  | 2021-08-08 | NOT STARTED | Jeremy Hornbuckle | 2021-08-13 | M |  |  | RTR | RTR-BI | NA | Deloitte
#N/A | CSTONE-2851 | CSTONE-2871 |  |  | REP-FSG-RTR-GL-013D |  | Record to Report | Manage General Ledger Accounting | Maintain Chart of Accounts | As the Accounting owner of the Teradata report Income Statement Journal Drilldown (Legacy), I will need to review report results with the updated COA. |  |  | 1a | 2-Gap-Build-Report | Gap | Build | Report |  | Dependency:BI-RICE-20 | Succesfully Validated |  |  | 2021-08-08 | NOT STARTED | Jeremy Hornbuckle | 2021-08-13 | M |  |  | RTR | RTR-BI | NA | Deloitte
#N/A | CSTONE-3584 |  |  |  | REP-FSG-RTR-GL-013E |  | Record to Report | Manage General Ledger Accounting | Maintain Chart of Accounts | As the Accounting owner of the Teradata report Billing Margin % by Shipment Type, I will need to review report results with the updated COA. |  |  | 1a | 2-Gap-Build-Report | Gap | Build | Report |  | Dependency:BI-RICE-20 | Succesfully Validated |  |  | 2021-08-08 | NOT STARTED | Jeremy Hornbuckle | 2021-08-13 | M |  |  | RTR | RTR-BI | NA | Deloitte
#N/A | CSTONE-3583 |  |  |  | REP-FSG-RTR-GL-013F |  | Record to Report | Manage General Ledger Accounting | Maintain Chart of Accounts | As the Accounting owner of the Teradata report Billing Margin Analysis by Month, I will need to review report results with the updated COA. |  |  | 1a | 2-Gap-Build-Report | Gap | Build | Report |  | Dependency:BI-RICE-20 | Succesfully Validated |  |  | 2021-08-08 | NOT STARTED | Jeremy Hornbuckle | 2021-08-13 | M |  |  | RTR | RTR-BI | NA | Deloitte
#N/A | CSTONE-3582 |  |  |  | REP-FSG-RTR-GL-013G |  | Record to Report | Manage General Ledger Accounting | Maintain Chart of Accounts | As the Accounting owner of the Teradata report Daily Sales by Current Workday, I will need to review report results with the updated COA. |  |  | 1a | 2-Gap-Build-Report | Gap | Build | Report |  | Dependency:BI-RICE-20 | Succesfully Validated |  |  | 2021-08-08 | NOT STARTED | Jeremy Hornbuckle | 2021-08-13 | M |  |  | RTR | RTR-BI | NA | Deloitte
#N/A | CSTONE-3581 |  |  |  | REP-FSG-RTR-GL-013H |  | Record to Report | Manage General Ledger Accounting | Maintain Chart of Accounts | As the Accounting owner of the Teradata report MTD vs Last Year, I will need to review report results with the updated COA. |  |  | 1a | 2-Gap-Build-Report | Gap | Build | Report |  | Dependency:BI-RICE-20 | Succesfully Validated |  |  | 2021-08-08 | NOT STARTED | Jeremy Hornbuckle | 2021-08-13 | M |  |  | RTR | RTR-BI | NA | Deloitte
#N/A | CSTONE-3580 |  |  |  | REP-FSG-RTR-GL-013I |  | Record to Report | Manage General Ledger Accounting | Maintain Chart of Accounts | As the Accounting owner of the Teradata report Sales $ by Shipment Type, I will need to review report results with the updated COA. |  |  | 1a | 2-Gap-Build-Report | Gap | Build | Report |  | Dependency:BI-RICE-20 | Succesfully Validated |  |  | 2021-08-08 | NOT STARTED | Jeremy Hornbuckle | 2021-08-13 | M |  |  | RTR | RTR-BI | NA | Deloitte
#N/A | CSTONE-3579 |  |  |  | REP-FSG-RTR-GL-013J |  | Record to Report | Manage General Ledger Accounting | Maintain Chart of Accounts | As the Accounting owner of the Teradata report YTD vs Last Year, I will need to review report results with the updated COA. |  |  | 1a | 2-Gap-Build-Report | Gap | Build | Report |  | Dependency:BI-RICE-20 | Succesfully Validated |  |  | 2021-08-08 | NOT STARTED | Jeremy Hornbuckle | 2021-08-13 | M |  |  | RTR | RTR-BI | NA | Deloitte
#N/A |  |  |  | CSTONE-3236 | RTR-AHCS-028A |  | Record to Report | Manage Subledger Accounting | Maintain Chart of Accounts | As the Accounting owner of the Teradata report EBS AP to AHCS Recon Report - Balances, I will need to review the report reconcilation results. |  |  | 1a | 2-Gap-Build-Report | Gap | Build | Report |  | Dependency: INT041 & Subledger feeds from EBS | Succesfully Validated |  |  | 2021-08-17 | NOT STARTED | Jeremy Hornbuckle | 2021-08-20 | M |  |  | EPM | EPM-BI | NA | Deloitte
#N/A |  |  |  | CSTONE-3237 | RTR-AHCS-029A |  | Record to Report | Manage Subledger Accounting | Maintain Chart of Accounts | As the Accounting owner of the Teradata report EBS AR to AHCS Recon Report - Balances, I will need to review the report reconcilation results. |  |  | 1a | 2-Gap-Build-Report | Gap | Build | Report |  | Dependency: INT041 & Subledger feeds from EBS | Succesfully Validated |  |  | 2021-08-17 | NOT STARTED | Jeremy Hornbuckle | 2021-08-20 | M |  |  | EPM | EPM-BI | NA | Deloitte
#N/A |  |  |  | CSTONE-3238 | RTR-AHCS-030A |  | Record to Report | Manage Subledger Accounting | Maintain Chart of Accounts | As the Accounting owner of the Teradata report EBS FA to AHCS Recon Report - Balances, I will need to review the report reconcilation results. |  |  | 1a | 2-Gap-Build-Report | Gap | Build | Report |  | Dependency: INT041 & Subledger feeds from EBS | Succesfully Validated |  |  | 2021-08-17 | NOT STARTED | Jeremy Hornbuckle | 2021-08-20 | M |  |  | EPM | EPM-BI | NA | Deloitte
#N/A |  |  |  | CSTONE-3239 | RTR-AHCS-030B |  | Record to Report | Manage Subledger Accounting | Maintain Chart of Accounts | As the Accounting owner of the Teradata report ERP POC to AHCS Recon Report - Detail, I will need to review the report reconcilation results. |  |  | 1a | 2-Gap-Build-Report | Gap | Build | Report |  | Dependency: INT041 & Subledger feeds from EBS | Succesfully Validated |  |  | 2021-08-17 | NOT STARTED | Jeremy Hornbuckle | 2021-08-20 | M |  |  | EPM | EPM-BI | NA | Deloitte
#N/A |  |  |  | CSTONE-3240 | RTR-AHCS-030C |  | Record to Report | Manage Subledger Accounting | Maintain Chart of Accounts | As the Accounting owner of the Teradata report ERP POC to AHCS Recon Report - Balances, I will need to review the report reconcilation results. |  |  | 1a | 2-Gap-Build-Report | Gap | Build | Report |  | Dependency: INT041 & Subledger feeds from EBS | Succesfully Validated |  |  | 2021-08-17 | NOT STARTED | Jeremy Hornbuckle | 2021-08-20 | M |  |  | EPM | EPM-BI | NA | Deloitte
#N/A | CSTONE-3572 |  |  |  | REP-FSG-RTR-GL-013K |  | Record to Report | Manage General Ledger Accounting | Maintain Chart of Accounts | As the Accounting owner of the Teradata report Accounts by Month - Actual, I will need to review report results with the updated COA. |  |  | 1a | 2-Gap-Build-Report | Gap | Build | Report |  | Dependency:BI-RICE-20 | Succesfully Validated |  |  | 2021-08-08 | NOT STARTED | Jeremy Hornbuckle | 2021-08-13 | M |  |  | RTR | RTR-BI | NA | Deloitte
#N/A | CSTONE-3571 |  |  |  | REP-FSG-RTR-GL-013L |  | Record to Report | Manage General Ledger Accounting | Maintain Chart of Accounts | As the Accounting owner of the Teradata report Accounts by Quarter - Actual, I will need to review report results with the updated COA. |  |  | 1a | 2-Gap-Build-Report | Gap | Build | Report |  | Dependency:BI-RICE-20 | Succesfully Validated |  |  | 2021-08-08 | NOT STARTED |  | 2021-08-13 | M |  |  | RTR | RTR-BI | NA | Deloitte
#N/A |  |  |  | RTR-AHCS-236 | RTR-AHCS-251 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to Import Late Fee,AR Cash Clearing & Other Cash Clearing Opening Balances into AHCS MF AR Subledger and mechanism to differentiate opening balances from daily transactions | Must Have |  | Phase 1B only | 10-Not Required-Not Required-Not Required | Not Required | Not Required | Not Required |  | Beginning Balances will be brought to AHCS through a different AR Beg Bal Event Type Applicable for Applicable for Late Fee,AR Cash Clearing & Other Cash Clearing Accounts. These users stories are marked as 'Not required' and 'Approved' under Subtype and added new User stories from RTR-AHCS-344 to 469 and added as "Initial Fit/Gap Complete" , Kindly review and have Acceptance Criteria Documented for these. | User should be able to Conversion of initial balances using event type for MF AR Subledger |  |  |  | Approved | ian | 2022-01-21 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  | Are these being generalized or are we listing out all beg loads? Ip 1-13 | [8 empty] | Approved on Wed 2/2/2022 4:45 AM
#N/A |  |  |  |  | RTR-AHCS-252 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to Import Inventory Opening Balances into AHCS MF Inventory Subledger and mechanism to differentaite opening balances from daily transactions | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV043 | Beginning Balances will be brought to AHCS through a different MF INV Beg Bal Event Type Applicable for Freight Accrual,WIP(WO) & Kava. | Opening balances are posted in AHCS MF Inventory Subledger and Inv Beg Bal event type, AHCS Opening balance should match Legacy systems ending balance |  |  |  | Approved | ian | 2022-01-21 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  | Are these being generalized or are we listing out all beg loads? Ip 1-13 | [8 empty] | Approved on Wed 2/2/2022 4:45 AM
#N/A |  |  |  |  | RTR-GL-154 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate an intercompany cross table report looking specifically for reconciling differences for certain new COA segment combination in French Language | Must Have |  | Not Required | 10-Not Required-Not Required-Not Required | Gap | Build | Report |  | 12/23 NG: Removed as per latest report rationalization master document Current Report Name in Legacy FAH- 'Intercompany Matching'. Used for comparing intercompany cross table report looking specifically for reconciling differences per BU-Affiliate combination in French Language | User should be able to generate an intercompany cross table report looking specifically for reconciling differences for certain new COA segment combination in French Language |  |  |  | Approved | [5 empty] | RTR | RTR-AHCS | AHCS
#N/A |  |  |  |  | RTR-AHCS-253 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report for viewing Purchases during the Year in Trade Nature in English (US) Language | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT181 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' 02/04 - Based on accounting hub data only. Current Report Name in Legacy FAH- 'Intercompany AP Invoice Statement Summary (Trade) For the Year Only'. This is in English (US) Language | User should be able to generate a report for viewing Purchases during the Year in Trade Nature in English (US) Language. I/C purchases detailed at invoice level YTD report | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs in English language. |  |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte | [11 empty] | Approved on Tue 2/1/2022 10:02 AM
#N/A |  |  |  |  | RTR-GL-155 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate an intercompany cross table report looking specifically for reconciling differences for certain new COA segment combination in Spanish Language | Must Have |  | Not Required | 10-Not Required-Not Required-Not Required | Gap | Build | Report |  | 12/23 NG: Removed as per latest report rationalization master document Current Report Name in Legacy FAH- 'Intercompany Matching'. Used for comparing intercompany cross table report looking specifically for reconciling differences per BU-Affiliate combination in Spanish Language | User should be able to generate an intercompany cross table report looking specifically for reconciling differences for certain new COA segment combination in Spanish Language |  |  |  | Approved | [5 empty] | RTR | RTR-AHCS | AHCS
#N/A |  |  |  |  | RTR-GL-156 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate an intercompany cross table report looking specifically for reconciling differences for certain new COA segment combination in German Language | Must Have |  | Not Required | 10-Not Required-Not Required-Not Required | Gap | Build | Report |  | 12/23 NG: Removed as per latest report rationalization master document Current Report Name in Legacy FAH- 'Intercompany Matching'. Used for comparing intercompany cross table report looking specifically for reconciling differences per BU-Affiliate combination in German Language | User should be able to generate an intercompany cross table report looking specifically for reconciling differences for certain new COA segment combination in German Language |  |  |  | Approved | [5 empty] | RTR | RTR-AHCS | AHCS
#N/A |  |  |  |  | RTR-GL-157 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate an intercompany cross table report looking specifically for reconciling differences for certain new COA segment combination in Polish Language | Must Have |  | Not Required | 2-Gap-Build-Report | Gap | Build | Report |  | Current Report Name in Legacy FAH- 'Intercompany Matching'. Used for comparing intercompany cross table report looking specifically for reconciling differences per BU-Affiliate combination in Polish Language | User should be able to generate an intercompany cross table report looking specifically for reconciling differences for certain new COA segment combination in Polish Language |  |  |  | Approved | [5 empty] | RTR | RTR-AHCS | AHCS
#N/A |  |  |  |  | RTR-GL-158 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate an intercompany cross table report looking specifically for reconciling differences for certain new COA segment combination in Arabic Language | Must Have |  | Not Required | 10-Not Required-Not Required-Not Required | Not Required | Not Required | Not Required |  | 12/23 NG: Removed as per latest report rationalization master document Current Report Name in Legacy FAH- 'Intercompany Matching'. Used for comparing intercompany cross table report looking specifically for reconciling differences per BU-Affiliate combination in Arabic Language | User should be able to generate an intercompany cross table report looking specifically for reconciling differences for certain new COA segment combination in Arabic Language |  |  |  | Approved | [5 empty] | RTR | RTR-AHCS | AHCS
#N/A |  |  |  |  | RTR-GL-159 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report for viewing the Opening Balance (in debit & Credit Format), Credit , Debit, Closing Balance (in debit & Credit Format) in French Language | Must Have |  | Not Required | 10-Not Required-Not Required-Not Required | Not Required | Not Required | Not Required |  | 12/23 NG: Removed as per latest report rationalization master document Current Report Name in Legacy FAH- 'Trial balance in a true debit and credit format'. This report is in in French Language | User should be able to generate a report or viewing the Opening Balance (in debit & Credit Format), Credit , Debit, Closing Balance (in debit & Credit Format) in French Language |  |  |  | Approved | [5 empty] | RTR | RTR-AHCS | AHCS
#N/A |  |  |  |  | RTR-GL-160 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report for viewing the Opening Balance (in debit & Credit Format), Credit , Debit, Closing Balance (in debit & Credit Format) in Spanish Language | Must Have |  | Not Required | 10-Not Required-Not Required-Not Required | Not Required | Not Required | Not Required |  | 12/23 NG: Removed as per latest report rationalization master document Current Report Name in Legacy FAH- 'Trial balance in a true debit and credit format'. This report is in Spanish Language | User should be able to generate a report or viewing the Opening Balance (in debit & Credit Format), Credit , Debit, Closing Balance (in debit & Credit Format) in Spanish Language |  |  |  | Approved | [5 empty] | RTR | RTR-AHCS | AHCS
#N/A |  |  |  |  | RTR-GL-161 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report for viewing the Opening Balance (in debit & Credit Format), Credit , Debit, Closing Balance (in debit & Credit Format) in German Language | Must Have |  | Not Required | 10-Not Required-Not Required-Not Required | Not Required | Not Required | Not Required |  | 12/23 NG: Removed as per latest report rationalization master document Current Report Name in Legacy FAH- 'Trial balance in a true debit and credit format'. This report is in German Language | User should be able to generate a report or viewing the Opening Balance (in debit & Credit Format), Credit , Debit, Closing Balance (in debit & Credit Format) in German Language |  |  |  | Approved | [5 empty] | RTR | RTR-AHCS | AHCS
#N/A |  |  |  |  | RTR-GL-162 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report for viewing the Opening Balance (in debit & Credit Format), Credit , Debit, Closing Balance (in debit & Credit Format) in Polish Language | Must Have |  | Not Required | 10-Not Required-Not Required-Not Required | Not Required | Not Required | Not Required |  | 12/23 NG: Removed as per latest report rationalization master document Current Report Name in Legacy FAH- 'Trial balance in a true debit and credit format'. This report is in Polish Language | User should be able to generate a report or viewing the Opening Balance (in debit & Credit Format), Credit , Debit, Closing Balance (in debit & Credit Format) in Polish Language |  |  |  | Approved | [5 empty] | RTR | RTR-AHCS | AHCS
#N/A |  |  |  |  | RTR-GL-163 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report for viewing the Opening Balance (in debit & Credit Format), Credit , Debit, Closing Balance (in debit & Credit Format) in Arabic Language | Must Have |  | Not Required | 10-Not Required-Not Required-Not Required | Not Required | Not Required | Not Required |  | 12/23 NG: Removed as per latest report rationalization master document Current Report Name in Legacy FAH- 'Trial balance in a true debit and credit format'. This report is in Arabic Language | User should be able to generate a report or viewing the Opening Balance (in debit & Credit Format), Credit , Debit, Closing Balance (in debit & Credit Format) in Arabic Language |  |  |  | Approved | [5 empty] | RTR | RTR-AHCS | AHCS
#N/A |  |  |  |  | RTR-AHCS-254 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report for viewing Purchases during the Year in Trade Material Nature in French Language | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT185 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' 02/04 - Based on accounting hub data only. Current Report Name in Legacy FAH- 'Intercompany AP Invoice Statement Summary (Trade) For the Year Only'. This is in French Language | User should be able to generate a report for viewing Purchases during the Year in Trade Nature in French Language. I/C purchases detailed at invoice level YTD report | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs in French language. |  |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte | [11 empty] | Approved on Tuesday, January 18, 2022 7:15 PM
#N/A |  |  |  |  | RTR-AHCS-255 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report for viewing Purchases during the Year in Trade Material Nature in German Language | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT185 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' 02/04 - Based on accounting hub data only. Current Report Name in Legacy FAH- 'Intercompany AP Invoice Statement Summary (Trade) For the Year Only'. This is in German Language | User should be able to generate a report for viewing Purchases during the Year in Trade Nature in German Language. I/C purchases detailed at invoice level YTD report | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs in German language. |  |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte | [11 empty] | Approved on Tuesday, January 18, 2022 7:15 PM
#N/A |  |  |  |  | RTR-AHCS-256 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report for viewing Purchases during the Year in Trade Material Nature in Polish Language | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT185 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' 02/04 - Based on accounting hub data only. Current Report Name in Legacy FAH- 'Intercompany AP Invoice Statement Summary (Trade) For the Year Only'. This is in Polish Language | User should be able to generate a report for viewing Purchases during the Year in Trade Nature in Polish Language. I/C purchases detailed at invoice level YTD report | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs in Polish language. |  |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte | [11 empty] | Approved on Tuesday, January 18, 2022 7:15 PM
#N/A |  |  |  |  | RTR-AHCS-257 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report for viewing Purchases during the Year in Trade Material Nature in Spanish Language | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT185 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' 02/04 - Based on accounting hub data only. Current Report Name in Legacy FAH- 'Intercompany AP Invoice Statement Summary (Trade) For the Year Only'. This is in Spanish Language | User should be able to generate a report for viewing Purchases during the Year in Trade Nature in Spanish Language. I/C purchases detailed at invoice level YTD report | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs in Spanish language. |  |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte | [11 empty] | Approved on Tuesday, January 18, 2022 7:15 PM
#N/A |  |  |  |  | RTR-AHCS-258 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report for viewing Purchases during the Year in Trade Material Nature in Arabic Language | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT185 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' 02/04 - Based on accounting hub data only. Current Report Name in Legacy FAH- 'Intercompany AP Invoice Statement Summary (Trade) For the Year Only'. This is in Arabic Language | User should be able to generate a report for viewing Purchases during the Year in Trade Nature in Arabic Language. I/C purchases detailed at invoice level YTD report | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs in Arabic language. |  |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte | [11 empty] | Approved on Tuesday, January 18, 2022 7:15 PM
#N/A |  |  |  |  | RTR-AHCS-259 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report that displays month ending balances by BU, Loc and Item# for transactions impacting Inventory Accounts in French Language | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT159 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' Current Report Name in Legacy FAH- 'Inventory Detailed Trial Balance'. PS Journals hitting Material Inventory or Direct Shipment accounts are not considered for this report. To include item quantity, unit cost, item description, product class, UOM, UOM Conversion.-APAC req in French Language | User should be able to generate a report which has the ability to generate a report that displays month ending balances by BU, Loc and Item# for transactions impacting Inventory Accounts in French Language | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs in French language. |  |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte | [11 empty] | Approved on Tuesday, January 18, 2022 7:15 PM
#N/A |  |  |  |  | RTR-AHCS-260 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report that displays month ending balances by BU, Loc and Item# for transactions impacting Inventory Accounts in German Language | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT159 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' Current Report Name in Legacy FAH- 'Inventory Detailed Trial Balance'. PS Journals hitting Material Inventory or Direct Shipment accounts are not considered for this report. To include item quantity, unit cost, item description, product class, UOM, UOM Conversion.-APAC req in German Language | User should be able to generate a report which has the ability to generate a report that displays month ending balances by BU, Loc and Item# for transactions impacting Inventory Accounts in German Language | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs in German language. |  |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte | [11 empty] | Approved on Tuesday, January 18, 2022 7:15 PM
#N/A |  |  |  |  | RTR-AHCS-261 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report that displays month ending balances by BU, Loc and Item# for transactions impacting Inventory Accounts in Spanish Language | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT159 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' Current Report Name in Legacy FAH- 'Inventory Detailed Trial Balance'. PS Journals hitting Material Inventory or Direct Shipment accounts are not considered for this report. To include item quantity, unit cost, item description, product class, UOM, UOM Conversion.-APAC req in Spanish Language | User should be able to generate a report which has the ability to generate a report that displays month ending balances by BU, Loc and Item# for transactions impacting Inventory Accounts in Spanish Language | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs in Spanish language. |  |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte | [11 empty] | Approved on Tuesday, January 18, 2022 7:15 PM
#N/A |  |  |  |  | RTR-AHCS-262 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report that displays month ending balances by BU, Loc and Item# for transactions impacting Inventory Accounts in Polish Language | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT159 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' Current Report Name in Legacy FAH- 'Inventory Detailed Trial Balance'. PS Journals hitting Material Inventory or Direct Shipment accounts are not considered for this report. To include item quantity, unit cost, item description, product class, UOM, UOM Conversion.-APAC req in Polish Language | User should be able to generate a report which has the ability to generate a report that displays month ending balances by BU, Loc and Item# for transactions impacting Inventory Accounts in Polish Language | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs in Polish language. |  |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte | [11 empty] | Approved on Tuesday, January 18, 2022 7:15 PM
#N/A |  |  |  |  | RTR-AHCS-263 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report that displays month ending balances by BU, Loc and Item# for transactions impacting Inventory Accounts in Arabic Language | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT159 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' Current Report Name in Legacy FAH- 'Inventory Detailed Trial Balance'. PS Journals hitting Material Inventory or Direct Shipment accounts are not considered for this report. To include item quantity, unit cost, item description, product class, UOM, UOM Conversion.-APAC req in Arabic Language | User should be able to generate a report which has the ability to generate a report that displays month ending balances by BU, Loc and Item# for transactions impacting Inventory Accounts in Arabic Language | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs in Arabic language. |  |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte | [11 empty] | Approved on Tuesday, January 18, 2022 7:15 PM
#N/A |  |  |  |  | RTR-AHCS-264 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report showing the open AP items by their aging buckets with invoice details as well in French Language | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT164 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' Current Report Name in Legacy FAH- 'AP Aging With Invoices' - Report to show the open AP items by their aging buckets with invoice details as well (INV_I & INV_D & INV_DUE_D) in French Language It should be able to run by the selected month.-APAC | User should be able to generate a report showing the open AP items by their aging buckets with invoice details in French Language | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs in French language. |  |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte | [11 empty] | Approved on Tuesday, January 18, 2022 7:15 PM
#N/A |  |  |  |  | RTR-AHCS-265 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report showing the open AP items by their aging buckets with invoice details as well in German Language | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT164 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' Current Report Name in Legacy FAH- 'AP Aging With Invoices' - Report to show the open AP items by their aging buckets with invoice details as well (INV_I & INV_D & INV_DUE_D) in German Language It should be able to run by the selected month.-APAC | User should be able to generate a report showing the open AP items by their aging buckets with invoice details in German Language | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs in German language. |  |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte | [11 empty] | Approved on Tuesday, January 18, 2022 7:15 PM
#N/A |  |  |  |  | RTR-AHCS-266 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report showing the open AP items by their aging buckets with invoice details as well in Spanish Language | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT164 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' Current Report Name in Legacy FAH- 'AP Aging With Invoices' - Report to show the open AP items by their aging buckets with invoice details as well (INV_I & INV_D & INV_DUE_D) in Spanish Language It should be able to run by the selected month.-APAC | User should be able to generate a report showing the open AP items by their aging buckets with invoice details in Spanish Language | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs in Spanish language. |  |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte | [11 empty] | Approved on Tuesday, January 18, 2022 7:15 PM
#N/A |  |  |  |  | RTR-AHCS-267 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report showing the open AP items by their aging buckets with invoice details as well in Polish Language | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT164 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' Current Report Name in Legacy FAH- 'AP Aging With Invoices' - Report to show the open AP items by their aging buckets with invoice details as well (INV_I & INV_D & INV_DUE_D) in Polish Language It should be able to run by the selected month.-APAC | User should be able to generate a report showing the open AP items by their aging buckets with invoice details in Polish Language | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs in Polish language. |  |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte | [11 empty] | Approved on Tuesday, January 18, 2022 7:15 PM
#N/A |  |  |  |  | RTR-AHCS-268 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report showing the open AP items by their aging buckets with invoice details as well in Arabic Language | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT164 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' Current Report Name in Legacy FAH- 'AP Aging With Invoices' - Report to show the open AP items by their aging buckets with invoice details as well (INV_I & INV_D & INV_DUE_D) in Arabic Language It should be able to run by the selected month.-APAC | User should be able to generate a report showing the open AP items by their aging buckets with invoice details in Arabic Language | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs in Arabic language. |  |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte | [11 empty] | Approved on Tuesday, January 18, 2022 7:15 PM
#N/A |  |  |  |  | RTR-AHCS-269 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report which shows a detailed report break down the of open transactions in account 310010009 in French Language | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT165 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' Current Report Name in Legacy FAH- 'AP Cash Clearing Aging Details' - report breaksdown the open transactions in account 310010009 by BU, Loc, Vendor, Source code type, Statement ID and aging amongst others in French Language | User should be able to generate a report which shows detailed report break down the open transactions in account 310010009 in French Language | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs in French language. |  |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte | [11 empty] | Approved on Tuesday, January 18, 2022 7:15 PM
#N/A |  |  |  |  | RTR-AHCS-270 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report which shows a detailed report break down the of open transactions in account 310010009 in Spanish Language | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT165 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' Current Report Name in Legacy FAH- 'AP Cash Clearing Aging Details' - report breaksdown the open transactions in account 310010009 by BU, Loc, Vendor, Source code type, Statement ID and aging amongst others in Spanish Language | User should be able to generate a report which shows detailed report break down the open transactions in account 310010009 in Spanish Language | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs in Spanish language. |  |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte | [11 empty] | Approved on Tuesday, January 18, 2022 7:15 PM
#N/A |  |  |  |  | RTR-AHCS-271 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report which shows a detailed report break down the of open transactions in account 310010009 in German Language | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT165 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' Current Report Name in Legacy FAH- 'AP Cash Clearing Aging Details' - report breaksdown the open transactions in account 310010009 by BU, Loc, Vendor, Source code type, Statement ID and aging amongst others in German Language | User should be able to generate a report which shows detailed report break down the open transactions in account 310010009 in German Language | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs in German language. |  |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte | [11 empty] | Approved on Tuesday, January 18, 2022 7:15 PM
#N/A |  |  |  |  | RTR-AHCS-272 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report which shows a detailed report break down the of open transactions in account 310010009 in Polish Language | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT165 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' Current Report Name in Legacy FAH- 'AP Cash Clearing Aging Details' - report breaksdown the open transactions in account 310010009 by BU, Loc, Vendor, Source code type, Statement ID and aging amongst others in Polish Language | User should be able to generate a report which shows detailed report break down the open transactions in account 310010009 in Polish Language | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs in Polish language. |  |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte | [11 empty] | Approved on Tuesday, January 18, 2022 7:15 PM
#N/A |  |  |  |  | RTR-AHCS-273 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report which shows a detailed report break down the of open transactions in account 310010009 in Arabic Language | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT165 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' Current Report Name in Legacy FAH- 'AP Cash Clearing Aging Details' - report breaksdown the open transactions in account 310010009 by BU, Loc, Vendor, Source code type, Statement ID and aging amongst others in Arabic Language | User should be able to generate a report which shows detailed report break down the open transactions in account 310010009 in Arabic Language | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs in Arabic language. |  |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte | [11 empty] | Approved on Tuesday, January 18, 2022 7:15 PM
#N/A |  |  |  |  | RTR-AHCS-274 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report which shows the movement by AP Intercompany invoices details within said month in French Language | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT166 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' 02/04 - Based on accounting hub data only. Current Report Name in Legacy FAH- 'AP Detailed Intercompany Trial Balance' - Detailed report that shows the movement by invoice details (INV_I, INV_D, JRNL_I, PAY_TERM, FRT_BILL_I) within said month in French Language | User should be able to generate a report which shows the movement by AP Intercompany invoice details within said month in French Language | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs in French language. |  |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte | [11 empty] | Approved on Tuesday, January 18, 2022 7:15 PM
#N/A |  |  |  |  | RTR-AHCS-275 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report which shows the movement by AP Intercompany invoices details within said month in Spanish Language | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT166 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' 02/04 - Based on accounting hub data only. Current Report Name in Legacy FAH- 'AP Detailed Intercompany Trial Balance' - Detailed report that shows the movement by invoice details (INV_I, INV_D, JRNL_I, PAY_TERM, FRT_BILL_I) within said month in Spanish Language | User should be able to generate a report which shows the movement by AP Intercompany invoice details within said month in Spanish Language | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs in Spanish language. |  |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte | [11 empty] | Approved on Tuesday, January 18, 2022 7:15 PM
#N/A |  |  |  |  | RTR-AHCS-276 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report which shows the movement by AP Intercompany invoices details within said month in German Language | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT166 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' 02/04 - Based on accounting hub data only. Current Report Name in Legacy FAH- 'AP Detailed Intercompany Trial Balance' - Detailed report that shows the movement by invoice details (INV_I, INV_D, JRNL_I, PAY_TERM, FRT_BILL_I) within said month in German Language | User should be able to generate a report which shows the movement by AP Intercompany invoice details within said month in German Language | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs in German language. |  |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte | [11 empty] | Approved on Tuesday, January 18, 2022 7:15 PM
#N/A |  |  |  |  | RTR-AHCS-277 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report which shows the movement by AP Intercompany invoices details within said month in Polish Language | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT166 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' 02/04 - Based on accounting hub data only. Current Report Name in Legacy FAH- 'AP Detailed Intercompany Trial Balance' - Detailed report that shows the movement by invoice details (INV_I, INV_D, JRNL_I, PAY_TERM, FRT_BILL_I) within said month in Polish Language | User should be able to generate a report which shows the movement by AP Intercompany invoice details within said month in Polish Language | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs in Polish language. |  |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte | [11 empty] | Approved on Tuesday, January 18, 2022 7:15 PM
#N/A |  |  |  |  | RTR-AHCS-278 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report which shows the movement by AP Intercompany invoices details within said month in Arabic Language | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT166 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' 02/04 - Based on accounting hub data only. Current Report Name in Legacy FAH- 'AP Detailed Intercompany Trial Balance' - Detailed report that shows the movement by invoice details (INV_I, INV_D, JRNL_I, PAY_TERM, FRT_BILL_I) within said month in Arabic Language | User should be able to generate a report which shows the movement by AP Intercompany invoice details within said month in Arabic Language | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs in Arabic language. |  |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte | [11 empty] | Approved on Tuesday, January 18, 2022 7:15 PM
#N/A |  |  |  |  | RTR-AHCS-279 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report which shows the movement by AP invoice details within said month in French Language | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT167 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' Current Report Name in Legacy FAH- 'AP Detailed Trial Balance' - Detailed report that shows the movement by invoice details (INV_I & INV_D & INV_DUE_D) within said month. It should be able to run by the selected month. Information such as vendor name, vendor invoice, invoice amounts, etc will be required | User should be able to generate a report which shows the movement by AP invoice details within said month in French Language | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs in French language. |  |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte | [11 empty] | Approved on Tuesday, January 18, 2022 7:15 PM
#N/A |  |  |  |  | RTR-AHCS-280 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report which shows the movement by AP invoice details within said month in Spanish Language | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT167 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' Current Report Name in Legacy FAH- 'AP Detailed Trial Balance' - Detailed report that shows the movement by invoice details (INV_I & INV_D & INV_DUE_D) within said month. It should be able to run by the selected month. Information such as vendor name, vendor invoice, invoice amounts, etc will be required in Spanish Language. | User should be able to generate a report which shows the movement by AP invoice details within said month in Spanish Language | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs in Spanish language. |  |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte | [11 empty] | Approved on Tuesday, January 18, 2022 7:15 PM
#N/A |  |  |  |  | RTR-AHCS-281 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report which shows the movement by AP invoice details within said month in German Language | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT167 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' Current Report Name in Legacy FAH- 'AP Detailed Trial Balance' - Detailed report that shows the movement by invoice details (INV_I & INV_D & INV_DUE_D) within said month. It should be able to run by the selected month. Information such as vendor name, vendor invoice, invoice amounts, etc will be required in German Language. | User should be able to generate a report which shows the movement by AP invoice details within said month in German Language | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs in German language. |  |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte | [11 empty] | Approved on Tuesday, January 18, 2022 7:15 PM
#N/A |  |  |  |  | RTR-AHCS-282 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report which shows the movement by AP invoice details within said month in Polish Language | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT167 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' Current Report Name in Legacy FAH- 'AP Detailed Trial Balance' - Detailed report that shows the movement by invoice details (INV_I & INV_D & INV_DUE_D) within said month. It should be able to run by the selected month. Information such as vendor name, vendor invoice, invoice amounts, etc will be required in Polish Language. | User should be able to generate a report which shows the movement by AP invoice details within said month in Polish Language | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs in Polish language. |  |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte | [11 empty] | Approved on Tuesday, January 18, 2022 7:15 PM
#N/A |  |  |  |  | RTR-AHCS-283 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report which shows the movement by AP invoice details within said month in Arabic Language | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT167 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' Current Report Name in Legacy FAH- 'AP Detailed Trial Balance' - Detailed report that shows the movement by invoice details (INV_I & INV_D & INV_DUE_D) within said month. It should be able to run by the selected month. Information such as vendor name, vendor invoice, invoice amounts, etc will be required in Arabic Language. | User should be able to generate a report which shows the movement by AP invoice details within said month in Arabic Language | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs in Arabic language. |  |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte | [11 empty] | Approved on Tuesday, January 18, 2022 7:15 PM
#N/A |  |  |  |  | RTR-AHCS-284 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report showing the open AR items by their aging buckets with invoice details as well in French Language | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT168 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' Current Report Name in Legacy FAH- 'AR Aging With Invoices' - Report to show the open AP items by their aging buckets with invoice details as well (INV_I & INV_D & INV_DUE_D) in French Language It should be able to run by the selected month | User should be able to generate a report showing the open AR items by their aging buckets with invoice details in French Language | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs in French language. |  |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte | [11 empty] | Approved on Tuesday, January 18, 2022 7:15 PM
#N/A |  |  |  |  | RTR-AHCS-285 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report showing the open AR items by their aging buckets with invoice details as well in Spanish Language | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT168 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' Current Report Name in Legacy FAH- 'AR Aging With Invoices' - Report to show the open AP items by their aging buckets with invoice details as well (INV_I & INV_D & INV_DUE_D) in Spanish Language It should be able to run by the selected month | User should be able to generate a report showing the open AR items by their aging buckets with invoice details in Spanish Language | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs in Spanish language. |  |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte | [11 empty] | Approved on Tuesday, January 18, 2022 7:15 PM
#N/A |  |  |  |  | RTR-AHCS-286 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report showing the open AR items by their aging buckets with invoice details as well in German Language | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT168 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' Current Report Name in Legacy FAH- 'AR Aging With Invoices' - Report to show the open AP items by their aging buckets with invoice details as well (INV_I & INV_D & INV_DUE_D) in German Language It should be able to run by the selected month | User should be able to generate a report showing the open AR items by their aging buckets with invoice details in German Language | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs in German language. |  |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte | [11 empty] | Approved on Tuesday, January 18, 2022 7:15 PM
#N/A |  |  |  |  | RTR-AHCS-287 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report showing the open AR items by their aging buckets with invoice details as well in Polish Language | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT168 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' Current Report Name in Legacy FAH- 'AR Aging With Invoices' - Report to show the open AP items by their aging buckets with invoice details as well (INV_I & INV_D & INV_DUE_D) in Polish Language It should be able to run by the selected month | User should be able to generate a report showing the open AR items by their aging buckets with invoice details in Polish Language | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs in Polish language. |  |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte | [11 empty] | Approved on Tuesday, January 18, 2022 7:15 PM
#N/A |  |  |  |  | RTR-AHCS-288 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report showing the open AR items by their aging buckets with invoice details as well in Arabic Language | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT168 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope'. Current Report Name in Legacy FAH- 'AR Aging With Invoices' - Report to show the open AP items by their aging buckets with invoice details as well (INV_I & INV_D & INV_DUE_D) in Arabic Language It should be able to run by the selected month | User should be able to generate a report showing the open AR items by their aging buckets with invoice details in Arabic Language | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs in Arabic language. |  |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte | [11 empty] | Approved on Tuesday, January 18, 2022 7:15 PM
#N/A |  |  |  |  | RTR-AHCS-289 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report which shows a detailed report break down the of open transactions in account 121100009 in French Language | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT169 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope'. Current Report Name in Legacy FAH- 'AR Cash Clearing Aging Details' - report breaksdown the open transactions in account 121100009 by Loc, Customer, Source code type, Statement ID and aging amongst other in French Language | User should be able to generate a report which shows detailed report break down the open transactions in account 121100009 in French Language | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs in French language. |  |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte | [11 empty] | Approved on Tuesday, January 18, 2022 7:15 PM
#N/A |  |  |  |  | RTR-AHCS-290 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report which shows a detailed report break down the of open transactions in account 121100009 in Spanish Language | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT169 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope'. Current Report Name in Legacy FAH- 'AR Cash Clearing Aging Details' - report breaksdown the open transactions in account 121100009 by Loc, Customer, Source code type, Statement ID and aging amongst other in Spanish Language | User should be able to generate a report which shows detailed report break down the open transactions in account 121100009 in Spanish Language | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs in Spanish language. |  |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte | [11 empty] | Approved on Tuesday, January 18, 2022 7:15 PM
#N/A |  |  |  |  | RTR-AHCS-291 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report which shows a detailed report break down the of open transactions in account 121100009 in German Language | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT169 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope'. Current Report Name in Legacy FAH- 'AR Cash Clearing Aging Details' - report breaksdown the open transactions in account 121100009 by Loc, Customer, Source code type, Statement ID and aging amongst other in German Language | User should be able to generate a report which shows detailed report break down the open transactions in account 121100009 in German Language | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs in German language. |  |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte | [11 empty] | Approved on Tuesday, January 18, 2022 7:15 PM
#N/A |  |  |  |  | RTR-AHCS-292 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report which shows a detailed report break down the of open transactions in account 121100009 in Polish Language | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT169 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope'. Current Report Name in Legacy FAH- 'AR Cash Clearing Aging Details' - report breaksdown the open transactions in account 121100009 by Loc, Customer, Source code type, Statement ID and aging amongst other in Polish Language | User should be able to generate a report which shows detailed report break down the open transactions in account 121100009 in Polish Language | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs in Polish language. |  |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte | [11 empty] | Approved on Tuesday, January 18, 2022 7:15 PM
#N/A |  |  |  |  | RTR-AHCS-293 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report which shows a detailed report break down the of open transactions in account 121100009 in Arabic Language | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT169 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope'. Current Report Name in Legacy FAH- 'AR Cash Clearing Aging Details' - report breaksdown the open transactions in account 121100009 by Loc, Customer, Source code type, Statement ID and aging amongst other in Arabic Language | User should be able to generate a report which shows detailed report break down the open transactions in account 121100009 in Arabic Language | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs in Arabic language. |  |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte | [11 empty] | Approved on Tuesday, January 18, 2022 7:15 PM
#N/A |  |  |  |  | RTR-AHCS-294 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report which shows the movement by Intercompany AR invoices details within said month in French Language | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT170 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope'. 02/04 - Based on accounting hub data only. Current Report Name in Legacy FAH- 'AR Detailed Intercompany Trial Balance' - Detailed report that the movement by invoice details (INV_I, INV_D, JRNL_I, PAY_TERM, FRT_BILL_I) within said month. Non Detailed version of this report is not needed if this is provided. Account 127000000 in French Language High volume report, performance may be impacted - but parked for AHCS as this is AUDIT report | User should be able to generate a report which shows the movement by AR Intercompany invoice details within said month in French Language | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs in French language. |  |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte | [11 empty] | Approved on Tuesday, January 18, 2022 7:15 PM
#N/A |  |  |  |  | RTR-AHCS-295 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report which shows the movement by Intercompany AR invoices details within said month in Spanish Language | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT170 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope'. 02/04 - Based on accounting hub data only. Current Report Name in Legacy FAH- 'AR Detailed Intercompany Trial Balance' - Detailed report that the movement by invoice details (INV_I, INV_D, JRNL_I, PAY_TERM, FRT_BILL_I) within said month. Non Detailed version of this report is not needed if this is provided. Account 127000000 in Spanish Language High volume report, performance may be impacted - but parked for AHCS as this is AUDIT report | User should be able to generate a report which shows the movement by AR Intercompany invoice details within said month in Spanish Language | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs in Spanish language. |  |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte | [11 empty] | Approved on Tuesday, January 18, 2022 7:15 PM
#N/A |  |  |  |  | RTR-AHCS-296 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report which shows the movement by Intercompany AR invoices details within said month in German Language | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT170 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope'. 02/04 - Based on accounting hub data only. Current Report Name in Legacy FAH- 'AR Detailed Intercompany Trial Balance' - Detailed report that the movement by invoice details (INV_I, INV_D, JRNL_I, PAY_TERM, FRT_BILL_I) within said month. Non Detailed version of this report is not needed if this is provided. Account 127000000 in German Language High volume report, performance may be impacted - but parked for AHCS as this is AUDIT report | User should be able to generate a report which shows the movement by AR Intercompany invoice details within said month in German Language | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs in German language. |  |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte | [11 empty] | Approved on Tuesday, January 18, 2022 7:15 PM
#N/A |  |  |  |  | RTR-AHCS-297 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report which shows the movement by Intercompany AR invoices details within said month in Polish Language | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT170 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope'. 02/04 - Based on accounting hub data only. Current Report Name in Legacy FAH- 'AR Detailed Intercompany Trial Balance' - Detailed report that the movement by invoice details (INV_I, INV_D, JRNL_I, PAY_TERM, FRT_BILL_I) within said month. Non Detailed version of this report is not needed if this is provided. Account 127000000 in Polish Language High volume report, performance may be impacted - but parked for AHCS as this is AUDIT report | User should be able to generate a report which shows the movement by AR Intercompany invoice details within said month in Polish Language | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs in Polish language. |  |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte | [11 empty] | Approved on Tuesday, January 18, 2022 7:15 PM
#N/A |  |  |  |  | RTR-AHCS-298 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report which shows the movement by Intercompany AR invoices details within said month in Arabic Language | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT170 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope'. 02/04 - Based on accounting hub data only. Current Report Name in Legacy FAH- 'AR Detailed Intercompany Trial Balance' - Detailed report that the movement by invoice details (INV_I, INV_D, JRNL_I, PAY_TERM, FRT_BILL_I) within said month. Non Detailed version of this report is not needed if this is provided. Account 127000000 in Arabic Language High volume report, performance may be impacted - but parked for AHCS as this is AUDIT report | User should be able to generate a report which shows the movement by AR Intercompany invoice details within said month in Arabic Language | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs in Arabic language. |  |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte | [11 empty] | Approved on Tuesday, January 18, 2022 7:15 PM
#N/A |  |  |  |  | RTR-AHCS-299 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report which shows the movement by AR invoice details within said month in French Language | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT171 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope'. Current Report Name in Legacy FAH- 'AR Detailed Trial Balance' - Detailed report that shows the movement by invoice details (INV_I & INV_D & INV_DUE_D) within said month. It should be able to run by the selected month. Information such as customer name, invoice number, invoice amounts, etc will be required in French Language | User should be able to generate a report which shows the movement by AR invoice details within said month in French Language | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs in French language. |  |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte | [11 empty] | Approved on Tuesday, January 18, 2022 7:15 PM
#N/A |  |  |  |  | RTR-AHCS-300 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report which shows the movement by AR invoice details within said month in Spanish Language | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT171 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope'. Current Report Name in Legacy FAH- 'AR Detailed Trial Balance' - Detailed report that shows the movement by invoice details (INV_I & INV_D & INV_DUE_D) within said month. It should be able to run by the selected month. Information such as customer name, invoice number, invoice amounts, etc will be required in Spanish Language | User should be able to generate a report which shows the movement by AR invoice details within said month in Spanish Language | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs in Spanish language. |  |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte | [11 empty] | Approved on Tuesday, January 18, 2022 7:15 PM
#N/A |  |  |  |  | RTR-AHCS-301 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report which shows the movement by AR invoice details within said month in German Language | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT171 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope'. Current Report Name in Legacy FAH- 'AR Detailed Trial Balance' - Detailed report that shows the movement by invoice details (INV_I & INV_D & INV_DUE_D) within said month. It should be able to run by the selected month. Information such as customer name, invoice number, invoice amounts, etc will be required in German Language | User should be able to generate a report which shows the movement by AR invoice details within said month in German Language | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs in German language. |  |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte | [11 empty] | Approved on Tuesday, January 18, 2022 7:15 PM
#N/A |  |  |  |  | RTR-AHCS-302 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report which shows the movement by AR invoice details within said month in Polish Language | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT171 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope'. Current Report Name in Legacy FAH- 'AR Detailed Trial Balance' - Detailed report that shows the movement by invoice details (INV_I & INV_D & INV_DUE_D) within said month. It should be able to run by the selected month. Information such as customer name, invoice number, invoice amounts, etc will be required in Polish Language | User should be able to generate a report which shows the movement by AR invoice details within said month in Polish Language | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs in Polish language. |  |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte | [11 empty] | Approved on Tuesday, January 18, 2022 7:15 PM
#N/A |  |  |  |  | RTR-AHCS-303 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report which shows the movement by AR invoice details within said month in Arabic Language | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT171 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope'. Current Report Name in Legacy FAH- 'AR Detailed Trial Balance' - Detailed report that shows the movement by invoice details (INV_I & INV_D & INV_DUE_D) within said month. It should be able to run by the selected month. Information such as customer name, invoice number, invoice amounts, etc will be required in Arabic Language | User should be able to generate a report which shows the movement by AR invoice details within said month in Arabic Language | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs in Arabic language. |  |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte | [11 empty] | Approved on Tuesday, January 18, 2022 7:15 PM
#N/A |  |  |  |  | RTR-AHCS-304 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report which breaksdown the open transactions for different Cash Clearing Accounts in French Language | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT172 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope'. Current Report Name in Legacy FAH- 'Bank Cash Clearing' - This detailed report breaksdown the open transactions in accounts 351100009, 328361009, 101400001, 101499999 and 379990009 by BU, Loc, Customer, Source code type, Statement ID amongst other in French Language High volume report, performance may be impacted - but parked for AHCS as this is AUDIT report | User should be able to generate a report which shows the open transactions for different Cash Clearing Accounts in French Language | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs in French language. |  |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte | [11 empty] | Approved on Tuesday, January 18, 2022 7:15 PM
#N/A |  |  |  |  | RTR-AHCS-305 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report which breaksdown the open transactions for different Cash Clearing Accounts in Spanish Language | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT172 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope'. Current Report Name in Legacy FAH- 'Bank Cash Clearing' - This detailed report breaksdown the open transactions in accounts 351100009, 328361009, 101400001, 101499999 and 379990009 by BU, Loc, Customer, Source code type, Statement ID amongst other in Spanish Language High volume report, performance may be impacted - but parked for AHCS as this is AUDIT report | User should be able to generate a report which shows the open transactions for different Cash Clearing Accounts in Spanish Language | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs in Spanish language. |  |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte | [11 empty] | Approved on Tuesday, January 18, 2022 7:15 PM
#N/A |  |  |  |  | RTR-AHCS-306 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report which breaksdown the open transactions for different Cash Clearing Accounts in German Language | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT172 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope'. Current Report Name in Legacy FAH- 'Bank Cash Clearing' - This detailed report breaksdown the open transactions in accounts 351100009, 328361009, 101400001, 101499999 and 379990009 by BU, Loc, Customer, Source code type, Statement ID amongst other in German Language High volume report, performance may be impacted - but parked for AHCS as this is AUDIT report | User should be able to generate a report which shows the open transactions for different Cash Clearing Accounts in German Language | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs in German language. |  |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte | [11 empty] | Approved on Tuesday, January 18, 2022 7:15 PM
#N/A |  |  |  |  | RTR-AHCS-307 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report which breaksdown the open transactions for different Cash Clearing Accounts in Polish Language | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT172 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope'. Current Report Name in Legacy FAH- 'Bank Cash Clearing' - This detailed report breaksdown the open transactions in accounts 351100009, 328361009, 101400001, 101499999 and 379990009 by BU, Loc, Customer, Source code type, Statement ID amongst other in Polish Language High volume report, performance may be impacted - but parked for AHCS as this is AUDIT report | User should be able to generate a report which shows the open transactions for different Cash Clearing Accounts in Polish Language | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs in Polish language. |  |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte | [11 empty] | Approved on Tuesday, January 18, 2022 7:15 PM
#N/A |  |  |  |  | RTR-AHCS-308 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report which breaksdown the open transactions for different Cash Clearing Accounts in Arabic Language | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT172 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope'. Current Report Name in Legacy FAH- 'Bank Cash Clearing' - This detailed report breaksdown the open transactions in accounts 351100009, 328361009, 101400001, 101499999 and 379990009 by BU, Loc, Customer, Source code type, Statement ID amongst other in Arabic Language High volume report, performance may be impacted - but parked for AHCS as this is AUDIT report | User should be able to generate a report which shows the open transactions for different Cash Clearing Accounts in Arabic Language | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs in Arabic language. |  |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte | [11 empty] | Approved on Tuesday, January 18, 2022 7:15 PM
#N/A |  |  |  |  | RTR-AHCS-309 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report that shows the movement by transaction within all the bank accounts by Legal Entity in French Language | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT173 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope'. Current Report Name in Legacy FAH- 'Bank Roll Forward detail'- Should show the movement by transaction within all the bank accounts grouped by LE in French Language | User should be able to generate a report that shows the movement by transaction within all the bank accounts by Legal Entity in French Language | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs in French language. |  |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte | [11 empty] | Approved on Tue 2/1/2022 10:02 AM
#N/A |  |  |  |  | RTR-AHCS-310 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report that shows the movement by transaction within all the bank accounts by Legal Entity in Spanish Language | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT173 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope'. Current Report Name in Legacy FAH- 'Bank Roll Forward detail'- Should show the movement by transaction within all the bank accounts grouped by LE in Spanish Language | User should be able to generate a report that shows the movement by transaction within all the bank accounts by Legal Entity in Spanish Language | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs in Spanish language. |  |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte | [11 empty] | Approved on Tue 2/1/2022 10:02 AM
#N/A |  |  |  |  | RTR-AHCS-311 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report that shows the movement by transaction within all the bank accounts by Legal Entity in German Language | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT173 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope'. Current Report Name in Legacy FAH- 'Bank Roll Forward detail'- Should show the movement by transaction within all the bank accounts grouped by LE in German Language | User should be able to generate a report that shows the movement by transaction within all the bank accounts by Legal Entity in German Language | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs in German language. |  |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte | [11 empty] | Approved on Tue 2/1/2022 10:02 AM
#N/A |  |  |  |  | RTR-AHCS-312 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report that shows the movement by transaction within all the bank accounts by Legal Entity in Polish Language | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT173 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope'. Current Report Name in Legacy FAH- 'Bank Roll Forward detail'- Should show the movement by transaction within all the bank accounts grouped by LE in Polish Language | User should be able to generate a report that shows the movement by transaction within all the bank accounts by Legal Entity in Polish Language | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs in Polish language. |  |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte | [11 empty] | Approved on Tue 2/1/2022 10:02 AM
#N/A |  |  |  |  | RTR-AHCS-313 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report that shows the movement by transaction within all the bank accounts by Legal Entity in Arabic Language | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT173 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope'. Current Report Name in Legacy FAH- 'Bank Roll Forward detail'- Should show the movement by transaction within all the bank accounts grouped by LE in Arabic Language | User should be able to generate a report that shows the movement by transaction within all the bank accounts by Legal Entity in Arabic Language | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs in Arabic language. |  |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte | [11 empty] | Approved on Tue 2/1/2022 10:02 AM
#N/A |  |  |  |  | RTR-AHCS-314 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report that shows the WIP, RTV, Warranty Replacement, Freight Claims aging which ties back to GL in French Language | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT175 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope'. Current Report Name in Legacy FAH- 'Special Sales Aging'- Should be able to tie back to GL in French Language This report show special sales aging by customer/invoice number/date | User should be able to generate a report that he WIP, RTV, Warrenty, Freight Claims and can be tied back to GL in French Language | Validate WIP, RTV, Warranty, Freight Claims are broken out by category | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs in French language. |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte | [11 empty] | Approved on Tuesday, January 18, 2022 7:15 PM
#N/A |  |  |  |  | RTR-AHCS-315 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report that shows the WIP, RTV, Warranty Replacement, Freight Claims aging which ties back to GL in Spanish Language | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT175 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope'. Current Report Name in Legacy FAH- 'Special Sales Aging'- Should be able to tie back to GL in Spanish Language This report show special sales aging by customer/invoice number/date | User should be able to generate a report that he WIP, RTV, Warrenty, Freight Claims and can be tied back to GL in Spanish Language | Validate WIP, RTV, Warranty, Freight Claims are broken out by category | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs in Spanish language. |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte | [11 empty] | Approved On Thu 1/20/2022 9:17 PM
#N/A |  |  |  |  | RTR-AHCS-316 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report that shows the WIP, RTV, Warranty Replacement, Freight Claims aging which ties back to GL in German Language | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT175 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope'. Current Report Name in Legacy FAH- 'Special Sales Aging'- Should be able to tie back to GL in German Language This report show special sales aging by customer/invoice number/date | User should be able to generate a report that he WIP, RTV, Warrenty, Freight Claims and can be tied back to GL in German Language | Validate WIP, RTV, Warranty, Freight Claims are broken out by category | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs in German language. |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte | [11 empty] | Approved On Thu 1/20/2022 9:17 PM
#N/A |  |  |  |  | RTR-AHCS-317 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report that shows the WIP, RTV, Warranty Replacement, Freight Claims aging which ties back to GL in Polish Language | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT175 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope'. Current Report Name in Legacy FAH- 'Special Sales Aging'- Should be able to tie back to GL in Polish Language This report show special sales aging by customer/invoice number/date | User should be able to generate a report that he WIP, RTV, Warrenty, Freight Claims and can be tied back to GL in Polish Language | Validate WIP, RTV, Warranty, Freight Claims are broken out by category | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs in Polish language. |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte | [11 empty] | Approved On Thu 1/20/2022 9:17 PM
#N/A |  |  |  |  | RTR-AHCS-318 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report that shows the WIP, RTV, Warranty Replacement, Freight Claims aging which ties back to GL in Arabic Language | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT175 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope'. Current Report Name in Legacy FAH- 'Special Sales Aging'- Should be able to tie back to GL in Arabic Language This report show special sales aging by customer/invoice number/date | User should be able to generate a report that he WIP, RTV, Warrenty, Freight Claims and can be tied back to GL in Arabic Language | Validate WIP, RTV, Warranty, Freight Claims are broken out by category | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs in Arabic language. |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte | [11 empty] | Approved on Tuesday, January 18, 2022 7:15 PM
#N/A |  |  |  |  | RTR-AHCS-319 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report that shows the Intercompany AP Aging (material & non material) process in French Language | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT176 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope'. 02/04 - Based on accounting hub data only. Current Report Name in Legacy FAH- 'Intercompany AP Aging (material & non material)'- Nees this in French Language | User should be able to generate a report that shows the Intercompany Aging (material & non material) process in French Language | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs in French language. |  |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte | [8 empty] | Sent email to Nilakanth 1-13 to revise story. IP |  |  | Approved on Tuesday, January 18, 2022 7:15 PM
#N/A |  |  |  |  | RTR-AHCS-320 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report that shows the Intercompany AP Aging (material & non material) process in Spanish Language | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT176 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope'. 02/04 - Based on accounting hub data only. Current Report Name in Legacy FAH- 'Intercompany AP Aging (material & non material)'- Nees this in Spanish Language | User should be able to generate a report that shows the Intercompany Aging (material & non material) process in Spanish Language | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs in Spanish language. |  |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte | [8 empty] | Sent email to Nilakanth 1-13 to revise story. IP |  |  | Approved on Tuesday, January 18, 2022 7:15 PM
#N/A |  |  |  |  | RTR-AHCS-321 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report that shows the Intercompany AP Aging (material & non material) process in German Language | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT176 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope'. 02/04 - Based on accounting hub data only. Current Report Name in Legacy FAH- 'Intercompany AP Aging (material & non material)'- Nees this in German Language | User should be able to generate a report that shows the Intercompany Aging (material & non material) process in German Language | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs in German language. |  |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte | [8 empty] | Sent email to Nilakanth 1-13 to revise story. IP |  |  | Approved on Tuesday, January 18, 2022 7:15 PM
#N/A |  |  |  |  | RTR-AHCS-322 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report that shows the Intercompany AP Aging (material & non material) process in Polish Language | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT176 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope'. 02/04 - Based on accounting hub data only. Current Report Name in Legacy FAH- 'Intercompany AP Aging (material & non material)'- Nees this in Polish Language | User should be able to generate a report that shows the Intercompany Aging (material & non material) process in Polish Language | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs in Polish language. |  |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte | [8 empty] | Sent email to Nilakanth 1-13 to revise story. IP |  |  | Approved On Thu 1/20/2022 9:17 PM
#N/A |  |  |  |  | RTR-AHCS-323 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report that shows the Intercompany AP Aging (material & non material) process in Arabic Language | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT176 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope'. 02/04 - Based on accounting hub data only. Current Report Name in Legacy FAH- 'Intercompany AP Aging (material & non material)'- Nees this in Arabic Language | User should be able to generate a report that shows the Intercompany Aging (material & non material) process in Arabic Language | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs in Arabic language. |  |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte | [8 empty] | Sent email to Nilakanth 1-13 to revise story. IP |  |  | Approved On Thu 1/20/2022 9:17 PM
#N/A |  |  |  |  | RTR-AHCS-324 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report that shows the Intercompany AP Trail balance (material & no material) details in French Language | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT177 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope'. 02/04 - Based on accounting hub data only. Current Report Name in Legacy FAH- 'Intercompany AP Trail balance (material & no material)'. This is in in French Language | User should be able to generate a report that shows the Intercompany Trail balance (material & no material) details in French Language | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs in French language. |  |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte | [8 empty] | Sent email to Nilakanth 1-13 to revise story. IP |  |  | Approved On Thu 1/20/2022 9:17 PM
#N/A |  |  |  |  | RTR-AHCS-325 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report that shows the Intercompany AP Trail balance (material & no material) details in Spanish Language | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT177 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope'. 02/04 - Based on accounting hub data only. Current Report Name in Legacy FAH- 'Intercompany AP Trail balance (material & no material)'. This is in in Spanish Language | User should be able to generate a report that shows the Intercompany Trail balance (material & no material) details in Spanish Language | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs in Spanish language. |  |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte | [8 empty] | Sent email to Nilakanth 1-13 to revise story. IP |  |  | Approved On Thu 1/20/2022 9:17 PM
#N/A |  |  |  |  | RTR-AHCS-326 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report that shows the Intercompany AP Trail balance (material & no material) details in German Language | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT177 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope'. 02/04 - Based on accounting hub data only. Current Report Name in Legacy FAH- 'Intercompany AP Trail balance (material & no material)'. This is in in German Language | User should be able to generate a report that shows the Intercompany Trail balance (material & no material) details in German Language | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs in German language. |  |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte | [8 empty] | Sent email to Nilakanth 1-13 to revise story. IP |  |  | Approved On Thu 1/20/2022 9:17 PM
#N/A |  |  |  |  | RTR-AHCS-327 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report that shows the Intercompany AP Trail balance (material & no material) details in Polish Language | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT177 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope'. 02/04 - Based on accounting hub data only. Current Report Name in Legacy FAH- 'Intercompany AP Trail balance (material & no material)'. This is in in Polish Language | User should be able to generate a report that shows the Intercompany Trail balance (material & no material) details in Polish Language | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs in Polish language. |  |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte | [8 empty] | Sent email to Nilakanth 1-13 to revise story. IP |  |  | Approved On Thu 1/20/2022 9:17 PM
#N/A |  |  |  |  | RTR-AHCS-328 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report that shows the Intercompany AP Trail balance (material & no material) details in Arabic Language | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT177 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope'. 02/04 - Based on accounting hub data only. Current Report Name in Legacy FAH- 'Intercompany AP Trail balance (material & no material)'. This is in in Arabic Language | User should be able to generate a report that shows the Intercompany Trail balance (material & no material) details in Arabic Language | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs in Arabic language. |  |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte | [8 empty] | Sent email to Nilakanth 1-13 to revise story. IP |  |  | Approved On Thu 1/20/2022 9:17 PM
#N/A |  |  |  |  | RTR-AHCS-329 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As IT User , I want the ability to send transaction details from AHCS to Cresus on daily basis in order to perform Integrity check | Must Have |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT238 | New Outbound to be created for Cresus from AHCS for Tranasction details on daily baisis. File fomrat would be finalised in Lean spec dicussion, however current assumption is it would be similar to MF. Per Simon Integrity check refres to comparision of Cresus Journal_ID / Journal Line ID with AHCS Journal_ID / Journal Line ID. | User will have an ability to send transaction details from AHCS to Cresus on daily basis to perform Integrity check | User will receive Cresus transaction details from AHCS on daily basis to perform Integrity check |  |  | Approved | Sijo John |  |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  | Based on accept criteria "who is the user in this case? Not sure how its being done with MF atm, scheduled or manual?" IP 1/18/22 |  | Bhim |  |  | N/A |  |  |  | Approved on Wed 2/2/2022 4:45 AM
#N/A |  |  |  |  | RTR-AHCS-330 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report that shows the Intercompany AR Trail balance (material & no material) details in English Language | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Gap | Build | Report | RPT180 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope'. 02/04 - Based on accounting hub data only. Current Report Name in Legacy FAH- 'Intercompany AR Trail balance (material & no material)'. This is in in English Language | User should be able to generate a report that shows the Intercompany Trail balance (material & no material) details in English (US) Language |  |  |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim, How is this different to the AP & AR IC reports mentioned above? is this Material and non-material while the above is only material? |  | N/A | Betty | Sent email to Nilakanth 1-13 to revise story. IP |  |  | Approved On Thu 1/20/2022 9:17 PM | 28
#N/A |  |  |  |  | RTR-AHCS-331 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report that shows the Intercompany AR Trail balance (material & no material) details in French Language | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Gap | Build | Report | RPT184 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope'. 02/04 - Based on accounting hub data only. Current Report Name in Legacy FAH- 'Intercompany AR Trail balance (material & no material)'. This is in in French Language | User should be able to generate a report that shows the Intercompany Trail balance (material & no material) details in French Language | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs in French language. |  |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte | [8 empty] | Sent email to Nilakanth 1-13 to revise story. IP |  |  | Approved On Thu 1/20/2022 9:17 PM
#N/A |  |  |  |  | RTR-AHCS-332 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report that shows the Intercompany AR Trail balance (material & no material) details in Spanish Language | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Gap | Build | Report | RPT184 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope'. 02/04 - Based on accounting hub data only. Current Report Name in Legacy FAH- 'Intercompany AR Trail balance (material & no material)'. This is in in Spanish Language | User should be able to generate a report that shows the Intercompany Trail balance (material & no material) details in Spanish Language | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs in Spanish language. |  |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte | [8 empty] | Sent email to Nilakanth 1-13 to revise story. IP |  |  | Approved On Thu 1/20/2022 9:17 PM
#N/A |  |  |  |  | RTR-AHCS-333 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report that shows the Intercompany AR Trail balance (material & no material) details in German Language | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Gap | Build | Report | RPT184 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope'. 02/04 - Based on accounting hub data only. Current Report Name in Legacy FAH- 'Intercompany AR Trail balance (material & no material)'. This is in in German Language | User should be able to generate a report that shows the Intercompany Trail balance (material & no material) details in German Language | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs in German language. |  |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte | [8 empty] | Sent email to Nilakanth 1-13 to revise story. IP |  |  | Approved On Thu 1/20/2022 9:17 PM
#N/A |  |  |  |  | RTR-AHCS-334 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report that shows the Intercompany AR Trail balance (material & no material) details in Polish Language | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Gap | Build | Report | RPT184 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope'. 02/04 - Based on accounting hub data only. Current Report Name in Legacy FAH- 'Intercompany AR Trail balance (material & no material)'. This is in in Polish Language | User should be able to generate a report that shows the Intercompany Trail balance (material & no material) details in Polish Language | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs in Polish language. |  |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte | [8 empty] | Sent email to Nilakanth 1-13 to revise story. IP |  |  | Approved On Thu 1/20/2022 9:17 PM
#N/A |  |  |  |  | RTR-AHCS-335 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report that shows the Intercompany AR Trail balance (material & no material) details in Arabic Language | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Gap | Build | Report | RPT184 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope'. 02/04 - Based on accounting hub data only. Current Report Name in Legacy FAH- 'Intercompany AR Trail balance (material & no material)'. This is in in Arabic Language | User should be able to generate a report that shows the Intercompany Trail balance (material & no material) details in Arabic Language | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs in Arabic language. |  |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte | [8 empty] | Sent email to Nilakanth 1-13 to revise story. IP |  |  | Approved On Thu 1/20/2022 9:17 PM
#N/A |  |  |  |  | RTR-AHCS-336 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report that shows the Intercompany AR Aging (material & non material) process in English Language | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Gap | Build | Report | RPT179 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope'. 02/04 - Based on accounting hub data only. Current Report Name in Legacy FAH- 'Intercompany AR Aging (material & non material)'- Nees this in English Language | User should be able to generate a report that shows the Intercompany Aging (material & non material) process in English Language | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs in English language. |  |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim |  | N/A | Betty | Sent email to Nilakanth 1-13 to revise story. IP |  |  | Approved On Thu 1/20/2022 9:17 PM | 28
#N/A |  |  |  |  | RTR-AHCS-337 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report that shows the Intercompany AR Aging (material & non material) process in Spanish Language | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Gap | Build | Report | RPT183 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope'. 02/04 - Based on accounting hub data only. Current Report Name in Legacy FAH- 'Intercompany AR Aging (material & non material)'- Nees this in Spanish Language | User should be able to generate a report that shows the Intercompany Aging (material & non material) process in Spanish Language | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs in Spanish language. |  |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte | [8 empty] | Sent email to Nilakanth 1-13 to revise story. IP |  |  | Approved On Thu 1/20/2022 9:17 PM
#N/A |  |  |  |  | RTR-AHCS-338 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report that shows the Intercompany AR Aging (material & non material) process in German Language | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Gap | Build | Report | RPT183 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope'. 02/04 - Based on accounting hub data only. Current Report Name in Legacy FAH- 'Intercompany AR Aging (material & non material)'- Nees this in German Language | User should be able to generate a report that shows the Intercompany Aging (material & non material) process in German Language | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs in German language. |  |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte | [8 empty] | Sent email to Nilakanth 1-13 to revise story. IP |  |  | Approved On Thu 1/20/2022 9:17 PM
#N/A |  |  |  |  | RTR-AHCS-339 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report that shows the Intercompany AR Aging (material & non material) process in Polish Language | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Gap | Build | Report | RPT183 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope'. 02/04 - Based on accounting hub data only. Current Report Name in Legacy FAH- 'Intercompany AR Aging (material & non material)'- Nees this in Polish Language | User should be able to generate a report that shows the Intercompany Aging (material & non material) process in Polish Language | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs in Polish language. |  |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte | [8 empty] | Sent email to Nilakanth 1-13 to revise story. IP |  |  | Approved On Thu 1/20/2022 9:17 PM
#N/A |  |  |  |  | RTR-AHCS-340 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report that shows the Intercompany AR Aging (material & non material) process in Arabic Language | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Gap | Build | Report | RPT183 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope'. 02/04 - Based on accounting hub data only. Current Report Name in Legacy FAH- 'Intercompany AR Aging (material & non material)'- Nees this in Arabic Language | User should be able to generate a report that shows the Intercompany Aging (material & non material) process in Arabic Language | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs in Arabic language. |  |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte | [8 empty] | Sent email to Nilakanth 1-13 to revise story. IP |  |  | Approved On Thu 1/20/2022 9:17 PM
#N/A |  |  |  |  | RTR-AHCS-341 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report that shows the 'Intercompany AR Invoice Statement Summary (Trade) (Material)For the Year Only' In English Language | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Gap | Build | Report | RPT182 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope'. 02/04 - Based on accounting hub data only. Current Report Name in Legacy FAH- 'Intercompany AR Invoice Statement Summary (Trade)' in English Language | User should be able to generate a report that shows Intercompany AR Invoice Statement Summary (Trade) in English Language | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs. |  |  | Approved | Ian | 2022-01-17 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte | [8 empty] | Sent email to Nilakanth 1-13 to revise story. IP |  |  | Approved On Thu 1/20/2022 9:17 PM
#N/A |  |  |  |  | RTR-AHCS-342 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report that shows the Intercompany AR Aging (material & non material) process in French Language | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Gap | Build | Report | RPT183 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope'. 02/04 - Based on accounting hub data only. Current Report Name in Legacy FAH- 'Intercompany AR Aging (material & non material)'- Nees this in French Language | User should be able to generate a report that shows the Intercompany Aging (material & non material) process in French Language | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs in French language. |  |  | Approved | Ian | 2022-01-18 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte | [8 empty] | Sent email to Nilakanth 1-13 to revise story. IP |  |  | Approved On Thu 1/20/2022 9:17 PM
#N/A | CSTONE-6251 |  |  |  | RTR-AHCS-343 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As IT Administrator, I want the ability to send back good transaction details which are processed in PAAS instance (Middleware) To Mainframe source system | Must Have |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT237 | 02/02 : Update this to Mainfarmae Good file from PAAS after Validation and transformation. Per Sijo This should be removed as RTR-AHCS-475 exists for Cresus Bad file New Outbound to be created for Cresus from AHCS for Tranasction details on daily baisis. File fomrat would be finalised in Lean spec dicussion, however current assumption is it would be similar to MF | User will have an ability to receive good file which are processed in PAAS instance (Middleware). | User will be able to get files for data processed (good) in AHCS with email notification for Mainframe interfaces |  |  | Approved | Sijo John |  |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte | [11 empty] | Approved on Mon 2/7/2022 7:10 PM
[5 empty] | RTR-AHCS-344 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view Trade Payable Invoice AP Beg Bal (Subledger) for North America Region ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV041 | AHCS Conversion to load Trade Payable Invoice AP Beg Bal (Subledger) for North America Region ledgers | User should be review opening balances under Trade Payable Invoice AP Beg Bal (event type) for North America Region ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting from FAH onprem. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | n/a | N/A | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-345 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view MF Intercompany – AP IC Beg Bal (Subledger) for North America Region ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV041 | AHCS Conversion to load MF Intercompany – AP IC Beg Bal (Subledger) for North America Region ledgers | User should be review opening balances under MF Intercompany – AP IC Beg Bal (event type) for North America Region ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting . Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | n/a | N/A | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-346 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view Unvouchered - Work Orders Unvouchered Beg Bal (AP Subledger) for North America Region ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV041 | AHCS Conversion to load Unvouchered - Work Orders Unvouchered Beg Bal (Subledger) for North America Region ledgers | User should be review opening balances under Unvouchered - Work Orders Unvouchered Beg Bal (event type) for North America Region ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting from FAH onprem. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | n/a | N/A | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-347 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view Unvouchered – Intercompany Unvouchered Beg Bal (AP Subledger) for North America Region ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV041 | AHCS Conversion to load Unvouchered – Intercompany Unvouchered Beg Bal (Subledger) for North America Region ledgers | User should be review opening balances under Unvouchered – Intercompany Unvouchered Beg Bal (event type) for North America Region ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting from FAH onprem. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | n/a | N/A | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-348 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view Unvouchered - Trade Unvouchered Beg Bal (AP Subledger) for North America Region ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV041 | AHCS Conversion to load Unvouchered - Trade Unvouchered Beg Bal (Subledger) for North America Region ledgers | User should be review opening balances under Unvouchered - Trade Unvouchered Beg Bal (event type) for North America Region ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting from FAH onprem. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | n/a | N/A | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-349 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view Unvouchered – Direct Ship Unvouchered Beg Bal (AP Subledger) for North America Region ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV041 | AHCS Conversion to load Unvouchered – Direct Ship Unvouchered Beg Bal (Subledger) for North America Region ledgers | User should be review opening balances under Unvouchered – Direct Ship Unvouchered Beg Bal (event type) for North America Region ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting from FAH onprem. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | n/a | N/A | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-350 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view Unvouchered - Return Unvouchered Beg Bal (AP Subledger) for North America Region ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV041 | AHCS Conversion to load Unvouchered - Return Unvouchered Beg Bal (Subledger) for North America Region ledgers | User should be review opening balances under Unvouchered - Return Unvouchered Beg Bal (event type) for North America Region ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting from FAH onprem. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | n/a | N/A | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-351 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view Trade Receivable AR Beg Bal (Subledger) for North America Region ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV042 | AHCS Conversion to load Trade Receivable AR Beg Bal (Subledger) for North America Region ledgers | User should be review opening balances under Trade Receivable AR Beg Bal (event type) for North America Region ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting from FAH onprem. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | n/a | N/A | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-352 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view Late Fees AR Beg Bal (Subledger) for North America Region ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV042 | AHCS Conversion to load Late Fees AR Beg Bal (Subledger) for North America Region ledgers | User should be review opening balances under Late Fees AR Beg Bal (event type) for North America Region ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting from FAH onprem. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | n/a | N/A | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-353 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view MF Intercompany – AR IC Beg Bal (Subledger) for North America Region ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV042 | AHCS Conversion to load MF Intercompany – AR IC Beg Bal (Subledger) for North America Region ledgers | User should be review opening balances under MF Intercompany – AR IC Beg Bal (event type) for North America Region ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting . Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | n/a | N/A | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-354 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view Trade Inventory Inv Beg Bal (Subledger) for North America Region ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV043 | AHCS Conversion to load Trade Inventory Inv Beg Bal (Subledger) for North America Region ledgers | User should be review opening balances under Trade Inventory Inv Beg Bal (event type) for North America Region ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting from FAH onprem. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | n/a | N/A | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-355 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view Reels Inv Beg Bal (Subledger) for North America Region (US only) ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV043 | AHCS Conversion to load Reels Inv Beg Bal (Subledger) for North America Region (US Only) ledgers | User should be review opening balances under Reels Inv Beg Bal (event type) for North America Region (US only )ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting . Verify that manual file ties to loaded beginning balance. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | n/a | N/A | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-356 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view InTransit Stock Inv Beg Bal (Subledger) for North America Region ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV043 | AHCS Conversion to load InTransit Stock Inv Beg Bal (Subledger) for North America Region ledgers | User should be review opening balances under InTransit Stock Inv Beg Bal (event type) for North America Region ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting from FAH onprem. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | n/a | N/A | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-357 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view Intra Intransit Inv Beg Bal (Subledger) for North America Region ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV043 | AHCS Conversion to load Intra Intransit Inv Beg Bal (Subledger) for North America Region ledgers | User should be review opening balances under Intra Intransit Inv Beg Bal (event type) for North America Region ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting from FAH onprem. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | n/a | N/A | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-358 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view RTV Inv Beg Bal (Subledger) for North America Region ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV043 | AHCS Conversion to load RTV Inv Beg Bal (Subledger) for North America Region ledgers | User should be review opening balances under RTV Inv Beg Bal (event type) for North America Region ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting . Verify that manual file ties to loaded beginning balance. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | n/a | N/A | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-359 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view Warranty Inv Beg Bal (Subledger) for North America Region ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV043 | AHCS Conversion to load Warranty Inv Beg Bal (Subledger) for North America Region ledgers | User should be review opening balances under Warranty Inv Beg Bal (event type) for North America Region ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting . Verify that manual file ties to loaded beginning balance. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | n/a | N/A | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-360 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view Freight Accruals Inv Beg Bal (Subledger) for North America Region ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV043 | AHCS Conversion to load Freight Accruals Inv Beg Bal (Subledger) for North America Region ledgers | User should be review opening balances under Freight Accruals Inv Beg Bal (event type) for North America Region ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting . Verify that manual file ties to loaded beginning balance. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | n/a | N/A | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-361 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view Freight Claims Inv Beg Bal (Subledger) for North America Region ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV043 | AHCS Conversion to load Freight Claims Inv Beg Bal (Subledger) for North America Region ledgers | User should be review opening balances under Freight Claims Inv Beg Bal (event type) for North America Region ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting . Verify that manual file ties to loaded beginning balance. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | n/a | N/A | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-362 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view WIP (WO) Inv Beg Bal (Subledger) for North America Region ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV043 | AHCS Conversion to load WIP (WO) Inv Beg Bal (Subledger) for North America Region ledgers | User should be review opening balances under WIP (WO) Inv Beg Bal (event type) for North America Region ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting . Verify that manual file ties to loaded beginning balance. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | n/a | N/A | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-363 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view Kava Inv Beg Bal (Subledger) for North America Region ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV043 | AHCS Conversion to load Kava Inv Beg Bal (Subledger) for North America Region ledgers | User should be review opening balances under Kava Inv Beg Bal (event type) for North America Region ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting from FAH onprem. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | n/a | N/A | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-364 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view Unvouchered - Work Orders Unvouchered Beg Bal (Inv Subledger) for North America Region ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV043 | AHCS Conversion to load Unvouchered - Work Orders Unvouchered Beg Bal (INV Subledger) for North America Region ledgers | User should be review opening balances under Unvouchered - Work Orders Unvouchered Beg Bal (event type) for North America Region ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting from FAH onprem. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | n/a | N/A | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-365 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view Unvouchered – Intercompany Unvouchered Beg Bal (Inv Subledger) for North America Region ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV043 | AHCS Conversion to load Unvouchered – Intercompany Unvouchered Beg Bal (INV Subledger) for North America Region ledgers | User should be review opening balances under Unvouchered – Intercompany Unvouchered Beg Bal (event type) for North America Region ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting from FAH onprem. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | n/a | N/A | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-366 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view Unvouchered – Trade Unvouchered Beg Bal (Inv Subledger) for North America Region ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV043 | AHCS Conversion to load Unvouchered – Trade Unvouchered Beg Bal (Subledger) for North America Region ledgers | User should be review opening balances under Unvouchered – Trade Unvouchered Beg Bal (event type) for North America Region ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting from FAH onprem. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | n/a | N/A | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-367 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view Unvouchered – Direct Ship Unvouchered Beg Bal (Inv Subledger) for North America Region ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV043 | AHCS Conversion to load Unvouchered – Direct Ship Unvouchered Beg Bal (INV Subledger) for North America Region ledgers | User should be review opening balances under Unvouchered – Direct Ship Unvouchered Beg Bal (event type) for North America Region ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting from FAH onprem. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | n/a | N/A | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-368 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view Unvouchered – Returns Unvouchered Beg Bal (Inv Subledger) for North America Region ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV043 | AHCS Conversion to load Unvouchered – Returns Unvouchered Beg Bal (Subledger) for North America Region ledgers | User should be review opening balances under Unvouchered – Returns Unvouchered Beg Bal (event type) for North America Region ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting from FAH onprem. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | n/a | N/A | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-369 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view Unvouchered – PPV/AP Variance Unvouchered Beg Bal (Inv Subledger) for North America Region ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV043 | AHCS Conversion to load Unvouchered – PPV/AP Variance Unvouchered Beg Bal (Subledger) for North America Region ledgers | User should be review opening balances under Unvouchered – PPV/AP Variance Unvouchered Beg Bal (event type) for North America Region ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting . Verify that manual file ties to loaded beginning balance. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | n/a | N/A | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-370 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view Unvouchered – Other Material Unvouchered Beg Bal (Inv Subledger) for North America Region ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV043 | AHCS Conversion to load Unvouchered – Other Material Unvouchered Beg Bal (Subledger) for North America Region ledgers | User should be review opening balances under Unvouchered – Other Material Unvouchered Beg Bal (event type) for North America Region ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting . Verify that manual file ties to loaded beginning balance. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | n/a | N/A | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-371 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view Trade Payable Invoice AP Beg Bal (Subledger) for EMEA Region ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV041 | AHCS Conversion to load Trade Payable Invoice AP Beg Bal (Subledger) for EMEA Region ledgers | User should be review opening balances under Trade Payable Invoice AP Beg Bal (event type) for EMEA Region ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting from FAH onprem. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | N/A | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-372 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view AP Cash Clearing AP Beg Bal (Subledger) for EMEA Region ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV041 | AHCS Conversion to load AP Cash Clearing AP Beg Bal (Subledger) for EMEA Region ledgers | User should be review opening balances under AP Cash Clearing AP Beg Bal (event type) for EMEA Region ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting from FAH onprem. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | N/A | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-373 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view MF Intercompany – AP IC Beg Bal (Subledger) for EMEA Region ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV041 | AHCS Conversion to load MF Intercompany – AP IC Beg Bal (Subledger) for EMEA Region ledgers | User should be review opening balances under MF Intercompany – AP IC Beg Bal (event type) for EMEA Region ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting from FAH onprem. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | N/A | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-374 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view Unvouchered - Work Orders Unvouchered Beg Bal (Subledger) for EMEA Region ledgers | Must Have |  | Phase 1B only | 10-Not Required-Not Required-Not Required | Not Required | Not Required | Not Required |  | This is duplicate User story, Hence marked as 'Not required' HCS Conversion to load Unvouchered - Work Orders Unvouchered Beg Bal (AP Subledger) for EMEA Region ledgers | User should be review opening balances under Unvouchered - Work Orders Unvouchered Beg Bal (event type) for EMEA Region ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting from FAH onprem. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | N/A | [5 empty] | Approved on Thu 2/3/2022 2:33 AM
[5 empty] | RTR-AHCS-375 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view Unvouchered – Intercompany Unvouchered Beg Bal (Subledger) for EMEA Region ledgers | Must Have |  | Phase 1B only | 10-Not Required-Not Required-Not Required | Not Required | Not Required | Not Required |  | This is duplicate User story, Hence marked as 'Not required' AHCS Conversion to load Unvouchered – Intercompany Unvouchered Beg Bal (AP Subledger) for EMEA Region ledgers | User should be review opening balances under Unvouchered – Intercompany Unvouchered Beg Bal (event type) for EMEA Region ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting from FAH onprem. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | N/A | [5 empty] | Approved on Thu 2/3/2022 2:33 AM
[5 empty] | RTR-AHCS-376 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view Unvouchered – Freight & Duty Unvouchered Beg Bal (Subledger) for EMEA Region ledgers | Must Have |  | Phase 1B only | 10-Not Required-Not Required-Not Required | Not Required | Not Required | Not Required |  | This is duplicate User story, Hence marked as 'Not required' AHCS Conversion to load Unvouchered – Freight & Duty Unvouchered Beg Bal (AP Subledger) for EMEA Region ledgers | User should be review opening balances under Unvouchered – Freight & Duty Unvouchered Beg Bal (event type) for EMEA Region ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting from FAH onprem. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | N/A | [5 empty] | Approved on Thu 2/3/2022 2:33 AM
[5 empty] | RTR-AHCS-377 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view Unvouchered - Trade Unvouchered Beg Bal (Subledger) for EMEA Region ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV041 | AHCS Conversion to load Unvouchered - Trade Unvouchered Beg Bal (AP Subledger) for EMEA Region ledgers | User should be review opening balances under Unvouchered - Trade Unvouchered Beg Bal (event type) for EMEA Region ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting from FAH onprem. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | N/A | [5 empty] | Approved on Wed 2/2/2022 4:45 AM
[5 empty] | RTR-AHCS-378 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view Unvouchered – Direct Ship Unvouchered Beg Bal (Subledger) for EMEA Region ledgers | Must Have |  | Phase 1B only | 10-Not Required-Not Required-Not Required | Not Required | Not Required | Not Required |  | This is duplicate User story, Hence marked as 'Not required' AHCS Conversion to load Unvouchered – Direct Ship Unvouchered Beg Bal (AP Subledger) for EMEA Region ledgers | User should be review opening balances under Unvouchered – Direct Ship Unvouchered Beg Bal (event type) for EMEA Region ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting from FAH onprem. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | N/A | [5 empty] | Approved on Thu 2/3/2022 2:33 AM
[5 empty] | RTR-AHCS-379 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view Unvouchered - Return Unvouchered Beg Bal (Subledger) for EMEA Region ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV041 | AHCS Conversion to load Unvouchered - Return Unvouchered Beg Bal (AP Subledger) for EMEA Region ledgers | User should be review opening balances under Unvouchered - Return Unvouchered Beg Bal (event type) for EMEA Region ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting from FAH onprem. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | N/A | [5 empty] | Approved on Wed 2/2/2022 4:45 AM
[5 empty] | RTR-AHCS-380 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view Trade Receivable AR Beg Bal (Subledger) for EMEA Region ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV042 | AHCS Conversion to load Trade Receivable AR Beg Bal (Subledger) for EMEA Region ledgers | User should be review opening balances under Trade Receivable AR Beg Bal (event type) for EMEA Region ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting from FAH onprem. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | N/A | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-381 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view AR Cash Clearing Account AR Beg Bal (Subledger) for EMEA Region ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV042 | AHCS Conversion to load AR Cash Clearing Account AR Beg Bal (Subledger) for EMEA Region ledgers | User should be review opening balances under AR Cash Clearing Account AR Beg Bal (event type) for EMEA Region ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting from FAH onprem. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | N/A | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-382 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view Other Cash Clearing Account AR Beg Bal (Subledger) for EMEA Region ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV042 | AHCS Conversion to load Other Cash Clearing Account AR Beg Bal (Subledger) for EMEA Region ledgers | User should be review opening balances under Other Cash Clearing Account AR Beg Bal (event type) for EMEA Region ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting from FAH onprem. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | N/A | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-383 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view MF Intercompany – AR IC Beg Bal (Subledger) for EMEA Region ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV042 | AHCS Conversion to load MF Intercompany – AR IC Beg Bal (Subledger) for EMEA Region ledgers | User should be review opening balances under MF Intercompany – AR IC Beg Bal (event type) for EMEA Region ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting from FAH onprem. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | N/A | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-384 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view Trade Inventory Inv Beg Bal (Subledger) for EMEA Region ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV043 | AHCS Conversion to load Trade Inventory Inv Beg Bal (Subledger) for EMEA Region ledgers | User should be review opening balances under Trade Inventory Inv Beg Bal (event type) for EMEA Region ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting from FAH onprem. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | N/A | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-385 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view InTransit Stock Inv Beg Bal (Subledger) for EMEA Region ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV043 | AHCS Conversion to load InTransit Stock Inv Beg Bal (Subledger) for EMEA Region ledgers | User should be review opening balances under InTransit Stock Inv Beg Bal (event type) for EMEA Region ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting from FAH onprem. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | N/A | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-386 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view Intra Intransit Inv Beg Bal (Subledger) for EMEA Region ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV043 | AHCS Conversion to load Intra Intransit Inv Beg Bal (Subledger) for EMEA Region ledgers | User should be review opening balances under Intra Intransit Inv Beg Bal (event type) for EMEA Region ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting from FAH onprem. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | N/A | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-387 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view RTV Inv Beg Bal (Subledger) for EMEA Region ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV043 | AHCS Conversion to load RTV Inv Beg Bal (Subledger) for EMEA Region ledgers | User should be review opening balances under RTV Inv Beg Bal (event type) for EMEA Region ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting . Verify that manual file ties to loaded beginning balance. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | N/A | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-388 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view Warranty Inv Beg Bal (Subledger) for EMEA Region ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV043 | AHCS Conversion to load Warranty Inv Beg Bal (Subledger) for EMEA Region ledgers | User should be review opening balances under Warranty Inv Beg Bal (event type) for EMEA Region ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting . Verify that manual file ties to loaded beginning balance. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | N/A | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-389 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view Freight Accruals Inv Beg Bal (Subledger) for EMEA Region ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV043 | AHCS Conversion to load Freight Accruals Inv Beg Bal (Subledger) for EMEA Region ledgers | User should be review opening balances under Freight Accruals Inv Beg Bal (event type) for EMEA Region ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting from FAH onprem. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | N/A | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-390 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view Freight Claims Inv Beg Bal (Subledger) for EMEA Region ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV043 | AHCS Conversion to load Freight Claims Inv Beg Bal (Subledger) for EMEA Region ledgers | User should be review opening balances under Freight Claims Inv Beg Bal (event type) for EMEA Region ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting . Verify that manual file ties to loaded beginning balance. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | N/A | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-391 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view WIP (WO) Inv Beg Bal (Subledger) for EMEA Region ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV043 | AHCS Conversion to load WIP (WO) Inv Beg Bal (Subledger) for EMEA Region ledgers | User should be review opening balances under WIP (WO) Inv Beg Bal (event type) for EMEA Region ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting . Verify that manual file ties to loaded beginning balance. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | N/A | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-392 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view Kava Inv Beg Bal (Subledger) for EMEA Region ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV043 | AHCS Conversion to load Kava Inv Beg Bal (Subledger) for EMEA Region ledgers | User should be review opening balances under Kava Inv Beg Bal (event type) for EMEA Region ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting from FAH onprem. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | N/A | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-393 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view Unvouchered - Work Orders Unvouchered Beg Bal (Subledger) for EMEA Region ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV041 | AHCS Conversion to load Unvouchered - Work Orders Unvouchered Beg Bal (Inv Subledger) for EMEA Region ledgers | User should be review opening balances under Unvouchered - Work Orders Unvouchered Beg Bal (event type) for EMEA Region ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting from FAH onprem. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | N/A | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-394 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view Unvouchered – Intercompany Unvouchered Beg Bal (Subledger) for EMEA Region ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV041 | AHCS Conversion to load Unvouchered – Intercompany Unvouchered Beg Bal (Inv Subledger) for EMEA Region ledgers | User should be review opening balances under Unvouchered – Intercompany Unvouchered Beg Bal (event type) for EMEA Region ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting from FAH onprem. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | N/A | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-395 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view Unvouchered – Freight & Duty Unvouchered Beg Bal (Subledger) for EMEA Region ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV041 | AHCS Conversion to load Unvouchered – Freight & Duty Unvouchered Beg Bal (Inv Subledger) for EMEA Region ledgers | User should be review opening balances under Unvouchered – Freight & Duty Unvouchered Beg Bal (event type) for EMEA Region ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting from FAH onprem. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | N/A | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-396 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view Unvouchered – Trade Unvouchered Beg Bal (Subledger) for EMEA Region ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV043 | AHCS Conversion to load Unvouchered – Trade Unvouchered Beg Bal (Inv Subledger) for EMEA Region ledgers | User should be review opening balances under Unvouchered – Trade Unvouchered Beg Bal (event type) for EMEA Region ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting from FAH onprem. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | N/A | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-397 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view Unvouchered – Direct Ship Unvouchered Beg Bal (Subledger) for EMEA Region ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV041 | AHCS Conversion to load Unvouchered – Direct Ship Unvouchered Beg Bal (Inv Subledger) for EMEA Region ledgers | User should be review opening balances under Unvouchered – Direct Ship Unvouchered Beg Bal (event type) for EMEA Region ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting from FAH onprem. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | N/A | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-398 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view Unvouchered – Returns Unvouchered Beg Bal (Subledger) for EMEA Region ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV043 | AHCS Conversion to load Unvouchered – Returns Unvouchered Beg Bal (Inv Subledger) for EMEA Region ledgers | User should be review opening balances under Unvouchered – Returns Unvouchered Beg Bal (event type) for EMEA Region ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting from FAH onprem. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | N/A | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-399 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view Unvouchered – PPV/AP Variance Unvouchered Beg Bal (Subledger) for EMEA Region ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV043 | AHCS Conversion to load Unvouchered – PPV/AP Variance Unvouchered Beg Bal (Inv Subledger) for EMEA Region ledgers | User should be review opening balances under Unvouchered – PPV/AP Variance Unvouchered Beg Bal (event type) for EMEA Region ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting . Verify that manual file ties to loaded beginning balance. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | N/A | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-400 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view Trade Payable Invoice AP Beg Bal (Subledger) for CALA Region ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV041 | AHCS Conversion to load Trade Payable Invoice AP Beg Bal (Subledger) for CALA Region ledgers | User should be review opening balances under Trade Payable Invoice AP Beg Bal (event type) for CALA ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting from FAH onprem. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | n/a | N/A | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-401 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view MF Intercompany – AP IC Beg Bal (Subledger) for CALA Region ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV041 | AHCS Conversion to load MF Intercompany – AP IC Beg Bal (Subledger) for CALA Region ledgers | User should be review opening balances under MF Intercompany – AP IC Beg Bal (event type) for CALA ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting . Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | n/a | N/A | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-402 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view Unvouchered - Work Orders Unvouchered Beg Bal (Subledger) for CALA Region ledgers | Must Have |  | Phase 1B only | 10-Not Required-Not Required-Not Required | Not Required | Not Required | Not Required |  | AHCS Conversion to load Unvouchered - Work Orders Unvouchered Beg Bal (AP Subledger) for CALA Region ledgers. Duplicate user story | User should be review opening balances under Unvouchered - Work Orders Unvouchered Beg Bal (event type) for CALA ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting from FAH onprem. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | n/a | N/A | [5 empty] | Approved on Thu 2/3/2022 2:33 AM
[5 empty] | RTR-AHCS-403 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view Unvouchered – Intercompany Unvouchered Beg Bal (Subledger) for CALA Region ledgers | Must Have |  | Phase 1B only | 10-Not Required-Not Required-Not Required | Not Required | Not Required | Not Required |  | AHCS Conversion to load Unvouchered – Intercompany Unvouchered Beg Bal (AP Subledger) for CALA Region ledgers Duplicate user story | User should be review opening balances under Unvouchered – Intercompany Unvouchered Beg Bal (event type) for CALA ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting from FAH onprem. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | n/a | N/A | [5 empty] | Approved on Thu 2/3/2022 2:33 AM
[5 empty] | RTR-AHCS-404 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view Unvouchered – Freight & Duty Unvouchered Beg Bal (Subledger) for CALA Region ledgers | Must Have |  | Phase 1B only | 10-Not Required-Not Required-Not Required | Not Required | Not Required | Not Required |  | AHCS Conversion to load Unvouchered – Freight & Duty Unvouchered Beg Bal (AP Subledger) for CALA Region ledgers Duplicate user story | User should be review opening balances under Unvouchered – Freight & Duty Unvouchered Beg Bal (event type) for CALA ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting from FAH onprem. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | n/a | N/A | [5 empty] | Approved on Thu 2/3/2022 2:33 AM
[5 empty] | RTR-AHCS-405 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view Unvouchered - Trade Unvouchered Beg Bal (Subledger) for CALA Region ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV041 | AHCS Conversion to load Unvouchered - Trade Unvouchered Beg Bal (AP Subledger) for CALA Region ledgers | User should be review opening balances under Unvouchered - Trade Unvouchered Beg Bal (event type) for CALA ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting from FAH onprem. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | n/a | N/A | [5 empty] | Approved on Wed 2/2/2022 4:45 AM
[5 empty] | RTR-AHCS-406 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view Unvouchered – Direct Ship Unvouchered Beg Bal (Subledger) for CALA Region ledgers | Must Have |  | Phase 1B only | 10-Not Required-Not Required-Not Required | Not Required | Not Required | Not Required |  | AHCS Conversion to load Unvouchered – Direct Ship Unvouchered Beg Bal (AP Subledger) for CALA Region ledgers Duplicate user story | User should be review opening balances under Unvouchered – Direct Ship Unvouchered Beg Bal (event type) for CALA ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting from FAH onprem. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | n/a | N/A | [5 empty] | Approved on Thu 2/3/2022 2:33 AM
[5 empty] | RTR-AHCS-407 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view Unvouchered - Return Unvouchered Beg Bal (Subledger) for CALA Region ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV041 | AHCS Conversion to load Unvouchered - Return Unvouchered Beg Bal (AP Subledger) for CALA Region ledgers | User should be review opening balances under Unvouchered - Return Unvouchered Beg Bal (event type) for CALA ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting from FAH onprem. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | n/a | N/A | [5 empty] | Approved on Wed 2/2/2022 4:45 AM
[5 empty] | RTR-AHCS-408 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view Trade Receivable AR Beg Bal (Subledger) for CALA Region ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV042 | AHCS Conversion to load Trade Receivable AR Beg Bal (Subledger) for CALA Region ledgers | User should be review opening balances under Trade Receivable AR Beg Bal (event type) for CALA ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting from FAH onprem. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | n/a | N/A | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-409 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view MF Intercompany – AR IC Beg Bal (Subledger) for CALA Region ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV042 | AHCS Conversion to load MF Intercompany – AR IC Beg Bal (Subledger) for CALA Region ledgers | User should be review opening balances under MF Intercompany – AR IC Beg Bal (event type) for CALA ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting . Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | n/a | N/A | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-410 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view Trade Inventory Inv Beg Bal (Subledger) for CALA Region ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV043 | AHCS Conversion to load Trade Inventory Inv Beg Bal (Subledger) for CALA Region ledgers | User should be review opening balances under Trade Inventory Inv Beg Bal (event type) for CALA ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting from FAH onprem. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | n/a | N/A | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-411 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view InTransit Stock Inv Beg Bal (Subledger) for CALA Region ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV043 | AHCS Conversion to load InTransit Stock Inv Beg Bal (Subledger) for CALA Region ledgers | User should be review opening balances under InTransit Stock Inv Beg Bal (event type) for CALA ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting from FAH onprem. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | n/a | N/A | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-412 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view Intra Intransit Inv Beg Bal (Subledger) for CALA Region ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV043 | AHCS Conversion to load Intra Intransit Inv Beg Bal (Subledger) for CALA Region ledgers | User should be review opening balances under Intra Intransit Inv Beg Bal (event type) for CALA ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting from FAH onprem. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | n/a | N/A | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-413 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view RTV Inv Beg Bal (Subledger) for CALA Region ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV043 | AHCS Conversion to load RTV Inv Beg Bal (Subledger) for CALA Region ledgers | User should be review opening balances under RTV Inv Beg Bal (event type) for CALA ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting . Verify that manual file ties to loaded beginning balance. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | n/a | N/A | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-414 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view Warranty Inv Beg Bal (Subledger) for CALA Region ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV043 | AHCS Conversion to load Warranty Inv Beg Bal (Subledger) for CALA Region ledgers | User should be review opening balances under Warranty Inv Beg Bal (event type) for CALA ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting . Verify that manual file ties to loaded beginning balance. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | n/a | N/A | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-415 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view Freight Accruals Inv Beg Bal (Subledger) for CALA Region ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV043 | AHCS Conversion to load Freight Accruals Inv Beg Bal (Subledger) for CALA Region ledgers | User should be review opening balances under Freight Accruals Inv Beg Bal (event type) for CALA ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting . Verify that manual file ties to loaded beginning balance. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | n/a | N/A | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-416 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view Freight Claims Inv Beg Bal (Subledger) for CALA Region ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV043 | AHCS Conversion to load Freight Claims Inv Beg Bal (Subledger) for CALA Region ledgers | User should be review opening balances under Freight Claims Inv Beg Bal (event type) for CALA ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting . Verify that manual file ties to loaded beginning balance. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | n/a | N/A | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-417 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view WIP (WO) Inv Beg Bal (Subledger) for CALA Region ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV043 | AHCS Conversion to load WIP (WO) Inv Beg Bal (Subledger) for CALA Region ledgers | User should be review opening balances under WIP (WO) Inv Beg Bal (event type) for CALA ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting . Verify that manual file ties to loaded beginning balance. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | n/a | N/A | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-418 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view Kava Inv Beg Bal (Subledger) for CALA Region ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV043 | AHCS Conversion to load Kava Inv Beg Bal (Subledger) for CALA Region ledgers | User should be review opening balances under Kava Inv Beg Bal (event type) for CALA ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting from FAH onprem. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | n/a | N/A | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-419 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view Unvouchered - Work Orders Unvouchered Beg Bal (Subledger) for CALA Region ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV041 | AHCS Conversion to load Unvouchered - Work Orders Unvouchered Beg Bal (Inv Subledger) for CALA Region ledgers | User should be review opening balances under Unvouchered - Work Orders Unvouchered Beg Bal (event type) for CALA ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting from FAH onprem. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | n/a | N/A | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-420 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view Unvouchered – Intercompany Unvouchered Beg Bal (Subledger) for CALA Region ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV041 | AHCS Conversion to load Unvouchered – Intercompany Unvouchered Beg Bal (Inv Subledger) for CALA Region ledgers | User should be review opening balances under Unvouchered – Intercompany Unvouchered Beg Bal (event type) for CALA ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting from FAH onprem. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | n/a | N/A | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-421 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view Unvouchered – Freight & Duty Unvouchered Beg Bal (Subledger) for CALA Region ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV041 | AHCS Conversion to load Unvouchered – Freight & Duty Unvouchered Beg Bal (Inv Subledger) for CALA Region ledgers | User should be review opening balances under Unvouchered – Freight & Duty Unvouchered Beg Bal (event type) for CALA ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting from FAH onprem. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | n/a | N/A | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-422 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view Unvouchered – Trade Unvouchered Beg Bal (Subledger) for CALA Region ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV043 | AHCS Conversion to load Unvouchered – Trade Unvouchered Beg Bal (Inv Subledger) for CALA Region ledgers | User should be review opening balances under Unvouchered – Trade Unvouchered Beg Bal (event type) for CALA ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting from FAH onprem. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | n/a | N/A | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-423 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view Unvouchered – Direct Ship Unvouchered Beg Bal (Subledger) for CALA Region ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV041 | AHCS Conversion to load Unvouchered – Direct Ship Unvouchered Beg Bal (Inv Subledger) for CALA Region ledgers | User should be review opening balances under Unvouchered – Direct Ship Unvouchered Beg Bal (event type) for CALA ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting from FAH onprem. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | n/a | N/A | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-424 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view Unvouchered – Returns Unvouchered Beg Bal (Subledger) for CALA Region ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV043 | AHCS Conversion to load Unvouchered – Returns Unvouchered Beg Bal (Inv Subledger) for CALA Region ledgers | User should be review opening balances under Unvouchered – Returns Unvouchered Beg Bal (event type) for CALA ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting from FAH onprem. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | n/a | N/A | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-425 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view Unvouchered – PPV/AP Variance Unvouchered Beg Bal (Subledger) for CALA Region ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV043 | AHCS Conversion to load Unvouchered – PPV/AP Variance Unvouchered Beg Bal (Inv Subledger) for CALA Region ledgers | User should be review opening balances under Unvouchered – PPV/AP Variance Unvouchered Beg Bal (event type) for CALA ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting . Verify that manual file ties to loaded beginning balance. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | n/a | N/A | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-426 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view Unvouchered – Other Material Unvouchered Beg Bal (Subledger) for CALA Region ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV043 | AHCS Conversion to load Unvouchered – Other Material Unvouchered Beg Bal (Inv Subledger) for CALA Region ledgers | User should be review opening balances under Unvouchered – Other Material Unvouchered Beg Bal (event type) for CALA ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting . Verify that manual file ties to loaded beginning balance. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | n/a | N/A | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-427 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view Trade Payable Invoice AP Beg Bal (Subledger) for APAC Region ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV041 | AHCS Conversion to load Trade Payable Invoice AP Beg Bal (Subledger) for APAC Region ledgers | User should be review opening balances under Trade Payable Invoice AP Beg Bal (event type) for APAC ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting from FAH onprem. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | n/a | Boon Hui | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-428 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view MF Intercompany – AP IC Beg Bal (Subledger) for APAC Region ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV041 | AHCS Conversion to load MF Intercompany – AP IC Beg Bal (Subledger) for APAC Region ledgers | User should be review opening balances under MF Intercompany – AP IC Beg Bal (event type) for APAC ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting . Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | n/a | Boon Hui | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-429 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view Unvouchered – Work Orders, Intercompany, Freight & Duty, Trade, Direct Ship, Return Unvouchered Beg Bal (Subledger) for APAC Region ledgers | Must Have |  | Phase 1B only | 10-Not Required-Not Required-Not Required | Not Required | Not Required | Not Required |  | This is duplicate User story, hence marked as 'Not required' AHCS Conversion to load Unvouchered – Work Orders, Intercompany, Freight & Duty, Trade, Direct Ship, Return Unvouchered Beg Bal (AP Subledger) for APAC Region ledgers Duplicate user story | User should be review opening balances under Unvouchered – Work Orders, Intercompany, Freight & Duty, Trade, Direct Ship, Return Unvouchered Beg Bal (event type) for APAC ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting . Verify that manual file ties to loaded beginning balance. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | n/a | Boon Hui | [5 empty] | Approved on Thu 2/3/2022 2:33 AM
[5 empty] | RTR-AHCS-430 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view Trade Receivable AR Beg Bal (Subledger) for APAC Region ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV042 | AHCS Conversion to load Trade Receivable AR Beg Bal (Subledger) for APAC Region ledgers | User should be review opening balances under Trade Receivable AR Beg Bal (event type) for APAC ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting from FAH onprem. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | n/a | Boon Hui | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-431 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view MF Intercompany – AR IC Beg Bal (Subledger) for APAC Region ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV042 | AHCS Conversion to load MF Intercompany – AR IC Beg Bal (Subledger) for APAC Region ledgers | User should be review opening balances under MF Intercompany – AR IC Beg Bal (event type) for APAC ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting . Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | n/a | Boon Hui | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-432 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view Trade Inventory Inv Beg Bal (Subledger) for APAC Region ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV043 | AHCS Conversion to load Trade Inventory Inv Beg Bal (Subledger) for APAC Region ledgers | User should be review opening balances under Trade Inventory Inv Beg Bal (event type) for APAC ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting from FAH onprem. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | n/a | Boon Hui | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-433 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view InTransit Stock Inv Beg Bal (Subledger) for APAC Region ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV043 | AHCS Conversion to load InTransit Stock Inv Beg Bal (Subledger) for APAC Region ledgers | User should be review opening balances under InTransit Stock Inv Beg Bal (event type) for APAC ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting from FAH onprem. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | n/a | Boon Hui | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-434 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view Intra Intransit Inv Beg Bal (Subledger) for APAC Region ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV043 | AHCS Conversion to load Intra Intransit Inv Beg Bal (Subledger) for APAC Region ledgers | User should be review opening balances under Intra Intransit Inv Beg Bal (event type) for APAC ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting from FAH onprem. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | n/a | Boon Hui | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-435 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view RTV Inv Beg Bal (Subledger) for APAC Region ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV043 | AHCS Conversion to load RTV Inv Beg Bal (Subledger) for APAC Region ledgers | User should be review opening balances under RTV Inv Beg Bal (event type) for APAC ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting . Verify that manual file ties to loaded beginning balance. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | n/a | Boon Hui | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-436 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view Warranty Inv Beg Bal (Subledger) for APAC Region ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV043 | AHCS Conversion to load Warranty Inv Beg Bal (Subledger) for APAC Region ledgers | User should be review opening balances under Warranty Inv Beg Bal (event type) for APAC ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting . Verify that manual file ties to loaded beginning balance. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | n/a | Boon Hui | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-437 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view Freight Accruals Inv Beg Bal (Subledger) for APAC Region ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV043 | AHCS Conversion to load Freight Accruals Inv Beg Bal (Subledger) for APAC Region ledgers | User should be review opening balances under Freight Accruals Inv Beg Bal (event type) for APAC ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting . Verify that manual file ties to loaded beginning balance. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | n/a | Boon Hui | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-438 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view Freight Claims Inv Beg Bal (Subledger) for APAC Region ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV043 | AHCS Conversion to load Freight Claims Inv Beg Bal (Subledger) for APAC Region ledgers | User should be review opening balances under Freight Claims Inv Beg Bal (event type) for APAC ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting . Verify that manual file ties to loaded beginning balance. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | n/a | Boon Hui | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-439 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view WIP (WO) Inv Beg Bal (Subledger) for APAC Region ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV043 | AHCS Conversion to load WIP (WO) Inv Beg Bal (Subledger) for APAC Region ledgers | User should be review opening balances under WIP (WO) Inv Beg Bal (event type) for APAC ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting . Verify that manual file ties to loaded beginning balance. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | n/a | Boon Hui | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-440 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view Kava Inv Beg Bal (Subledger) for APAC Region ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV043 | AHCS Conversion to load Kava Inv Beg Bal (Subledger) for APAC Region ledgers | User should be review opening balances under Kava Inv Beg Bal (event type) for APAC ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting from FAH onprem. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | n/a | Boon Hui | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-441 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view Unvouchered – Work Orders, Intercompany, Freight & Duty, Trade, Direct Ship, Return Unvouchered Beg Bal (Subledger) for APAC Region ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV043 | AHCS Conversion to load Unvouchered – Work Orders, Intercompany, Freight & Duty, Trade, Direct Ship, Return Unvouchered Beg Bal (Inv Subledger) for APAC Region ledgers | User should be review opening balances under Unvouchered – Work Orders, Intercompany, Freight & Duty, Trade, Direct Ship, Return Unvouchered Beg Bal (event type) for APAC ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting . Verify that manual file ties to loaded beginning balance. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | n/a | Boon Hui | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-442 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view Trade Payable Invoice AP Beg Bal (Subledger) Local GAAP ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV041 | AHCS Conversion to load Trade Payable Invoice AP Beg Bal (Subledger) for Local GAAP ledgers | User should be review opening balances under Trade Payable Invoice AP Beg Bal (event type) for Local GAAP ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting from FAH onprem. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | N/A | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-443 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view AP Cash Clearing AP Beg Bal (Subledger) Local GAAP ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV041 | AHCS Conversion to load AP Cash Clearing AP Beg Bal (Subledger) for Local GAAP ledgers | User should be review opening balances under AP Cash Clearing AP Beg Bal (event type) for Local GAAP ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting from FAH onprem. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | N/A | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-444 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view MF Intercompany – AP IC Beg Bal (Subledger) Local GAAP ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV041 | AHCS Conversion to load MF Intercompany – AP IC Beg Bal (Subledger) for Local GAAP ledgers | User should be review opening balances under MF Intercompany – AP IC Beg Bal (event type) for Local GAAP ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting from FAH onprem. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | N/A | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-445 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view Unvouchered - Work Orders Unvouchered Beg Bal (Subledger) Local GAAP ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV041 | AHCS Conversion to load Unvouchered - Work Orders Unvouchered Beg Bal (AP Subledger) for Local GAAP ledgers | User should be review opening balances under Unvouchered - Work Orders Unvouchered Beg Bal (event type) for Local GAAP ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting from FAH onprem. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | N/A | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-446 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view Unvouchered – Intercompany Unvouchered Beg Bal (Subledger) Local GAAP ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV041 | AHCS Conversion to load Unvouchered – Intercompany Unvouchered Beg Bal (AP Subledger) for Local GAAP ledgers | User should be review opening balances under Unvouchered – Intercompany Unvouchered Beg Bal (event type) for Local GAAP ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting from FAH onprem. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | N/A | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-447 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view Unvouchered – Freight & Duty Unvouchered Beg Bal (Subledger) Local GAAP ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV041 | AHCS Conversion to load Unvouchered – Freight & Duty Unvouchered Beg Bal (AP Subledger) for Local GAAP ledgers | User should be review opening balances under Unvouchered – Freight & Duty Unvouchered Beg Bal (event type) for Local GAAP ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting from FAH onprem. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | N/A | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-448 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view Unvouchered - Trade Unvouchered Beg Bal (Subledger) Local GAAP ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV041 | AHCS Conversion to load Unvouchered - Trade Unvouchered Beg Bal (AP Subledger) for Local GAAP ledgers | User should be review opening balances under Unvouchered - Trade Unvouchered Beg Bal (event type) for Local GAAP ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting from FAH onprem. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | N/A | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-449 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view Unvouchered – Direct Ship Unvouchered Beg Bal (Subledger) Local GAAP ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV041 | AHCS Conversion to load Unvouchered – Direct Ship Unvouchered Beg Bal (AP Subledger) for Local GAAP ledgers | User should be review opening balances under Unvouchered – Direct Ship Unvouchered Beg Bal (event type) for Local GAAP ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting from FAH onprem. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | N/A | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-450 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view Unvouchered - Return Unvouchered Beg Bal (Subledger) Local GAAP ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV041 | AHCS Conversion to load Unvouchered - Return Unvouchered Beg Bal (AP Subledger) for Local GAAP ledgers | User should be review opening balances under Unvouchered - Return Unvouchered Beg Bal (event type) for Local GAAP ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting from FAH onprem. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | N/A | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-451 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view Trade Receivable AR Beg Bal (Subledger) Local GAAP ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV042 | AHCS Conversion to load Trade Receivable AR Beg Bal (Subledger) for Local GAAP ledgers | User should be review opening balances under Trade Receivable AR Beg Bal (event type) for Local GAAP ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting from FAH onprem. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | N/A | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-452 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view AR Cash Clearing Account AR Beg Bal (Subledger) Local GAAP ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV042 | AHCS Conversion to load AR Cash Clearing Account AR Beg Bal (Subledger) for Local GAAP ledgers | User should be review opening balances under AR Cash Clearing Account AR Beg Bal (event type) for Local GAAP ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting from FAH onprem. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | N/A | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-453 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view Other Cash Clearing Account AR Beg Bal (Subledger) Local GAAP ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV042 | AHCS Conversion to load Other Cash Clearing Account AR Beg Bal (Subledger) for Local GAAP ledgers | User should be review opening balances under Other Cash Clearing Account AR Beg Bal (event type) for Local GAAP ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting from FAH onprem. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | N/A | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-454 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view MF Intercompany – AR IC Beg Bal (Subledger) Local GAAP ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV042 | AHCS Conversion to load MF Intercompany – AR IC Beg Bal (Subledger) for Local GAAP ledgers | User should be review opening balances under MF Intercompany – AR IC Beg Bal (event type) for Local GAAP ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting from FAH onprem. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | N/A | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-455 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view Trade Inventory Inv Beg Bal (Subledger) Local GAAP ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV043 | AHCS Conversion to load Trade Inventory Inv Beg Bal (Subledger) for Local GAAP ledgers | User should be review opening balances under Trade Inventory Inv Beg Bal (event type) for Local GAAP ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting from FAH onprem. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | N/A | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-456 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view InTransit Stock Inv Beg Bal (Subledger) Local GAAP ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV043 | AHCS Conversion to load InTransit Stock Inv Beg Bal (Subledger) for Local GAAP ledgers | User should be review opening balances under InTransit Stock Inv Beg Bal (event type) for Local GAAP ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting from FAH onprem. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | N/A | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-457 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view Intra Intransit Inv Beg Bal (Subledger) Local GAAP ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV043 | AHCS Conversion to load Intra Intransit Inv Beg Bal (Subledger) for Local GAAP ledgers | User should be review opening balances under Intra Intransit Inv Beg Bal (event type) for Local GAAP ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting from FAH onprem. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | N/A | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-458 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view RTV Inv Beg Bal (Subledger) Local GAAP ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV043 | AHCS Conversion to load RTV Inv Beg Bal (Subledger) for Local GAAP ledgers | User should be review opening balances under RTV Inv Beg Bal (event type) for Local GAAP ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting . Verify that manual file ties to loaded beginning balance. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | N/A | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-459 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view Warranty Inv Beg Bal (Subledger) Local GAAP ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV043 | AHCS Conversion to load Warranty Inv Beg Bal (Subledger) for Local GAAP ledgers | User should be review opening balances under Warranty Inv Beg Bal (event type) for Local GAAP ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting . Verify that manual file ties to loaded beginning balance. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | N/A | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-460 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view Freight Accruals Inv Beg Bal (Subledger) Local GAAP ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV043 | AHCS Conversion to load Freight Accruals Inv Beg Bal (Subledger) for Local GAAP ledgers | User should be review opening balances under Freight Accruals Inv Beg Bal (event type) for Local GAAP ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting from FAH onprem. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | N/A | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-461 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view Freight Claims Inv Beg Bal (Subledger) Local GAAP ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV043 | AHCS Conversion to load Freight Claims Inv Beg Bal (Subledger) for Local GAAP ledgers | User should be review opening balances under Freight Claims Inv Beg Bal (event type) for Local GAAP ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting . Verify that manual file ties to loaded beginning balance. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | N/A | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-462 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view WIP (WO) Inv Beg Bal (Subledger) Local GAAP ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV043 | AHCS Conversion to load WIP (WO) Inv Beg Bal (Subledger) for Local GAAP ledgers | User should be review opening balances under WIP (WO) Inv Beg Bal (event type) for Local GAAP ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting . Verify that manual file ties to loaded beginning balance. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | N/A | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-463 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view Kava Inv Beg Bal (Subledger) Local GAAP ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV043 | AHCS Conversion to load Kava Inv Beg Bal (Subledger) for Local GAAP ledgers | User should be review opening balances under Kava Inv Beg Bal (event type) for Local GAAP ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting from FAH onprem. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | N/A | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-464 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view Unvouchered - Work Orders Unvouchered Beg Bal (Subledger) Local GAAP ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV041 | AHCS Conversion to load Unvouchered - Work Orders Unvouchered Beg Bal (Inv Subledger) for Local GAAP ledgers | User should be review opening balances under Unvouchered - Work Orders Unvouchered Beg Bal (event type) for Local GAAP ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting from FAH onprem. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | N/A | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-465 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view Unvouchered – Intercompany Unvouchered Beg Bal (Subledger) Local GAAP ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV041 | AHCS Conversion to load Unvouchered – Intercompany Unvouchered Beg Bal (Inv Subledger) for Local GAAP ledgers | User should be review opening balances under Unvouchered – Intercompany Unvouchered Beg Bal (event type) for Local GAAP ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting from FAH onprem. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | N/A | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-466 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view Unvouchered – Freight & Duty Unvouchered Beg Bal (Subledger) Local GAAP ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV041 | AHCS Conversion to load Unvouchered – Freight & Duty Unvouchered Beg Bal (Inv Subledger) for Local GAAP ledgers | User should be review opening balances under Unvouchered – Freight & Duty Unvouchered Beg Bal (event type) for Local GAAP ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting from FAH onprem. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | N/A | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-467 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view Unvouchered – Trade Unvouchered Beg Bal (Subledger) Local GAAP ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV043 | AHCS Conversion to load Unvouchered – Trade Unvouchered Beg Bal (Inv Subledger) for Local GAAP ledgers | User should be review opening balances under Unvouchered – Trade Unvouchered Beg Bal (event type) for Local GAAP ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting from FAH onprem. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | N/A | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-468 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view Unvouchered – Direct Ship Unvouchered Beg Bal (Subledger) Local GAAP ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV041 | AHCS Conversion to load Unvouchered – Direct Ship Unvouchered Beg Bal (Inv Subledger) for Local GAAP ledgers | User should be review opening balances under Unvouchered – Direct Ship Unvouchered Beg Bal (event type) for Local GAAP ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting from FAH onprem. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | N/A | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-469 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want the ability to view Unvouchered – Returns Unvouchered Beg Bal (Subledger) Local GAAP ledgers | Must Have |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV043 | AHCS Conversion to load Unvouchered – Returns Unvouchered Beg Bal (Inv Subledger) for Local GAAP ledgers | User should be review opening balances under Unvouchered – Returns Unvouchered Beg Bal (event type) for Local GAAP ledgers | Validate Legacy System ending balance ties to AHCS Beginning Balance through reporting from FAH onprem. Verify that there are no differences.Validate that Beginning balance is loaded through create accounting with a status of Final. Validate that Beginning balance event type did not load to GL by reviewing the transfer to GL status in journal panel in AHCS. |  |  | Approved | Ian | 2022-01-24 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | N/A | [5 empty] | Approved on Tue 2/1/2022 10:02 AM
| CSTONE-6189 | CSTONE-6298 |  |  | RTR-AHCS-470 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As IT Administrator , I want the ability to send Eclipse bad files from Middleware | Must Have |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT124 | Middleware should send Eclipse bad files with email notification | User should be able to get bad files data with email notification for Eclipse | All error transactions for Eclipse are sent back to user via email notification |  |  | Approved | Sijo John |  |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte | [11 empty] | Approved on Wed 2/2/2022 4:45 AM
| Not in Jira | CSTONE-6299 |  |  | RTR-AHCS-471 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As IT Administrator , I want the ability to send PS FA bad files from Middleware | Must Have |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT184 | Middleware should send email notification for PS FA bad files | User should be able to get bad files data with email notification for PS FA | All error transactions for Peoplesoft FA are sent back to user via email notification |  |  | Approved | sijo John |  |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte | [11 empty] | Approved on Wed 2/2/2022 4:45 AM
| CSTONE-6252 |  |  |  | RTR-AHCS-472 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As IT Administrator , I want the ability to send Treasury bad files from Middleware | Must Have |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT045 | Middleware should send email notification for Treasury bad files | User should be able to get bad files data with email notification for Treasury | All error transactions for Treasury are sent back to user via email notification |  |  | Approved | Sijo John |  |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte | [11 empty] | Approved on Wed 2/2/2022 4:45 AM
| Not in Jira |  |  |  | RTR-AHCS-473 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As IT Administrator , I want the ability to send Leases bad files from Middleware | Must Have |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT020 | Middleware should send email notification for Leases bad files | User should be able to get bad files data with email notification for Leases | All error transactions for Leases are sent back to user via email notification |  |  | Approved | Sijo John |  |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte | [11 empty] | Approved on Wed 2/2/2022 4:45 AM
| CSTONE-6190 | CSTONE-6300 |  |  | RTR-AHCS-474 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As IT Administrator , I want the ability to send SXE bad files from Middleware | Must Have |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT123 | Middleware should send email notification for SXE bad files | User should be able to get bad files data with email notification for SXE | All error transactions for SXE are sent back to user via email notification |  |  | Approved | Sijo John |  |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte | [11 empty] | Approved on Wed 2/2/2022 4:45 AM
| CSTONE-6253 |  |  |  | RTR-AHCS-475 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As IT Administrator , I want the ability to send Cresus bad files from Middleware | Must Have |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT123 INT124 | Middleware should send email notification for Cresus bad files | User should be able to get bad files data with email notification for Cresus | All error transactions for Cresus are sent back to user via email notification |  |  | Approved | Sijo John |  |  | Interface | Sprint Manually overridden | RTR | RTR-AHCS | AHCS | Deloitte | [11 empty] | Approved on Wed 2/2/2022 4:45 AM
[5 empty] | RTR-AHCS-476 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report that shows the 'Intercompany AR Invoice Statement Summary (Trade) (Material) For the Year Only' In French Language | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Gap | Build | Report | RPT186 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' 02/04 - Based on accounting hub data only. Current Report Name in Legacy FAH- 'Intercompany AR Invoice Statement Summary (Trade)' in French Language | User should be able to generate a report that shows Intercompany AR Invoice Statement Summary (Trade) in French Language | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs. |  |  | Approved | Ian | 2022-01-31 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte | [11 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-477 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report that shows the 'Intercompany AR Invoice Statement Summary (Trade) (Material) For the Year Only' In German Language | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Gap | Build | Report | RPT186 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' 02/04 - Based on accounting hub data only. Current Report Name in Legacy FAH- 'Intercompany AR Invoice Statement Summary (Trade)' in German Language | User should be able to generate a report that shows Intercompany AR Invoice Statement Summary (Trade) in German Language | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs. |  |  | Approved | Ian | 2022-01-31 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte | [11 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-478 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report that shows the 'Intercompany AR Invoice Statement Summary (Trade) For the Year Only' In Spanish Language | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Gap | Build | Report | RPT186 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' 02/04 - Based on accounting hub data only. Current Report Name in Legacy FAH- 'Intercompany AR Invoice Statement Summary (Trade)' in Spanish Language | User should be able to generate a report that shows Intercompany AR Invoice Statement Summary (Trade) in Spanish Language | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs. |  |  | Approved | Ian | 2022-01-31 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte | [11 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-479 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report that shows the 'Intercompany AR Invoice Statement Summary (Trade) (Material) For the Year Only' In Polish Language | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Gap | Build | Report | RPT186 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' 02/04 - Based on accounting hub data only. Current Report Name in Legacy FAH- 'Intercompany AR Invoice Statement Summary (Trade)' ) in Polish Language | User should be able to generate a report that shows Intercompany AR Invoice Statement Summary (Trade) in Polish Language | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs. |  |  | Approved | Ian | 2022-01-31 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte | [11 empty] | Approved on Tue 2/1/2022 10:02 AM
[5 empty] | RTR-AHCS-480 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As GL Accountant, I want the ability to generate a report that shows the 'Intercompany AR Invoice Statement Summary (Trade) For the Year Only' In Arabic Language | Must Have |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Gap | Build | Report | RPT186 | 04/21 NG : Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' 02/04 - Based on accounting hub data only. Current Report Name in Legacy FAH- 'Intercompany AR Invoice Statement Summary (Trade)' in Arabic Language | User should be able to generate a report that shows Intercompany AR Invoice Statement Summary (Trade) in Arabic Language | Verify able to run report based on specific parameters. Review for completeness and verify that layout and data agrees with report specs. |  |  | Approved | Ian | 2022-01-31 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte | [11 empty] | Approved on Tue 2/1/2022 10:02 AM
|  | Not in Jira |  |  | RTR-AHCS-481 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want review accounted data in MF AR and MF AP Subledgers in AHCS for Cresus Interface along with Supporting Reference and other details. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | As user, I want review accounted data in AHCS for Cresus Interface along with Supporting Reference and other details. | Verify transactions are accounted correctly in relevant subledger with appropriate attributes | Verified that total amount entered and accounted in MF AR and MF AP Subledgers in AHCS is denoted with status of final through review subledger journal panel. Validate that total amounts in AHCS ties to total from source application through reporting. Validate that items were reflected correctly in AHCS based on business and accounting rules. Verified that able to review detail transactions at line level through supporting references a per business design. |  |  | Approved | Ian | 2022-02-03 |  | #REF! |  | RTR | RTR-AHCS | AHCS | Deloitte |  |  |  |  | Bhim | N/A | N/A | N/A |  |  |  | Approved on Mon 2/7/2022 7:10 PM | 25
[5 empty] | RTR-AHCS-482 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As a IT Administrator, I need a process to ensure to process inbound file from CloseOut tool in new COA format. | Must Have |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT241 INT242 EXT127 | Based on Closeout tool meeting decision business is inclined to option1 "Retrofit current Close out tool" as part of which new inbound file from CloseOut tool in new COA format. | Inbound interface to get records from closeout tool for processing entries in new COA format. | All attributes defined in Close out data model are brought in AHCS and detailed information is available in AHCS |  |  | Approved | Sijo John |  |  | Interface | Sprint Manually overridden | RTR | RTR-AHCS | AHCS | Deloitte | [10 empty] | 2/3/2022 Sijo | Approved on Thu 2/3/2022 2:33 AM | 31
[5 empty] | RTR-AHCS-483 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | FTI, FII, ISI & IRI Account to Department Mapping | Must Have |  | Phase 1B only | 1-Fit-Configuration-Functional |  |  |  |  | FTI, FII, ISI & IRI have transactions previously posted to 838200000 go to a different department then the mapping rule there was discussion if the business rule was set up to look at the COA mapping. In Dept mapping rule 3 - anything that goes to account 838200000 should have department 1223. - INC2691575
[5 empty] | RTR-IC-068 |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | Intercompany AR Invoices Conversion - North America with EMEA (FAH) |  |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV015 | Replace RTR-IC-056 with User Story specific to creation of NA conversion upload template from successfully loaded EMEA AP conversion files. |  |  |  | Sprint 10 | Approved | Rita Nanni |  |  | #REF! |  | RTR | RTR-GL | IC | Deloitte |  |  | Ian/Vitaliy | [8 empty] | Update to 1B User Stories
[5 empty] | RTR-IC-069 |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | Intercompany AR Invoices Conversion - North America with CALA (Excel) |  |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV015 | Replace RTR-IC-056 with User Story specific to creation of NA conversion upload template from successfully loaded CALA AP conversion files. |  |  |  | Sprint 10 | Approved | Rita Nanni |  |  | #REF! |  | RTR | RTR-GL | IC | Deloitte |  |  | Ian/Vitaliy | [8 empty] | Update to 1B User Stories
[5 empty] | RTR-IC-070 |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | Intercompany AR Invoices Conversion - North America with APAC (ICDB) |  |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV015 | Replace RTR-IC-056 with User Story specific to creation of NA conversion upload template from successfully loaded APAC AP conversion files. |  |  |  | Sprint 10 | Approved | Rita Nanni |  |  | #REF! |  | RTR | RTR-GL | IC | Deloitte |  |  | Ian/Vitaliy | [8 empty] | Update to 1B User Stories
[5 empty] | RTR-IC-071 |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | Intercompany AP Invoices Conversion (non-material) - North America with EMEA (FAH) |  |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV016 | Replace RTR-IC-056 with User Story specific to creation of NA conversion upload template from successfully loaded EMEA AR conversion files. |  |  |  | Sprint 10 | Approved | Rita Nanni |  |  | #REF! |  | RTR | RTR-GL | IC | Deloitte |  |  | Ian/Vitaliy | [8 empty] | Update to 1B User Stories
[5 empty] | RTR-IC-072 |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | Intercompany AP Invoices Conversion (non-material) - North America with CALA (Excel) |  |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV016 | Replace RTR-IC-056 with User Story specific to creation of NA conversion upload template from successfully loaded CALA AR conversion files. |  |  |  | Sprint 10 | Approved | Rita Nanni |  |  | #REF! |  | RTR | RTR-GL | IC | Deloitte |  |  | Ian/Vitaliy | [8 empty] | Update to 1B User Stories
[5 empty] | RTR-IC-073 |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | Intercompany AP Invoices Conversion (non-material) - North America with APAC (ICDB) |  |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV016 | Replace RTR-IC-056 with User Story specific to creation of NA conversion upload template from successfully loaded APAC AR conversion files. |  |  |  | Sprint 10 | Approved | Rita Nanni |  |  | #REF! |  | RTR | RTR-GL | IC | Deloitte |  |  | Ian/Vitaliy | [8 empty] | Update to 1B User Stories
[5 empty] | REP-FSG-RTR-GL-013L |  | Record to Report
[5 empty] | RTR-GL-164 |  | Record to Report | Manage General Ledger Accounting | Maintain Chart of Accounts | COA Engine - Validate Cache Table |  |  | Phase 1A+1B
[5 empty] | RTR-IC-074 |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As an Intercompany User, it is important to note that Non-Trade and Trade transactions cannot be paid together. Therefore, please ensure that when paying from the Cornerstone lense, Invoices are restricted accordingly. |  |  | Phase 1B
[5 empty] | RTR-IC-075 |  | Record to Report | Manage Intercompany Invoicing | Process Intercompany AR Invoices | View Image under Transaction Workbench is showing Tax Invoice format for Trade Invoices |  |  | Phase 1B | [5 empty] | Please restrict the Tax Invoice format under Transaction Workbench > View Image section limited to the Global Intercompany Invoice source only. (INC2679223)
Note on R84: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Marked Not Required as business has striked thru the user story
Note on O230: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: CNV002 is descoped and currency rate conversion is not required for reporting ledger
Note on T320: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: RTR-AHCS-118
Note on T321: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: RTR-AHCS-118
Note on O432: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Changed to "Not Required" from "Gap-Build-Conversions" after Lean Spec discussions. 01/31/2022
Note on F498: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: ID already used in another User Story Reply: Changed to RTR-GL-164 as original number was repeated RTR-GL-148
Note on F499: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: ID already used in another User Story Reply: Changed to RTR-GL-165 as original number was repeated RTR-GL-149

## 2. Deliver Phase User Stories
Aggregate Epic ID | JIRA ID Functional | JIRA ID Tech Build | JIRA ID TUT/FUT | JIRA ID | Unique ID | Updated Unique ID (BI Only) | L0 | L1 | L2 | User Story | Priority | Country | Release | User Story Disposition | Fit/Gap | Type | Subtype | Build ID | Comments / High-level Approach Notes | Acceptance Criteria 1 | Acceptance Criteria 2 | Acceptance Criteria 3 | User Story Due Date | Subtype Status | Approved By | Actual User Story Approval Date | Design Sprint [Lean Specs] | User Story Size | Build Sprint [Tech Build OR FIT DEMO] | Delivery Sprint [TUT/FUT] | RICE type from RICE Tracker / Overridden for 1A delivered objects | OSS Type for 1B JIRA analysis | OSS Sprint Plan Notes | Track | SubTrack | Oracle Module | Based on | Source | Reference ID | Legacy ABC Corp Review Status (ABC Corp internal column, not used by PMO) | Legacy ABC Corp Review Status (ABC Corp internal column, not used by PMO) | Tax team approval | Discussion Questions during User Story review - Logged by ABC Corp/ABC Corp | Discussion Questions during User Story review - Logged by Deloitte | RTR Wave | Approval Email Tracker for GPO Approval | JIRA ID Functional | JIRA ID Tech Build | JIRA ID TUT/FUT | IS in RMO tracker?
[5 empty] | DP-RTR-IC-122 |  | Record to Report | Manage Intercompany Accounting | Job Schduling | Create ESS job set for GL, AR, AP Outbound interfaces |  |  | Phase 1A + Phase 1B | 3-Gap-Build-Interface | Gap | Build | Interface |  | Following AHCS BI outbound interface objects are planned to be converted in ESS job set for placing the file in a sequential manner(Data, CTL, Done). done file to be placed after completion of data and CTL file. INT185-86 Intercompany AP Invoice Feed to IAP and Teradata INT187-88 Intercompany AP Payment Feed to IAP and Teradata(Netting, Settlement, LSI) INT232-33 Open AP Invoice Balance to IAP and Terada INT010/INT021 GL Data to IAP - Journals INT011/INT042 GL Data to IAP - Balances INT189 190 Intercompany AR invoice feed to IAP and Teradata INT191 192 Intercompany AR Receipt Feed to IAP and Teradata INT234 235 Open AP Invoice Balance to Teradata and IAP Impact of moving BI jobs to ESS Job set is as below: 1) Multiselect is not feasible for LOVs 2) Depended LOVs are not possible 3) bursting cant be disabled while ad-hoc run of the ESS job set | GL& AHCS BI outbound interface objects are planned to be converted in ESS job set for placing the file in a sequential manner(Data, CTL, Done). done file to be placed after completion of data and CTL file. | [13 empty] | RTR | RTR-GL | IC | [13 empty] | No
| CSTONE-4199 |  |  | CSTONE-4199 | DP-RTR-GL-001 |  | Record to Report | Manage General Ledger Accounting | Process Manual Journal Entries | Enter a journal with Debit in USD and Credit in CAD, unbalanced by Entered currency and balanced by accounted currency. |  |  | Phase 1A+1B | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | This will be controlled by the ‘Limit journal to a single currency’ flag. This flag will be kept unchecked. Journal will be balanced by Entered currency by Oracle during posting by using Entered currency balancing account. This will allow users to create journals with multiple currency in GL. Change for WESCO EBS team - awareness was created. Note: This is applicable only for GL Journals and not IC batches |  |  |  |  | Approved | Rita | 2022-02-08 | [7 empty] | RTR | RTR-GL | GL | WESCO | [9 empty] | CSTONE-1089 | Not Applicable | Not Applicable | N/A
| CSTONE-4200 |  |  | CSTONE-4200 | DP-RTR-GL-002 |  | Record to Report | Manage General Ledger Accounting | Process Manual Journal Entries | As an Intercompany Accountant, I want my journal entries to automatically create an intercompany balancing line to streamline and speed processing [US and Canada ledgers only] |  |  | Phase 1A+1B | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | GL Auto-balancing: In US & CA for journals that are unbalanced by LE but balanced as a whole for accounted currency, will use auto-balancing. If journal is then unbalanced by entered currency, balancing as per DP-RTR-GL-002 will also happen 1B only -> IC batch: Balancing setup will add IC AR and IC AP lines which cannot be edited by users | Validate that balancing lines were correctly created for each IC journal. Validate both entered and accounted currencies. Validate balancing is only enabled for US and Canadian entities. |  |  |  | Approved | Erica | 2021-08-05 | [7 empty] | RTR | RTR-GL | GL | Deloitte |  |  | Ian/Vitaliy |  |  |  |  | W2 | WESCO -Deliver Phase User Stories - GL - Batch1 - GPO Approval | CSTONE-4200 | Not Applicable | Not Applicable | N/A
[7 empty] | Close, Consolidate, and Report | Close | Prepare Financial Statements | An entity-by-entity presentation across columns using prescribed chart of account headings and numbering in USD and LC/FC for each legal entity, branch or other unit that has a legal, tax compliance, or financial reporting requirement... Report to be developed similar to workbook 2020 Foreign Functional Trial Balances.xls The system must reflect all tax legal entities (e.g. corporations, partnerships, joint ventures and branches) with company codes. | Must Have |  | Phase 1A+1B | 2-Gap-Build-Report | Gap | Build | Report |  | report can be built in SmartView | Ensure report provided to tax meets requirements necessary for tax. | User should check that the formatting is correct | User can validate the values with historical data | [11 empty] | EPM | EPM - CCR | FCCS | WESCO - Tax Stories |  | RTR-TX-034 |  |  | Approved - Jessica | [7 empty] | N/A
[7 empty] | Close, Consolidate, and Report | Close | Prepare Financial Statements | Tax requires continued use of control totals report provided by accounting group. Vicki is references IBT formula on Consolidated TB | Must Have |  | Phase 1A+1B | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | there is a line item from the system that reports on Income Before Tax that can be used for this requirement | Ensure report provided to tax meets requirements necessary for tax. | [13 empty] | EPM | EPM - CCR | FCCS | WESCO - Tax Stories |  | TXC-TX-024 |  |  | Approved - Jessica | [7 empty] | N/A
[7 empty] | Close, Consolidate, and Report | Consolidate | Collect Data | A single extract/output of trial balance data in a pre-formatted report from accounting for each close period is required. | Must Have |  | Phase 1A+1B | 3-Gap-Build-Interface | Gap | Build | Interface |  | Standard extract can be built using Data Management to extract a flat file to load to OneSource Tax Provision. -- EPM-FCCS-075 | Ensure report provided to tax meets requirements necessary for tax. | User can load data from Close and Consolidations to OneSource Tax Provision via flatfiles | [12 empty] | EPM | EPM - CCR | FCCS | WESCO - Tax Stories |  | RTR-TX-035 |  |  | Approved - Jessica | [7 empty] | N/A
[7 empty] | Close, Consolidate, and Report | Master Data Management | Maintain Industry and Company Specific Attributes | The financial accounting system shall compute, and report amounts in both USD and functional currency | Must Have |  | Phase 1A+1B | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | EPM-FCCS-019 - As a Financial Analyst, I need the application to capture data in the functional currency of the entity EPM-FCCS-017 - As a GL Accountant, I need the ability for the application to consolidate financials in USD | Ensure report provided to tax meets requirements necessary for tax. | [13 empty] | EPM | EPM - CCR | FCCS | WESCO - Tax Stories |  | RTR-TX-036 |  |  | Approved - Jessica | [7 empty] | N/A
[7 empty] | Close, Consolidate, and Report | Consolidate | Prepare Group Financial Statements | The financial accounting system shall report journal entries (including but not limited to: closing, consolidating, elimination, or other "top side" entries) by legal entity by account in USD, functional currency and local currency. | Could Have |  | Phase 1A+1B | 6-Gap-Work Around-Work Around | Gap | Work Around | Work Around |  | story is similar to EPM-FCCS-154 As a Financial Reporting Manager, I need the ability to monitor journal entries through a journal audit report. The out of the box report will display the functional currency of the entity. Will not display the USD value. Alternatively a report could be created to show the data source in the columns and report in either functional or USD; however, it would not display the lines of the journal. Only the values | Ensure report provided to tax meets requirements necessary for tax. | [13 empty] | EPM | EPM - CCR | FCCS | WESCO - Tax Stories |  | RTR-TX-037 |  |  | Approved - Jessica | [7 empty] | N/A
[7 empty] | Close, Consolidate, and Report | Master Data Management | Manage Users and Access Rights | The system shall allow authorized Tax Team members to have display/read only access across all Oracle financial accounting system(s) with drill down capability to the transaction level of detail to facilitate determination of correct tax treatment and analysis. [EPM component] |  |  | Phase 1A+1B | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | FCCS will contain the full legal entity data and consolidated results. Users will be able to drilldown from FCCS to ERP GL. FCCS will only have the off-system TB loads. Tax will need to request transactional detail from the off-systems (same process as today). ERP GL will have journal entries and summarized subledger data from HUB. Users can drilldown from ERP GL to the HUB to view transactional detail from the legacy subledgers however not all data elements will be available. Users will continue to have access to the legacy subledgers and data-warehouses to continue to access subledger data as they do today. | Tax team will have access to display/ read only FCCS, Hub and ERP GL | [13 empty] | EPM | EPM - CCR | FCCS | WESCO - Tax Stories |  | RTR-TX-001 |  |  | Approved - Jessica | [7 empty] | N/A
| CSTONE-4201 |  |  | CSTONE-4201 | DP-RTR-GL-003 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | The system shall allow authorized Tax Team members to have display/read only access across all Oracle financial accounting system(s) with drill down capability to the transaction level of detail to facilitate determination of correct tax treatment and analysis. [ERP component] |  |  | Phase 1A+1B | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | FCCS will contain the full legal entity data and consolidated results. Users will be able to drilldown from FCCS to ERP GL. Only FCCS will have the off-system TB loads. Tax will need to request transactional detail from the off-systems (same process as today). ERP GL will have journal entries and summarized subledger data from HUB. Users can drilldown from ERP GL to the HUB to view transactional detail from the legacy subledgers however not all data elements will be available. Users will continue to have access to the legacy subledgers and data-warehouses to continue to access subledger data as they do today. Acceptance Criteria 1: Security team to cover access requirements for Tax team | Tax team will have access to display/ read only FCCS, Hub and ERP GL |  |  |  | Approved | Erica | 2021-08-05 | [7 empty] | RTR | RTR-GL | GL | WESCO - Tax Stories |  | RTR-TX-001 | Ian/Vitaliy |  | Approved - Jessica |  |  |  | WESCO -Deliver Phase User Stories - GL - Batch1 - GPO Approval | CSTONE-4201 | Not Applicable | Not Applicable | N/A
[7 empty] | Close, Consolidate, and Report |  |  | Report listing newly added G/L accounts within specific timeframe. |  |  | Phase 1A+1B | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | out-of-box audit capabilities in EDM can be utilized to filter specific changes within a given time frame and shared as an excel file | Accounting will provide newly added GL accounts to tax or have a report available in the first week of new month, assuming 1st of month is effective date for new accounts | [13 empty] | EPM | EPM - COA MDM | EDMCS | WESCO - Tax Stories |  | RTR-TX-002 |  |  | Approved - Jessica | [7 empty] | N/A
|  |  |  | N/A |  |  | Record to Report |  |  | The COA contains tax accounts in sufficient detail for US GAAP and local country GAAP and tax reporting. The COA will maintain a 1:1 mapping for accounts identified as tax sensitive from G/L to ERP to FCCS. The Legacy tax sensitized accounts identified can only be combined with any newly created tax sensitized accounts within the new Chart of Accounts, once created in the new system. See separate lists of legacy tax sensitive accounts for Wesco and Anixter. In addition, there are local country tax sensitive accounts that need to be addressed (additional information available upon request). |  |  | Phase 1A+1B | [6 empty] | Successful updated chart of accounts which includes tax-approved tax-sensitized accounts | [13 empty] | COA | COA | COA | WESCO - Tax Stories |  | RTR-TX-003 |  |  | Approved - Jessica | [7 empty] | N/A
|  |  |  | N/A |  |  | Record to Report |  |  | Interest expense and Debt Issuance costs amortization (e.g. Commitment and other fees that are paid not upon issuance but periodically over the life of the debt instrument) will be broken out into separate accounts in the chart of accounts. |  |  | Phase 1A+1B | [6 empty] | Successful updated chart of accounts which includes tax-approved tax-sensitized accounts | [13 empty] | COA | COA | COA | WESCO - Tax Stories |  | RTR-TX-004 |  |  | Approved - Jessica | [7 empty] | N/A
|  |  |  | N/A |  |  | Record to Report |  |  | The COA will contain a Federal Current Tax Expense account, Federal Deferred Tax Expense account, State Current Expense, State Deferred Tax Expense, Foreign Current Expense, and Foreign Deferred Expense. |  |  | Phase 1A+1B | [6 empty] | Successful updated chart of accounts which includes tax-approved tax-sensitized accounts | [13 empty] | COA | COA | COA | WESCO - Tax Stories |  | RTR-TX-005 |  |  | Approved - Jessica | [7 empty] | N/A
|  |  |  | N/A |  |  | Record to Report |  |  | Intercompany Interest Income, Intercompany Interest Expense, Third-Party Interest Income, and Third-Party Interest Expense shall be recorded into separate accounts in the chart of accounts, on a gross basis instead of net. |  |  | Phase 1A+1B | [6 empty] | Successful updated chart of accounts which includes tax-approved tax-sensitized accounts | [13 empty] | COA | COA | COA | WESCO - Tax Stories |  | RTR-TX-006 | [10 empty] | N/A
[7 empty] | Close, Consolidate, and Report |  |  | Tax Department is included in Chart of Accounts decisions |  |  | Phase 1A+1B | 6-Gap-Work Around-Work Around | Gap | Work Around | Work Around |  | Tax Department will be involved in COA governance process before change requests approved by Governance Council reach EDM. No notifications will be generated from EDM. | Tax team will be include in COA decisions | [13 empty] | EPM | EPM - COA MDM | EDMCS | WESCO - Tax Stories |  | RTR-TX-008 |  |  | Approved - Jessica | [7 empty] | N/A
| CSTONE-4202 |  |  | CSTONE-4202 | DP-RTR-GL-005 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | For non-US provision purposes, entries to statistical accounts (local country) are not allowed. |  |  | Phase 1A+1B | 6-Gap-Work Around-Work Around | Gap | Work Around | Work Around |  | Oracle Cloud like EBS does not put any restriction on currency that can be used for account. User training & monitoring using reports like Journal line report to review if monetary journals are booked to STAT accounts | Per tax user story review, Oracle cloud cannot block journal entries to statistical accounts. Tax will review user training and monitoring reports to ensure both meet tax requirements. |  |  |  | Approved | Erica | 2021-08-05 | [7 empty] | RTR | RTR-GL | GL | WESCO - Tax Stories |  | RTR-TX-017 | Ian/Vitaliy |  | Approved - Jessica |  |  |  | WESCO -Deliver Phase User Stories - GL - Batch1 - GPO Approval | CSTONE-4202 | Not Applicable | Not Applicable | N/A
| CSTONE-4203 |  |  | CSTONE-4203 | DP-RTR-GL-007 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | In order to comply with the separate legal entity reporting requirements mandated by specific jurisdictions, each legal entity should be assigned at least one unique Company Code. Additionally, branches and other units legally required to file financials or tax returns must be established in ERP as a company code to enable the same financial reporting including required currency for any separate local reporting. [ERP Component] |  |  | Phase 1A+1B | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Confirmed by tax team on call on 7/20 or 7/19 that current LE structure as noted in Enterprise structure document is good & meets this user story requirement Acceptance criteria 1 - There is no additional custom report planned for this user story. Standard or already planned custom reports will be used | Ensure legal entity structure and reports provided to tax meet requirements necessary for tax. |  |  |  | Approved | Erica | 2021-08-05 | [7 empty] | RTR | RTR-GL | GL | WESCO - Tax Stories |  | RTR-TX-021 | Ian/Vitaliy |  | Approved - Jessica |  |  |  | WESCO -Deliver Phase User Stories - GL - Batch1 - GPO Approval | CSTONE-4203 | Not Applicable | Not Applicable | N/A
[7 empty] | Close, Consolidate, and Report | Master Data Management | Maintain Reporting Entities | In order to comply with the separate legal entity reporting requirements mandated by specific jurisdictions, each legal entity should be assigned at least one unique Company Code. Additionally, branches and other units legally required to file financials or tax returns must be established in ERP as a company code to enable the same financial reporting including required currency for any separate local reporting. [EPM Component] | Must Have |  | Phase 1A+1B | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Legal Entity structure will be configured in FCCS as part of build | Ensure legal entity structure and reports provided to tax meet requirements necessary for tax. | [13 empty] | EPM | EPM - CCR | FCCS | WESCO - Tax Stories |  | RTR-TX-021 |  |  | Approved - Jessica | [7 empty] | N/A
[7 empty] | Close, Consolidate, and Report |  |  | Notification to Tax team of organizational changes or company changes are required in advance of change being made in Oracle. |  |  | Phase 1A+1B | 6-Gap-Work Around-Work Around | Gap | Work Around | Work Around |  | Tax Department will be involved in COA governance process before change requests approved by Governance Council reach EDM. No notifications will be generated from EDM. | Ensure tax is included in organizational change process | [13 empty] | EPM | EPM - COA MDM | EDMCS | WESCO - Tax Stories |  | RTR-TX-022 |  |  | Approved - Jessica | [7 empty] | N/A
[7 empty] | Close, Consolidate, and Report | Consolidate | Prepare Group Financial Statements | Custom reports (Trial Balance, Income Statement, Balance Sheet, and Account Detail) will be created to show amounts in true debit/credit format. [EPM component] | Must Have |  | Phase 1A+1B | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | reports have to be manually modified to present liabilities, equity and revenue as negatives. Outside of journals in FCCS, dr and cr do not exist in the application | Ensure report provided to tax meets requirements necessary for tax. | [13 empty] | EPM | EPM - CCR | FCCS | WESCO - Tax Stories |  | RTR-TX-023 |  |  | Approved - Jessica | [7 empty] | N/A
| CSTONE-4685 | CSTONE-4204 | CSTONE-4686 | CSTONE-4686 | DP-RTR-GL-008A |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | Custom reports (Trial Balance, Income Statement, Balance Sheet, and Account Detail) will be created to show amounts in true debit/credit format. [ERP GL component - Trial Balance] |  |  | Phase 1A+1B | 2-Gap-Build-Report | Gap | Build | Report | RPT047 | Build Trial Balance report as per Tax requirement Confirmed by Jess that this is required for 1A | Ensure report provided to tax meets requirements necessary for tax. |  |  |  | Approved | Erica | 2021-08-05 | [7 empty] | RTR | RTR-GL | GL | WESCO - Tax Stories |  | RTR-TX-023 | Ian/Vitaliy |  | Approved - Jessica |  |  |  | WESCO -Deliver Phase User Stories - GL - Batch1 - GPO Approval | CSTONE-4685 | CSTONE-4204 | CSTONE-4686 | N/A
| CSTONE-4688 | CSTONE-4205 | CSTONE-4687 | CSTONE-4687 | DP-RTR-GL-008B |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | Custom reports (Trial Balance, Income Statement, Balance Sheet, and Account Detail) will be created to show amounts in true debit/credit format. [ERP GL component - Income Statement] |  |  | Phase 1A+1B | 2-Gap-Build-Report | Gap | Build | Report | RPT047 | Income Statement report as per Tax requirement Confirmed by Jess that this is required for 1A | Ensure report provided to tax meets requirements necessary for tax. |  |  |  | Approved | Erica | 2021-08-05 | [7 empty] | RTR | RTR-GL | GL | WESCO - Tax Stories |  | RTR-TX-023 | Ian/Vitaliy |  | Approved - Jessica |  |  |  | WESCO -Deliver Phase User Stories - GL - Batch1 - GPO Approval | CSTONE-4688 | CSTONE-4205 | CSTONE-4687 | N/A
| CSTONE-4689 | CSTONE-4206 | CSTONE-4690 | CSTONE-4690 | DP-RTR-GL-008C |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | Custom reports (Trial Balance, Income Statement, Balance Sheet, and Account Detail) will be created to show amounts in true debit/credit format. [ERP GL component - Balance Sheet] |  |  | Phase 1A+1B | 2-Gap-Build-Report | Gap | Build | Report | RPT047 | Balance Sheet report as per Tax requirement Confirmed by Jess that this is required for 1A | Ensure report provided to tax meets requirements necessary for tax. |  |  |  | Approved | Erica | 2021-08-05 | [7 empty] | RTR | RTR-GL | GL | WESCO - Tax Stories |  | RTR-TX-023 | Ian/Vitaliy |  | Approved - Jessica |  |  |  | WESCO -Deliver Phase User Stories - GL - Batch1 - GPO Approval | CSTONE-4689 | CSTONE-4206 | CSTONE-4690 | N/A
|  |  | CSTONE-4692 |  | DP-RTR-AHCS-001 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | Custom reports (Trial Balance, Income Statement, Balance Sheet, and Account Detail) will be created to show amounts in true debit/credit format. [ERP AHCS Component - Account Detail] |  |  | Phase 1A+1B | 2-Gap-Build-Report | Gap | Build | Report | RPT009 | Planned subledger account analysis report has Dr and Cr as separate columns Tax team to review lean specification already available on SharePoint to ensure if there are any gaps as there is no additional report planned for this user story | Ensure report provided to tax meets requirements necessary for tax. |  |  |  | Approved | Chris Demko | 2021-08-04 | [7 empty] | RTR | RTR-AHCS | AHCS | ABC Corp - Tax Stories |  | RTR-TX-023 | Ian/Vitaliy |  | Approved - Jessica |  |  |  |  | CSTONE-4691 | CSTONE-4207 | CSTONE-4692 | N/A
| CSTONE-4208 | CSTONE-4693 | CSTONE-4666 | CSTONE-4666 | DP-RTR-GL-009 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | Documentation/Substantiation is required to be attached to journal entries and other postings. [ERP Component] |  |  | Phase 1A+1B | 2-Gap-Build-Report | Gap | Build | Report | RPT101 | Not sure what "other postings" in user story mean Journals cannot be stopped from getting created, approved or posted if attachment is not there. Oracle Cloud ERP supports uploading attachment at Journal level and also at Journal batch level 7/28: Confirmed by Tax team that "other postings" means journals. New custom report to be created that will flag journal batches where there is no attachment at both journal batch and header level Confirmed by Jess this is needed for 1A as well | If Oracle Cloud does not have a mechanism to stop journal entries posting without documentation, per tax user story review, tax will ensure training process addresses attachments in journal entry review process and review report structure for journal entries posted without attachment. |  |  |  | Approved | Erica | 2021-08-05 | [7 empty] | RTR | RTR-GL | GL | WESCO - Tax Stories |  | RTR-TX-026 | Ian/Vitaliy |  | Approved - Jessica |  |  |  | WESCO -Deliver Phase User Stories - GL - Batch1 - GPO Approval | CSTONE-4208 | CSTONE-4693 | CSTONE-4666 | N/A
[7 empty] | Close, Consolidate, and Report | Consolidate | Prepare Group Financial Statements | Documentation/Substantiation is required to be attached to journal entries and other postings. [EPM Component] | Could Have |  | Phase 1A+1B | 6-Gap-Work Around-Work Around | Gap | Work Around | Work Around |  | System allows for user to upload supporting documentation to an entry; however, the system does not enforce a user to load that documentation | If Oracle Cloud does not have a mechanism to stop journal entries posting without documentation, per tax user story review, tax will ensure training process addresses attachments in journal entry review process and review report structure for journal entries posted without attachment. | [13 empty] | EPM | EPM - CCR | FCCS | WESCO - Tax Stories |  | RTR-TX-026 |  |  | Approved - Jessica | [7 empty] | N/A
|  |  |  | N/A |  |  | Close, Consolidate, and Report |  |  | Tax requires continued access and functionality of SmartView or equivalent technology enabling ad-hoc reporting to source trial balance data. [EPM Component] |  |  | Phase 1A+1B | [6 empty] | Tax will have access and training to SmartView or equivalent technology | [13 empty] | TECH | TECH | LEGACY | WESCO - Tax Stories |  | RTR-TX-038 |  |  | Approved - Jessica | [7 empty] | N/A
[7 empty] | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | Tax requires continued access and functionality of SmartView or equivalent technology enabling ad-hoc reporting to source trial balance data. [ERP Component] |  |  | Phase 1A+1B | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | WESCO IT to ensure required software are deployed for SmartView. Security - role and data review to ensure ability to use SmartView is available | Agreed per tax user review session. All tax users have access and training to Smart view or equivalent technology |  |  |  | Initial Fit/Gap Complete | [9 empty] | TECH | TECH | LEGACY | WESCO - Tax Stories |  | RTR-TX-038 |  |  | Approved - Jessica | [5 empty] | Not Applicable | Not Applicable | N/A
[7 empty] | Close, Consolidate, and Report | Master Data Management | Maintain Chart of Accounts | Wesco/Anixter produce or provide financials from a single source for tax provision account mapping purposes | Must Have |  | Phase 1A+1B | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | EPM-FCCS-001 - As a Financial Analyst, I need the ability to add ERP GL account structure to match the structure in Close and Consolidations | Ensure report provided to tax meets requirements necessary for tax | [13 empty] | EPM | EPM - CCR | FCCS | WESCO - Tax Stories |  | RTR-TX-039 |  |  | Approved - Jessica | [7 empty] | N/A
| CSTONE-4209 |  | CSTONE-4671 | CSTONE-4671 | DP-RTR-GL-015 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | The financial accounting system shall provide a report of journal entries that do not have supporting documentation or attachments. |  |  | Phase 1A+1B | 2-Gap-Build-Report | Gap | Build | Report | RPT101 | Journals cannot be stopped from getting created, approved or posted if attachment is not there. Oracle Cloud ERP supports uploading attachment at Journal level and also at Journal batch level 7/28: New custom report to be created that will flag journal batches where there is no attachment at both journal batch and header level Confirmed by Jess this is needed for 1A as well | If Oracle Cloud does not have a mechanism to stop journal entries posting without documentation, per tax user story review, tax will ensure training process addresses attachments in journal entry review process and review report structure for journal entries posted without attachment. |  |  |  | Approved | Erica | 2021-08-05 | [7 empty] | RTR | RTR-GL | GL | WESCO - Tax Stories |  | TXC-TX-025 | Ian/Vitaliy |  | Approved - Jessica |  |  |  | WESCO -Deliver Phase User Stories - GL - Batch1 - GPO Approval | CSTONE-4209 | CSTONE-4695 | CSTONE-4671 | N/A
[7 empty] | Close, Consolidate, and Report |  |  | Source Data from FP&A group needs to be output in a format that’s conducive to Legal Entity Reporting |  |  | Phase 1A+1B | [6 empty] | Ensure report provided to tax meets requirements necessary for tax | [13 empty] | EPM | EPM - CCR | EPBCS | WESCO - Tax Stories |  | TXI-TX-009 |  |  | Approved - Jessica | [7 empty] | N/A
[7 empty] | Close, Consolidate, and Report |  |  | Forecast PTBI from FP&A group to retain same entity- and account-level granularity and formatting as exists today. |  |  | Phase 1A+1B | [6 empty] | Ensure report provided to tax meets requirements necessary for tax | [13 empty] | EPM | EPM - CCR | EPBCS | WESCO - Tax Stories |  | TXP-TX-019 |  |  | Approved - Jessica | [7 empty] | N/A
[7 empty] | Close, Consolidate, and Report | Master Data Management | Maintain Reporting Entities | The GL activity should be available in USD, functional currency and local currency [EPM Component] | Must Have |  | Phase 1A+1B | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | ERP GL will only provide functional and entered currency. Translation to USD reporting currency will only occur in FCCS. FCCS will also support the full legal entity reporting. FCCS will have USD and functional currency | Ensure all currency needs are met in GL and FCCS, as discussed in tax user story review session. | [13 empty] | EPM | EPM - CCR | FCCS | WESCO - Tax Stories |  | RTR-TP-013 |  |  | Approved - Jessica | [7 empty] | N/A
[7 empty] | Close, Consolidate, and Report | Master Data Management | Manage Users and Access Rights | The system shall allow authorized Tax Team members to have display/read only access across all Oracle financial accounting system(s) with drill down capability to the transaction level of detail to facilitate implementation, monitoring and reporting of transfer pricing policies. [EPM Component] |  |  | Phase 1A+1B | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | FCCS will contain the full legal entity data and consolidated results. Users will be able to drilldown from FCCS to ERP GL. FCCS will only have the off-system TB loads. Tax will need to request transactional detail from the off-systems (same process as today). ERP GL will have journal entries and summarized subledger data from HUB. Users can drilldown from ERP GL to the HUB to view transactional detail from the legacy subledgers however not all data elements will be available. Users will continue to have access to the legacy subledgers and data-warehouses to continue to access subledger data as they do today. | Tax team will have access to display/ read only FCCS, Hub and ERP GL |  |  |  | Approved | Erica | 2021-08-05 | [7 empty] | EPM | EPM - CCR | FCCS | WESCO - Tax Stories |  | RTR-TP-021 |  |  | Approved - Jessica | [7 empty] | N/A
| CSTONE-4697 | CSTONE-4698 | CSTONE-4699 | CSTONE-4699 | DP-RTR-GL-019 |  | Record to Report | Manage General Ledger Accounting | Process Manual Journal Entries | As an accountant I need a COA mapping template similar to journal entry ADFDI so that I can copy paste data from mapping sheet directly to ADFDI template |  |  | Phase 1A+1B | 5-Gap-Build-Extension | Gap | Build | Extension | EXT013 | Update EXT013 to support a new template that looks similar to ADFDI multi journal spreadsheet | Ensure template looks similar to multi journal spreadsheet | Should be able to copy to multijournal spreadsheet |  |  | Approved | RMO | Oct RMO | Sprint 6 |  | Sprint 6 | Sprint 6 |  |  |  | RTR | RTR-AHCS | AHCS | WESCO |  | CTPFS-904 | [7 empty] | CSTONE-4697 | CSTONE-4698 | CSTONE-4699 | N/A
| CSTONE-5086 |  |  | CSTONE-5086 | DP-RTR-GL-020 |  | Record to Report | Manage General Ledger Accounting | Approve and Post Journal Entries | The Approval Notification should expire if the approver doesn't action within 4 days. Reminders will be enabled and will be send twice before Expiration |  |  | Phase 1A+1B | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | In Task configuration setting for Journal Approvals, the expiration settings under deadline tab will be used at Assignee level and expire only. Under notifications tab reminder will be enabled to configure reminder settings. |  Deadlines • Expiration Settings will be set at Assignee level. • Expiration Duration will be set to 4 days. • Notification will be set to Expire Only. • Weekends (Saturday and Sunday will not be excluded from the set 4 days expiration duration).  Reminders • Reminders will be enabled and will be send twice before Expiration. Frequency will be set to 2 Days. |  |  | - | [10 empty] | RTR | RTR-GL | GL | [13 empty] | N/A
| CSTONE-6879 | CSTONE-7637 | CSTONE-9921 | Sprint 11 | DP-RTR-IC-001A |  | Record to Report | Manage General Ledger Accounting | Process Manual Journal Entries | As a tax analyst, I would like all I/C invoices to be archived monthly. Invoices must show the historical data on the invoice. (if address for entity changes, historical invoices should still show the old address). [For invoice template bursting to SFTP by invoice template] |  |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report | RPT102 | Invoice template can be bursted to SFTP folders. WESCO IT may pick from SFTP folders and move to required archiving tools like FileNet etc. 2 invoice templates to be built as per assumptions and alignment via email "Non material Intercompany Invoice Template from PeopleSoft" | Ensure all I/C invoices have been archived. Ensure historical data is captured on the invoices. |  |  | Sprint 11 | Approved | Erica | 2021-08-05 | Sprint 11 |  | Sprint 12 | Sprint 13 | Report | Report |  | RTR | RTR-GL | IC | WESCO - Tax Stories |  | IT14 - Archiving | Ian/Vitaliy |  | Approved - Jessica |  | Invoice print |  | WESCO -Deliver Phase User Stories - GL - Batch1 - GPO Approval |  |  |  | N/A
| CSTONE-6880 | CSTONE-7638 | CSTONE-9922 | Sprint 11 | DP-RTR-IC-001B |  | Record to Report | Manage General Ledger Accounting | Process Manual Journal Entries | As a tax analyst, I would like all I/C invoices to be archived monthly. Invoices must show the historical data on the invoice. (if address for entity changes, historical invoices should still show the old address). [For invoice template bursting to SFTP by invoice template] |  |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report | RPT103 | Invoice template can be bursted to SFTP folders. WESCO IT may pick from SFTP folders and move to required archiving tools like FileNet etc. 2 invoice templates to be built as per assumptions and alignment via email "Non material Intercompany Invoice Template from PeopleSoft" | Ensure all I/C invoices have been archived. Ensure historical data is captured on the invoices. |  |  | Sprint 11 | Approved | Erica | 2021-08-05 | Sprint 11 |  | Sprint 12 | Sprint 13 | Report | Report |  | RTR | RTR-GL | IC | WESCO - Tax Stories |  | IT14 - Archiving | Ian/Vitaliy |  | Approved - Jessica |  | Invoice print |  | WESCO -Deliver Phase User Stories - GL - Batch1 - GPO Approval |  |  |  | N/A
| - | - | - | N/A | - |  | Record to Report | Manage General Ledger Accounting | Process Manual Journal Entries | As a tax analyst, I would like all I/C invoices to be archived monthly. Invoices must show the historical data on the invoice. (if address for entity changes, historical invoices should still show the old address). [For WESCO IT to pick SFTP files and archive] |  |  | Phase 1B only | [5 empty] | Invoice template can be bursted to SFTP folders. WESCO IT may pick from SFTP folders and move to required archiving tools like FileNet etc. WESCO IT to update comments. This user story is for taking from SFTP folder to applicable archiving solution | Ensure all I/C invoices have been archived. Ensure historical data is captured on the invoices. |  |  | - | TBD |  |  | - | [6 empty] | RTR | LEGACY | LEGACY | WESCO - Tax Stories |  | IT14 - Archiving |  |  | Approved - Jessica | [7 empty] | N/A
| CSTONE-6881 | CSTONE-7639 | CSTONE-9923 | Sprint 11 | DP-RTR-IC-002A |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | (IC Transactions) Oracle GL must have sufficient fields to capture Legal Entity attributes which require printing on an invoice template, such as Registered address, VAT number, Tax and/or Company registration number, Share capital, Directors, the label "Tax invoice", etc... | RTR-TP-050 |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report | RPT102 | PF 7/13: A question to the team is whether Oracle foresees fields to store (and maintain) certain data, or whether this is hard coded on every invoice template? OSS Notes: Alignment on tax team call not all fields will be in Oracle tables, some will be in templates. User story DP-RTR-IC-001 will be used to track archiving requirement on reports Vitaliy to work with Patrick for 1B to finalize Intercompany transaction types that are required 7/28 email sent: Note: As mentioned on call, tax computation and related field population is currently not in scope for IC currently in 1B – irrespective as a Tax engine OR as Oracle tax module config. Seems recently a KDD has been created for this which Nanda/Farnaz are working on. Invoice template assumes that data required for template is there on invoice – static [E.g. LE Name], user entered [E.g. Amount ] OR tax related [E.g. Tax Code] which is derived either by Tax engine OR Tax configs [both currently not in scope for Release 1] OR user entered. 7/29: As per email "Non material Intercompany Invoice Template from PeopleSoft" 2 invoice print templates planned based on noted assumptions. Expectation based on noted assumptions is it should address local requirements | Ensure required attributes for local country requirements are included and maintained for Intercompany Invoice Templates |  | email: IC Meeting Notes | Sprint 11 | Approved | Erica | 2021-08-05 | Sprint 11 |  | Sprint 12 | Sprint 13 | Report | Report |  | RTR | RTR-GL | IC | WESCO - Tax Stories |  | IT01 | Ian/Vitaliy |  | Approved - Jessica |  | Invoice print |  | WESCO -Deliver Phase User Stories - GL - Batch1 - GPO Approval |  |  |  | N/A
| CSTONE-6882 | CSTONE-7640 | CSTONE-9924 | Sprint 11 | DP-RTR-IC-002B |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | (IC Transactions) Oracle GL must have sufficient fields to capture Legal Entity attributes which require printing on an invoice template, such as Registered address, VAT number, Tax and/or Company registration number, Share capital, Directors, the label "Tax invoice", etc... | RTR-TP-050 |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report | RPT103 | PF 7/13: A question to the team is whether Oracle foresees fields to store (and maintain) certain data, or whether this is hard coded on every invoice template? OSS Notes: Alignment on tax team call not all fields will be in Oracle tables, some will be in templates. User story DP-RTR-IC-001 will be used to track archiving requirement on reports Vitaliy to work with Patrick for 1B to finalize Intercompany transaction types that are required 7/28 email sent: Note: As mentioned on call, tax computation and related field population is currently not in scope for IC currently in 1B – irrespective as a Tax engine OR as Oracle tax module config. Seems recently a KDD has been created for this which Nanda/Farnaz are working on. Invoice template assumes that data required for template is there on invoice – static [E.g. LE Name], user entered [E.g. Amount ] OR tax related [E.g. Tax Code] which is derived either by Tax engine OR Tax configs [both currently not in scope for Release 1] OR user entered. 7/29: As per email "Non material Intercompany Invoice Template from PeopleSoft" 2 invoice print templates planned based on noted assumptions. Expectation based on noted assumptions is it should address local requirements | Ensure required attributes for local country requirements are included and maintained for Intercompany Invoice Templates |  | email: IC Meeting Notes | Sprint 11 | Approved | Erica | 2021-08-05 | Sprint 11 |  | Sprint 12 | Sprint 13 | Report | Report |  | RTR | RTR-GL | IC | WESCO - Tax Stories |  | IT01 | Ian/Vitaliy |  | Approved - Jessica |  | Invoice print |  | WESCO -Deliver Phase User Stories - GL - Batch1 - GPO Approval |  |  |  | N/A
| CSTONE-6316 | CSTONE-11627 | CSTONE-6907 | CSTONE-6316 | DP-RTR-GL-014D |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | The financial accounting system shall have the ability to extract data from the system at a legal entity level in a machine-readable format, capable of being processed by another system, before any data archival. Tax requires the ability to meet mandatory OECD SAF-T reporting. Data from any "sunset" or no longer utilized systems should be maintained and made available in a similar manner for a period consistent with existing data retention policies. Specifically: a. Tax needs the data to be extractable by tax year and legal entity. b. Data must also be accessible, and large volumes of transaction level detail data must be able to be extracted from the system and capable of being processed by another system to be presented to tax authorities. c. All transaction data must also contain the related master data (e.g., an archived purchase transaction with a vendor number must also include the relevant vendor master record details; Vendor name, vendor address, etc.). d. Data extraction should be enabled by an intuitive interface accessible by tax/finance personnel and must be executable in formats including .txt, .csv, .xls, among others. e. Journal entry sequencing requirement to comply with local country accounting/audit rules and standards. [ERP Component - GL] |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT189 | Sequencing: Journal sequencing for outside US and Canada to be enabled at LE level [no requirement to sequencing at a lower level than LE]. Report: France FEC report RPT026 is planned to be built on Oracle Cloud ERP. Rest of reports to be pulled from IAP. Integrations planned to send GL Journals, GL balances, AHCS Balances, AHCS Journals, IC AR Invoices, IC AP Invoices, IC AR Receipts, IC AP Payments to IAP. Rest of the mentioned requirements [E.g. reports and their archiving etc.] would be pulled from IAP. IAP to address rest of requirements. | Ensure noted integration data is sent over to BI for subsequent reporting from BI |  |  | Sprint 10 | Approved | Erica | 2021-08-05 | Sprint 10 |  | Sprint 11 | Sprint 12 | Interface | Interface |  | RTR | RTR-GL | GL | WESCO - Tax Stories |  | TXC-TX-011 | Ian/Vitaliy |  | Approved - Jessica |  |  |  | WESCO -Deliver Phase User Stories - GL - Batch1 - GPO Approval |  |  |  | N/A
| CSTONE-6108 | - | - | CSTONE-6108 | DP-RTR-IC-004 |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | An accountant should understand which intercompany transactions require an invoice and which ones don't (Process) |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | IC transaction types will drive whether invoicing is required or not. Training to IC users required to determine which IC transaction type is required | Tax will review training materials to ensure process meets tax requirements |  |  | Sprint 8 | Approved | Erica | 2021-08-05 |  |  | Sprint 8 |  |  | 1-Fit-Configuration-Functional |  | RTR | RTR-GL | IC | WESCO - Tax Stories |  | IT11 | Ian/Vitaliy |  | Approved - Jessica |  |  |  | WESCO -Deliver Phase User Stories - GL - Batch1 - GPO Approval |  |  |  | N/A
| CSTONE-6109 | - | - | CSTONE-6109 | DP-RTR-IC-005 |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | An accountant should understand which intercompany transactions require an invoice and which ones require a credit note. From an accounting point of view the debits and credits are identical when entity A invoices entity B or entity B issues a credit note to entity A (Process) |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | In IC Provider determines entity that has AR transaction and Receiver has AP transaction. In AR currently if amounts are flipped it will create negative AR invoice. In AP system will flip and create credit memo. [In future release Oracle may release on AR side ability to create credit memo instead of negative invoice, currently not yet available in Cloud]. Training issue to select appropriate provider and receiver and also transaction type. Appropriate provider and receiver selection with amounts would then drive behavior as noted above | Tax will review training materials to ensure process meets tax requirements |  |  | Sprint 8 | Approved | Erica | 2021-08-05 |  |  | Sprint 8 |  |  | 1-Fit-Configuration-Functional |  | RTR | RTR-GL | IC | WESCO - Tax Stories |  | IT12 | Ian/Vitaliy |  | Approved - Jessica |  |  |  | WESCO -Deliver Phase User Stories - GL - Batch1 - GPO Approval |  |  |  | N/A
| CSTONE-6110 | - | - | CSTONE-6110 | DP-RTR-IC-006 |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | The transactions related to sale of goods and services billed on intercompany invoices should interface to appropriate revenue accounts. A rebate from MD to LRD should debit intercompany sales & COS for example |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Intercompany module in scope for Release 1 does not have material intercompany in scope. IC AR and IC AP accounts on AR and AP invoice will be derived systematically based on selected transaction type in IC batch. Revenue and expense account will be user training. User training to select appropriate transaction type on IC batch. Tax to work with RTR Core team to finalize list of IC transaction types for 1B | Tax will review training materials to ensure process meets tax requirements |  |  | Sprint 8 | Approved | Erica | 2021-08-05 |  |  | Sprint 8 |  |  | 1-Fit-Configuration-Functional |  | RTR | RTR-GL | IC | WESCO - Tax Stories |  | IT13 | Ian/Vitaliy |  | Approved - Jessica |  |  |  | WESCO -Deliver Phase User Stories - GL - Batch1 - GPO Approval |  |  |  | N/A
| CSTONE-6111 | - | - | CSTONE-6111 | DP-RTR-IC-007 |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | There should be a capability to consolidate multiple Intercompany transactions of the same nature into a monthly consolidated intercompany invoice |  |  | Phase 1B only | 6-Gap-Work Around-Work Around | Gap | Work Around | Work Around |  | IC tracked as journals throughout the month. At month end users to convert balances to single invoice using IC module. Alignment as per OID-44 meeting notes "Option 2 – Allocations/GL Journals to hit a clearing account. Manual month end process to create one invoice to move charges from clearing account to IC AR/AP accounts" | Ensure process meets tax requirements |  |  | Sprint 8 | Approved | Erica | 2021-08-06 |  |  | Sprint 8 |  |  | 6-Gap-Work Around-Work Around |  | RTR | RTR-GL | IC | WESCO - Tax Stories |  | IT15 |  |  | Approved - Jessica |  | Sandra CALA |  | WESCO -Deliver Phase User Stories - GL - Batch1 - GPO Approval |  |  |  | N/A
| - | - | - | N/A | DP-RTR-IC-008 |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | Oracle GL must be able to capture and store multiple Tax Registration Number (VAT) for a Legal Entity |  |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope |  | Cloud Legal Entity Structure setup allows adding registrations. This setup is owned by team owning tax setups/tax integrations. Even if data is loaded, how these multiple registrations are used is driven based off tax engine/regime to rate flow [Tax module configurations]. In Cornerstone solution how it is used essentially is dependent on Tax engine / Tax solution KDD. Currently both Tax engine and also Tax module configs are not in scope | Ensure process for storing VAT registration numbers for each legal entity meets tax requirements |  |  | - | Submitted for Approval |  |  | - | [6 empty] | RTR | RTR-GL | IC | WESCO - Tax Stories |  | IT02 |  |  |  |  | Tax engine decision | [5 empty] | N/A
| - | - | - | N/A | DP-RTR-IC-009 |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | The Intercompany Invoicing module should calculate: a) indirect taxes and indirect tax exemption messages (IT04 & IT05) b) supplier and customer VAT registrations c) in both AR and AP d) at the line level e) in foreign and local currency f) at the authority level if more than 1 tax applies |  |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope |  | Currently both Tax engine and also Tax module configs are not in scope | Ensure tax calculation requirements are met on IC transactions |  |  | - | Submitted for Approval |  |  | - | [6 empty] | RTR | RTR-GL | IC | WESCO - Tax Stories |  | IT03 |  |  |  |  | Tax engine decision | [5 empty] | N/A
| - | - | - | N/A | DP-RTR-IC-010 |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | The intercompany invoicing module must be able to calculate indirect taxes. A third party tax engine is best suited in order to avoid rates and rules maintenance. |  |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope |  | Currently both Tax engine and also Tax module configs are not in scope | Ensure tax calculation requirements are met on IC transactions |  |  | - | Submitted for Approval |  |  | - | [6 empty] | RTR | RTR-GL | IC | WESCO - Tax Stories |  | IT04 |  |  |  |  | Tax engine decision | [5 empty] | N/A
| - | - | - | N/A | DP-RTR-IC-011 |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | The indirect taxes and indirect tax exemption messages returned from the tax engine must display on the printed invoices |  |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope |  | Currently both Tax engine and also Tax module configs are not in scope | Ensure tax calculation requirements are met on IC transactions and required tax calculation results display on invoices |  |  | - | Submitted for Approval |  |  | - | [6 empty] | RTR | RTR-GL | IC | WESCO - Tax Stories |  | IT05 |  |  |  |  | Tax engine decision | [5 empty] | N/A
| - | - | - | N/A | DP-RTR-IC-012 |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | The indirect taxes and indirect tax exemption messages or tax codes returned from the tax engine should be available on reports |  |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope |  | Currently both Tax engine and also Tax module configs are not in scope | Ensure reports provided to tax meet requirements |  |  | - | Submitted for Approval |  |  | - | [6 empty] | RTR | RTR-GL | IC | WESCO - Tax Stories |  | IT06 |  |  |  |  | Tax engine decision | [5 empty] | N/A
| CSTONE-6310 | CSTONE-6669 | CSTONE-7663 | CSTONE-6310 | DP-RTR-IC-013A |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | All invoice data must be available for feeding into invoicing software or eInvoicing solutions (Edicom, Tungsten,..) [ERP Component] |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT185 | Integration will not be built to various software from Oracle Cloud ERP. Oracle Cloud ERP will feed AR and AP invoice and payment details to IAP. Required data for tax reporting will be pulled from IAP. If any field required for reporting is not available in Oracle Cloud ERP, data will be enhanced by users from IAP for tax reporting | Ensure required data for feeding into invoices solutions is available in IAP or data warehouse equivalent |  |  | Sprint 10 | Approved | Erica | 2021-08-05 | Sprint 10 |  | Sprint 10 | Sprint 12 | Interface | Interface |  | RTR | RTR-GL | IC | WESCO - Tax Stories |  | IT07 | Ian/Vitaliy |  | Approved - Jessica |  |  |  | WESCO -Deliver Phase User Stories - GL - Batch1 - GPO Approval |  |  |  | N/A
| CSTONE-6311 | CSTONE-6673 | CSTONE-7664 | CSTONE-6311 | DP-RTR-IC-013B |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | All invoice data must be available for feeding into invoicing software or eInvoicing solutions (Edicom, Tungsten,..) [ERP Component] |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT187 | Integration will not be built to various software from Oracle Cloud ERP. Oracle Cloud ERP will feed AR and AP invoice and payment details to IAP. Required data for tax reporting will be pulled from IAP. If any field required for reporting is not available in Oracle Cloud ERP, data will be enhanced by users from IAP for tax reporting | Ensure required data for feeding into invoices solutions is available in IAP or data warehouse equivalent |  |  | Sprint 10 | Approved | Erica | 2021-08-05 | Sprint 10 |  | Spritnt 10 | Sprint 12 | Interface | Interface |  | RTR | RTR-GL | IC | WESCO - Tax Stories |  | IT07 | Ian/Vitaliy |  | Approved - Jessica |  |  |  | WESCO -Deliver Phase User Stories - GL - Batch1 - GPO Approval |  |  |  | N/A
| CSTONE-6317 | CSTONE-11628 | CSTONE-6908 | CSTONE-6317 | DP-RTR-GL-014E |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | The financial accounting system shall have the ability to extract data from the system at a legal entity level in a machine-readable format, capable of being processed by another system, before any data archival. Tax requires the ability to meet mandatory OECD SAF-T reporting. Data from any "sunset" or no longer utilized systems should be maintained and made available in a similar manner for a period consistent with existing data retention policies. Specifically: a. Tax needs the data to be extractable by tax year and legal entity. b. Data must also be accessible, and large volumes of transaction level detail data must be able to be extracted from the system and capable of being processed by another system to be presented to tax authorities. c. All transaction data must also contain the related master data (e.g., an archived purchase transaction with a vendor number must also include the relevant vendor master record details; Vendor name, vendor address, etc.). d. Data extraction should be enabled by an intuitive interface accessible by tax/finance personnel and must be executable in formats including .txt, .csv, .xls, among others. e. Journal entry sequencing requirement to comply with local country accounting/audit rules and standards. [ERP Component - GL] |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT191 | Sequencing: Journal sequencing for outside US and Canada to be enabled at LE level [no requirement to sequencing at a lower level than LE]. Report: France FEC report RPT026 is planned to be built on Oracle Cloud ERP. Rest of reports to be pulled from IAP. Integrations planned to send GL Journals, GL balances, AHCS Balances, AHCS Journals, IC AR Invoices, IC AP Invoices, IC AR Receipts, IC AP Payments to IAP. Rest of the mentioned requirements [E.g. reports and their archiving etc.] would be pulled from IAP. IAP to address rest of requirements. | Ensure noted integration data is sent over to BI for subsequent reporting from BI |  |  | Sprint 10 | Approved | Erica | 2021-08-05 | Sprint 10 |  | Sprint 11 | Sprint 12 | Interface | Interface |  | RTR | RTR-GL | GL | WESCO - Tax Stories |  | TXC-TX-011 | Ian/Vitaliy |  | Approved - Jessica |  |  |  | WESCO -Deliver Phase User Stories - GL - Batch1 - GPO Approval |  |  |  | N/A
| CSTONE-11630 | CSTONE-6306 | CSTONE-6308 | CSTONE-6308 | DP-RTR-GL-014F |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | The financial accounting system shall have the ability to extract data from the system at a legal entity level in a machine-readable format, capable of being processed by another system, before any data archival. Tax requires the ability to meet mandatory OECD SAF-T reporting. Data from any "sunset" or no longer utilized systems should be maintained and made available in a similar manner for a period consistent with existing data retention policies. Specifically: a. Tax needs the data to be extractable by tax year and legal entity. b. Data must also be accessible, and large volumes of transaction level detail data must be able to be extracted from the system and capable of being processed by another system to be presented to tax authorities. c. All transaction data must also contain the related master data (e.g., an archived purchase transaction with a vendor number must also include the relevant vendor master record details; Vendor name, vendor address, etc.). d. Data extraction should be enabled by an intuitive interface accessible by tax/finance personnel and must be executable in formats including .txt, .csv, .xls, among others. e. Journal entry sequencing requirement to comply with local country accounting/audit rules and standards. [ERP Component - GL] |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT021 | Sequencing: Journal sequencing for outside US and Canada to be enabled at LE level [no requirement to sequencing at a lower level than LE]. Report: France FEC report RPT026 is planned to be built on Oracle Cloud ERP. Rest of reports to be pulled from IAP. Integrations planned to send GL Journals, GL balances, AHCS Balances, AHCS Journals, IC AR Invoices, IC AP Invoices, IC AR Receipts, IC AP Payments to IAP. Rest of the mentioned requirements [E.g. reports and their archiving etc.] would be pulled from IAP. IAP to address rest of requirements. | Ensure noted integration data is sent over to BI for subsequent reporting from BI |  |  | Sprint 8 | Approved | Erica | 2021-08-05 | Sprint 8 |  | Sprint 10 | Sprint 10 | Interface | Interface |  | RTR | RTR-GL | GL | WESCO - Tax Stories |  | TXC-TX-011 | Ian/Vitaliy |  | Approved - Jessica |  |  |  | WESCO -Deliver Phase User Stories - GL - Batch1 - GPO Approval |  |  |  | N/A
| - | - | - | N/A | - |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | All invoice data must be available for feeding into invoicing software or eInvoicing solutions (Edicom, Tungsten,..) [BI Component] |  |  | Phase 1B only | [5 empty] | Integration will not be built to various software from Oracle Cloud ERP. Oracle Cloud ERP will feed AR and AP invoice and payment details to IAP. Required data for tax reporting will be pulled from IAP. If any field required for reporting is not available in Oracle Cloud ERP, data will be enhanced by users from IAP for tax reporting Above comment is placeholder from related RTR user story. BI team to update | Ensure required data for feeding into invoices solutions is available in IAP or data warehouse equivalent |  |  | - |  |  |  | - | [6 empty] | RTR | BI | BI | WESCO - Tax Stories |  | IT07 |  |  | Approved - Jessica | [7 empty] | N/A
| - | - | - | N/A | DP-RTR-IC-014 |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | The intercompany invoicing module needs to be able to map journals into meaningful goods and services for the tax engine to interpret for proper tax calculations |  |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope |  | Material intercompany is not in scope. This user story is about use of intercompany transaction types / accounts and use of it by tax engine for tax determination. Currently both Tax engine and also Tax module configs are not in scope | Pending further discussion |  |  | - | Submitted for Approval |  |  | - | [6 empty] | RTR | RTR-GL | IC | WESCO - Tax Stories |  | IT08 |  |  |  |  | Tax engine decision | [5 empty] | N/A
| CSTONE-6112 | - | - | CSTONE-6112 | DP-RTR-IC-015 |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | The intercompany invoicing module should generate a chronological and gapless by legal entity (not tax ID) invoice sequence |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Setup IC invoice sequencing in AR by Legal entity. AR Invoice number will be generated in order in which invoice is generated and not in order of invoice date. AR invoice number will be copied to AP invoice number. 7/28: Acceptance criteria 1 - Jess confirmed numbering is by LE. During build phase starting values by LE will be provided | Ensure invoice sequencing meets tax and local country requirements |  |  | Sprint 8 | Approved | Erica | 2021-08-05 |  |  | Sprint 8 |  |  | 1-Fit-Configuration-Functional |  | RTR | RTR-GL | IC | WESCO - Tax Stories |  | IT09 | Ian/Vitaliy |  | Approved - Jessica |  |  |  | WESCO -Deliver Phase User Stories - GL - Batch1 - GPO Approval |  |  |  | N/A
| CSTONE-6113 | - | - | CSTONE-6117 | DP-RTR-IC-016 |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | The invoice copies should be easy to retrieve and print in PDF, the invoice search should be possible based on invoice number (range), journal number, invoice date/period (range), supplier, customer |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | This user story is about ability to search AR and AP invoices from front end using filter criteria as provided by Oracle. Archiving requirement of ability to send to SFTP is covered in user story DP-RTR-IC-001. Corresponding user story under LEGACY track is added for WESCO IT to take file from SFTP and make available in WESCO archiving tool as per requirement to search etc. Note: Invoice in AR and AP screen cannot be searched by Journal batch name | 1) As a tax analyst, when I access the invoice search screen and enter an invoice number in the search field and hit enter or search button, then I should get a PDF copy of the invoice I can download or print 2) As a tax analyst, when I access the invoice search screen and enter a journal number in the search field and hit enter or search button, then I should get a PDF copy of the invoice I can download or print 3) As a tax analyst, when I access the invoice search screen and enter a bill from and/or bill to party and a period (month and year range) in the search field and hit enter or search button, then I should get a list of PDF copies of the invoices I can download or print individually or in 1 batch of multiple PDFs (it’s important I can choose to search by bill from or by bill to only or by both combined; same for period, it must be a range, the year is mandatory, the month is optional, I should be able to enter from January 2023 to December 2025 in case of a tax audit) | Ensure ability to search and obtain PDFs in archiving system. |  | Sprint 8 | Approved | Erica | 2021-08-05 |  |  | Sprint 8 |  |  | 1-Fit-Configuration-Functional |  | RTR | RTR-GL | IC | WESCO - Tax Stories |  | IT14 | Ian/Vitaliy |  | Approved - Jessica |  |  |  | WESCO -Deliver Phase User Stories - GL - Batch1 - GPO Approval |  |  |  | N/A
| CSTONE-7586 | CSTONE-9868 | CSTONE-9925 | Sprint 12 | DP-RTR-GL-004 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | FX rates will be at the legal entity level (not BU level). |  |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report | RPT104 | This story pertains to reporting ledgers required for UK entity having MD-LRD structure in EMEA. For example "a BU is in Euro, but the LE is GBP. If Oracle could provide the LE GBP trial balance and US trial balance this would eliminate the manual manipulation of data."- PW Reporting Ledgers will be setup as per approved KDD2. Primary ledgers [USGAAP] will be setup as per approved KDD2 Acceptance criteria 1: Reporting ledger accounted balances will be will currency of reporting ledger Add a new TB report for MDR entities based on reporting ledger restricting it to specific entities [ignore non relevant entities in reporting ledger which will get copied over from primary as they co-exist in same ledger but are not part of MD-LRD structure] | This will be captured at the reporting ledger, per tax user story review session. Tax will ensure reports provided are in the correct functional currency for legal entity. |  |  | Sprint 12 | Approved | Erica | 2021-08-05 | Sprint 12 |  | Sprint 13 | Sprint 13 | Report | Report |  | RTR | RTR-GL | GL | WESCO - Tax Stories |  | RTR-TX-013 | Ian/Vitaliy |  | Approved - Jessica |  |  |  | WESCO -Deliver Phase User Stories - GL - Batch1 - GPO Approval |  |  |  | N/A
|  |  |  | N/A | DP-RTR-GL-006 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | Local country Tax teams require localized languages (e.g., French, Spanish, German, Polish, and Arabic) at report level, account level and department level. |  |  | Phase 1B only | [5 empty] | As per confirmation from Patrick, local language required only for legacy FAH layer 2/8: This user story covers language patch application being led by Satheesh. Reports: Individual user stories for reports in GL and AHCS logged AHCS Source/category field on reports: See above comment GL Source/category standard field: New story to be logged COA Descrption: to flow from EDMCS AR Invoice print: English only as per agreed assumption | Ensure reports provided to tax meet requirements for localized language |  |  |  | TBD | [9 empty] | RTR | LEGACY | GL | ABC Corp - Tax Stories |  | RTR-TX-020 |  |  |  |  | Awaiting alignment with legacy FAH local solution proposed from Incorta | [5 empty] | N/A
| CSTONE-6114 | - | - | CSTONE-6114 | DP-RTR-GL-011 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | Local country tax and accounting requirement to have the ability to maintain a separate chart of accounts for statutory reporting. Mapping needs to be created between global COA and local country COA in order to align localized account and account descriptions. Additionally, Local Country teams require the ability to group or classify accounts for presentation purposes in local country Financial Statements. [ERP Component] |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Local COA for secondary ledger for France only. Rest secondary ledgers will use global COA as per KDD11. It was highlighted to team on call that even in a future release secondary ledgers that are part of 1B will continue to use same COA as defined in 1B and Patrick confirmed that's the expectation as well. For secondary ledgers using global COA, see user story RTR-GL-149 Any local presentation if required may mean additional hierarchies. Tax team to work with COA team Local COA feed from EDMCS to IAP should meet Query 69 requirement. Confirmed by EDMCS team that whatever feed from EDMCS comes to Oracle ERP will go to IAP and TeraData as well. Looped in EDMCS team [Elizabeth] on email "Language Requirement for 1B" to take it forward from EDMCS perspective | Successful updated chart of accounts for Local country tax and accounting requirements |  |  | Sprint 7 | Approved | Erica | 2021-08-05 |  |  | Sprint 7 |  |  | 1-Fit-Configuration-Functional |  | RTR | RTR-GL | GL | WESCO - Tax Stories |  | RTR-TX-041 | Ian/Vitaliy |  | Approved - Jessica |  |  |  | WESCO -Deliver Phase User Stories - GL - Batch1 - GPO Approval |  |  |  | N/A
[7 empty] | Enterprise Planning, Budgeting, and Reporting |  |  | Local country tax and accounting requirement to have the ability to maintain a separate chart of accounts for statutory reporting. Mapping needs to be created between global COA and local country COA in order to align localized account and account descriptions. Additionally, Local Country teams require the ability to group or classify accounts for presentation purposes in local country Financial Statements. [EDMCS Component] |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Local COA for secondary ledger for France only. Rest secondary ledgers will use global COA as per KDD11. It was highlighted to team on call that even in a future release secondary ledgers that are part of 1B will continue to use same COA as defined in 1B and Patrick confirmed that's the expectation as well. For secondary ledgers using global COA, see user story RTR-GL-149 Any local presentation if required may mean additional hierarchies. Tax team to work with COA team Local COA feed from EDMCS to IAP should meet Query 69 requirement. Confirmed by EDMCS team that whatever feed from EDMCS comes to Oracle ERP will go to IAP and TeraData as well. Looped in EDMCS team [Elizabeth] on email "Language Requirement for 1B" to take it forward from EDMCS perspective This is placeholder comment copied from corresponding RTR story. EDMCS team to update EDM - Application will provide framework to capture various language descriptions. International team should be providing the translated values to be loaded in the metadata. Direct integration to IAP not in scope. The metadata files generated for Teradata can be consumed as needed | Successful updated chart of accounts for Local country tax and accounting requirements | [13 empty] | EPM | EPM - COA MDM | EDMCS | WESCO - Tax Stories |  | RTR-TX-041 |  |  | Approved - Jessica | [7 empty] | N/A
|  |  |  | N/A |  |  | Close, Consolidate, and Report |  |  | Local country tax and accounting requirement to have the ability to maintain a separate chart of accounts for statutory reporting. Mapping needs to be created between global COA and local country COA in order to align localized account and account descriptions. Additionally, Local Country teams require the ability to group or classify accounts for presentation purposes in local country Financial Statements. [EPM Component - 1 to 1 mapping between ERP COA and EPM COA] |  |  | Phase 1B only | [6 empty] | Successful updated chart of accounts for Local country tax and accounting requirements | [13 empty] | EPM | EPM - CCR | FCCS | WESCO - Tax Stories |  | RTR-TX-041 |  |  | Approved - Jessica | [7 empty] | N/A
| CSTONE-6883 | CSTONE-7641 | CSTONE-11626 | Sprint 11 | DP-RTR-GL-012 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | Local country accountants require the ability or a report to output differences between Local GAAP and US GAAP basis reporting. |  |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report | RPT011 | 1. SmartView can be used for all ledgers except France local COA [separate cube due to local COA] to see data side by side for primary and secondary ledger for given set of accounts 2. Report planned to "RPT011-Confirm relevant manual journals copied to secondary" planned to confirm required journals are copied to secondary 3. If Mainframe sends two separate feeds for primary and secondary ledgers, both feeds independently will be part of reconciliation process for AHCS 7/28 Acceptance Criteria 1: Tax Team understands intent of RPT011 as noted above. No additional report planned for this user story. Tax team to perform analysis using points noted above | Ensure report provided to tax meets requirements necessary for tax |  |  | Sprint 11 | Approved | Erica | 2021-08-05 | Sprint 11 |  | Sprint 12 | Sprint 12 | Report | Report |  | RTR | RTR-GL | GL | WESCO - Tax Stories |  | RTR-TX-042 | Ian/Vitaliy |  | Approved - Jessica |  |  |  | WESCO -Deliver Phase User Stories - GL - Batch1 - GPO Approval |  |  |  | N/A
| CSTONE-6115 | - | - | CSTONE-6115 | DP-RTR-GL-013 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | Local country accountants require the ability to book statutory adjustments. The nature of statutory adjustments can be Local GAAP/US GAAP differences, audit imposed statutory adjustments, or reclass. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Secondary ledgers will be configured as per approved KDD2. These secondary ledgers can be used to book local GAAP adjustments i.e. these journals don’t need to be booked to primary / USGAAP ledgers | 1) As a statutory accountant, when I access the journal entry screen, I should be able to change the ledger to secondary or reporting ledger and successfully enter and post a journal 2) As a statutory accountant, when I use the spreadsheet journal upload, I should be able to change the ledger to secondary or reporting ledger and successfully upload and post a journal |  |  | Sprint 7 | Approved | Erica | 2021-08-05 |  |  | Sprint 7 |  |  | 1-Fit-Configuration-Functional |  | RTR | RTR-GL | GL | WESCO - Tax Stories |  | RTR-TX-043 | Ian/Vitaliy |  | Approved - Jessica |  |  |  | WESCO -Deliver Phase User Stories - GL - Batch1 - GPO Approval |  |  |  | N/A
| CSTONE-7587 | CSTONE-9869 | CSTONE-9926 | Sprint 12 | DP-RTR-GL-014A |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | The financial accounting system shall have the ability to extract data from the system at a legal entity level in a machine-readable format, capable of being processed by another system, before any data archival. Tax requires the ability to meet mandatory OECD SAF-T reporting. Data from any "sunset" or no longer utilized systems should be maintained and made available in a similar manner for a period consistent with existing data retention policies. Specifically: a. Tax needs the data to be extractable by tax year and legal entity. b. Data must also be accessible, and large volumes of transaction level detail data must be able to be extracted from the system and capable of being processed by another system to be presented to tax authorities. c. All transaction data must also contain the related master data (e.g., an archived purchase transaction with a vendor number must also include the relevant vendor master record details; Vendor name, vendor address, etc.). d. Data extraction should be enabled by an intuitive interface accessible by tax/finance personnel and must be executable in formats including .txt, .csv, .xls, among others. e. Journal entry sequencing requirement to comply with local country accounting/audit rules and standards. [ERP Component - GL] |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | RPT026 | Sequencing: Journal sequencing for outside US and Canada to be enabled at LE level [no requirement to sequencing at a lower level than LE]. Report: France FEC report RPT026 is planned to be built on Oracle Cloud ERP. Rest of reports to be pulled from IAP. Integrations planned to send GL Journals, GL balances, AHCS Balances, AHCS Journals, IC AR Invoices, IC AP Invoices, IC AR Receipts, IC AP Payments to IAP. Rest of the mentioned requirements [E.g. reports and their archiving etc.] would be pulled from IAP. IAP to address rest of requirements. | Ensure noted integration data is sent over to BI for subsequent reporting from BI |  |  | Sprint 12 | Approved | Erica | 2021-08-05 | Sprint 12 |  | Sprint 13 | Sprint 13 | Report | Report |  | RTR | RTR-GL | GL | WESCO - Tax Stories |  | TXC-TX-011 | Ian/Vitaliy |  | Approved - Jessica |  |  |  | WESCO -Deliver Phase User Stories - GL - Batch1 - GPO Approval |  |  |  | N/A
| CSTONE-6314 | CSTONE-6670 | CSTONE-7668 | CSTONE-6670 | DP-RTR-GL-014B |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | The financial accounting system shall have the ability to extract data from the system at a legal entity level in a machine-readable format, capable of being processed by another system, before any data archival. Tax requires the ability to meet mandatory OECD SAF-T reporting. Data from any "sunset" or no longer utilized systems should be maintained and made available in a similar manner for a period consistent with existing data retention policies. Specifically: a. Tax needs the data to be extractable by tax year and legal entity. b. Data must also be accessible, and large volumes of transaction level detail data must be able to be extracted from the system and capable of being processed by another system to be presented to tax authorities. c. All transaction data must also contain the related master data (e.g., an archived purchase transaction with a vendor number must also include the relevant vendor master record details; Vendor name, vendor address, etc.). d. Data extraction should be enabled by an intuitive interface accessible by tax/finance personnel and must be executable in formats including .txt, .csv, .xls, among others. e. Journal entry sequencing requirement to comply with local country accounting/audit rules and standards. [ERP Component - GL] |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT185 | Sequencing: Journal sequencing for outside US and Canada to be enabled at LE level [no requirement to sequencing at a lower level than LE]. Report: France FEC report RPT026 is planned to be built on Oracle Cloud ERP. Rest of reports to be pulled from IAP. Integrations planned to send GL Journals, GL balances, AHCS Balances, AHCS Journals, IC AR Invoices, IC AP Invoices, IC AR Receipts, IC AP Payments to IAP. Rest of the mentioned requirements [E.g. reports and their archiving etc.] would be pulled from IAP. IAP to address rest of requirements. | Ensure noted integration data is sent over to BI for subsequent reporting from BI |  |  | Sprint 10 | Approved | Erica | 2021-08-05 | Sprint 10 |  | Sprint 10 | Sprint 12 | Interface | Interface |  | RTR | RTR-GL | GL | WESCO - Tax Stories |  | TXC-TX-011 | Ian/Vitaliy |  | Approved - Jessica |  |  |  | WESCO -Deliver Phase User Stories - GL - Batch1 - GPO Approval |  |  |  | N/A
| CSTONE-6315 | CSTONE-6674 | CSTONE-7669 | CSTONE-6674 | DP-RTR-GL-014C |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | The financial accounting system shall have the ability to extract data from the system at a legal entity level in a machine-readable format, capable of being processed by another system, before any data archival. Tax requires the ability to meet mandatory OECD SAF-T reporting. Data from any "sunset" or no longer utilized systems should be maintained and made available in a similar manner for a period consistent with existing data retention policies. Specifically: a. Tax needs the data to be extractable by tax year and legal entity. b. Data must also be accessible, and large volumes of transaction level detail data must be able to be extracted from the system and capable of being processed by another system to be presented to tax authorities. c. All transaction data must also contain the related master data (e.g., an archived purchase transaction with a vendor number must also include the relevant vendor master record details; Vendor name, vendor address, etc.). d. Data extraction should be enabled by an intuitive interface accessible by tax/finance personnel and must be executable in formats including .txt, .csv, .xls, among others. e. Journal entry sequencing requirement to comply with local country accounting/audit rules and standards. [ERP Component - GL] |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT187 | Sequencing: Journal sequencing for outside US and Canada to be enabled at LE level [no requirement to sequencing at a lower level than LE]. Report: France FEC report RPT026 is planned to be built on Oracle Cloud ERP. Rest of reports to be pulled from IAP. Integrations planned to send GL Journals, GL balances, AHCS Balances, AHCS Journals, IC AR Invoices, IC AP Invoices, IC AR Receipts, IC AP Payments to IAP. Rest of the mentioned requirements [E.g. reports and their archiving etc.] would be pulled from IAP. IAP to address rest of requirements. | Ensure noted integration data is sent over to BI for subsequent reporting from BI |  |  | Sprint 10 | Approved | Erica | 2021-08-05 | Sprint 10 |  | Spritnt 10 | Sprint 12 | Interface | Interface |  | RTR | RTR-GL | GL | WESCO - Tax Stories |  | TXC-TX-011 | Ian/Vitaliy |  | Approved - Jessica |  |  |  | WESCO -Deliver Phase User Stories - GL - Batch1 - GPO Approval |  |  |  | N/A
| CSTONE-11631 | CSTONE-6307 | CSTONE-6309 | CSTONE-6309 | DP-RTR-GL-014G |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | The financial accounting system shall have the ability to extract data from the system at a legal entity level in a machine-readable format, capable of being processed by another system, before any data archival. Tax requires the ability to meet mandatory OECD SAF-T reporting. Data from any "sunset" or no longer utilized systems should be maintained and made available in a similar manner for a period consistent with existing data retention policies. Specifically: a. Tax needs the data to be extractable by tax year and legal entity. b. Data must also be accessible, and large volumes of transaction level detail data must be able to be extracted from the system and capable of being processed by another system to be presented to tax authorities. c. All transaction data must also contain the related master data (e.g., an archived purchase transaction with a vendor number must also include the relevant vendor master record details; Vendor name, vendor address, etc.). d. Data extraction should be enabled by an intuitive interface accessible by tax/finance personnel and must be executable in formats including .txt, .csv, .xls, among others. e. Journal entry sequencing requirement to comply with local country accounting/audit rules and standards. [ERP Component - GL] |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT042 | Sequencing: Journal sequencing for outside US and Canada to be enabled at LE level [no requirement to sequencing at a lower level than LE]. Report: France FEC report RPT026 is planned to be built on Oracle Cloud ERP. Rest of reports to be pulled from IAP. Integrations planned to send GL Journals, GL balances, AHCS Balances, AHCS Journals, IC AR Invoices, IC AP Invoices, IC AR Receipts, IC AP Payments to IAP. Rest of the mentioned requirements [E.g. reports and their archiving etc.] would be pulled from IAP. IAP to address rest of requirements. | Ensure noted integration data is sent over to BI for subsequent reporting from BI |  |  | Sprint 8 | Approved | Erica | 2021-08-05 | Sprint 8 |  | Sprint 10 | Sprint 10 | Interface | Interface |  | RTR | RTR-GL | GL | WESCO - Tax Stories |  | TXC-TX-011 | Ian/Vitaliy |  | Approved - Jessica |  |  |  | WESCO -Deliver Phase User Stories - GL - Batch1 - GPO Approval |  |  |  | N/A
| CSTONE-11693 | CSTONE-11694 | CSTONE-11695 |  | DP-RTR-GL-066 |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As an Intercompany Accountant, I need to have converted intercompany invoice data available in IAP and Teradata |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT185-INT186 INT189-INT190 INT232-INT233 INT234-INT235 | These interfaces are currently considering only Global intercompany source which will only pull new transactions (not-converted). As a solution for this we are considering and recommending to use source values from custom lookup for extraction. In this lookup we will store conversion related source along with Global intercompany source which will be used by impacted interfaces. | Ensure noted integration data is sent over to BI for subsequent reporting from BI |  |  |  | Approved | Rita Nanni | 2022-05-13 | Sprint 13 |  |  | Sprint 15 | [19 empty] | N/A
| CSTONE-11696 | CSTONE-11697 | CSTONE-11698 |  | DP-RTR-GL-067 |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As a GL Intercompany Accountant, I need to have converted intercompany invoice data included in reporting for IC Non Material AP and AR |  |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report | RPT019 RPT020 RPT027 RPT028 RPT209 RPT210 | These reports are currently considering only Global intercompany source which will only pull new transactions (not-converted). As a solution for this we are considering and recommending to use source values from custom lookup for extraction. In this lookup we will store conversion related source along with Global intercompany source which will be used by impacted reports. | Ensure noted integration data is sent over to BI for subsequent reporting from BI |  |  |  | Approved | Rita Nanni | 2022-05-13 | Sprint 13 |  |  | Sprint 15 | [19 empty] | N/A
| CSTONE-11699 | CSTONE-11700 | CSTONE-11701 |  | DP-RTR-GL-075 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | User story to retrofit 1A object to have the creator of Inter/Intra journals included in the Created By field in RICE ID:RPT016 reports so that there is consistency with all of the reporting. Should also include the correct Approver in the Approved by field. |  |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report | RPT016_R | Consumer of the report can filter and/or sort the fields with no need to leverage another column | Creator of journal submitted via inter/intra custom data loader is identified in creator field of report, as opposed to "FIN_INT". Correct approver is also captured in Approved by field |  |  |  | Approved | Rita |  | Sprint 14 |  |  | Sprint 16 |  |  |  | RTR | RTR-GL | GL | [9 empty] | [EXT] RE: 1B - Outbound to BI for Intercompany invoices |  |  |  | N/A
| CSTONE-7588 | CSTONE-9870 | CSTONE-9927 | Sprint 12 | DP-RTR-GL-014H |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | The financial accounting system shall have the ability to extract data from the system at a legal entity level in a machine-readable format, capable of being processed by another system, before any data archival. Tax requires the ability to meet mandatory OECD SAF-T reporting. Data from any "sunset" or no longer utilized systems should be maintained and made available in a similar manner for a period consistent with existing data retention policies. Specifically: a. Tax needs the data to be extractable by tax year and legal entity. b. Data must also be accessible, and large volumes of transaction level detail data must be able to be extracted from the system and capable of being processed by another system to be presented to tax authorities. c. All transaction data must also contain the related master data (e.g., an archived purchase transaction with a vendor number must also include the relevant vendor master record details; Vendor name, vendor address, etc.). d. Data extraction should be enabled by an intuitive interface accessible by tax/finance personnel and must be executable in formats including .txt, .csv, .xls, among others. e. Journal entry sequencing requirement to comply with local country accounting/audit rules and standards. [ERP Component - GL] |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT043 | Sequencing: Journal sequencing for outside US and Canada to be enabled at LE level [no requirement to sequencing at a lower level than LE]. Report: France FEC report RPT026 is planned to be built on Oracle Cloud ERP. Rest of reports to be pulled from IAP. Integrations planned to send GL Journals, GL balances, AHCS Balances, AHCS Journals, IC AR Invoices, IC AP Invoices, IC AR Receipts, IC AP Payments to IAP. Rest of the mentioned requirements [E.g. reports and their archiving etc.] would be pulled from IAP. IAP to address rest of requirements. | Ensure noted integration data is sent over to BI for subsequent reporting from BI |  |  | Sprint 12 | Approved | Erica | 2021-08-05 | Sprint 12 |  | Sprint 13 | Sprint 13 | Interface | Interface |  | RTR | RTR-GL | GL | WESCO - Tax Stories |  | TXC-TX-011 | Ian/Vitaliy |  | Approved - Jessica |  |  |  | WESCO -Deliver Phase User Stories - GL - Batch1 - GPO Approval |  |  |  | N/A
| CSTONE-7589 | CSTONE-9871 | CSTONE-9928 | Sprint 12 | DP-RTR-GL-014I |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | The financial accounting system shall have the ability to extract data from the system at a legal entity level in a machine-readable format, capable of being processed by another system, before any data archival. Tax requires the ability to meet mandatory OECD SAF-T reporting. Data from any "sunset" or no longer utilized systems should be maintained and made available in a similar manner for a period consistent with existing data retention policies. Specifically: a. Tax needs the data to be extractable by tax year and legal entity. b. Data must also be accessible, and large volumes of transaction level detail data must be able to be extracted from the system and capable of being processed by another system to be presented to tax authorities. c. All transaction data must also contain the related master data (e.g., an archived purchase transaction with a vendor number must also include the relevant vendor master record details; Vendor name, vendor address, etc.). d. Data extraction should be enabled by an intuitive interface accessible by tax/finance personnel and must be executable in formats including .txt, .csv, .xls, among others. e. Journal entry sequencing requirement to comply with local country accounting/audit rules and standards. [ERP Component - GL] |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT044 | Sequencing: Journal sequencing for outside US and Canada to be enabled at LE level [no requirement to sequencing at a lower level than LE]. Report: France FEC report RPT026 is planned to be built on Oracle Cloud ERP. Rest of reports to be pulled from IAP. Integrations planned to send GL Journals, GL balances, AHCS Balances, AHCS Journals, IC AR Invoices, IC AP Invoices, IC AR Receipts, IC AP Payments to IAP. Rest of the mentioned requirements [E.g. reports and their archiving etc.] would be pulled from IAP. IAP to address rest of requirements. | Ensure noted integration data is sent over to BI for subsequent reporting from BI |  |  | Sprint 12 | Approved | Erica | 2021-08-05 | Sprint 12 |  | Sprint 13 | Sprint 13 | Interface | Interface |  | RTR | RTR-GL | GL | WESCO - Tax Stories |  | TXC-TX-011 | Ian/Vitaliy |  | Approved - Jessica |  |  |  | WESCO -Deliver Phase User Stories - GL - Batch1 - GPO Approval |  |  |  | N/A
| - | - | - | N/A | - |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | The financial accounting system shall have the ability to extract data from the system at a legal entity level in a machine-readable format, capable of being processed by another system, before any data archival. Tax requires the ability to meet mandatory OECD SAF-T reporting. Data from any "sunset" or no longer utilized systems should be maintained and made available in a similar manner for a period consistent with existing data retention policies. Specifically: a. Tax needs the data to be extractable by tax year and legal entity. b. Data must also be accessible, and large volumes of transaction level detail data must be able to be extracted from the system and capable of being processed by another system to be presented to tax authorities. c. All transaction data must also contain the related master data (e.g., an archived purchase transaction with a vendor number must also include the relevant vendor master record details; Vendor name, vendor address, etc.). d. Data extraction should be enabled by an intuitive interface accessible by tax/finance personnel and must be executable in formats including .txt, .csv, .xls, among others. e. Journal entry sequencing requirement to comply with local country accounting/audit rules and standards. [BI Component] |  |  | Phase 1B only | [5 empty] | Sequencing: Journal sequencing for outside US and Canada to be enabled at LE level [no requirement to sequencing at a lower level than LE]. Report: France FEC report RPT026 is planned to be built on Oracle Cloud ERP. Rest of reports to be pulled from IAP. Integrations planned to send GL Journals, GL balances, AHCS Balances, AHCS Journals, IC AR Invoices, IC AP Invoices, IC AR Receipts, IC AP Payments to IAP. Rest of the mentioned requirements [E.g. reports and their archiving etc.] would be pulled from IAP. IAP to address rest of requirements. This is placeholder comment as a copy of related RTR user story. BI team to update | Ensure report provided to tax meets requirements necessary for tax |  |  | - |  |  |  | - | [6 empty] | RTR | BI | BI | WESCO - Tax Stories |  | TXC-TX-011 |  |  | Approved - Jessica | [7 empty] | N/A
[7 empty] | Record to Report |  |  | The CoA should provide sufficient detail to identify activity by third-party vs. intercompany and, for intercompany activity, identify the transacting party/counterparty for the purposes of recording, monitoring and reporting intercompany activity. |  |  | Phase 1B only | [6 empty] | Chart of accounts account listing includes proposed intercompany accounts that differentiate third party activity and intercompany activity (listing reviewed/approved by tax); intercompany journal entry process requires a specified trading partner; process rules in place for booking entries to intercompany accounts | [13 empty] | COA | COA | COA | WESCO - Tax Stories |  | RTR-TP-001 | [10 empty] | N/A
[7 empty] | Record to Report |  |  | The CoA should provide sufficient detail to identify intercompany activity by revenues vs. expenses for the purposes of recording, monitoring and reporting intercompany transaction volume (i.e. not netting multiple intercompany transactions) |  |  | Phase 1B only | [6 empty] | Chart of accounts account listing includes proposed intercompany accounts that differentiate between intercompany revenue activity and intercompany expense activity (listing reviewed/approved by tax); intercompany journal entry process requires a specified trading partner; process rules in place for booking entries to intercompany accounts | [13 empty] | COA | COA | COA | WESCO - Tax Stories |  | RTR-TP-002 | [10 empty] | N/A
[7 empty] | Record to Report |  |  | The CoA should provide sufficient detail to identify intercompany activity by intercompany transaction type (see intercompany transaction inventory maintained by the tax department) for the purposes of recording, monitoring and reporting intercompany transaction volume by transaction type. |  |  | Phase 1B only | [6 empty] | Intercompany journal entry process requires selection of configured transaction type field (configuration to be reviewed/approved by tax) | [13 empty] | COA | COA | COA | WESCO - Tax Stories |  | RTR-TP-003 | [10 empty] | N/A
[7 empty] | Record to Report |  |  | The CoA structure should provide sufficient detail to identify qualifying revenues and costs used as the basis for calculating, monitoring and reporting transfer pricing polices |  |  | Phase 1B only | [6 empty] | Chart of accounts account listing maintains existing account level detail (listing reviewed/approved by tax) | [13 empty] | COA | COA | COA | WESCO - Tax Stories |  | RTR-TP-004 | [10 empty] | N/A
[7 empty] | Record to Report |  |  | The CoA should provide sufficient detail to identify activity by activity included in operating income (above-the-line) vs. activity not included in operating income (below-the-line) for selected intercompany transactions for the purposes of recording, monitoring and reporting intercompany activity for management purposes vs. tax purposes. |  |  | Phase 1B only | [6 empty] | Chart of accounts account listing includes proposed intercompany accounts (reviewed/approved by tax); mapping of accounts to above-the-line/below-the-line is documented and maintained | [13 empty] | COA | COA | COA | WESCO - Tax Stories |  | RTR-TP-005 | [10 empty] | N/A
[7 empty] | Record to Report |  |  | The CoA should provide sufficient detail to identify the originator of revenues/expenses when subject to a multistep journal entry process (i.e. centralization/aggregation of revenues/expenses in pass-through legal entities) |  |  | Phase 1B only | [6 empty] | Chart of accounts account listing includes proposed intercompany accounts to accommodate pass-through transactions (reviewed/approved by tax); intercompany journal entry process requires a specified trading partner | [13 empty] | COA | COA | COA | WESCO - Tax Stories |  | RTR-TP-006 | [10 empty] | N/A
[7 empty] | Record to Report |  |  | The CoA should provide sufficient detail to track the base costs vs. the profit margin (cost plus markup) for applicable intercompany transactions. |  |  | Phase 1B only | [6 empty] | Intercompany journal entry process maintains separate detail of base costs and profit component; detail is available as a report configuration option | [13 empty] | COA | COA | COA | WESCO - Tax Stories |  | RTR-TP-007 | [10 empty] | N/A
[7 empty] | Record to Report |  |  | The CoA should provide sufficient detail to separately track the intercompany interest charged on Accounts Receivable balances separate from the associated intercompany charge. |  |  | Phase 1B only | [6 empty] | Chart of accounts account listing includes proposed intercompany account to book intercompany interest charges (listing reviewed/approved by tax); intercompany journal entry process requires a specified trading partner; process rules in place for booking entries to intercompany accounts | [13 empty] | COA | COA | COA | WESCO - Tax Stories |  | RTR-TP-008 | [10 empty] | N/A
| CSTONE-6116 | - | - | CSTONE-6116 | DP-RTR-IC-017 |  | Record to Report | Manage Intercompany Accounting | Perform Intercompany Transactions | Each legal entity and applicable branches/other units subject to intercompany agreements and/or required to report by specific jurisdictions should be assigned at least one unique legal entity/company code in the system. [ERP Component] |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Enterprise Structure as per KDD2 will be configured. IC orgs for each LE will be created one to one except as noted in IC Approval KDD for Miami Anixter Inc where for given LE two orgs will be created. IC Customers and IC Suppliers will be created one for each LE. They will be assigned to various BUs [multiple sites] to support invoicing with different partners Tax team confirmed all above meets requirement for this user story | Ensure enterprise structure does not merge more than one LE in a single LE code and Ent Structure meets tax needs. |  |  | Sprint 8 | Approved | Erica | 2021-08-05 |  |  | Sprint 8 |  |  | 1-Fit-Configuration-Functional |  | RTR | RTR-GL | IC | WESCO - Tax Stories |  | RTR-TP-009 | Ian/Vitaliy |  | Approved - Jessica |  |  |  | WESCO -Deliver Phase User Stories - GL - Batch1 - GPO Approval |  |  |  | N/A
[7 empty] | Close, Consolidate, and Report | Master Data Management | Maintain Reporting Entities | Each legal entity and applicable branches/other units subject to intercompany agreements and/or required to report by specific jurisdictions should be assigned at least one unique legal entity/company code in the system. [EPM Component] | Must Have |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | EPM-FCCS-003 - As a GL Accountant, I need the ability to set up my Entity hierarchy geographically so that it facilitates external reporting requirements | Ensure enterprise structure has one unique legal entity code and meets tax needs. | [13 empty] | EPM | EPM - CCR | FCCS | WESCO - Tax Stories |  | RTR-TP-009 |  |  | Approved - Jessica | [7 empty] | N/A
[7 empty] | Record to Report |  |  | The CoA should provide sufficient detail to identify general ledger activity by legal entity/branch/other units to support tax reporting. |  |  | Phase 1B only | [6 empty] | Account values can be sourced by legal entity for preconfigured/configurable reports | [13 empty] | COA | COA | COA | WESCO - Tax Stories |  | RTR-TP-010 |  |  | Approved - Jessica | [7 empty] | N/A
[7 empty] | Record to Report |  |  | The CoA should provide sufficient detail to identify general ledger activity by selected period (year, YTD, month, MTD). |  |  | Phase 1B only | [6 empty] | Account values can be sourced for a specified period for preconfigured/configurable reports | [13 empty] | COA | COA | COA | WESCO - Tax Stories |  | RTR-TP-011 |  |  | Approved - Jessica | [7 empty] | N/A
| CSTONE-6117 | - | - | CSTONE-6117 | DP-RTR-GL-016 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | The GL activity should be available in both US GAAP and local country GAAP |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Enterprise structure will be setup as per KDD2. Secondary ledgers will receive data for manual journals in GL [if category is setup to copy to secondary] and from AHCS [via a secondary ledger feed legacy FAH or Mainframe] | Ensure enterprise structure meets tax needs and secondary ledgers meet needs for Local Country GAAP |  |  | Sprint 7 | Approved | Erica | 2021-08-05 |  |  | Sprint 7 |  |  | 1-Fit-Configuration-Functional |  | RTR | RTR-GL | GL | WESCO - Tax Stories |  | RTR-TP-012 | Ian/Vitaliy |  | Approved - Jessica |  |  |  | WESCO -Deliver Phase User Stories - GL - Batch1 - GPO Approval |  |  |  | N/A
| CSTONE-6118 | - | - | CSTONE-6118 | DP-RTR-GL-017 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | The GL activity should be available in USD, functional currency and local currency [ERP Component] |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | ERP GL will only provide functional and entered currency. Translation to USD reporting currency will only occur in FCCS. FCCS will also support the full legal entity reporting. | Ensure all currency needs are met in GL and FCCS, as discussed in tax user story review session. |  |  | Sprint 7 | Approved | Erica | 2021-08-05 |  |  | Sprint 7 |  |  | 1-Fit-Configuration-Functional |  | RTR | RTR-GL | GL | WESCO - Tax Stories |  | RTR-TP-013 | Ian/Vitaliy |  | Approved - Jessica |  |  |  | WESCO -Deliver Phase User Stories - GL - Batch1 - GPO Approval |  |  |  | N/A
[7 empty] | Close, Consolidate, and Report |  |  | The Tax department is proactively made aware of proposed changes to the CoA (including accounts, legal entities/organization structure) that may impact transfer pricing and is included in the decision-making process. |  |  | Phase 1B only | 6-Gap-Work Around-Work Around | Gap | Work Around | Work Around |  | Tax Department will be involved in COA governance process before change requests approved by Governance Council reach EDM. No notifications will be generated from EDM. | Tax is active participant in deployed process for CoA change discussions, validation and sign-off | [13 empty] | EPM | EPM - COA MDM | EDMCS | WESCO - Tax Stories |  | RTR-TP-014 |  |  | Approved - Jessica | [7 empty] | N/A
[7 empty] | Close, Consolidate, and Report |  |  | The Tax department is party to a process to propose changes to the CoA configuration, including proposing new accounts/legal entities or requesting the use of the program/projects string to support transfer pricing requirements, as applicable. |  |  | Phase 1B only | 6-Gap-Work Around-Work Around | Gap | Work Around | Work Around |  | Tax Department will be involved in COA governance process before change requests approved by Governance Council reach EDM. No notifications will be generated from EDM. | Tax is active participant in deployed process for CoA change discussions, validation and sign-off | [13 empty] | EPM | EPM - COA MDM | EDMCS | WESCO - Tax Stories |  | RTR-TP-015 |  |  | Approved - Jessica | [7 empty] | N/A
[7 empty] | Close, Consolidate, and Report |  |  | Report listing newly added or amended G/L accounts within specific timeframe. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | out-of-box audit capabilities in EDM can be utilized to filter specific changes within a given time frame and shared as an excel file | Process in place for Tax to receive a preconfigured report with specified detail (CoA additions/modifications) on a monthly basis | [13 empty] | EPM | EPM - COA MDM | EDMCS | WESCO - Tax Stories |  | RTR-TP-016 |  |  | Approved - Jessica | [7 empty] | N/A
[7 empty] | Close, Consolidate, and Report |  |  | Report listing newly added or amended legal entities within specific timeframe. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | out-of-box audit capabilities in EDM can be utilized to filter specific changes within a given time frame and shared as an excel file | Process in place for Tax to receive a preconfigured report with specified detail (CoA additions/modifications) on a monthly basis | [13 empty] | EPM | EPM - COA MDM | EDMCS | WESCO - Tax Stories |  | RTR-TP-017 |  |  | Approved - Jessica | [7 empty] | N/A
[7 empty] | Close, Consolidate, and Report |  |  | Report listing newly added or amended operating groups within specific timeframe. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | out-of-box audit capabilities in EDM can be utilized to filter specific changes within a given time frame and shared as an excel file | Process in place for Tax to receive a preconfigured report with specified detail (CoA additions/modifications) on a monthly basis | [13 empty] | EPM | EPM - COA MDM | EDMCS | WESCO - Tax Stories |  | RTR-TP-018 |  |  | Approved - Jessica | [7 empty] | N/A
[7 empty] | Close, Consolidate, and Report |  |  | Report listing newly added or amended departments within specific timeframe. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | out-of-box audit capabilities in EDM can be utilized to filter specific changes within a given time frame and shared as an excel file | Process in place for Tax to receive a preconfigured report with specified detail (CoA additions/modifications) on a monthly basis | [13 empty] | EPM | EPM - COA MDM | EDMCS | WESCO - Tax Stories |  | RTR-TP-019 |  |  | Approved - Jessica | [7 empty] | N/A
[7 empty] | Close, Consolidate, and Report |  |  | Report listing newly added or amended sites within specific timeframe. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | out-of-box audit capabilities in EDM can be utilized to filter specific changes within a given time frame and shared as an excel file | Process in place for Tax to receive a preconfigured report with specified detail (CoA additions/modifications) on a monthly basis | [13 empty] | EPM | EPM - COA MDM | EDMCS | WESCO - Tax Stories |  | RTR-TP-020 |  |  | Approved - Jessica | [7 empty] | N/A
| CSTONE-6119 | - | - | CSTONE-6119 | DP-RTR-GL-018 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | The system shall allow authorized Tax Team members to have display/read only access across all Oracle financial accounting system(s) with drill down capability to the transaction level of detail to facilitate implementation, monitoring and reporting of transfer pricing policies. [ERP Component] |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | FCCS will contain the full legal entity data and consolidated results. Users will be able to drilldown from FCCS to ERP GL. Only FCCS will have the off-system TB loads. Tax will need to request transactional detail from the off-systems (same process as today). ERP GL will have journal entries and summarized subledger data from HUB. Users can drilldown from ERP GL to the HUB to view transactional detail from the legacy subledgers however not all data elements will be available. Users will continue to have access to the legacy subledgers and data-warehouses to continue to access subledger data as they do today. Acceptance Criteria 1: Security team to cover access requirements for Tax team | Tax team will have access to display/ read only FCCS, Hub and ERP GL |  |  | Sprint 8 | Approved | Erica | 2021-08-05 |  |  | Sprint 8 |  |  | 1-Fit-Configuration-Functional |  | RTR | RTR-GL | GL | WESCO - Tax Stories |  | RTR-TP-021 | Ian/Vitaliy |  | Approved - Jessica |  |  |  | WESCO -Deliver Phase User Stories - GL - Batch1 - GPO Approval |  |  |  | N/A
[7 empty] | Close, Consolidate, and Report | Close | Prepare Financial Statements | Tax department can generate trial balance report by selected legal entity or legal entities by time period, and report to include all available detail (account, operating group, department, site, etc.) and available in US GAAP/Local country GAAP and USD/Functional Currency/Local Currency |  |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report |  | Similar to user story EPM-FCCS-048 As a financial reporting manager, I need a report TAX_TB_LE_ACCOUNT so I can report my Tax Trial Balance by Legal Entity & Account | Ensure report meets tax needs | User should check that the formatting is correct | User can validate the values with historical data | [11 empty] | EPM | EPM - CCR | FCCS | WESCO - Tax Stories |  | RTR-TP-048 |  |  | Approved - Jessica | [7 empty] | N/A
[7 empty] | Close, Consolidate, and Report | Close | Prepare Financial Statements | Tax department can generate trial balance report by selected legal entity or legal entities by time period with monthly breakout, and report to include all available detail (account, operating group, department, site, etc.) and available in US GAAP/Local country GAAP and USD/Functional Currency/Local Currency. Report to be developed similar to workbook 2020 Foreign Functional Trial Balances.xls |  |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report |  | report can be built in SmartView | Ensure report meets tax needs | User should check that the formatting is correct | User can validate the values with historical data | [11 empty] | EPM | EPM - CCR | FCCS | WESCO - Tax Stories |  | RTR-TP-049 |  |  | Approved - Jessica | [7 empty] | N/A
| CSTONE-6318 | CSTONE-6671 | CSTONE-7672 | CSTONE-6671 | DP-RTR-IC-018A |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | Tax department can generate custom intercompany transaction volume report by legal entity/period detailing intercompany transaction volume by transaction type, transacting party, etc. and available in US GAAP/Local country GAAP and USD/Functional Currency/Local Currency [ERP Component] |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT185 | IC data [IC AR invoice, IC AP Invoice, IC AR receipts, IC AP Payments] will be sent to IAP. Required reports to be pulled from IAP. Note: Oracle ERP will only track data in entered currency and ledger currency. It will not track any data in consolidation currency 8/2 Acceptance criteria 1: If a data element is not available in Cloud ERP, IAP report to add required data element | Ensure all data needed for reporting is available in IAP or equivalent solution. |  |  | Sprint 10 | Approved | Erica | 2021-08-05 | Sprint 10 |  | Sprint 10 | Sprint 12 | Interface | Interface |  | RTR | RTR-GL | IC | WESCO - Tax Stories |  | RTR-TP-051 | Ian/Vitaliy |  | Approved - Jessica |  |  |  | WESCO -Deliver Phase User Stories - GL - Batch1 - GPO Approval |  |  |  | N/A
| CSTONE-6319 | CSTONE-6675 | CSTONE-7673 | CSTONE-6675 | DP-RTR-IC-018B |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | Tax department can generate custom intercompany transaction volume report by legal entity/period detailing intercompany transaction volume by transaction type, transacting party, etc. and available in US GAAP/Local country GAAP and USD/Functional Currency/Local Currency [ERP Component] |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT187 | IC data [IC AR invoice, IC AP Invoice, IC AR receipts, IC AP Payments] will be sent to IAP. Required reports to be pulled from IAP. Note: Oracle ERP will only track data in entered currency and ledger currency. It will not track any data in consolidation currency 8/2 Acceptance criteria 1: If a data element is not available in Cloud ERP, IAP report to add required data element | Ensure all data needed for reporting is available in IAP or equivalent solution. |  |  | Sprint 10 | Approved | Erica | 2021-08-05 | Sprint 10 |  | Spritnt 10 | Sprint 12 | Interface | Interface |  | RTR | RTR-GL | IC | WESCO - Tax Stories |  | RTR-TP-051 | Ian/Vitaliy |  | Approved - Jessica |  |  |  | WESCO -Deliver Phase User Stories - GL - Batch1 - GPO Approval |  |  |  | N/A
| CSTONE-6107 | CSTONE-11706 | CSTONE-11707 | CSTONE-6107 | DP-RTR-IC-003 |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | The intercompany invoicing module should not generate invoices with zero value |  |  | Phase 1B only | 5-Gap-Build-Extension | Gap | Build | Extension | EXT041 | This pertains to logic of LSI processor of splitting in intercompany vs intracompany. Logic details to be covered in lean specs [This is a bug in current state legacy Anixter solution] | Ensure no zero value IC invoices created |  |  | Sprint 9 | Approved | Erica | 2021-08-05 | Sprint 9 |  | Sprint 11 | Sprint 12 | Extension | Extension |  | RTR | RTR-GL | IC | WESCO - Tax Stories |  | IT10 | Ian/Vitaliy |  | Approved - Jessica |  |  |  | WESCO -Deliver Phase User Stories - GL - Batch1 - GPO Approval |  |  |  | N/A
| CSTONE-6312 | CSTONE-11708 | CSTONE-6905 | CSTONE-6312 | DP-RTR-IC-013C |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | All invoice data must be available for feeding into invoicing software or eInvoicing solutions (Edicom, Tungsten,..) [ERP Component] |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT189 | Integration will not be built to various software from Oracle Cloud ERP. Oracle Cloud ERP will feed AR and AP invoice and payment details to IAP. Required data for tax reporting will be pulled from IAP. If any field required for reporting is not available in Oracle Cloud ERP, data will be enhanced by users from IAP for tax reporting | Ensure required data for feeding into invoices solutions is available in IAP or data warehouse equivalent |  |  | Sprint 10 | Approved | Erica | 2021-08-05 | Sprint 10 |  | Sprint 11 | Sprint 12 | Interface | Interface |  | RTR | RTR-GL | IC | WESCO - Tax Stories |  | IT07 | Ian/Vitaliy |  | Approved - Jessica |  |  |  | WESCO -Deliver Phase User Stories - GL - Batch1 - GPO Approval |  |  |  | N/A
[7 empty] | Enterprise Planning, Budgeting, and Reporting |  |  | Tax department can generate custom intercompany transaction volume report by legal entity/period detailing intercompany transaction volume by transaction type, transacting party, etc. and available in US GAAP/Local country GAAP and USD/Functional Currency/Local Currency [EDMCS Component - Need ability to send EDMCS COA details with DFF/Language to IAP] |  |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope |  | Placeholder - EDMCS team to update. EDM - no new ask for EDM application as no direct integration to IAP. The metadata files generated for Teradata can be consumed as needed. | Ensure all data needed for reporting is available in IAP or equivalent solution. | [13 empty] | EPM | EPM - COA MDM | EDMCS | WESCO - Tax Stories |  | RTR-TP-051 | [10 empty] | N/A
| #N/A | #N/A | #N/A | N/A | DP-RTR-IC-084 |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | Tax department can generate custom intercompany transaction volume report by legal entity/period detailing intercompany transaction volume by transaction type, transacting party, etc. and available in US GAAP/Local country GAAP and USD/Functional Currency/Local Currency [BI Component] |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT185, INT187, INT189, INT191 | IC data [IC AR invoice, IC AP Invoice, IC AR receipts, IC AP Payments] will be sent to IAP. Required reports to be pulled from IAP. Note: Oracle ERP will only track data in entered currency and ledger currency. It will not track any data in consolidation currency BI team to update comments. Above comments are placeholder from related RTR user story | Ensure all data needed for reporting is available in IAP or equivalent solution. |  |  | - | N/A |  |  | - | [6 empty] | RTR | BI | BI | WESCO - Tax Stories |  | RTR-TP-051 |  |  | Approved - Jessica |  | Tax's update of acceptance criteria pending | [5 empty] | N/A
[7 empty] | Close, Consolidate, and Report | Close | Prepare Financial Statements | Tax department can generate intercompany journal entry summary report by legal entity/period, detailing prepared journal entries and available in USD/Functional Currency/Local Currency. Journal entry details in translated USD will be handled with a separate solution. |  |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report |  | this was originally listed as out of scope and not part of any track…Not sure the requirement is a fit for FCCS. Eliminations are automated and therefore journals do not exist…Reports can be pulled that provide this detail… per meeting with Jennifer and subsequent email follow-up this is not an EPM user story | Ensure report meets tax needs | User should check that the formatting is correct | User can validate the values with historical data | [14 empty] | WESCO - Tax Stories |  | RTR-TP-050 |  |  | Approved - Jessica | [7 empty] | N/A
| - | - | - | Sprint 12 | DP-RTR-GL-021 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | User story to make headers and other relevant labels available in French language. RICE ID:RPT026 |  |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT195 | 08/26 AR: Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' |  |  |  | Sprint 12 | Approved | Rita |  | Sprint 12 |  | Sprint 13 | Sprint 13 | Language Translation | Language Translation |  | RTR | RTR-GL | GL | [9 empty] | [EXT] RE: 1B - Outbound to BI for Intercompany invoices |  |  |  | N/A
| - | - | - | Sprint 12 | DP-RTR-GL-022 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | User story to make headers and other relevant labels available in French language. RICE ID:RPT018 |  |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT204 | 08/26 AR: Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' |  |  |  | Sprint 12 | Approved | Rita |  | Sprint 12 |  | Sprint 13 | Sprint 13 | Language Translation | Language Translation |  | RTR | RTR-GL | GL | [9 empty] | [EXT] RE: 1B - Outbound to BI for Intercompany invoices |  |  |  | N/A
| - | - | - | Sprint 12 | DP-RTR-GL-023 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | User story to make headers and other relevant labels available in French language. RICE ID:RPT046 |  |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT191 | 08/26 AR: Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' |  |  |  | Sprint 12 | Approved | Rita |  | Sprint 15 |  | Sprint 16 | Sprint 16 | Language Translation | Language Translation |  | RTR | RTR-GL | GL | [9 empty] | [EXT] RE: 1B - Outbound to BI for Intercompany invoices |  |  |  | N/A
| - | - | - | Sprint 12 | DP-RTR-GL-024 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | User story to make headers and other relevant labels available in French language. RICE ID:RPT047 |  |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT192 | 08/26 AR: Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' |  |  |  | Sprint 12 | Approved | Rita |  | Sprint 15 |  | Sprint 16 | Sprint 16 | Language Translation | Language Translation |  | RTR | RTR-GL | GL | [9 empty] | [EXT] RE: 1B - Outbound to BI for Intercompany invoices |  |  |  | N/A
| - | - | - | Sprint 12 | DP-RTR-GL-025 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | User story to make headers and other relevant labels available in French language. RICE ID:RPT049 |  |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT196 | 08/26 AR: Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' |  |  |  | Sprint 12 | Approved | Rita |  | Sprint 12 |  | Sprint 13 | Sprint 13 | Language Translation | Language Translation |  | RTR | RTR-GL | GL | [9 empty] | [EXT] RE: 1B - Outbound to BI for Intercompany invoices |  |  |  | N/A
| - | - | - | Sprint 12 | DP-RTR-GL-026 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | User story to make headers and other relevant labels available in French language. RICE ID:RPT052 |  |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT193 | 08/26 AR: Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' |  |  |  | Sprint 12 | Approved | Rita |  | Sprint 15 |  | Sprint 16 | Sprint 16 | Language Translation | Language Translation |  | RTR | RTR-GL | GL | [9 empty] | [EXT] RE: 1B - Outbound to BI for Intercompany invoices |  |  |  | N/A
| - | - | - | Sprint 12 | DP-RTR-GL-027 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | User story to make headers and other relevant labels available in French language. RICE ID:RPT054 |  |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT194 | 08/26 AR: Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' |  |  |  | Sprint 12 | Approved | Rita |  | Sprint 15 |  | Sprint 16 | Sprint 16 | Language Translation | Language Translation |  | RTR | RTR-GL | GL | [9 empty] | [EXT] RE: 1B - Outbound to BI for Intercompany invoices |  |  |  | N/A
| - | - | - | Sprint 12 | DP-RTR-GL-028 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | User story to make headers and other relevant labels available in Spanish language. RICE ID:RPT018 |  |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT204 | 08/26 AR: Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' |  |  |  | Sprint 12 | Approved | Rita |  | Sprint 12 |  | Sprint 13 | Sprint 13 | Language Translation | Language Translation |  | RTR | RTR-GL | GL | [9 empty] | [EXT] RE: 1B - Outbound to BI for Intercompany invoices |  |  |  | N/A
| - | - | - | Sprint 12 | DP-RTR-GL-029 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | User story to make headers and other relevant labels available in Spanish language. RICE ID:RPT046 |  |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT191 | 08/26 AR: Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' |  |  |  | Sprint 12 | Approved | Rita |  | Sprint 15 |  | Sprint 16 | Sprint 16 | Language Translation | Language Translation |  | RTR | RTR-GL | GL | [9 empty] | [EXT] RE: 1B - Outbound to BI for Intercompany invoices |  |  |  | N/A
| - | - | - | Sprint 12 | DP-RTR-GL-030 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | User story to make headers and other relevant labels available in Spanish language. RICE ID:RPT047 |  |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT192 | 08/26 AR: Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' |  |  |  | Sprint 12 | Approved | Rita |  | Sprint 15 |  | Sprint 16 | Sprint 16 | Language Translation | Language Translation |  | RTR | RTR-GL | GL | [9 empty] | [EXT] RE: 1B - Outbound to BI for Intercompany invoices |  |  |  | N/A
| - | - | - | Sprint 12 | DP-RTR-GL-031 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | User story to make headers and other relevant labels available in Spanish language. RICE ID:RPT049 |  |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT196 | 08/26 AR: Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' |  |  |  | Sprint 12 | Approved | Rita |  | Sprint 12 |  | Sprint 13 | Sprint 13 | Language Translation | Language Translation |  | RTR | RTR-GL | GL | [9 empty] | [EXT] RE: 1B - Outbound to BI for Intercompany invoices |  |  |  | N/A
| - | - | - | Sprint 12 | DP-RTR-GL-032 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | User story to make headers and other relevant labels available in Spanish language. RICE ID:RPT052 |  |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT193 | 08/26 AR: Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' |  |  |  | Sprint 12 | Approved | Rita |  | Sprint 15 |  | Sprint 16 | Sprint 16 | Language Translation | Language Translation |  | RTR | RTR-GL | GL | [9 empty] | [EXT] RE: 1B - Outbound to BI for Intercompany invoices |  |  |  | N/A
| - | - | - | Sprint 12 | DP-RTR-GL-033 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | User story to make headers and other relevant labels available in Spanish language. RICE ID:RPT054 |  |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT194 | 08/26 AR: Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' |  |  |  | Sprint 12 | Approved | Rita |  | Sprint 15 |  | Sprint 16 | Sprint 16 | Language Translation | Language Translation |  | RTR | RTR-GL | GL | [9 empty] | [EXT] RE: 1B - Outbound to BI for Intercompany invoices |  |  |  | N/A
| - | - | - | Sprint 12 | DP-RTR-GL-034 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | User story to make headers and other relevant labels available in German (Austria & Germany) language. RICE ID:RPT018 |  |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT204 | 08/26 AR: Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' |  |  |  | Sprint 12 | Approved | Rita |  | Sprint 12 |  | Sprint 13 | Sprint 13 | Language Translation | Language Translation |  | RTR | RTR-GL | GL | [9 empty] | [EXT] RE: 1B - Outbound to BI for Intercompany invoices |  |  |  | N/A
| - | - | - | Sprint 12 | DP-RTR-GL-035 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | User story to make headers and other relevant labels available in German (Austria & Germany) language. RICE ID:RPT046 |  |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT191 | 08/26 AR: Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' |  |  |  | Sprint 12 | Approved | Rita |  | Sprint 15 |  | Sprint 16 | Sprint 16 | Language Translation | Language Translation |  | RTR | RTR-GL | GL | [9 empty] | [EXT] RE: 1B - Outbound to BI for Intercompany invoices |  |  |  | N/A
| - | - | - | Sprint 12 | DP-RTR-GL-036 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | User story to make headers and other relevant labels available in German (Austria & Germany) language. RICE ID:RPT047 |  |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT192 | 08/26 AR: Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' |  |  |  | Sprint 12 | Approved | Rita |  | Sprint 15 |  | Sprint 16 | Sprint 16 | Language Translation | Language Translation |  | RTR | RTR-GL | GL | [9 empty] | [EXT] RE: 1B - Outbound to BI for Intercompany invoices |  |  |  | N/A
| - | - | - | Sprint 12 | DP-RTR-GL-037 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | User story to make headers and other relevant labels available in German (Austria & Germany) language. RICE ID:RPT049 |  |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT196 | 08/26 AR: Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' |  |  |  | Sprint 12 | Approved | Rita |  | Sprint 12 |  | Sprint 13 | Sprint 13 | Language Translation | Language Translation |  | RTR | RTR-GL | GL | [9 empty] | [EXT] RE: 1B - Outbound to BI for Intercompany invoices |  |  |  | N/A
| - | - | - | Sprint 12 | DP-RTR-GL-038 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | User story to make headers and other relevant labels available in German (Austria & Germany) language. RICE ID:RPT052 |  |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT193 | 08/26 AR: Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' |  |  |  | Sprint 12 | Approved | Rita |  | Sprint 15 |  | Sprint 16 | Sprint 16 | Language Translation | Language Translation |  | RTR | RTR-GL | GL | [9 empty] | [EXT] RE: 1B - Outbound to BI for Intercompany invoices |  |  |  | N/A
| - | - | - | Sprint 12 | DP-RTR-GL-039 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | User story to make headers and other relevant labels available in German (Austria & Germany) language. RICE ID:RPT054 |  |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT194 | 08/26 AR: Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' |  |  |  | Sprint 12 | Approved | Rita |  | Sprint 15 |  | Sprint 16 | Sprint 16 | Language Translation | Language Translation |  | RTR | RTR-GL | GL | [9 empty] | [EXT] RE: 1B - Outbound to BI for Intercompany invoices |  |  |  | N/A
| - | - | - | Sprint 12 | DP-RTR-GL-040 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | User story to make headers and other relevant labels available in Polish language. RICE ID:RPT018 |  |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT204 | 08/26 AR: Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' |  |  |  | Sprint 12 | Approved | Rita |  | Sprint 12 |  | Sprint 13 | Sprint 13 | Language Translation | Language Translation |  | RTR | RTR-GL | GL | [9 empty] | [EXT] RE: 1B - Outbound to BI for Intercompany invoices |  |  |  | N/A
| - | - | - | Sprint 12 | DP-RTR-GL-041 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | User story to make headers and other relevant labels available in Polish language. RICE ID:RPT046 |  |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT191 | 08/26 AR: Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' |  |  |  | Sprint 12 | Approved | Rita |  | Sprint 15 |  | Sprint 16 | Sprint 16 | Language Translation | Language Translation |  | RTR | RTR-GL | GL | [9 empty] | [EXT] RE: 1B - Outbound to BI for Intercompany invoices |  |  |  | N/A
| - | - | - | Sprint 12 | DP-RTR-GL-042 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | User story to make headers and other relevant labels available in Polish language. RICE ID:RPT047 |  |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT192 | 08/26 AR: Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' |  |  |  | Sprint 12 | Approved | Rita |  | Sprint 15 |  | Sprint 16 | Sprint 16 | Language Translation | Language Translation |  | RTR | RTR-GL | GL | [9 empty] | [EXT] RE: 1B - Outbound to BI for Intercompany invoices |  |  |  | N/A
| - | - | - | Sprint 12 | DP-RTR-GL-043 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | User story to make headers and other relevant labels available in Polish language. RICE ID:RPT049 |  |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT196 | 08/26 AR: Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' |  |  |  | Sprint 12 | Approved | Rita |  | Sprint 12 |  | Sprint 13 | Sprint 13 | Language Translation | Language Translation |  | RTR | RTR-GL | GL | [9 empty] | [EXT] RE: 1B - Outbound to BI for Intercompany invoices |  |  |  | N/A
| - | - | - | Sprint 12 | DP-RTR-GL-044 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | User story to make headers and other relevant labels available in Polish language. RICE ID:RPT052 |  |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT193 | 08/26 AR: Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' |  |  |  | Sprint 12 | Approved | Rita |  | Sprint 15 |  | Sprint 16 | Sprint 16 | Language Translation | Language Translation |  | RTR | RTR-GL | GL | [9 empty] | [EXT] RE: 1B - Outbound to BI for Intercompany invoices |  |  |  | N/A
| - | - | - | Sprint 12 | DP-RTR-GL-045 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | User story to make headers and other relevant labels available in Polish language. RICE ID:RPT054 |  |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT194 | 08/26 AR: Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' |  |  |  | Sprint 12 | Approved | Rita |  | Sprint 15 |  | Sprint 16 | Sprint 16 | Language Translation | Language Translation |  | RTR | RTR-GL | GL | [9 empty] | [EXT] RE: 1B - Outbound to BI for Intercompany invoices |  |  |  | N/A
| - | - | - | Sprint 12 | DP-RTR-GL-046 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | User story to make headers and other relevant labels available in Arabic language. RICE ID:RPT018 |  |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT204 | 08/26 AR: Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' |  |  |  | Sprint 12 | Approved | Rita |  | Sprint 12 |  | Sprint 13 | Sprint 13 | Language Translation | Language Translation |  | RTR | RTR-GL | GL | [9 empty] | [EXT] RE: 1B - Outbound to BI for Intercompany invoices |  |  |  | N/A
| - | - | - | Sprint 12 | DP-RTR-GL-047 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | User story to make headers and other relevant labels available in Arabic language. RICE ID:RPT046 |  |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT191 | 08/26 AR: Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' |  |  |  | Sprint 12 | Approved | Rita |  | Sprint 15 |  | Sprint 16 | Sprint 16 | Language Translation | Language Translation |  | RTR | RTR-GL | GL | [9 empty] | [EXT] RE: 1B - Outbound to BI for Intercompany invoices |  |  |  | N/A
| - | - | - | Sprint 12 | DP-RTR-GL-048 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | User story to make headers and other relevant labels available in Arabic language. RICE ID:RPT047 |  |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT192 | 08/26 AR: Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' |  |  |  | Sprint 12 | Approved | Rita |  | Sprint 15 |  | Sprint 16 | Sprint 16 | Language Translation | Language Translation |  | RTR | RTR-GL | GL | [9 empty] | [EXT] RE: 1B - Outbound to BI for Intercompany invoices |  |  |  | N/A
| - | - | - | Sprint 12 | DP-RTR-GL-049 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | User story to make headers and other relevant labels available in Arabic language. RICE ID:RPT049 |  |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT196 | 08/26 AR: Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' |  |  |  | Sprint 12 | Approved | Rita |  | Sprint 12 |  | Sprint 13 | Sprint 13 | Language Translation | Language Translation |  | RTR | RTR-GL | GL | [9 empty] | [EXT] RE: 1B - Outbound to BI for Intercompany invoices |  |  |  | N/A
| - | - | - | Sprint 12 | DP-RTR-GL-050 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | User story to make headers and other relevant labels available in Arabic language. RICE ID:RPT052 |  |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT193 | 08/26 AR: Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' |  |  |  | Sprint 12 | Approved | Rita |  | Sprint 15 |  | Sprint 16 | Sprint 16 | Language Translation | Language Translation |  | RTR | RTR-GL | GL | [9 empty] | [EXT] RE: 1B - Outbound to BI for Intercompany invoices |  |  |  | N/A
| - | - | - | Sprint 12 | DP-RTR-GL-051 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | User story to make headers and other relevant labels available in Arabic language. RICE ID:RPT054 |  |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT194 | 08/26 AR: Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' |  |  |  | Sprint 12 | Approved | Rita |  | Sprint 15 |  | Sprint 16 | Sprint 16 | Language Translation | Language Translation |  | RTR | RTR-GL | GL | [9 empty] | [EXT] RE: 1B - Outbound to BI for Intercompany invoices |  |  |  | N/A
| CSTONE-7601 | CSTONE-9883 | CSTONE-9940 | Sprint 12 | DP-RTR-GL-052 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | User story to retrofit 1A object to include additional sequence column. RICE ID:RPT002 |  |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report | RPT002_R |  |  |  |  | Sprint 12 | Approved | Rita |  | Sprint 12 |  | Sprint 13 | Sprint 13 | Report | Report |  | RTR | RTR-GL | GL | [9 empty] | [EXT] RE: 1B - Outbound to BI for Intercompany invoices |  |  |  | N/A
| CSTONE-6884 | CSTONE-7642 | CSTONE-11692 | Sprint 12 | DP-RTR-GL-053 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | User story to retrofit 1A object to include additional sequence column. RICE ID:RPT011 |  |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report | RPT011 |  |  |  |  | Sprint 12 | Approved | Rita |  | Sprint 11 |  | Sprint 12 | Sprint 12 | Report | Report |  | RTR | RTR-GL | GL | [9 empty] | [EXT] RE: 1B - Outbound to BI for Intercompany invoices |  |  |  | N/A
| CSTONE-7602 | CSTONE-9884 | CSTONE-9941 | Sprint 12 | DP-RTR-GL-054 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | User story to retrofit 1A object to include additional sequence column. RICE ID:RPT016 |  |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report | RPT016_R |  |  |  |  | Sprint 12 | Approved | Rita |  | #N/A |  | #N/A | #N/A | #N/A | #N/A |  | RTR | RTR-GL | GL | [9 empty] | [EXT] RE: 1B - Outbound to BI for Intercompany invoices |  |  |  | N/A
| CSTONE-7603 | CSTONE-9885 | CSTONE-9942 | Sprint 12 | DP-RTR-GL-055 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | User story to retrofit 1A object to include additional sequence column. RICE ID:RPT042 |  |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report | RPT042_R |  |  |  |  | Sprint 12 | Approved | Rita |  | Sprint 12 |  | Sprint 13 | Sprint 13 | Report | Report |  | RTR | RTR-GL | GL | [9 empty] | [EXT] RE: 1B - Outbound to BI for Intercompany invoices |  |  |  | N/A
| CSTONE-7604 | CSTONE-9886 | CSTONE-9943 | Sprint 12 | DP-RTR-GL-056 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | User story to retrofit 1A object to include additional sequence column. RICE ID:RPT043 |  |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report | RPT043_R |  |  |  |  | Sprint 12 | Approved | Rita |  | Sprint 12 |  | Sprint 13 | Sprint 13 | Report | Report |  | RTR | RTR-GL | GL | [9 empty] | [EXT] RE: 1B - Outbound to BI for Intercompany invoices |  |  |  | N/A
| CSTONE-7605 | CSTONE-13158 | CSTONE-13159 | Sprint 12 | DP-RTR-GL-057 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | User story to retrofit 1A object to include additional sequence column. RICE ID:RPT101 |  |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report | RPT101_R | 2/3: Retrofit required for sequencing column. During retrofit discussion to be discussed whether this should work for secondary ledger or not. Current assumption is it should work for secondary as well | Updated report should have GL journal sequence |  |  | Sprint 12 | Approved | Rita |  | Sprint 12 |  |  | Sprint 13 |  |  |  | RTR | RTR-GL | GL | [9 empty] | [EXT] RE: 1B - Outbound to BI for Intercompany invoices |  |  |  | N/A
| CSTONE-7606 | CSTONE-9887 | CSTONE-9944 | Sprint 12 | DP-RTR-GL-058 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | User story to retrofit 1A object to include additional sequence column. RICE ID:RPT026 |  |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report | RPT026 |  |  |  |  | Sprint 12 | Approved | Rita |  | Sprint 12 |  |  | Sprint 13 | Report | Report |  | RTR | RTR-GL | GL | [9 empty] | [EXT] RE: 1B - Outbound to BI for Intercompany invoices |  |  |  | N/A
| CSTONE-7607 | CSTONE-9888 | CSTONE-9945 | Sprint 12 | DP-RTR-GL-059 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | User story to retrofit 1A object to include additional sequence column. RICE ID:RPT046 |  |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report | RPT046_R |  |  |  |  | Sprint 12 | Approved | Rita |  | Sprint 12 |  |  | Sprint 13 | Report | Report |  | RTR | RTR-GL | GL | [9 empty] | [EXT] RE: 1B - Outbound to BI for Intercompany invoices |  |  |  | N/A
| - | - | - | Sprint 12 | DP-RTR-IC-019 |  | Record to Report | Manage Intercompany Accounting | Perform Intercompany Transactions | User story to make headers and other relevant labels available in French language. RICE ID:RPT019 |  |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT197 | 08/26 AR: Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' |  |  |  | Sprint 12 | Approved | Rita |  | Sprint 12 |  |  | Sprint 13 | Language Translation | Language Translation |  | RTR | RTR-GL | IC | [9 empty] | [EXT] RE: 1B - Outbound to BI for Intercompany invoices |  |  |  | N/A
| - | - | - | Sprint 12 | DP-RTR-IC-020 |  | Record to Report | Manage Intercompany Accounting | Perform Intercompany Transactions | User story to make headers and other relevant labels available in French language. RICE ID:RPT027 |  |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT198 | 08/26 AR: Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' |  |  |  | Sprint 12 | Approved | Rita |  | Sprint 11 |  |  | Sprint 12 | Language Translation | Language Translation |  | RTR | RTR-GL | IC | [9 empty] | [EXT] RE: 1B - Outbound to BI for Intercompany invoices |  |  |  | N/A
| - | - | - | Sprint 12 | DP-RTR-IC-021 |  | Record to Report | Manage Intercompany Accounting | Perform Intercompany Transactions | User story to make headers and other relevant labels available in French language. RICE ID:RPT028 |  |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT199 | 08/26 AR: Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' |  |  |  | Sprint 12 | Approved | Rita |  | Sprint 11 |  |  | Sprint 12 | Language Translation | Language Translation |  | RTR | RTR-GL | IC | [9 empty] | [EXT] RE: 1B - Outbound to BI for Intercompany invoices |  |  |  | N/A
| - | - | - | Sprint 12 | DP-RTR-IC-025 |  | Record to Report | Manage Intercompany Accounting | Perform Intercompany Transactions | User story to make headers and other relevant labels available in French language. RICE ID:RPT032 |  |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT205 | 08/26 AR: Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' |  |  |  | Sprint 12 | Approved | Rita |  | Sprint 12 |  |  | Sprint 13 | Language Translation | Language Translation |  | RTR | RTR-GL | IC | [9 empty] | [EXT] RE: 1B - Outbound to BI for Intercompany invoices |  |  |  | N/A
| - | - | - | Sprint 12 | DP-RTR-IC-026 |  | Record to Report | Manage Intercompany Accounting | Perform Intercompany Transactions | User story to make headers and other relevant labels available in French language. RICE ID:RPT033 |  |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT200 | 08/26 AR: Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' |  |  |  | Sprint 12 | Approved | Rita |  | Sprint 12 |  |  | Sprint 13 | Language Translation | Language Translation |  | RTR | RTR-GL | IC | [9 empty] | [EXT] RE: 1B - Outbound to BI for Intercompany invoices |  |  |  | N/A
| - | - | - | Sprint 12 | DP-RTR-IC-027 |  | Record to Report | Manage Intercompany Accounting | Perform Intercompany Transactions | User story to make headers and other relevant labels available in French language. RICE ID:RPT034 |  |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT201 | 08/26 AR: Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' |  |  |  | Sprint 12 | Approved | Rita |  | Sprint 12 |  |  | Sprint 13 | Language Translation | Language Translation |  | RTR | RTR-GL | IC | [9 empty] | [EXT] RE: 1B - Outbound to BI for Intercompany invoices |  |  |  | N/A
| - | - | - | Sprint 12 | DP-RTR-IC-028 |  | Record to Report | Manage Intercompany Accounting | Perform Intercompany Transactions | User story to make headers and other relevant labels available in French language. RICE ID:RPT035 |  |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT202 | 08/26 AR: Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' |  |  |  | Sprint 12 | Approved | Rita |  | Sprint 12 |  |  | Sprint 13 | Language Translation | Language Translation |  | RTR | RTR-GL | IC | [9 empty] | [EXT] RE: 1B - Outbound to BI for Intercompany invoices |  |  |  | N/A
| - | - | - | Sprint 12 | DP-RTR-IC-029 |  | Record to Report | Manage Intercompany Accounting | Perform Intercompany Transactions | User story to make headers and other relevant labels available in French language. RICE ID:RPT036 |  |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT203 | 08/26 AR: Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' |  |  |  | Sprint 12 | Approved | Rita |  | Sprint 11 |  |  | Sprint 12 | Language Translation | Language Translation |  | RTR | RTR-GL | IC | [9 empty] | [EXT] RE: 1B - Outbound to BI for Intercompany invoices |  |  |  | N/A
| - | - | - | Sprint 12 | DP-RTR-IC-031 |  | Record to Report | Manage Intercompany Accounting | Perform Intercompany Transactions | User story to make headers and other relevant labels available in Spanish language. RICE ID:RPT019 |  |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT197 | 08/26 AR: Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' |  |  |  | Sprint 12 | Approved | Rita |  | Sprint 12 |  |  | Sprint 13 | Language Translation | Language Translation |  | RTR | RTR-GL | IC | [9 empty] | [EXT] RE: 1B - Outbound to BI for Intercompany invoices |  |  |  | N/A
| - | - | - | Sprint 12 | DP-RTR-IC-033 |  | Record to Report | Manage Intercompany Accounting | Perform Intercompany Transactions | User story to make headers and other relevant labels available in Spanish language. RICE ID:RPT027 |  |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT198 | 08/26 AR: Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' |  |  |  | Sprint 12 | Approved | Rita |  | Sprint 11 |  |  | Sprint 12 | Language Translation | Language Translation |  | RTR | RTR-GL | IC | [9 empty] | [EXT] RE: 1B - Outbound to BI for Intercompany invoices |  |  |  | N/A
| - | - | - | Sprint 12 | DP-RTR-IC-034 |  | Record to Report | Manage Intercompany Accounting | Perform Intercompany Transactions | User story to make headers and other relevant labels available in Spanish language. RICE ID:RPT028 |  |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT199 | 08/26 AR: Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' |  |  |  | Sprint 12 | Approved | Rita |  | Sprint 11 |  |  | Sprint 12 | Language Translation | Language Translation |  | RTR | RTR-GL | IC | [9 empty] | [EXT] RE: 1B - Outbound to BI for Intercompany invoices |  |  |  | N/A
| - | - | - | Sprint 12 | DP-RTR-IC-037 |  | Record to Report | Manage Intercompany Accounting | Perform Intercompany Transactions | User story to make headers and other relevant labels available in Spanish language. RICE ID:RPT032 |  |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT205 | 08/26 AR: Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' |  |  |  | Sprint 12 | Approved | Rita |  | Sprint 12 |  |  | Sprint 13 | Language Translation | Language Translation |  | RTR | RTR-GL | IC | [9 empty] | [EXT] RE: 1B - Outbound to BI for Intercompany invoices |  |  |  | N/A
| - | - | - | Sprint 12 | DP-RTR-IC-038 |  | Record to Report | Manage Intercompany Accounting | Perform Intercompany Transactions | User story to make headers and other relevant labels available in Spanish language. RICE ID:RPT033 |  |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT200 | 08/26 AR: Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' |  |  |  | Sprint 12 | Approved | Rita |  | Sprint 12 |  |  | Sprint 13 | Language Translation | Language Translation |  | RTR | RTR-GL | IC | [9 empty] | [EXT] RE: 1B - Outbound to BI for Intercompany invoices |  |  |  | N/A
| - | - | - | Sprint 12 | DP-RTR-IC-039 |  | Record to Report | Manage Intercompany Accounting | Perform Intercompany Transactions | User story to make headers and other relevant labels available in Spanish language. RICE ID:RPT034 |  |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT201 | 08/26 AR: Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' |  |  |  | Sprint 12 | Approved | Rita |  | Sprint 12 |  |  | Sprint 13 | Language Translation | Language Translation |  | RTR | RTR-GL | IC | [9 empty] | [EXT] RE: 1B - Outbound to BI for Intercompany invoices |  |  |  | N/A
| - | - | - | Sprint 12 | DP-RTR-IC-040 |  | Record to Report | Manage Intercompany Accounting | Perform Intercompany Transactions | User story to make headers and other relevant labels available in Spanish language. RICE ID:RPT035 |  |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT202 | 08/26 AR: Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' |  |  |  | Sprint 12 | Approved | Rita |  | Sprint 12 |  |  | Sprint 13 | Language Translation | Language Translation |  | RTR | RTR-GL | IC | [9 empty] | [EXT] RE: 1B - Outbound to BI for Intercompany invoices |  |  |  | N/A
| - | - | - | Sprint 12 | DP-RTR-IC-041 |  | Record to Report | Manage Intercompany Accounting | Perform Intercompany Transactions | User story to make headers and other relevant labels available in Spanish language. RICE ID:RPT036 |  |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT203 | 08/26 AR: Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' |  |  |  | Sprint 12 | Approved | Rita |  | Sprint 11 |  |  | Sprint 12 | Language Translation | Language Translation |  | RTR | RTR-GL | IC | [9 empty] | [EXT] RE: 1B - Outbound to BI for Intercompany invoices |  |  |  | N/A
| - | - | - | Sprint 12 | DP-RTR-IC-043 |  | Record to Report | Manage Intercompany Accounting | Perform Intercompany Transactions | User story to make headers and other relevant labels available in German (Austria & Germany) language. RICE ID:RPT019 |  |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT197 | 08/26 AR: Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' |  |  |  | Sprint 12 | Approved | Rita |  | Sprint 12 |  |  | Sprint 13 | Language Translation | Language Translation |  | RTR | RTR-GL | IC | [9 empty] | [EXT] RE: 1B - Outbound to BI for Intercompany invoices |  |  |  | N/A
| - | - | - | Sprint 12 | DP-RTR-IC-045 |  | Record to Report | Manage Intercompany Accounting | Perform Intercompany Transactions | User story to make headers and other relevant labels available in German (Austria & Germany) language. RICE ID:RPT027 |  |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT198 | 08/26 AR: Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' |  |  |  | Sprint 12 | Approved | Rita |  | Sprint 11 |  |  | Sprint 12 | Language Translation | Language Translation |  | RTR | RTR-GL | IC | [9 empty] | [EXT] RE: 1B - Outbound to BI for Intercompany invoices |  |  |  | N/A
| - | - | - | Sprint 12 | DP-RTR-IC-046 |  | Record to Report | Manage Intercompany Accounting | Perform Intercompany Transactions | User story to make headers and other relevant labels available in German (Austria & Germany) language. RICE ID:RPT028 |  |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT199 | 08/26 AR: Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' |  |  |  | Sprint 12 | Approved | Rita |  | Sprint 11 |  |  | Sprint 12 | Language Translation | Language Translation |  | RTR | RTR-GL | IC | [9 empty] | [EXT] RE: 1B - Outbound to BI for Intercompany invoices |  |  |  | N/A
| - | - | - | Sprint 12 | DP-RTR-IC-049 |  | Record to Report | Manage Intercompany Accounting | Perform Intercompany Transactions | User story to make headers and other relevant labels available in German (Austria & Germany) language. RICE ID:RPT032 |  |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT205 | 08/26 AR: Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' |  |  |  | Sprint 12 | Approved | Rita |  | Sprint 12 |  |  | Sprint 13 | Language Translation | Language Translation |  | RTR | RTR-GL | IC | [9 empty] | [EXT] RE: 1B - Outbound to BI for Intercompany invoices |  |  |  | N/A
| - | - | - | Sprint 12 | DP-RTR-IC-050 |  | Record to Report | Manage Intercompany Accounting | Perform Intercompany Transactions | User story to make headers and other relevant labels available in German (Austria & Germany) language. RICE ID:RPT033 |  |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT200 | 08/26 AR: Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' |  |  |  | Sprint 12 | Approved | Rita |  | Sprint 12 |  |  | Sprint 13 | Language Translation | Language Translation |  | RTR | RTR-GL | IC | [9 empty] | [EXT] RE: 1B - Outbound to BI for Intercompany invoices |  |  |  | N/A
| - | - | - | Sprint 12 | DP-RTR-IC-051 |  | Record to Report | Manage Intercompany Accounting | Perform Intercompany Transactions | User story to make headers and other relevant labels available in German (Austria & Germany) language. RICE ID:RPT034 |  |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT201 | 08/26 AR: Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' |  |  |  | Sprint 12 | Approved | Rita |  | Sprint 12 |  |  | Sprint 13 | Language Translation | Language Translation |  | RTR | RTR-GL | IC | [9 empty] | [EXT] RE: 1B - Outbound to BI for Intercompany invoices |  |  |  | N/A
| - | - | - | Sprint 12 | DP-RTR-IC-052 |  | Record to Report | Manage Intercompany Accounting | Perform Intercompany Transactions | User story to make headers and other relevant labels available in German (Austria & Germany) language. RICE ID:RPT035 |  |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT202 | 08/26 AR: Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' |  |  |  | Sprint 12 | Approved | Rita |  | Sprint 12 |  |  | Sprint 13 | Language Translation | Language Translation |  | RTR | RTR-GL | IC | [9 empty] | [EXT] RE: 1B - Outbound to BI for Intercompany invoices |  |  |  | N/A
| - | - | - | Sprint 12 | DP-RTR-IC-053 |  | Record to Report | Manage Intercompany Accounting | Perform Intercompany Transactions | User story to make headers and other relevant labels available in German (Austria & Germany) language. RICE ID:RPT036 |  |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT203 | 08/26 AR: Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' |  |  |  | Sprint 12 | Approved | Rita |  | Sprint 11 |  |  | Sprint 12 | Language Translation | Language Translation |  | RTR | RTR-GL | IC | [9 empty] | [EXT] RE: 1B - Outbound to BI for Intercompany invoices |  |  |  | N/A
| - | - | - | Sprint 12 | DP-RTR-IC-055 |  | Record to Report | Manage Intercompany Accounting | Perform Intercompany Transactions | User story to make headers and other relevant labels available in Polish language. RICE ID:RPT019 |  |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT197 | 08/26 AR: Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' |  |  |  | Sprint 12 | Approved | Rita |  | Sprint 12 |  |  | Sprint 13 | Language Translation | Language Translation |  | RTR | RTR-GL | IC | [9 empty] | [EXT] RE: 1B - Outbound to BI for Intercompany invoices |  |  |  | N/A
| - | - | - | Sprint 12 | DP-RTR-IC-057 |  | Record to Report | Manage Intercompany Accounting | Perform Intercompany Transactions | User story to make headers and other relevant labels available in Polish language. RICE ID:RPT027 |  |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT198 | 08/26 AR: Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' |  |  |  | Sprint 12 | Approved | Rita |  | Sprint 11 |  |  | Sprint 12 | Language Translation | Language Translation |  | RTR | RTR-GL | IC | [9 empty] | [EXT] RE: 1B - Outbound to BI for Intercompany invoices |  |  |  | N/A
| - | - | - | Sprint 12 | DP-RTR-IC-058 |  | Record to Report | Manage Intercompany Accounting | Perform Intercompany Transactions | User story to make headers and other relevant labels available in Polish language. RICE ID:RPT028 |  |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT199 | 08/26 AR: Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' |  |  |  | Sprint 12 | Approved | Rita |  | Sprint 11 |  |  | Sprint 12 | Language Translation | Language Translation |  | RTR | RTR-GL | IC | [9 empty] | [EXT] RE: 1B - Outbound to BI for Intercompany invoices |  |  |  | N/A
| - | - | - | Sprint 12 | DP-RTR-IC-061 |  | Record to Report | Manage Intercompany Accounting | Perform Intercompany Transactions | User story to make headers and other relevant labels available in Polish language. RICE ID:RPT032 |  |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT205 | 08/26 AR: Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' |  |  |  | Sprint 12 | Approved | Rita |  | Sprint 12 |  |  | Sprint 13 | Language Translation | Language Translation |  | RTR | RTR-GL | IC | [9 empty] | [EXT] RE: 1B - Outbound to BI for Intercompany invoices |  |  |  | N/A
| - | - | - | Sprint 12 | DP-RTR-IC-062 |  | Record to Report | Manage Intercompany Accounting | Perform Intercompany Transactions | User story to make headers and other relevant labels available in Polish language. RICE ID:RPT033 |  |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT200 | 08/26 AR: Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' |  |  |  | Sprint 12 | Approved | Rita |  | Sprint 12 |  |  | Sprint 13 | Language Translation | Language Translation |  | RTR | RTR-GL | IC | [9 empty] | [EXT] RE: 1B - Outbound to BI for Intercompany invoices |  |  |  | N/A
| - | - | - | Sprint 12 | DP-RTR-IC-063 |  | Record to Report | Manage Intercompany Accounting | Perform Intercompany Transactions | User story to make headers and other relevant labels available in Polish language. RICE ID:RPT034 |  |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT201 | 08/26 AR: Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' |  |  |  | Sprint 12 | Approved | Rita |  | Sprint 12 |  |  | Sprint 13 | Language Translation | Language Translation |  | RTR | RTR-GL | IC | [9 empty] | [EXT] RE: 1B - Outbound to BI for Intercompany invoices |  |  |  | N/A
| - | - | - | Sprint 12 | DP-RTR-IC-064 |  | Record to Report | Manage Intercompany Accounting | Perform Intercompany Transactions | User story to make headers and other relevant labels available in Polish language. RICE ID:RPT035 |  |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT202 | 08/26 AR: Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' |  |  |  | Sprint 12 | Approved | Rita |  | Sprint 12 |  |  | Sprint 13 | Language Translation | Language Translation |  | RTR | RTR-GL | IC | [9 empty] | [EXT] RE: 1B - Outbound to BI for Intercompany invoices |  |  |  | N/A
| - | - | - | Sprint 12 | DP-RTR-IC-065 |  | Record to Report | Manage Intercompany Accounting | Perform Intercompany Transactions | User story to make headers and other relevant labels available in Polish language. RICE ID:RPT036 |  |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT203 | 08/26 AR: Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' |  |  |  | Sprint 12 | Approved | Rita |  | Sprint 11 |  |  | Sprint 12 | Language Translation | Language Translation |  | RTR | RTR-GL | IC | [9 empty] | [EXT] RE: 1B - Outbound to BI for Intercompany invoices |  |  |  | N/A
| - | - | - | Sprint 12 | DP-RTR-IC-067 |  | Record to Report | Manage Intercompany Accounting | Perform Intercompany Transactions | User story to make headers and other relevant labels available in Arabic language. RICE ID:RPT019 |  |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT197 | 08/26 AR: Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' |  |  |  | Sprint 12 | Approved | Rita |  | Sprint 12 |  |  | Sprint 13 | Language Translation | Language Translation |  | RTR | RTR-GL | IC | [9 empty] | [EXT] RE: 1B - Outbound to BI for Intercompany invoices |  |  |  | N/A
| - | - | - | Sprint 12 | DP-RTR-IC-069 |  | Record to Report | Manage Intercompany Accounting | Perform Intercompany Transactions | User story to make headers and other relevant labels available in Arabic language. RICE ID:RPT027 |  |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT198 | 08/26 AR: Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' |  |  |  | Sprint 12 | Approved | Rita |  | Sprint 11 |  |  | Sprint 12 | Language Translation | Language Translation |  | RTR | RTR-GL | IC | [9 empty] | [EXT] RE: 1B - Outbound to BI for Intercompany invoices |  |  |  | N/A
| - | - | - | Sprint 12 | DP-RTR-IC-070 |  | Record to Report | Manage Intercompany Accounting | Perform Intercompany Transactions | User story to make headers and other relevant labels available in Arabic language. RICE ID:RPT028 |  |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT199 | 08/26 AR: Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' |  |  |  | Sprint 12 | Approved | Rita |  | Sprint 11 |  |  | Sprint 12 | Language Translation | Language Translation |  | RTR | RTR-GL | IC | [9 empty] | [EXT] RE: 1B - Outbound to BI for Intercompany invoices |  |  |  | N/A
| - | - | - | Sprint 12 | DP-RTR-IC-073 |  | Record to Report | Manage Intercompany Accounting | Perform Intercompany Transactions | User story to make headers and other relevant labels available in Arabic language. RICE ID:RPT032 |  |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT205 | 08/26 AR: Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' |  |  |  | Sprint 12 | Approved | Rita |  | Sprint 12 |  |  | Sprint 13 | Language Translation | Language Translation |  | RTR | RTR-GL | IC | [9 empty] | [EXT] RE: 1B - Outbound to BI for Intercompany invoices |  |  |  | N/A
| - | - | - | Sprint 12 | DP-RTR-IC-074 |  | Record to Report | Manage Intercompany Accounting | Perform Intercompany Transactions | User story to make headers and other relevant labels available in Arabic language. RICE ID:RPT033 |  |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT200 | 08/26 AR: Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' |  |  |  | Sprint 12 | Approved | Rita |  | Sprint 12 |  |  | Sprint 13 | Language Translation | Language Translation |  | RTR | RTR-GL | IC | [9 empty] | [EXT] RE: 1B - Outbound to BI for Intercompany invoices |  |  |  | N/A
| - | - | - | Sprint 12 | DP-RTR-IC-075 |  | Record to Report | Manage Intercompany Accounting | Perform Intercompany Transactions | User story to make headers and other relevant labels available in Arabic language. RICE ID:RPT034 |  |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT201 | 08/26 AR: Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' |  |  |  | Sprint 12 | Approved | Rita |  | Sprint 12 |  |  | Sprint 13 | Language Translation | Language Translation |  | RTR | RTR-GL | IC | [9 empty] | [EXT] RE: 1B - Outbound to BI for Intercompany invoices |  |  |  | N/A
| - | - | - | Sprint 12 | DP-RTR-IC-076 |  | Record to Report | Manage Intercompany Accounting | Perform Intercompany Transactions | User story to make headers and other relevant labels available in Arabic language. RICE ID:RPT035 |  |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT202 | 08/26 AR: Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' |  |  |  | Sprint 12 | Approved | Rita |  | Sprint 12 |  |  | Sprint 13 | Language Translation | Language Translation |  | RTR | RTR-GL | IC | [9 empty] | [EXT] RE: 1B - Outbound to BI for Intercompany invoices |  |  |  | N/A
| - | - | - | Sprint 12 | DP-RTR-IC-077 |  | Record to Report | Manage Intercompany Accounting | Perform Intercompany Transactions | User story to make headers and other relevant labels available in Arabic language. RICE ID:RPT036 |  |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT203 | 08/26 AR: Report has been moved to BI per latest SteerCo decision. Hence this User Story Disposition is done as 'Out of scope' |  |  |  | Sprint 12 | Approved | Rita |  | Sprint 11 |  |  | Sprint 12 | Language Translation | Language Translation |  | RTR | RTR-GL | IC | [9 empty] | [EXT] RE: 1B - Outbound to BI for Intercompany invoices |  |  |  | N/A
| CSTONE-6313 | CSTONE-11710 | CSTONE-6906 | CSTONE-6313 | DP-RTR-IC-013D |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | All invoice data must be available for feeding into invoicing software or eInvoicing solutions (Edicom, Tungsten,..) [ERP Component] |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT191 | Integration will not be built to various software from Oracle Cloud ERP. Oracle Cloud ERP will feed AR and AP invoice and payment details to IAP. Required data for tax reporting will be pulled from IAP. If any field required for reporting is not available in Oracle Cloud ERP, data will be enhanced by users from IAP for tax reporting | Ensure required data for feeding into invoices solutions is available in IAP or data warehouse equivalent |  |  | Sprint 10 | Approved | Erica | 2021-08-05 | Sprint 10 |  |  | Sprint 11 | Interface | Interface |  | RTR | RTR-GL | IC | WESCO - Tax Stories |  | IT07 | Ian/Vitaliy |  | Approved - Jessica |  |  |  | WESCO -Deliver Phase User Stories - GL - Batch1 - GPO Approval |  |  |  | N/A
| CSTONE-6322 | CSTONE-6677 | CSTONE-9976 | CSTONE-6677 | DP-RTR-IC-080 |  | Record to Report | Manage Intercompany Accounting | Perform Intercompany Transactions | Open AP Invoice Balance to IAP |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT232 |  |  |  |  | Sprint 10 | Approved | Rita |  | Sprint 12 |  |  | Sprint 10 | Interface | Interface |  | RTR | RTR-GL | IC | [9 empty] | [EXT] RE: 1B - Outbound to BI for Intercompany invoices |  |  |  | N/A
| CSTONE-6323 | CSTONE-6678 | CSTONE-9977 | CSTONE-6678 | DP-RTR-IC-081 |  | Record to Report | Manage Intercompany Accounting | Perform Intercompany Transactions | Open AP Invoice Balance to TeraData |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT233 |  |  |  |  | Sprint 10 | Approved | Rita |  | Sprint 10 |  |  | Sprint 13 | Interface | Interface |  | RTR | RTR-GL | IC | [9 empty] | [EXT] RE: 1B - Outbound to BI for Intercompany invoices |  |  |  | N/A
| CSTONE-6324 | CSTONE-9915 | CSTONE-9978 | CSTONE-6324 | DP-RTR-IC-082 |  | Record to Report | Manage Intercompany Accounting | Perform Intercompany Transactions | Open AR Invoice Balance to IAP |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT234 |  |  |  |  | Sprint 10 | Approved | Rita |  | Sprint 12 |  |  | Sprint 13 | Interface | Interface |  | RTR | RTR-GL | IC | [9 empty] | [EXT] RE: 1B - Outbound to BI for Intercompany invoices |  |  |  | N/A
| CSTONE-6325 | CSTONE-9916 | CSTONE-9979 | CSTONE-6325 | DP-RTR-IC-083 |  | Record to Report | Manage Intercompany Accounting | Perform Intercompany Transactions | Open AR Invoice Balance to TeraData |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT235 |  |  |  |  | Sprint 10 | Approved | Rita |  | Sprint 12 |  |  | Sprint 13 | Interface | Interface |  | RTR | RTR-GL | IC | [9 empty] | [EXT] RE: 1B - Outbound to BI for Intercompany invoices |  |  |  | N/A
| CSTONE-6900 | CSTONE-7658 | CSTONE-11725 | Sprint 11 | DP-RTR-IC-085 |  | Record to Report | Manage Intercompany Accounting | Perform AP Period Close | As a GL Accountant, I need ability to reconcile IC AP to GL across ledger sets |  |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report | RPT190 | New report similar to RPT007 (based on SLA & GL) but also having opening balance from GL, closing balance from GL and computed closing balance based on SLA+ direct GL activities for a given period. Should run by ledger set. Common report for DP-RTR-IC-085 and DP-RTR-IC-086 i.e. for AR to GL and AP to GL Additionally unlike RPT007 this report is not expected to go to every site level | Report should tie AP SLA to GL |  |  |  | Approved | Rita |  | Sprint 11 |  |  | Sprint 12 | Report | Report |  | RTR | RTR-GL | IC | [13 empty] | N/A
| CSTONE-6901 | CSTONE-7659 | CSTONE-11726 | Sprint 11 | DP-RTR-IC-086 |  | Record to Report | Manage Intercompany Accounting | Perform AR Period Close | As a GL Accountant, I need ability to reconcile IC AR to GL across ledger sets |  |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report | RPT190 | New report similar to RPT007 (based on SLA & GL) but also having opening balance from GL, closing balance from GL and computed closing balance based on SLA+ direct GL activities for a given period. Should run by ledger set. Common report for DP-RTR-IC-085 and DP-RTR-IC-086 i.e. for AR to GL and AP to GL Additionally unlike RPT007 this report is not expected to go to every site level | Report should tie AR SLA to GL |  |  |  | Approved | Rita |  | Sprint 11 |  |  | Sprint 12 | Report | Report |  | RTR | RTR-GL | IC | [13 empty] | N/A
| CSTONE-7636 | CSTONE-9917 | CSTONE-9980 | Sprint 12 | DP-RTR-IC-087 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | User story to retrofit 1A object to include Secondary ledger journals. RICE ID:RPT101 |  |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report | RPT101_R | 2/4: Retrofit required to include secondary ledger journals. | Report should include secondary ledger data |  |  |  | Approved | Rita |  | Sprint 12 |  |  | Sprint 13 | Report | Report |  | RTR | RTR-GL | GL | [13 empty] | N/A
| CSTONE-6902 | CSTONE-7660 | CSTONE-9981 | Sprint 11 | DP-RTR-IC-088 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | User story to capture requirements for India Invoice Print. RICE ID:RPT102 |  |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report | RPT102 | Because India will be separated by BSV, Invoice will show as India to India. Invoice will need a way to pull BSV information to correctly display invoices between states |  |  |  |  | Approved | Rita |  | Sprint 11 |  |  | Sprint 12 | Report | Report |  | RTR | RTR-GL | GL | [9 empty] | [EXT] RE: 1B - India Requirement - Summary |  |  |  | N/A
| CSTONE-6903 | CSTONE-7661 | CSTONE-9982 | Sprint 11 | DP-RTR-IC-089 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | User story to capture requirements for India Invoice Print. RICE ID:RPT103 |  |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report | RPT103 | Because India will be separated by BSV, Invoice will show as India to India. Invoice will need a way to pull BSV information to correctly display invoices between states |  |  |  |  | Approved | Rita |  | Sprint 11 |  |  | Sprint 12 | Report | Report |  | RTR | RTR-GL | GL | [9 empty] | [EXT] RE: 1B - India Requirement - Summary |  |  |  | N/A
| CSTONE-13153 | - | - |  | DP-RTR-IC-090 |  | Record to Report | Manage General Ledger Accounting | Maintain Chart of Accounts | User Story to update Journal Source and Journal Category Name and Description to local languages |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | There are 10 newly created Journal Sources and 11 Journal Categories. Currently all Names and Descriptions are in English, this story is to update these to each local language in the system. This can only be accomplished by going in the sytem and changing the session language and then updatin one by the local Name and Description. |  |  |  | - | Approved | Rita | 2022-07-06 | [7 empty] | RTR | RTR-GL | GL | [13 empty] | N/A
| CSTONE-6320 | CSTONE-11712 | CSTONE-6909 | CSTONE-6320 | DP-RTR-IC-018C |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | Tax department can generate custom intercompany transaction volume report by legal entity/period detailing intercompany transaction volume by transaction type, transacting party, etc. and available in US GAAP/Local country GAAP and USD/Functional Currency/Local Currency [ERP Component] |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT189 | IC data [IC AR invoice, IC AP Invoice, IC AR receipts, IC AP Payments] will be sent to IAP. Required reports to be pulled from IAP. Note: Oracle ERP will only track data in entered currency and ledger currency. It will not track any data in consolidation currency 8/2 Acceptance criteria 1: If a data element is not available in Cloud ERP, IAP report to add required data element | Ensure all data needed for reporting is available in IAP or equivalent solution. |  |  | Sprint 10 | Approved | Erica | 2021-08-05 | Sprint 10 |  |  | Sprint 11 | Interface | Interface |  | RTR | RTR-GL | IC | WESCO - Tax Stories |  | RTR-TP-051 | Ian/Vitaliy |  | Approved - Jessica |  |  |  | WESCO -Deliver Phase User Stories - GL - Batch1 - GPO Approval |  |  |  | N/A
| CSTONE-6321 | CSTONE-11713 | CSTONE-6910 | CSTONE-6321 | DP-RTR-IC-018D |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | Tax department can generate custom intercompany transaction volume report by legal entity/period detailing intercompany transaction volume by transaction type, transacting party, etc. and available in US GAAP/Local country GAAP and USD/Functional Currency/Local Currency [ERP Component] |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT191 | IC data [IC AR invoice, IC AP Invoice, IC AR receipts, IC AP Payments] will be sent to IAP. Required reports to be pulled from IAP. Note: Oracle ERP will only track data in entered currency and ledger currency. It will not track any data in consolidation currency 8/2 Acceptance criteria 1: If a data element is not available in Cloud ERP, IAP report to add required data element | Ensure all data needed for reporting is available in IAP or equivalent solution. |  |  | Sprint 10 | Approved | Erica | 2021-08-05 | Sprint 10 |  |  | Sprint 11 | Interface | Interface |  | RTR | RTR-GL | IC | WESCO - Tax Stories |  | RTR-TP-051 | Ian/Vitaliy |  | Approved - Jessica |  |  |  | WESCO -Deliver Phase User Stories - GL - Batch1 - GPO Approval |  |  |  | N/A
| CSTONE-6120 | CSTONE-11724 | CSTONE-6911 | CSTONE-6120 | DP-RTR-IC-079 |  | Record to Report | Manage Intercompany Accounting | Perform Intercompany Transactions | User story to retrofit 1A object to include additional sequence column. RICE ID:RPT100 |  |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report | RPT100 |  |  |  |  | Sprint 9 | Approved | Rita |  | Sprint 9 |  |  | Sprint 11 | Report | Report |  | RTR | RTR-GL | IC | [9 empty] | [EXT] RE: 1B - Outbound to BI for Intercompany invoices |  |  |  | N/A
| CSTONE-8833 | CSTONE-11727 | CSTONE-11728 |  | DP-RTR-IC-091 |  | Record to Report | Manage Intercompany Accounting | Perform Intercompany Transactions | Revise integrations to include supplier number to support use with BI tools |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT232 |  |  |  |  | Sprint 10 | Approved | Rita |  | Sprint 10 |  |  | Sprint 12 |  |  |  | RTR | RTR-GL | GL | [9 empty] | RE: IC AR and AP Balance to IAP/TD |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-002 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As a GL accountant, I want a report to reconcile AHCS to GL YTD balances in view of Opening Balance, Period Acivity and End balance for the period in both Entered and accounted currency. |  |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report | RPT208 | New report similar to RPT007 (based on SLA & GL) but also having opening balance from GL, closing balance from GL and computed closing balance based on SLA+ direct GL activities for a given period. Should run by ledger set. | AHCS Opening Balance, Activites and Ending balance should map GL Balance & Activites. Reviewed report to ensure no variances between AHCS and GL. |  |  |  | Approved | Ian Plummer | 2022-04-08 | Sprint 12 |  |  | Sprint 12 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | RE: 1B AHCS : Delivery phase User stories approval Batch 1 Approved on Thu 5/5/2022 4:39 AM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-003 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL accountant, I want truncated value of STATEMENT ID (Take string of 8 characters from 14 and removes all dashes. Then concatenates that to anything from 22nd character) to be stored in supporting reference and complete STATEMENT ID as line description |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT216, INT217, EXT118, INT218, INT219, EXT119 INT240 | Enhance existing MF AP and MF AR interfaces for deriving truncated STATEMENT ID value INT216, INT217, EXT118, INT218, INT219, EXT119 INT240 | SR value are store & displayed as per business rule. Also ensure able to view full statement ID (non truncated value) in line description field. |  |  |  | Approved | Ian Plummer | 2022-04-18 | Sprint 12 |  |  | Sprint 12 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | RE: 1B AHCS : Delivery phase User stories approval Batch 1 Approved on Thu 5/5/2022 4:39 AM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-004 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL accountant, I want all Lease transaction to be posted to last day of the current month, store APPLY DATE in line description and use revised file naming so that transactions are posted to correct period and source information is stored for reference File Naming <Batch Id 021660 – NREAXE> <Batch Id 021660 – REAXE> <Batch Id 021660 – NREWSC> <Batch Id 021660 - REWSC> |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT020 | Enhance INT020 for Lease integration to derive correct accounting date. Use AHCS configuration store correct values in SRs | Validate last day of month is used for accounting date and new file naming convention is used in AHCS. Validate transactions get applied to the correct period and apply date from Lease Harbor is part of line description. |  |  |  | Approved | Ian Plummer | 2022-04-08 | Sprint 12 |  |  | Sprint 12 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | RE: 1B AHCS : Delivery phase User stories approval Batch 1 Approved on Thu 5/5/2022 4:39 AM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-005 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL accountant, I want to view SPER event types as part of MF AR subledger and SPEC event type as MF Inventory subledger. split SSI mainframe interface across MF AR and MF Inventory subledger as two different event types SPER and SPEC respectively so that WO, RTV etc. net / balance at Invoice level |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Split SSI mainframe interface across MF AR and MF Inventory subledger as two different event types SPER and SPEC respectively so that WO, RTV etc. net / balance at Invoice level Based on File Name | Reviewed SPER transactions in AR subleger and SPEC transactions in Inventory subledger. Verified that amounts posted in AHCS and transferred to GL. Reviewed supporting references. |  |  |  | Approved | Ian Plummer | 2022-04-11 | Sprint 12 |  |  | Sprint 12 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | RE: 1B AHCS : Delivery phase User stories approval Batch 1 Approved on Thu 5/5/2022 4:39 AM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-006 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As an IT Administrator, I want to split SSI mainframe interface across MF AR and MF Inventory subledger as two different event types SPER and SPEC respectively. |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT222, INT223, INT216, INT217 | Split SSI mainframe interface across MF AR and MF Inventory subledger as two different event types SPER and SPEC respectively so that WO, RTV etc. net / balance at Invoice level Based on File Name | Enhance MF AR subledger to process SPER business event/ interface Enhance MF Inventory subledger to remove SPER business event and only process SPEC business events |  |  |  | Approved | Sijo John Ian P | 2022-04-11 | Sprint 12 |  |  | Sprint 12 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | RE: 1B AHCS : Delivery phase User stories approval Batch 1 Approved on Thu 5/5/2022 4:39 AM |  |  |  | N/A
| CSTONE-9198 | CSTONE-9199 | CSTONE-9200 |  | DP-RTR-GL-060 |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As a GL accountant, I need a non-material I/C TB report by legal entity. Report should provide a detail at invoice level. |  |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report | RPT019 | non-material I/C TB report by legal entity. Report should provide a detail at invoice level. 4/15/22: This will be used for AP extract | Reviewed detailed non-material I/C TB report |  |  | Sprint 12 | Approved | Rita |  | Sprint 12 |  |  | Sprint 13 | Report | Report |  | RTR | RTR-GL | IC | [13 empty] | N/A
| CSTONE-9201 | CSTONE-9202 | CSTONE-9203 |  | DP-RTR-GL-061 |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As a GL accountant, I need a non-material I/C TB report by legal entity. Report should provide a summary at account level. |  |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report | RPT020 | need a non-material I/C TB report by legal entity. Report should provide a summary at account level. 4/15/22: This will be used for AP extract | Reviewed summarized non-material I/C TB report |  |  | Sprint 12 | Approved | Rita |  | Sprint 12 |  |  | Sprint 13 | Report | Report |  | RTR | RTR-GL | IC | [13 empty] | N/A
[5 empty] | DP-RTR-AHCS-007 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As an IT Administrator, I want Revised Mainframe AP mandatory fields to be validated |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT218, INT219, INT240 | Updated Mainframe AP mandatory fields for which OIC needs to revise Mandatory validation on Inbound file | If any mandatory fields are missing, file should be rejected. |  |  |  | Approved | Sijo John Ian P | 2022-04-26 | Sprint 12 |  |  | Sprint 12 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | RE: 1B AHCS : Delivery phase User stories approval Batch 1 Approved on Thu 5/5/2022 4:39 AM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-008 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As an IT Administrator, I want Revised Mainframe AR mandatory fields to be validated |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT216, INT217, INT 240 | Updated Mainframe AR mandatory fields for which OIC needs to revise Mandatory validation on Inbound file | If any mandatory fields are missing, file should be rejected. |  |  |  | Approved | Sijo John Ian P | 2022-04-26 | Sprint 12 |  |  | Sprint 12 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | RE: 1B AHCS : Delivery phase User stories approval Batch 1 Approved on Thu 5/5/2022 4:39 AM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-009 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As an IT Administrator, I want Revised BKIR and BKIP mandatory fields to be validated |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT216, INT217, INT 240 INT218, INT219 | Updated BKIP and BKIR for which OIC needs to revise Mandatory validation on Inbound file | If any mandatory fields are missing, file should be rejected. |  |  |  | Approved | Sijo John Ian P | 2022-04-26 | Sprint 12 |  |  | Sprint 12 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | RE: 1B AHCS : Delivery phase User stories approval Batch 1 Approved on Thu 5/5/2022 4:39 AM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-010 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL accountant, For MF AP subledger event based interface, if account and department segments missing or not received from MF. Then constant values to derive future segment using the business rules. |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT218, INT219, INT240 | For MF AP Event Based interface , COA Engine to send 'DNU' values for Account and Department, when no values received from MF. Based on Override rules available in AHCS needs to be overriden. | If rules are not defined for any segments missing values from Mainframe should not get posted into GL |  |  |  | Approved | Sijo John Ian P | 2022-04-27 | Sprint 12 |  |  | Sprint 12 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | RE: 1B AHCS : Delivery phase User stories approval Batch 1 Approved on Thu 5/5/2022 4:39 AM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-011 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL accountant, For MF AR subledger event based interface, if account and department segments missing or not received from MF. Then constant values to derive future segment using the business rules. |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT216, INT217, INT 240 | For MF AR Event Based interface , COA Engine to send 'DNU' values for Account and Department, when no values received from MF. Based on Override rules available in AHCS needs to be overriden. | If rules are not defined for any segments missing values from Mainframe should not get posted into GL |  |  |  | Approved | Sijo John Ian P | 2022-04-27 | Sprint 12 |  |  | Sprint 12 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | RE: 1B AHCS : Delivery phase User stories approval Batch 1 Approved on Thu 5/5/2022 4:39 AM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-012 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL accountant, For MF INV subledger event based interface, if account and department segments missing or not received from MF. Then constant values to derive future segment using the business rules. |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT222, INT223 | For MF INV Event Based interface , COA Engine to send 'DNU' values for Account and Department, when no values received from MF. Based on Override rules available in AHCS needs to be overriden. | If rules are not defined for any segments missing values from Mainframe should not get posted into GL |  |  |  | Approved | Sijo John Ian P | 2022-04-27 | Sprint 12 |  |  | Sprint 12 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | RE: 1B AHCS : Delivery phase User stories approval Batch 1 Approved on Thu 5/5/2022 4:39 AM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-013 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL accountant, For MF AR subledger event based interfaces CRI and SII use GL loc as BSR and location value as NSR. Then constant values to derive future segment using the business rules. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | For MF AR subledger event based interfaces CRI and SII, use 5 digit GL loc as Balance SR and location value(will come as 5 digits) as Non Balance SR. | Verify 5 digit GL loc populated as bsr and location( will be 5 digits) for nsr |  |  |  | Approved | Sijo John Ian P | 4/27/2022 4/29/22 | Sprint 12 |  |  | Sprint 12 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | RE: 1B AHCS : Delivery phase User stories approval Batch 1 Approved on Mon 5/9/2022 8:00 PM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-014 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL accountant, For MF AP subledger event based interfaces CAI use GL loc as BSR and location value as NSR. Then constant values to derive future segment using the business rules. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | For MF AP subledger event based interfaces CAI, use 5 digit GL loc as Balance SR and location value(will come as 5 digits) as Non Balance SR. | Verify 5 digit GL loc populated as bsr and location( will be 5 digits) for nsr |  |  |  | Approved | Sijo John Ian P | 4/27/2022 4/29/22 | Sprint 12 |  |  | Sprint 12 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | RE: 1B AHCS : Delivery phase User stories approval Batch 1 Approved on Mon 5/9/2022 8:00 PM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-015 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL accountant, For MF INV subledger event based interfaces ISI,CQI,IBI,AII,ICI,IRI, FII, FTI use GL loc as BSR and location value as NSR. Then constant values to derive future segment using the business rules. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | For MF Inventory subledger event based interfaces ISI,CQI,IBI,AII,ICI,IRI, FTI,FII uuse 5 digit GL loc as Balance SR and location value(will come as 5 digits) as Non Balance SR. | Verify 5 digit GL loc populated as bsr and location( will be 5 digits) for nsr |  |  |  | Approved | Sijo John Ian P | 4/27/2022 4/29/22 | Sprint 12 |  |  | Sprint 12 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | RE: 1B AHCS : Delivery phase User stories approval Batch 1 Approved on Mon 5/9/2022 8:00 PM |  |  |  | N/A
| CSTONE-13101 | - | - |  | DP-RTR-GL-062 |  | Record to Report | Manage General Ledger Accounting | Maintain Chart of Accounts | Order of Anixter Legacy GL COA in mapping engine should be: Business Unit, Location, Deaprtment, Account, Vendor, Affiliate |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | This is critical change given excel approach used in PS today uses this order, which would a front end use case of COA engine |  |  |  |  | Approved | Rita Nanni | 2022-04-28 | Sprint 12 |  |  | Sprint 12 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | RE: 1B AHCS : Delivery phase User stories approval Batch 1 Approved on Tue 5/17/2022 5:52 AM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-017 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL accountant, Unvouchered – Freight & Duty for AP subledger and Inventory subledger to be added in the beginning balance load for FAH onprem for CALA Region |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | For MF AP Subledger and Inventory Subledger able to view Unouchered Freight and Duty via onprem fah source for CALA | Review MF AP and Inventory Subledger and verified beg bal via fah onprem source for unvouchered freight and duty related to CALA |  |  |  | Approved | Ian Plummer | 4/28/2022 4/29/22 | Sprint 12 |  |  | Sprint 12 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | RE: 1B AHCS : Delivery phase User stories approval Batch 1 Approved on Mon 5/9/2022 8:00 PM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-018 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As an IT Administrator, I want to make sure COA Engine send Legacy COA in correct order "Business Unit-Location-Deaprtment-Account-Vendor-Affiliate". |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT184 | PSFA -After changing the mapping COA order, AHCS integration is still bring the right COA data to the Legacy COA fields.as below Legacy 1-4 SR is “BU-Location-Account-Dept”. | PSFA - Review Legacy COA 1-4 and 5-7 chartfileds on Subledger sample journals and ensure that right values are going to the right chartfield. |  |  |  | Approved | Manisha Deshpande Ian P | 5/2/2022, 5/5/2022 5/6/22 | Sprint 12 |  |  | Sprint 12 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | RE: 1B AHCS : Delivery phase User stories approval Batch 1 Approved on Mon 5/9/2022 8:00 PM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-019 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As an IT Administrator, I want CQI mapping to be revised for GL_LOCATION and GL_VENDOR and to be replaced by PS_LOCATION and AXE_VENDOR respectively. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | In CQI Template the fields GL_LOCATION and GL_VENDOR should be replaced by PS_LOCATION and AXE_VENDOR respectively. PS_LOCATION will be used for Location COA transformaion and AXE_VENDOR will have the Legacy Vendor Number. | Verify PS_LOCATION and AXE_VENDOR details are used for AHCS integration |  |  |  | Approved | Sijo John | 2022-05-04 | Sprint 12 |  |  | Sprint 12 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | RE: 1B AHCS : Delivery phase User stories approval Batch 1 Approved on Mon 5/9/2022 8:00 PM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-020 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As an IT Administrator, I want Revised Mainframe INV mandatory fields to be validated |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT222, INT223 | Updated Mainframe Inv mandatory fields for which OIC needs to revise Mandatory validation on Inbound file | If any mandatory fields are missing, file should be rejected. |  |  |  | Approved | Ian P | 2022-05-04 | Sprint 12 |  |  | Sprint 12 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | RE: 1B AHCS : Delivery phase User stories approval Batch 1 Approved on Mon 5/9/2022 8:00 PM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-021 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL accountant, I want to make sure For MF AR subledger pass through interfaces to have GL loc as BSR and location value as Non Supporting Reference. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | For MF AR subledger pass through interfaces no change to GL loc as BSR (Leg Seg 1-4) and location SR will be moved to Non Balance SR. | Verify GL loc populated as bsr and location for nsr |  |  |  | Approved | Ian P | 2022-05-04 | Sprint 12 |  |  | Sprint 12 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | RE: 1B AHCS : Delivery phase User stories approval Batch 1 Approved on Mon 5/9/2022 8:00 PM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-022 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL accountant, I want to make sure For MF AP subledger pass through interfaces to have GL loc as BSR and location value as Non Supporting Reference. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | For MF AP subledger pass through interfaces no change to GL loc as BSR (Leg Seg 1-4) and location SR will be moved to Non Balance SR. | Verify GL loc populated as bsr and location for nsr |  |  |  | Approved | Ian P | 2022-05-04 | Sprint 12 |  |  | Sprint 12 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | RE: 1B AHCS : Delivery phase User stories approval Batch 1 Approved on Mon 5/9/2022 8:00 PM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-023 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL accountant, I want to make sure For MF INV subledger pass through interfaces to have GL loc as BSR and location value as Non Supporting Reference. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | For MF INV subledger pass through interfaces no change to GL loc as BSR (Leg Seg 1-4) and location SR will be moved to Non Balance SR. | Verify GL loc populated as bsr and location for nsr |  |  |  | Approved | Ian P | 2022-05-04 | Sprint 12 |  |  | Sprint 12 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | RE: 1B AHCS : Delivery phase User stories approval Batch 1 Approved on Mon 5/9/2022 8:00 PM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-024 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As an IT Administrator, I want to Exclude the control record at the bottom for every SXEUS and ECLUS files |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT123, INT124 | The file will always contain the control record at the bottom for both SXEUS and ECLUS. Exclude the control record at the bottom for both SXEUS and ECLUS files | The control record is excluded and the remaining records are processed for both SXEUS and ECLUS |  |  |  | Approved | Sijo John | 2022-05-05 | Sprint 12 |  |  | Sprint 12 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | RE: 1B AHCS : Delivery phase User stories approval Batch 1 Approved on Mon 5/9/2022 8:00 PM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-025 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As an IT Administrator, I do not want any changes in MF AP, AR validation even though the short names are not matching with the current Mainframe formats. |  |  | Phase 1B only | 10-Not Required-Not Required-Not Required | Not Required | Not Required | Not Required |  | 05/09 - Based on CTPFS-4914 updates, This is not required to be changed hence marked User story as 'Not Required'. In MF AP, AR Templates the short names are not matching with the current Mainframe formats but no addition or deletion of fields or any other changes are required. | Verify the modified Short names are used for AHCS integration |  |  |  | Approved | Sijo John |  | Sprint 12 |  |  | Sprint 12 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | RE: 1B AHCS : Delivery phase User stories approval Batch 1 Thu 5/19/2022 7:15 PM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-026 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL accountant, I want to Remove Unvouchered – Freight & Duty from AP subledger and Inventory subledger from the beginning balance load for EMEA Region |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | NG 05/10 : Removed Unvouchered – Freight & Duty from AP subledger and Inventory subledger from the beginning balance load for EMEA Region | Ensure Unvouchered – Freight & Duty removed from AP subledger and Inventory subledger from the beginning balance load for EMEA Region |  |  |  | Approved | Ian Plummer | 2022-05-10 | Sprint 12 |  |  | Sprint 12 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | RE: 1B AHCS : Delivery phase User stories approval Batch 1 Approved on Tue 5/17/2022 5:52 AM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-027 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL accountant, I want to Remove Freight Accrual from Inventory subledger from the beginning balance load for all regions |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | NG 05/10 :Removed Freight Accrual from Inventory subledger from the beginning balance load for all Region | Ensure Freight Accrual removed from Inventory subledger from the beginning balance load for all Region |  |  |  | Approved | Ian Plummer | 5/10/2022 5/11/22 | Sprint 12 |  |  | Sprint 12 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | RE: 1B AHCS : Delivery phase User stories approval Batch 1 Approved on Tue 5/17/2022 5:52 AM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-028 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL accountant, I want to make sure for RPT006 , Source Transaction Number will be updated with separator ~ and its as per logic mentioned under Ext 123 lean spec |  |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report | RPT006_R | NG 05/11 : For RPT 006, Source Transaction Number will be updated with separator ~ and its as per logic used for Ext 123. | Run RPT 006 and ensure that Source Transaction Number is updated with separator ~ and is created as per new logic provided by Mike. |  |  |  | Approved | Manisha Deshpande | 2022-05-09 | Sprint 12 |  |  | Sprint 12 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | RE: 1B AHCS : Delivery phase User stories approval Batch 1 Approved on Tue 5/17/2022 5:52 AM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-029 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL accountant, I want to make sure for EXT123 , Source Transaction Number will be updated with separator ~ and its as per logic provided by Mike |  |  | Phase 1B only | 5-Gap-Build-Extension | Gap | Build | Extension | EXT123 | NG 05/11 : For EXT 123, Source Transaction Number will be updated with separator ~ and its as per logic provided by Mike | Ensure that Source Transaction Number is updated with separator ~ and is created as per new logic provided by Mike |  |  |  | Approved | Manisha Deshpande | 2022-05-09 | Sprint 12 |  |  | Sprint 12 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | RE: 1B AHCS : Delivery phase User stories approval Batch 1 Approved on Tue 5/17/2022 5:52 AM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-030 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As an IT Administrator, I want to make sure for Treasury COA Engine send Legacy COA in correct order "Business Unit-Location-Deaprtment-Account-Vendor-Affiliate". |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT045 | Treasury -After changing the mapping COA order, AHCS integration is still bring the right COA data to the Legacy COA fields. as below Legacy 1-4 SR is “BU-Location-Account-Dept”. | Treasury - Review Legacy COA 1-4 and 5-7 chartfileds on Subledger sample journals and ensure that right values are going to the right chartfield. |  |  |  | Approved | Manisha Deshpande Ian P | 2022-05-10 | Sprint 12 |  |  | Sprint 12 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | RE: 1B AHCS : Delivery phase User stories approval Batch 1 Approved on Mon 5/9/2022 8:00 PM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-031 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As an IT Administrator, I want to make sure for SXE COA Engine send Legacy COA in correct order "Business Unit-Location-Deaprtment-Account-Vendor-Affiliate". |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT123 | SXE -After changing the mapping COA order, AHCS integration is still bring the right COA data to the Legacy COA fields. as below Legacy 1-4 SR is “BU-Location-Account-Dept”. | SXE - Review Legacy COA 1-4 and 5-7 chartfileds on Subledger sample journals and ensure that right values are going to the right chartfield. |  |  |  | Approved | Manisha Deshpande Ian P | 2022-05-10 | Sprint 12 |  |  | Sprint 12 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | RE: 1B AHCS : Delivery phase User stories approval Batch 1 Approved on Mon 5/9/2022 8:00 PM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-032 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As an IT Administrator, I want to make sure for ECLIPSE COA Engine send Legacy COA in correct order "Business Unit-Location-Deaprtment-Account-Vendor-Affiliate". |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT124 | Eclipse -After changing the mapping COA order, AHCS integration is still bring the right COA data to the Legacy COA fields. as below Legacy 1-4 SR is “BU-Location-Account-Dept”. | Eclipse - Review Legacy COA 1-4 and 5-7 chartfileds on Subledger sample journals and ensure that right values are going to the right chartfield. |  |  |  | Approved | Manisha Deshpande Ian P | 2022-05-10 | Sprint 12 |  |  | Sprint 12 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | RE: 1B AHCS : Delivery phase User stories approval Batch 1 Approved on Mon 5/9/2022 8:00 PM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-033 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As an IT Administrator, I want to make sure for CLOUDPAY COA Engine send Legacy COA in correct order "Business Unit-Location-Deaprtment-Account-Vendor-Affiliate". |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT018 | CloudPay -After changing the mapping COA order, AHCS integration is still bring the right COA data to the Legacy COA fields. as below Legacy 1-4 SR is “BU-Location-Account-Dept”. | CloudPay - Review Legacy COA 1-4 and 5-7 chartfileds on Subledger sample journals and ensure that right values are going to the right chartfield. |  |  |  | Approved | Manisha Deshpande Ian P | 2022-05-10 | Sprint 12 |  |  | Sprint 12 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | RE: 1B AHCS : Delivery phase User stories approval Batch 1 Approved on Mon 5/9/2022 8:00 PM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-034 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As an IT Administrator, I want to make sure for LEASES COA Engine send Legacy COA in correct order "Business Unit-Location-Deaprtment-Account-Vendor-Affiliate". |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT020 | Leases -After changing the mapping COA order, AHCS integration is still bring the right COA data to the Legacy COA fields. as below Legacy 1-4 SR is “BU-Location-Account-Dept”. | Leases - Review Legacy COA 1-4 and 5-7 chartfileds on Subledger sample journals and ensure that right values are going to the right chartfield. |  |  |  | Approved | Manisha Deshpande Ian P | 2022-05-10 | Sprint 12 |  |  | Sprint 12 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | RE: 1B AHCS : Delivery phase User stories approval Batch 1 Approved on Mon 5/9/2022 8:00 PM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-035 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As an IT Administrator, I want to make sure for MF AP COA Engine send Legacy COA in correct order "Business Unit-Location-Deaprtment-Account-Vendor-Affiliate". |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT218, INT219, INT240 | MF AP -After changing the mapping COA order, AHCS integration is still bring the right COA data to the Legacy COA fields. as below Legacy 1-4 SR is “BU-Location-Account-Dept”. | MF AP - Review Legacy COA 1-4 and 5-7 chartfileds on Subledger sample journals and ensure that right values are going to the right chartfield. |  |  |  | Approved | Manisha Deshpande Ian P | 2022-05-10 | Sprint 12 |  |  | Sprint 12 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | RE: 1B AHCS : Delivery phase User stories approval Batch 1 Approved on Mon 5/9/2022 8:00 PM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-036 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As an IT Administrator, I want to make sure for MF AR COA Engine send Legacy COA in correct order "Business Unit-Location-Deaprtment-Account-Vendor-Affiliate". |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT216, INT217, INT 240 | MF AR -After changing the mapping COA order, AHCS integration is still bring the right COA data to the Legacy COA fields. as below Legacy 1-4 SR is “BU-Location-Account-Dept”. | MF AR - Review Legacy COA 1-4 and 5-7 chartfileds on Subledger sample journals and ensure that right values are going to the right chartfield. |  |  |  | Approved | Manisha Deshpande Ian P | 2022-05-10 | Sprint 12 |  |  | Sprint 12 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | RE: 1B AHCS : Delivery phase User stories approval Batch 1 Approved on Mon 5/9/2022 8:00 PM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-037 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As an IT Administrator, I want to make sure for MF INV COA Engine send Legacy COA in correct order "Business Unit-Location-Deaprtment-Account-Vendor-Affiliate". |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT222, INT223 | MF INV -After changing the mapping COA order, AHCS integration is still bring the right COA data to the Legacy COA fields. as below Legacy 1-4 SR is “BU-Location-Account-Dept”. | MF INV - Review Legacy COA 1-4 and 5-7 chartfileds on Subledger sample journals and ensure that right values are going to the right chartfield. |  |  |  | Approved | Manisha Deshpande Ian P | 2022-05-10 | Sprint 12 |  |  | Sprint 13 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | RE: 1B AHCS : Delivery phase User stories approval Batch 1 Approved on Mon 5/9/2022 8:00 PM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-038 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As an IT Administrator, I want to make sure forConcur COA Engine send Legacy COA in correct order "Business Unit-Location-Deaprtment-Account-Vendor-Affiliate". |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT016 | Concur -After changing the mapping COA order, AHCS integration is still bring the right COA data to the Legacy COA fields. as below Legacy 1-4 SR is “BU-Location-Account-Dept”. | Concur - Review Legacy COA 1-4 and 5-7 chartfileds on Subledger sample journals and ensure that right values are going to the right chartfield. |  |  |  | Approved | Manisha Deshpande Ian P | 2022-05-10 | Sprint 12 |  |  | Sprint 13 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | RE: 1B AHCS : Delivery phase User stories approval Batch 1 Approved on Mon 5/9/2022 8:00 PM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-039 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL accountant, I want to make sure for RPT008 , Source Transaction Number will be updated with separator ~ and its as per logic provided by Mike |  |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report | RPT008_R | For RPT 008, Source Transaction Number will be updated with separator ~ and its as per logic provided by Mike F. | Run RPT 008 and ensure that Source Transaction Number is updated with separator ~ and is created as per new logic provided by Mike. |  |  |  | Approved | Manisha Deshpande | 2022-09-12 | Sprint 12 |  |  | Sprint 13 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | RE: 1B AHCS : Delivery phase User stories approval Batch 1 Thu 5/19/2022 7:15 PM |  |  |  | N/A
| CSTONE-13154 | - | - |  | DP-RTR-GL-063 |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As an intercompany Accountant, I need to be able to process netting of Payables and Receivables transactions for related intercompany organizations |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Expanding list of countries to which intercompany netting would be applicable beyond Mexico/KDD22 to include Peru, Barbados, Guatemala, Dominican, Colombia, Panama, and Trinidad. | Validate the netting process accurately closed the required AP and AR invoices and posted to the GL. Ensure the netting agreements are set up in the module per business design. Ensure netting was performed for the correct entities as per business design. Ensure all clearing accounts used for netting zeroes out. Validate proper FX gain/loss was recognized. |  |  |  | Approved | Rita Nanni | 2022-05-13 | [19 empty] | RE: 1B AHCS : Delivery phase User stories approval Batch 1 Thu 5/19/2022 7:15 PM |  |  |  | N/A
| CSTONE-13105 | CSTONE-13110 | CSTONE-13113 |  | DP-RTR-GL-064 |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As an Intercompany Accountant, I need to be able to track the user who creates intercompany journals and invoices using the intra/intercompany custom loader. |  |  | Phase 1B only | 5-Gap-Build-Extension | Gap | Build | Extension |  | Creator of invoice/journal to be visible for reference on intercompany invoicing as requirement for tax, and required for GL for tracking on intercompany journals. Option 1: Work with Oracle to explore if Created By from FBDI can be transferred over to GL journal and IC batch Option 2: For GL flow, explore DFF capture at line level. Use line DFF in journal approvals. Need to find alternate solution for rejections Common: In Inter / Intra solution: Discuss with Devang how to track User who is logging in & pass the information either via option 1 or option 2. |  |  |  |  | Approved | Rita Nanni | 2022-05-13 | Sprint 11 |  |  | Sprint 13 | [15 empty] | RE: 1B AHCS : Delivery phase User stories approval Batch 1 Thu 5/19/2022 7:15 PM |  |  |  | N/A
| CSTONE-13106 | CSTONE-13111 | CSTONE-13114 |  | DP-RTR-GL-065 |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As an Intercompany Accountant, I need to be able to track the user who creates an intercompany journal using the intra/intercompany custom loader for the purposes of journal entry approvals. |  |  | Phase 1B only | 5-Gap-Build-Extension | Gap | Build | Extension |  | User ID needs to be captured so that journals can be routed to the appropriate superviser/approver, and for routing of inquiry/rejection back to user. Option 1: Work with Oracle to explore if Created By from FBDI can be transferred over to GL journal and IC batch Option 2: For GL flow, explore DFF capture at line level. Use line DFF in journal approvals. Need to find alternate solution for rejections Common: In Inter / Intra solution: Discuss with Devang how to track User who is logging in & pass the information either via option 1 or option 2. |  |  |  |  | Approved | Rita Nanni | 2022-05-13 | Sprint 11 |  |  | Sprint 13 | [15 empty] | RE: 1B AHCS : Delivery phase User stories approval Batch 1 Thu 5/19/2022 7:15 PM |  |  |  | N/A
| CSTONE-8834 | CSTONE-11729 | CSTONE-11730 |  | DP-RTR-IC-092 |  | Record to Report | Manage Intercompany Accounting | Perform Intercompany Transactions | Revise integrations to include supplier number to support use with BI tools |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT233 |  |  |  |  | Sprint 10 | Approved | Rita |  | Sprint 10 |  |  | Sprint 12 |  |  |  | RTR | RTR-GL | GL | [9 empty] | RE: IC AR and AP Balance to IAP/TD |  |  |  | N/A
| CSTONE-8835 | CSTONE-11731 | CSTONE-11732 |  | DP-RTR-IC-093 |  | Record to Report | Manage Intercompany Accounting | Perform Intercompany Transactions | Revise integrations to include customer number to support use with BI tools |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT234 |  |  |  |  | Sprint 10 | Approved | Rita |  | Sprint 10 |  |  | Sprint 12 |  |  |  | RTR | RTR-GL | GL | [9 empty] | RE: IC AR and AP Balance to IAP/TD |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-040 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As an IT Administrator, I want to Modify the “HDR amt = SUM of the Line amt” and “SUM Line Debit = SUM Line Credit” validations for MF AP interfaces |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT218, INT219, INT240 | Modify the “HDR amt = SUM of the Line amt” and “SUM Line Debit = SUM Line Credit” validations for MF AP interfaces. This validation should happen at interface level for MF AP | OIC validation works for each interface as per the rules requested |  |  |  | Approved | Sijo John | 2022-05-31 | Sprint 13 |  |  | Sprint 13 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | RE: 1B AHCS : Delivery phase User stories approval Batch 1 Approved on Thursday, June 9, 2022 11:28 PM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-041 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As an IT Administrator, I want to Modify the “HDR amt = SUM of the Line amt” and “SUM Line Debit = SUM Line Credit” validations for MF AR interfaces |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT216, INT217, INT 240 | Modify the “HDR amt = SUM of the Line amt” and “SUM Line Debit = SUM Line Credit” validations for MF AR interfaces. This validation should happen at interface level for MF AR | OIC validation works for each interface as per the rules requested |  |  |  | Approved | Sijo John | 2022-05-31 | Sprint 13 |  |  | Sprint 13 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | RE: 1B AHCS : Delivery phase User stories approval Batch 1 Approved on Thursday, June 9, 2022 11:28 PM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-042 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As an IT Administrator, I want to Modify the “HDR amt = SUM of the Line amt” and “SUM Line Debit = SUM Line Credit” validations for MF INV interfaces |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT222, INT223 | Modify the “HDR amt = SUM of the Line amt” and “SUM Line Debit = SUM Line Credit” validations for MF AR interfaces. This validation should happen at interface level for MF INV. | OIC validation works for each interface as per the rules requested |  |  |  | Approved | Sijo John | 2022-05-31 | Sprint 13 |  |  | Sprint 13 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | RE: 1B AHCS : Delivery phase User stories approval Batch 1 Approved on Thursday, June 9, 2022 11:28 PM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-043 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL accountant, I want to use Accounting date on the line transaction detail from source file for SXE and Eclipse to derive Accounting date in AHCS. |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT123, INT124 | For SXE and Eclipse , Accounting datefrom source file will be used for Tranaction grouping. And Transaction numebr logic will be as below; File Name + Accounting Date - For US File Name + Accounting Date - For Canada | Review that transactions for Sxe and Eclipse are posted in correct accounting period with correct accounting date. |  |  |  | Approved | Ian Plummer | 2022-06-02 | Sprint 13 |  |  | Sprint 14 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | RE: 1B AHCS : Delivery phase User stories approval Batch 1 Approved on Thursday, June 9, 2022 11:28 PM |  |  |  | N/A
| #N/A | #N/A | #N/A |  | DP-RTR-GL-068 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | Legacy Report Name:WESCO GL Journal Approval Status Report Workflow From User field should reference Batch Level Description if UserID field contains FIN INT (user from custom data loader template) |  |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report | RPT003 | Workflow From User field should contain the UserID captured in the Batch Level Description if the journal was created using the custom inter/intra data loader. |  |  |  |  | Approved | Rita | 2022-06-08 |  |  |  |  | Report |  |  | RTR | RTR-GL | GL | WESCO | [12 empty] | N/A
[5 empty] | DP-RTR-AHCS-044 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant, I want to enable Invoice date as balance enabled supporting reference for AP Subledger so that balances can be maintained at Invoice number and Invoice date level |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Need balance Enabled Supporting Reference "Invoice date" MF AP Subledger. | Able to extract and review balances by invoice date for AP Invoices |  |  |  | Approved | Ian | 2022-06-22 | Sprint 14 |  |  | Sprint 14 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | RE: 1B AHCS : Delivery phase User stories approval Batch 1 Approved on Thursday, June 9, 2022 11:28 PM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-045 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant, I want INT044 AHCS balances to BI outbound to include AP subledger balances at existing balanced SR and Invoice date |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT044 | INT044 (AHCS to IAP Balances) outbound to include Invoice date as balance enabled supporting reference for MF AP Subledger. | Verify that INT044 has invoice date as BSR on MF AP data | Verify that AHCS balances for MF AP is maintained as existing BSR and invoice date |  |  | Approved | Ian | 2022-06-22 | Sprint 14 |  |  | Sprint 15 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | RE: 1B AHCS : Delivery phase User stories approval Batch 1 Approved on Thursday, June 9, 2022 11:28 PM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-046 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant, I need to maintain subledger balances at Invoice Date for AP subledger and send these details the balances to BI for reconciliation (INT043) |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT043 | Update INT043 (AHCS to IAP Details) to change reference from a non balanced SR to balanced SR for Invoice date for MF AP Subledger. | Verify that INT043 has invoice date as Non BSR on MF AP data |  |  |  | Approved | Ian | 2022-06-22 | Sprint 14 |  |  | Sprint 15 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | RE: 1B AHCS : Delivery phase User stories approval Batch 1 Approved on Thursday, June 9, 2022 11:28 PM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-047 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant, I need to view the subledger balances by invoice date for AP subledger in the subledger account analysis report (RPT009) |  |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report | RPT009_R | RPT009 to change reference from a non balanced SR to balanced SR for Invoice date for MF AP Subledger. | Verify that RPT009 has invoice date as Non BSR on MF AP data |  |  |  | Approved | Ian | 2022-06-22 | Sprint 14 |  |  | Sprint 15 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | RE: 1B AHCS : Delivery phase User stories approval Batch 1 Approved on Thursday, June 9, 2022 11:28 PM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-048 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I need to view SL transaction accounting sequence in subledger account analysis report (RPT009) |  |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report | RPT009_R | Retest SR sequecning impact for RPT009 | Verify that RPT009 has sequencing |  |  |  | Approved | Ian | 2022-06-22 | Sprint 14 |  |  | Sprint 15 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | RE: 1B AHCS : Delivery phase User stories approval Batch 1 Approved on Thursday, June 9, 2022 11:28 PM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-049 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountantr, I need to send subledger transaction accounting sequence details to BI (INT043) for reconciliation |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT043 | Retest SR sequecning impact for INT043 | Verify that INT043 has sequencing |  |  |  | Approved | Ian | 2022-06-22 | Sprint 14 |  |  | Sprint 15 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | RE: 1B AHCS : Delivery phase User stories approval Batch 1 Approved on Thursday, June 9, 2022 11:28 PM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-050 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I need to send subledger YTD balances to BI (INT044) for reconciliation |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT044 | Update INT044 to be changed to YTD from PTD | Verify able to pull YTD balances |  |  |  | Approved | Ian | 2022-06-22 | Sprint 14 |  |  | Sprint 15 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | RE: 1B AHCS : Delivery phase User stories approval Batch 1 Approved on Wed 6/29/2022 1:34 AM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-051 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I need to view subledger balances by Legacy Location (under COA 1-4), and not by BU, Account and Department for AP, AR, Cresus and Inventory |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | I need to view subledger balances by Legacy Location (under COA 1-4), and not by BU, Account and Department for AP, AR, Cresus and Inventory | Review results showing only location as bsr for coa 1-4. Verify that Bu, account and dept are part of non bsr |  |  |  | Approved | Ian | 2022-06-22 | Sprint 14 |  |  | Sprint 14 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | RE: 1B AHCS : Delivery phase User stories approval Batch 1 Approved on Wed 6/29/2022 1:34 AM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-052 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I do not need to maintain subledger balances by Legacy COA 1-4 for PSFA, SXE, Eclipse, Cloud pay and Treasury (APS) |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Do not need to maintain subledger balances by Legacy COA 1-4 for PSFA, SXE, Eclipse, Cloud pay and Treasury (APS) | verify coa 1-4 from BSR is now non BSR for PSFA, SXE, Eclipse, Cloud pay and Treasury (APS) in the results |  |  |  | Approved | Ian | 2022-06-22 | Sprint 14 |  |  | Sprint 14 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | RE: 1B AHCS : Delivery phase User stories approval Batch 1 Approved on Wed 6/29/2022 1:34 AM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-053 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I need the MF AP BKI and LSI transactions to be balanced by LE |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT218, INT219, INT240 | Need the MF AP BKI and LSI transactions to be balanced by LE | Review results in AHCS based on design and config. Transactions are balanced within LEs |  |  |  | Approved | Ian | 2022-06-22 | Sprint 14 |  |  | Sprint 15 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | RE: 1B AHCS : Delivery phase User stories approval Batch 1 Approved on Wed 6/29/2022 1:34 AM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-054 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I need the MF AR BKI and LSI transactions to be balanced by LE |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT216, INT217, INT 240 | Need the MF AR BKI and LSI transactions to be balanced by LE | Review results in AHCS based on design and config. Transactions are balanced within LEs |  |  |  | Approved | Ian | 2022-06-22 | Sprint 14 |  |  | Sprint 15 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | RE: 1B AHCS : Delivery phase User stories approval Batch 1 Approved on Wed 6/29/2022 1:34 AM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-055 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I need the MF Inventory transactions to be balanced by LE |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT222, INT223 | Need the MF Inventory transactions to be balanced by LE | Review results in AHCS based on design and config. Transactions are balanced within LEs |  |  |  | Approved | Ian | 2022-06-22 | Sprint 14 |  |  | Sprint 15 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | RE: 1B AHCS : Delivery phase User stories approval Batch 1 Approved on Wed 6/29/2022 1:34 AM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-056 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I need to send accounting class for subledger transactions to BI (INT043) for reconciliation |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT043 | Need to send accounting class for subledger transactions to BI (INT043) for reconciliation | Review results in BI (INT043) that all transactions include Accounting Class |  |  |  | Approved | Ian | 2022-06-22 | Sprint 14 |  |  | Sprint 15 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | RE: 1B AHCS : Delivery phase User stories approval Batch 1 Approved on Wed 6/29/2022 1:34 AM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-057 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I need to send subledger transaction details to BI by each subledger to avoid performance issues due to large volume |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT043 | Need to send subledger transaction details to BI by each subledger to avoid performance issues due to large volume | Verify able to extract data by subledger in BI (INT043) |  |  |  | Approved | Ian | 2022-06-22 | Sprint 14 |  |  | Sprint 15 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | RE: 1B AHCS : Delivery phase User stories approval Batch 1 Approved on Wed 6/29/2022 1:34 AM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-058 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I need to send the converted data balances from the past periods to BI for reconciliation |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT244 | Need to send the converted data balances from the past periods to BI for reconciliation | Verify able to extract conversion data in BI |  |  |  | Approved | Ian | 2022-06-22 | Sprint 14 |  |  | Sprint 15 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | RE: 1B AHCS : Delivery phase User stories approval Batch 1 Approved on Fri 7/1/2022 9:15 PM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-059 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As IT Administrator, I need Lease file generated date to be used and sent as part of file name so can be used as Accounting date. |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT020 | For Leases File name will include date in MMDDYYY format, which would be used as 'Accounting Date' in AHCS. | Review file name to ensure file generated date is populated as part of file name. Ensure file is processed and posted in correct period based on date in file name |  |  |  | Approved | Ian Plummer | 2022-06-30 | Sprint 14 |  |  | Sprint 15 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | RE: 1B AHCS : Delivery phase User stories approval Batch 1 Approved on Fri 7/1/2022 9:15 PM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-060 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant , I need to view on RPT009 1.Transaction Number & Accounting Class fields for AHCS,Receivables & Payables 2. Conversion rate & conversion type fields for leases , cloudpay & Concur should populate the data from subledger level. |  |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report | RPT009_R | 1.Transaction Number & Accountng Class fields should populate the data related to AHCS,Payables & Receivables 2. Conversion rate & conversion type for leases , cloudpay & Concur should populate the data from subledger level. | Reviewed RPT009 and confirmed able to view Trans number and accounting class for MF AR and AP. Also reviewed data found under Conversion rate and conversion type fields for leases, cloudpay and concur. |  |  |  | Approved | Ian Plummer | 2022-06-30 | Sprint 14 |  |  | Sprint 15 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | RE: 1B AHCS : Delivery phase User stories approval Batch 1 Approved on Fri 7/1/2022 9:15 PM |  |  |  | N/A
| CSTONE-13122 | CSTONE-13132 | CSTONE-13142 |  | DP-RTR-GL-069 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | User story to retrofit 1A object to have the creator of Inter/Intra journals included in the Created By field in RICE ID:RPT002 reports so that there is consistency with all of the reporting. Should also include the correct Approver in the Approved by field. |  |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report | RPT002_R | Consumer of the report can filter and/or sort the fields with no need to leverage another column | Creator of journal submitted via inter/intra custom data loader is identified in creator field of report, as opposed to "FIN_INT". Correct approver is also captured in Approved by field |  |  |  | Approved | Rita |  | Sprint 14 | [6 empty] | RTR | RTR-GL | GL | [13 empty] | N/A
| CSTONE-13123 | CSTONE-13133 | CSTONE-13143 |  | DP-RTR-GL-070 |  | Record to Report | Manage General Ledger Accounting | Approve and Post Journal Entries | User story to retrofit 1A object to have the creator of Inter/Intra journals included in the Created By field in RICE ID:RPT004 reports. Correct user to also be referenced for the Submitted by field. Journals are to route to correct approver based on the userIDs and not default FIN_INT source. |  |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report | RPT004_R | Consumer of the report can filter and/or sort the fields with no need to leverage another column | Creator and submitter of journal submitted via inter/intra custom data loader is identified in , as opposed to "FIN_INT". Batch is routed to correct Approver leveraging these fields |  |  |  | Approved | Rita |  | Sprint 14 | [6 empty] | RTR | RTR-GL | GL | [13 empty] | N/A
| CSTONE-13124 | CSTONE-13134 | CSTONE-13144 |  | DP-RTR-GL-071 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | User story to retrofit 1A object to have the creator of Inter/Intra journals included in the Created By field in RICE ID:RPT101 reports so that there is consistency with all of the reporting. Should also include the correct Approver in the Approved by field. |  |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report | RPT101_R | Consumer of the report can filter and/or sort the fields with no need to leverage another column | Creator of journal submitted via inter/intra custom data loader is identified in creator field of report, as opposed to "FIN_INT". Correct approver is also captured in Approved by field |  |  |  | Approved | Rita |  | Sprint 14 | [6 empty] | RTR | RTR-GL | GL | [13 empty] | N/A
| CSTONE-13125 | CSTONE-13135 | CSTONE-13145 |  | DP-RTR-GL-072 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | User story to retrofit 1A object to have the creator of Inter/Intra journals included in the Created By field in RICE ID:RPT043 reports so that there is consistency with all of the reporting. |  |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report | RPT043_R | Consumer of the report can filter and/or sort the fields with no need to leverage another column | Creator of journal submitted via inter/intra custom data loader is identified in creator field of report, as opposed to "FIN_INT" |  |  |  | Approved | Rita |  | Sprint 14 | [6 empty] | RTR | RTR-GL | GL | [13 empty] | N/A
| CSTONE-13126 | CSTONE-13136 | CSTONE-13146 |  | DP-RTR-GL-073 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | User story to retrofit 1A object to have the creator of Inter/Intra journals included in the Created By field in RICE ID:RPT042 reports so that there is consistency with all of the reporting. Should also include the correct Approver in the Approved by field. |  |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report | RPT042_R | Consumer of the report can filter and/or sort the fields with no need to leverage another column | Creator of journal submitted via inter/intra custom data loader is identified in creator field of report, as opposed to "FIN_INT". Correct approver is also captured in Approved by field |  |  |  | Approved | Rita |  | Sprint 14 | [6 empty] | RTR | RTR-GL | GL | [9 empty] | [EXT] RE: 1B - Outbound to BI for Intercompany invoices |  |  |  | N/A
| - | - | - |  | DP-RTR-GL-074 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | User story to retrofit 1A object to have the creator of Inter/Intra journals included in the Created By field in RICE ID:RPT046 reports so that there is consistency with all of the reporting. Should also include the correct Approver in the Approved by field. |  |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT046_R | Consumer of the report can filter and/or sort the fields with no need to leverage another column Gaurav:- The User story is out of scope as RPT046 does not have created by column | Approver of journal submitted via inter/intra custom data loader is identified in Approved By field of report |  |  |  | Approved | Rita |  | Sprint 14 | [6 empty] | RTR | RTR-GL | GL | [9 empty] | [EXT] RE: 1B - Outbound to BI for Intercompany invoices |  |  |  | N/A
| CSTONE-8836 | CSTONE-11733 | CSTONE-11734 |  | DP-RTR-IC-094 |  | Record to Report | Manage Intercompany Accounting | Perform Intercompany Transactions | Revise integrations to include customer number to support use with BI tools |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT235 |  |  |  |  | Sprint 10 | Approved | Rita |  | Sprint 10 |  |  | Sprint 12 |  |  |  | RTR | RTR-GL | GL | [9 empty] | RE: IC AR and AP Balance to IAP/TD |  |  |  | N/A
| CSTONE-11735 | CSTONE-11736 | CSTONE-11737 |  | DP-RTR-IC-095 |  | Record to Report | Manage Intercompany Accounting | Process Intercompany Journal Entries | User story to retrofit 1B object to have the Submitter of Inter/Intra journals included in the Submitted By field in RICE ID:RPT017 reports so information is captured correctly on notification |  |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope | RPT017_R | Consumer of the report can filter and/or sort the fields with no need to leverage another column Gaurav:- The User story is out of scope as no change impact on RPT017. Users will submit their IC batch themselves | User ID of person that submitted journal for posting on batches that were submitted via inter/intra custom data loader is identified in Submitted By field of report |  |  |  | Approved | Rita |  | Sprint 14 |  |  | Sprint 16 |  |  |  | RTR | RTR-GL | IC | [13 empty] | N/A
| CSTONE-11738 | CSTONE-11739 | CSTONE-11740 |  | DP-RTR-IC-096 |  | Record to Report | Manage General Ledger Accounting | Process Intercompany Journal Entries | User story to retrofit 1B object to have the creator of Inter/Intra journals included in the Created By field in RICE ID:RPT036 reports so that there is consistency with all of the reporting. Also need to add a column name ‘PaaS ID’ in RPT036 to capture the unique id for IC Batches created from Inter-Intra custom loader |  |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report | RPT036_R | Consumer of the report can filter and/or sort the fields with no need to leverage another column | Creator of journal submitted via inter/intra custom data loader is identified in creator field of report, as opposed to "FIN_INT" |  |  |  | Approved | Rita |  | Sprint 14 |  |  | Sprint 16 |  |  |  | RTR | RTR-GL | IC | [13 empty] | N/A
| CSTONE-13116 | CSTONE-13118 | CSTONE-12561 |  | DP-RTR-GL-076 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | User story to retrofit 1A object to have the creator of Inter/Intra journals included in the Created By field in RICE ID:INT011 extracts so that usable data in this field is available for extract. Should also be able to access the correct Approved by data for extract |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT011 |  | Creator of journal submitted via inter/intra custom data loader is identified in creator field of extract, as opposed to "FIN_INT" |  |  |  | Approved | Rita |  | Sprint 14 |  |  | Sprint 16 |  |  |  | RTR | RTR-GL | GL | [13 empty] | N/A
| CSTONE-13155 | CSTONE-13156 | CSTONE-13157 |  | DP-RTR-GL-078 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | User story to retrofit 1A object to have the creator of Inter/Intra journals included in the Created By field in RICE ID:RPT005 reports so that there is consistency with all of the reporting. Should also include the correct Approver in the Approved by field. |  |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report | RPT005_R | Consumer of the report can filter and/or sort the fields with no need to leverage another column | Creator of journal submitted via inter/intra custom data loader is identified in creator field of report, as opposed to "FIN_INT". Correct approver is also captured in Approved by field |  |  |  | Approved | Rita |  | Sprint 14 | [6 empty] | RTR | LEGACY - IT | GL | [13 empty] | N/A
[5 empty] | DP-RTR-AHCS-061 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | AS IT Administrator, I want to show the accounting error only for primary ledger on Subledger Dashboard and create accounting status based on accounting status in primary ledger for Subledger Dashboard. EXT123 |  |  | Phase 1B only | 5-Gap-Build-Extension | Gap | Build | Extension | EXT123 | User will be able to see the create accounting errors for primary ledger on Subledger Dashboard | [7 empty] | Sprint 15 |  | Sprint 16 | Sprint 16 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | RE: 1B AHCS : Delivery phase User stories approval Batch 1 Approved on Fri 7/29/2022 9:15 PM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-062 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I need SWO to be recognized as valid for event type CASH_APPLICATION for CRI. |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT216, INT217, INT 240 | This should be configured as part of OIC event type for CRI. | Reviewed transactions in AHCS and verified the Accounting for CRI for event type SWO. |  |  |  | Approved | Ian Plummer | 2022-07-19 | Sprint 15 |  | Sprint 16 | Sprint 16 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | RE: 1B AHCS : Delivery phase User stories approval Batch 1 Approved on Fri 7/29/2022 9:15 PM |  |  |  | N/A
| CSTONE-13160 | - | - |  | DP-RTR-IC-104 |  | Record to Report | Manage Intercompany Accounting | Perform Intercompany Transactions | Auto accounting defaults to be setup for each BU for Tax line |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  |  | Correct accounting on tax lines |  |  |  | Approved | Rita Nanni | 2022-07-20 | [7 empty] | RTR | RTR-GL | IC | [13 empty] | N/A
| CSTONE-13102 | - | - |  | DP-RTR-IC-097 |  | Record to Report | Manage Intercompany Accounting | Perform Intercompany Transactions | AR SLA for Tax Liability line to populate LE based on Account Class |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  |  | Correct accounting on tax lines |  |  |  | Approved | Rita Nanni | 2022-07-20 | [7 empty] | RTR | RTR-GL | IC | [13 empty] | N/A
| CSTONE-13103 | - | - |  | DP-RTR-IC-098 |  | Record to Report | Manage Intercompany Accounting | Perform Intercompany Transactions | AP SLA for Tax Liability line to populate LE based on Account Class |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  |  | Correct accounting on tax lines |  |  |  | Approved | Rita Nanni | 2022-07-20 | [7 empty] | RTR | RTR-GL | IC | [13 empty] | N/A
| CSTONE-13104 | - | - |  | DP-RTR-IC-099 |  | Record to Report | Manage Intercompany Accounting | Perform Intercompany Transactions | AP SLA for IC Tax Line for reverse charge case to populate LE based on Account Class |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  |  | Correct accounting on tax lines |  |  |  | Approved | Rita Nanni | 2022-07-20 | [7 empty] | RTR | RTR-GL | IC | [13 empty] | N/A
[5 empty] | DP-RTR-AHCS-063 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As Financial Systems Analyst, I want a report (RPT008) to show the missing transactions in Secondary ledger that are processed for Primary ledger. I want to view the missing transactions between Secondary and the related Primary ledger to confirm both ledgers in sync. |  |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report | RPT008_R | Enhancement to RPT008. Only RPT008 is going to show the transactions which are missing/not created in AHCS but part of the source file. RPT006 will not have such transactions | RPT008 should show the count of success, error and missing transaction between selected ledger and related secondary ledger |  |  |  | Approved | Manisha Ian Plummer | 2022-07-22 | Sprint 15 |  | Sprint 16 | Sprint 16 | Report | Report | Sprint Manually overridden | RTR | RTR-AHCS | AHCS | Deloitte | [8 empty] | RE: 1B AHCS : Delivery phase User stories approval Batch 1 Approved on Fri 7/29/2022 9:15 PM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-064 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant, I need to view IC payable lines in Accounting Hub (eg ICI, AII). This should have both Foreign and Base currencies. |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT222, INT223 | Requires change in OIC to pass the required amount and currency details at header level | Reviewed transactions in AHCS and verified Accounting lines generated for IC lines in both Foreign(entered) and Base(accounted) currencies. |  |  |  | Approved | Ian Plummer | 2022-07-22 | Sprint 15 |  | Sprint 16 | Sprint 16 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | RE: 1B AHCS : Delivery phase User stories approval Batch 1 Approved on Fri 7/29/2022 9:15 PM |  |  |  | N/A
| CSTONE-13152 | - | - |  | DP-RTR-IC-100 |  | Record to Report | Manage Intercompany Accounting | Perform Intercompany Transactions | Enhancement to RPT031 to incorporate logic for conversion invoices so that AR and AP invoices can be linked |  |  | Phase 1B only | 6-Gap-Work Around-Work Around | Gap | Work Around | Work Around | RPT031 | RPT031 will display like AR and AP invoices on same line in report (RMN email to regional leads for input 8/5/22) For converted invoices, we see that there is not always alignment between payable and receivable invoices, so these “unmatched” invoices will not be displayed in the report. While invoice numbers may be different for AP and AR, there are still offsetting balances, or we would see variances in intercompany. I cannot think of another type of criteria that would allow the system to pull the offsetting invoices together to automate this, but please let us know if there is any way to do so. This will therefor require that keep track of the unmatched converted invoices offline, so you can manually apply payments to settle them. I strongly encourage you to work with your teams, as well as the other regions, to clean up as many of these invoices as possible. |  |  |  |  | Approved | Rita Nanni | 2022-07-25 | [7 empty] | RTR | RTR-GL | IC | [13 empty] | N/A
| CSTONE-13107 | CSTONE-13112 | CSTONE-13115 |  | DP-RTR-IC-101 |  | Record to Report | Manage Intercompany Accounting | Perform Intercompany Transactions | Need reprocessing option for LSI for AR Receipts or AP Payments that go into error. |  |  | Phase 1B only | 5-Gap-Build-Extension | Gap | Build | Extension |  | Appropriate notification details are to be provided as part of error message | User has ability to reprocess LSI after correction of AR receipt or AP payment that went into error |  |  |  | Approved | Rita Nanni | 2022-07-25 | [7 empty] | RTR | RTR-GL | IC | [13 empty] | N/A
| CSTONE-13108 | CSTONE-12556 | CSTONE-12567 |  | DP-RTR-IC-102 |  | Record to Report | Manage Intercompany Accounting | Perform Intercompany Transactions | LSI process requires a solution for addressing open credit memos/invoices in AR for non material Intercompany invoices |  |  | Phase 1B only | 5-Gap-Build-Extension | Gap | Build | Extension |  |  | User will be able to close open AR non material intercompany invoices |  |  |  | Approved | Rita Nanni | 2022-08-02 | [7 empty] | RTR | RTR-GL | IC | [13 empty] | N/A
| CSTONE-13109 | CSTONE-12557 | CSTONE-12568 |  | DP-RTR-IC-103 |  | Record to Report | Manage Intercompany Accounting | Perform Intercompany Transactions | LSI process requires a solution for addressing open credit memos/invoices in AP for non material Intercompany invoices |  |  | Phase 1B only | 5-Gap-Build-Extension | Gap | Build | Extension |  |  | User will be able to close open AP non material intercompany invoices |  |  |  | Approved | Rita Nanni | 2022-08-02 | [7 empty] | RTR | RTR-GL | IC | [13 empty] | N/A
[5 empty] | DP-RTR-AHCS-065 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant, I need invoice number enbaled as balanced enabled supporting reference in Inventory Subledger for ICI, AII and send these details the balances to BI for reconciliation (INT043) |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT043, INT244 | INT043 will include 'Invoice Number' as Balanced SR for ICI and AII (MF INV) and send to BI. | Confirm through review that able to pull balances by Invoice number for AII and ICI in Inventory subledger |  |  |  | Approved | Ian Plummer | 2022-08-12 | Sprint 16 |  | Sprint 17 | Sprint 17 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | RE: 1B AHCS : Delivery phase User stories approval Batch 1 Approved on Tue 8/16/2022 5:39 PM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-066 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant, I need Freight Claims to be tracked as a separate event type in CRI interface |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT216, INT217, INT 240 | Freight claims needs to be added as a separate Event type, OIC to add logic for separate event type derivation | Reviewed transactions and verified accounting looks correct for event type freight claims as part of CRI interface. |  |  |  | Approved | Ian Plummer | 2022-08-12 | Sprint 16 |  | Sprint 17 | Sprint 17 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | RE: 1B AHCS : Delivery phase User stories approval Batch 1 Approved on Tue 8/16/2022 5:39 PM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-067 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant, I want INT044 AHCS balances to BI outbound to include Inventory subledger balances at existing balanced SR and Invoice number for ICI and AII |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT044 | INT044 will include 'Invoice Number' as Balanced SR for ICI and AII (MF INV) and send to BI. | Confirm through review that able to pull balances by Invoice number for AII and ICI in Inventory subledger |  |  |  | Approved | Ian Plummer | 2022-08-15 | Sprint 16 |  | Sprint 17 | Sprint 17 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | RE: 1B AHCS : Delivery phase User stories approval Batch 1 Approved on Tue 8/16/2022 5:39 PM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-068 | Record to Report | Manage Subledger Accounting | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant, I need invoice number enbaled as balanced enabled supporting reference in Inventory Subledger for ICI, AII |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Update AHCS Configuration to adding Invoice# to AII & ICI transactions | Confirm through review that able to pull balances by Invoice number for AII and ICI in Inventory subledger |  |  |  | Approved | Ian Plummer | 2022-08-16 | Sprint 16 |  | Sprint 17 | Sprint 17 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | 1B AHCS : Delivery phase User stories approval Approved on Wed 9/21/2022 4:33 AM |  |  |  | N/A
| CSTONE-13127 | CSTONE-13137 | CSTONE-13147 |  | DP-RTR-GL-079 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | Retrofit for RPT041 as it should work for global COA, as well as for local COA |  |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report | RPT041-R |  | User should be able to run TB with drill down access for secondary and reporting ledgers that use local COA |  |  |  | Approved | Rita | 2022-08-16 | [7 empty] | RTR | RTR-GL | GL | [13 empty] | N/A
| CSTONE-13128 | CSTONE-13138 | CSTONE-13148 |  | DP-RTR-GL-080 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | Retrofit for RPT047 as it should work for global COA, as well as for local COA |  |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report | RPT047_R |  | User should be able to run TB by entered and accounted amounts for secondary and reporting ledgers that use local COA |  |  |  | Approved | Rita | 2022-08-16 | [7 empty] | RTR | RTR-GL | GL | [13 empty] | N/A
| CSTONE-13129 | CSTONE-13139 | CSTONE-13149 |  | DP-RTR-GL-081 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | Retrofit for RPT046 as it should work for global COA, as well as for local COA |  |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report | RPT046_R |  | User should be able to run TB by entered and accounted amounts for secondary and reporting ledgers that use local COA |  |  |  | Approved | Rita | 2022-08-17 | [7 empty] | RTR | RTR-GL | GL | [13 empty] | N/A
| CSTONE-13130 | CSTONE-13140 | CSTONE-13150 |  | DP-RTR-GL-082 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | Retrofit for RPT049 as it should work for global COA, as well as for local COA |  |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report | RPT049_R |  | User should be able to run TB by entered and accounted amounts for secondary and reporting ledgers that use local COA |  |  |  | Approved | Rita | 2022-08-17 | [7 empty] | RTR | RTR-GL | GL | [13 empty] | N/A
| CSTONE-13131 | CSTONE-13141 | CSTONE-13151 |  | DP-RTR-GL-083 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | Retrofit for RPT050 as it should work for global COA, as well as for local COA |  |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report | RPT050_R |  | User should be able to run TB by entered and accounted amounts for secondary and reporting ledgers that use local COA |  |  |  | Approved | Rita | 2022-08-17 | [7 empty] | RTR | RTR-GL | GL | [13 empty] | N/A
[5 empty] | DP-RTR-AHCS-069 | Record to Report | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As a GL Accountant, I need invoice number enbaled as balanced enabled supporting reference in Inventory Subledger for ICI, AII and send these details the balances to BI for reconciliation (RPT009) |  |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report | RPT009_R | RPT009 will include 'Invoice Number' as Balanced SR for ICI and AII (MF INV) and send to BI. | Confirm through review that able to pull balances by Invoice number for AII and ICI in Inventory subledger and review this data in RPT009 |  |  |  | Approved | Ian Plummer | 2022-08-16 | Sprint 17 |  | Sprint 17 | Sprint 17 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | RE: 1B AHCS : Delivery phase User stories approval Batch 1 Approved on Tue 8/16/2022 5:39 PM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-070 | Record to Report | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant, I need BSRs to be enbaled only for control accounts [ All BSR or Location based on account type ] in the MF Inventory Subledger. |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT222, INT223 | For MF Inventory Subledger : Additional field (BSR_Assignment) to be added to inbound format OIC to populate ABSR/ UBSR/NBSR in BSR_Assigment field based on lookup (NBSR to be passed if account not in lookup) OIC to populate 'null' based on lookup ('NULL" if PS account not in available in source data) | Confirm through review of reports that BSR only exist on control accounts as per design |  |  |  | Approved | Ian Plummer | 2022-08-30 | Sprint 17 |  | Sprint 17 | Sprint 17 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | EXT RE 1B AHCS Delivery phase User stories approval Approved on Tue Wed 8/31/2022 9:30 PM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-071 | Record to Report | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant, I need BSRs to be enbaled only for control accounts [ All BSR or Location based on account type ] in the MF AP Subledger. |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT218, INT219, INT240 | For MF AP Subledger : Additional field (BSR_Assignment) to be added to inbound format OIC to populate ABSR/ UBSR/NBSR in BSR_Assigment field based on lookup (NBSR to be passed if account not in lookup) OIC to populate 'null' based on lookup ('NULL" if PS account not in available in source data) | Confirm through review of reports that BSR only exist on control accounts as per design |  |  |  | Approved | Ian Plummer | 2022-08-30 | Sprint 17 |  | Sprint 17 | Sprint 17 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | EXT RE 1B AHCS Delivery phase User stories approval Approved on Tue Wed 8/31/2022 9:30 PM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-072 | Record to Report | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant, I need BSRs to be enbaled only for control accounts [ All BSR or Location based on account type ] in the MF AR Subledger. |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT216, INT217 | For MF AR Subledger : Additional field (BSR_Assignment) to be added to inbound format OIC to populate ABSR/ UBSR/NBSR in BSR_Assigment field based on lookup (NBSR to be passed if account not in lookup) OIC to populate 'null' based on lookup ('NULL" if PS account not in available in source data) | Confirm through review of reports that BSR only exist on control accounts as per design |  |  |  | Approved | Ian Plummer | 2022-08-30 | Sprint 17 |  | Sprint 17 | Sprint 17 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | EXT RE 1B AHCS Delivery phase User stories approval Approved on Tue Wed 8/31/2022 9:30 PM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-073 | Manage Subledger Accounting | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant, I need to enable revised list of Non-BSRs for MF AP Subledger and assign all or limited set to transaction lines |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Add new Non - BSR to MF AP Subledger Assign only limited set to control account related lines and assign all Non -BSR to remaining lines | Verified through reporting that specified non BSRs are accounted for as per business design |  |  |  | Approved | Ian Plummer | 2022-08-30 | Sprint 17 |  | Sprint 17 |  |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | EXT RE 1B AHCS Delivery phase User stories approval Approved on Tue Wed 8/31/2022 9:30 PM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-074 | Manage Subledger Accounting | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant, I need to enable revised list of Non-BSRs for MF AR Subledger and assign all or limited set to transaction lines |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Add new Non - BSR to MF AP Subledger Assign only limited set to control account related lines and assign all Non -BSR to remaining lines | Verified through reporting that specified non BSRs are accounted for as per business design |  |  |  | Approved | Ian Plummer | 2022-08-30 | Sprint 17 |  | Sprint 17 |  |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | EXT RE 1B AHCS Delivery phase User stories approval Approved on Tue Wed 8/31/2022 9:30 PM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-075 | Manage Subledger Accounting | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant, I need to enable revised list of Non-BSRs for MF Inventory Subledger and assign all or limited set to transaction lines |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Add new Non - BSR to MF AP Subledger Assign only limited set to control account related lines and assign all Non -BSR to remaining lines | Verified through reporting that specified non BSRs are accounted for as per business design |  |  |  | Approved | Ian Plummer | 2022-08-30 | Sprint 17 |  | Sprint 17 |  |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | EXT RE 1B AHCS Delivery phase User stories approval Approved on Tue Wed 8/31/2022 9:30 PM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-076 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant, I need references data to be displayed in the existing outbound fields irrespective of information being stored in BSR or Non BSR with in AHCS [INT043] |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT043 | Display common BSR or Non BSR under same outbound field | Review INT043 and confirm all fields have corresponding data as per expectation based on business design |  |  |  | Approved | Ian Plummer | 2022-08-30 | Sprint 17 |  | Sprint 17 | Sprint 17 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | EXT RE 1B AHCS Delivery phase User stories approval Approved on Tue Wed 8/31/2022 9:30 PM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-077 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant, I need references data to be displayed in the existing outbound fields irrespective of information being stored in BSR or Non BSR with in AHCS [INT244] |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT244 | Display common BSR or Non BSR under same outbound field | Review INT244 and confirm all fields have corresponding data as per expectation based on business design |  |  |  | Approved | Ian Plummer | 2022-08-30 | Sprint 17 |  | Sprint 17 | Sprint 17 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | EXT RE 1B AHCS Delivery phase User stories approval Approved on Tue Wed 8/31/2022 9:30 PM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-078 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant, I need references data to be displayed in the existing report fields irrespective of information being stored in BSR or Non BSR with in AHCS [RPT009] |  |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report | RPT009_R | Display common BSR or Non BSR under same report field | Review RPT009 and confirm all fields have corresponding data as per expectation based on business design |  |  |  | Approved | Ian Plummer | 2022-08-30 | Sprint 17 |  | Sprint 17 | Sprint 17 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | EXT RE 1B AHCS Delivery phase User stories approval Approved on Tue Wed 8/31/2022 9:30 PM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-079 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant, I need BSRs to be enbaled only for control accounts [ All BSR or Location based on account type ] for Java Tools inbound interfaces |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT241 | For Java Tools Inbound Additional field (BSR_Assignment) to be added to inbound format OIC to populate ABSR/ UBSR/NBSR in BSR_Assigment field based on lookup (NBSR to be passed if account not in lookup) OIC to populate 'null' based on lookup ('NULL" if PS account not in available in source data) | Confirm through review of reports that BSR only exist on control accounts as per design |  |  |  | Approved | Ian Plummer | 2022-08-30 | Sprint 17 |  | Sprint 17 | Sprint 17 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | EXT RE 1B AHCS Delivery phase User stories approval Approved on Tue Wed 8/31/2022 9:30 PM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-080 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant, I need BSRs to be enbaled only for control accounts [ All BSR or Location based on account type ] for France Secondary Ledger |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Additional field (BSR_Assignment) to be added to inbound format OIC to populate ABSR/ UBSR/NBSR in BSR_Assigment field based on lookup (NBSR to be passed if account not in lookup) OIC to populate 'null' based on lookup ('NULL" if PS account not in available in source data) | Confirm through review of reports that BSR only exist on control accounts as per design |  |  |  | Approved | Ian Plummer | 2022-08-30 | Sprint 17 |  | Sprint 17 | Sprint 17 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | EXT RE 1B AHCS Delivery phase User stories approval Approved on Tue Wed 8/31/2022 9:30 PM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-081 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant, I need BSRs to be enbaled only for control accounts [ All BSR or Location based on account type ] for Spain Secondary Ledger |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Additional field (BSR_Assignment) to be added to inbound format OIC to populate ABSR/ UBSR/NBSR in BSR_Assigment field based on lookup (NBSR to be passed if account not in lookup) OIC to populate 'null' based on lookup ('NULL" if PS account not in available in source data) | Confirm through review of reports that BSR only exist on control accounts as per design |  |  |  | Approved | Ian Plummer | 2022-08-30 | Sprint 17 |  | Sprint 17 | Sprint 17 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | EXT RE 1B AHCS Delivery phase User stories approval Approved on Tue Wed 8/31/2022 9:30 PM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-082 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant, I need BSRs to be enbaled only for control accounts [ All BSR or Location based on account type ] for Poland Secondary Ledger |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Additional field (BSR_Assignment) to be added to inbound format OIC to populate ABSR/ UBSR/NBSR in BSR_Assigment field based on lookup (NBSR to be passed if account not in lookup) OIC to populate 'null' based on lookup ('NULL" if PS account not in available in source data) | Confirm through review of reports that BSR only exist on control accounts as per design |  |  |  | Approved | Ian Plummer | 2022-08-30 | Sprint 17 |  | Sprint 17 | Sprint 17 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | EXT RE 1B AHCS Delivery phase User stories approval Approved on Tue Wed 8/31/2022 9:30 PM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-083 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant, I need BSRs to be enbaled only for control accounts [ All BSR or Location based on account type ] for Norway Secondary Ledger |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Additional field (BSR_Assignment) to be added to inbound format OIC to populate ABSR/ UBSR/NBSR in BSR_Assigment field based on lookup (NBSR to be passed if account not in lookup) OIC to populate 'null' based on lookup ('NULL" if PS account not in available in source data) | Confirm through review of reports that BSR only exist on control accounts as per design |  |  |  | Approved | Ian Plummer | 2022-08-30 | Sprint 17 |  | Sprint 17 | Sprint 17 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | EXT RE 1B AHCS Delivery phase User stories approval Approved on Tue Wed 8/31/2022 9:30 PM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-084 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant, I need BSRs to be enbaled only for control accounts [ All BSR or Location based on account type ] for Saudi Arabia Secondary Ledger |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Additional field (BSR_Assignment) to be added to inbound format OIC to populate ABSR/ UBSR/NBSR in BSR_Assigment field based on lookup (NBSR to be passed if account not in lookup) OIC to populate 'null' based on lookup ('NULL" if PS account not in available in source data) | Confirm through review of reports that BSR only exist on control accounts as per design |  |  |  | Approved | Ian Plummer | 2022-08-30 | Sprint 17 |  | Sprint 17 | Sprint 17 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | EXT RE 1B AHCS Delivery phase User stories approval Approved on Tue Wed 8/31/2022 9:30 PM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-085 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant, I need BSRs to be enbaled only for control accounts [ All BSR or Location based on account type ] for Austria Secondary Ledger |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Additional field (BSR_Assignment) to be added to inbound format OIC to populate ABSR/ UBSR/NBSR in BSR_Assigment field based on lookup (NBSR to be passed if account not in lookup) OIC to populate 'null' based on lookup ('NULL" if PS account not in available in source data) | Confirm through review of reports that BSR only exist on control accounts as per design |  |  |  | Approved | Ian Plummer | 2022-08-30 | Sprint 17 |  | Sprint 17 | Sprint 17 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | EXT RE 1B AHCS Delivery phase User stories approval Approved on Tue Wed 8/31/2022 9:30 PM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-086 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant, I need BSRs to be enbaled only for control accounts [ All BSR or Location based on account type ] for Germany Secondary Ledger |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Additional field (BSR_Assignment) to be added to inbound format OIC to populate ABSR/ UBSR/NBSR in BSR_Assigment field based on lookup (NBSR to be passed if account not in lookup) OIC to populate 'null' based on lookup ('NULL" if PS account not in available in source data) | Confirm through review of reports that BSR only exist on control accounts as per design |  |  |  | Approved | Ian Plummer | 2022-08-30 | Sprint 17 |  | Sprint 17 | Sprint 17 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | EXT RE 1B AHCS Delivery phase User stories approval Approved on Tue Wed 8/31/2022 9:30 PM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-087 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant, I need only Location BSRs to be enbaled only for unvouchered beginnning balances |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Assign only Location BSR for Unvouchered beginning balances load | Review Unvouchered BB through reporting. Verify that only location is BSR based on business design |  |  |  | Approved | Ian Plummer | 2022-08-30 | Sprint 17 |  | Sprint 17 | Sprint 17 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | EXT RE 1B AHCS Delivery phase User stories approval Approved on Tue Wed 8/31/2022 9:30 PM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-088 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | Modify the “HDR amt = SUM of the Line amt” validation for ISI interface to exclude STAT lines |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT222, INT223 | Modify the “HDR amt = SUM of the Line amt” validation for ISI interface to exclude STAT lines | OIC excludes STAT lines from “HDR amt = SUM of the Line amt” validatio for ISI interface |  |  |  | Approved | Sijo John | 2022-08-31 | Sprint 17 |  | Sprint 17 | Sprint 17 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | RE: 1B AHCS : Delivery phase User stories approval Batch 1 Approved on Thu 9/1/2022 4:24 AM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-089 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | Modify validation for BKI “HDR amt = SUM of the Line amt” as "N" and "SUM Line Debit=SUM Line Credit" as "Y" |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT216, INT217, INT218, INT219 | Modify the validation for BKI “HDR amt = SUM of the Line amt” as "N" and "SUM Line Debit=SUM Line Credit" as "Y" | OIC validation works for BKI interface as per the rule requested |  |  |  | Approved | Sijo John | 2022-08-31 | Sprint 17 |  | Sprint 17 | Sprint 17 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | 1B AHCS : Delivery phase User stories approval Approved on Wed 9/21/2022 4:33 AM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-090 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant I need SII interface to derive affiliate/IC on the IC receivable line for Intercompany transactions based on Header level location value. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Update AHCS configuration to use Header level PS_AFFILATE_BU field for deriving Intercompany segment | Verify through reporting that IC is populated on IC receivable line for Intercompany transaction in the sales interface. |  |  |  | Approved | Ian Plummer | 2022-08-31 | Sprint 17 |  |  | Sprint 17 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | 1B AHCS : Delivery phase User stories approval Approved on Wed 9/21/2022 4:33 AM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-091 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant I need Header Level PS_AFFILITE_BU field added to MF AR layout so that AHCS configuration can use that to derive correct Intercompany value. |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT216, INT217 | Include PS_AFFILIATE_BU field to MF AR - Transaction object layout | Verify through reporting that IC is populated on IC receivable line for Intercompany transaction in the sales interface. |  |  |  | Approved | Ian Plummer | 2022-09-01 | Sprint 17 |  | Sprint 17 | Sprint 17 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | 1B AHCS : Delivery phase User stories approval Approved on Wed 9/21/2022 4:33 AM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-092 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | Remove “HDR amt = SUM of the Line amt” validation for ISI interface |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT222, INT223 | Remove the validation “HDR amt = SUM of the Line amt” for ISI | ISI interface records are not validated for “HDR amt = SUM of the Line amt” |  |  |  | Approved | Sijo John | 2022-09-02 | Sprint 17 |  | Sprint 17 | Sprint 17 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | RE: 1B AHCS : Delivery phase User stories approval Batch 1 Approved on Tue 9/6/2022 5:55 PM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-093 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | Java Tools file name should be changed to have HDR, LIN, TRG before date and time stamp Example: MF_AR_HDR_MMDDYY_HHMMSS.txt |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT241 | Java Tools file name should be changed to have HDR, LIN, TRG before date and time stamp Example: MF_AR_HDR_MMDDYY_HHMMSS.txt , MF_AR_LIN_MMDDYY_HHMMSS.txt , MF_AR_TRG_MMDDYY_HHMMSS.txt | The Java Tools files with these file names are successfully processed through AHCS |  |  |  | Approved | Sijo John | 2022-09-20 | Sprint 17 |  | Sprint 17 | Sprint 17 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | 1B AHCS : Delivery phase User stories approval Approved on Wed 9/21/2022 4:33 AM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-094 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | Separate lookup is needed for RPT208 with BSR accounts |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | RPT208 | Separate lookup is needed for RPT208 with BSR accounts | RPT 208 will have data only for the BSR accounts |  |  |  | Approved | Sijo John | 2022-09-20 | Sprint 17 |  | Sprint 17 | Sprint 17 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | 1B AHCS : Delivery phase User stories approval Approved on Wed 9/21/2022 4:33 AM |  |  |  | N/A
[5 empty] | DP-RTR-IC-105 |  | Record to Report | Manage Intercompany Accounting | Perform Intercompany Transactions | Async solution to be introduced for Credit Memo LSI solution |  |  | Phase 1B only | 6-Gap-Work Around-Work Around | Gap | Work Around | Work Around |  | Previously credit memo creation, validation and settlement, were synchronised and triggered by PaaS. Async solution to be introduced for Credit Memo LSI soln We have received a confirmation form Tax team and the same has been tested on Dev22 environment as well to exclude the ‘LSI’ source for tax call. This means we do not need make any change in regards to the asynchronous solution for Credit memo handling in LSI solution as the LSI source invoices shall get validated without any time lag. | LSI CM to be validated and settled |  |  |  | Approved | Rita Nanni | [8 empty] | RTR | RTR-GL | IC | [13 empty] | N/A
[5 empty] | DP-RTR-AHCS-095 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant I need Duty Unvouchered ( legacy PS Account 310028003) to be configured as part of the BSR changes. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Duty Unvouchered ( legacy PS Account 310028003) to be configured as UBSR | Reviewed results to confirm that Duties Unvouchered is configured and added to as part of BSR config. |  |  |  | Approved | Ian Plummer | 2022-09-20 | Sprint 17 |  | Sprint 17 | Sprint 17 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | 1B AHCS : Delivery phase User stories approval Approved on Fri 10/7/2022 2:58 AM |  |  |  | N/A
[5 empty] | DP-RTR-IC-106 |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As a tax accountant, I need tax data elements added to Wesco_AXE_GBL_AR_INT189_INT190_IC_AR_Invoice_to_IAP_Teradata_Report_Output so that data needed for tax compliance can be extracted. |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT189, INT190 | 1C Tax Team to review and determine which required fields are missing from current specs and provide to Deloitte for revision. | Ensure required data for feeding into invoices solutions is available in IAP or data warehouse equivalent |  |  | Sprint 18 | Approved | Rita Nanni | 2022-10-03 |  |  | Sprint 18 | Sprint 18 |  |  |  | RTR | RTR-GL | IC | WESCO - Tax Stories | [12 empty] | N/A
[5 empty] | DP-RTR-IC-107 |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As a tax accountant, I need tax data elements added to Wesco_AXE_GBL_AP_INT185_INT186_IC_AP_Invoices_Feed_To_IAP_Teradata_Report_Output so that I can extract the data needed for tax compliance. |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT185, INT186 | 1C Tax Team to review and determine which required fields are missing from current specs and provide to Deloitte for revision. | Ensure required data for feeding into invoices solutions is available in IAP or data warehouse equivalent |  |  | Sprint 18 | Approved | Rita Nanni | 2022-10-03 |  |  | Sprint 18 | Sprint 18 |  |  |  | RTR | RTR-GL | IC | WESCO - Tax Stories | [12 empty] | N/A
[5 empty] | DP-RTR-IC-107a |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As a tax accountant, I need access to all Cornerstone database tables so that I can access the data needed for tax compliance |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT185, INT186 | 1C Tax Team to review and determine which required fields are missing from current specs and provide to Deloitte for revision. | Ensure required data for feeding into invoices solutions is available in IAP or data warehouse equivalent |  |  | Sprint 18 | Approved | Rita Nanni | 2022-10-03 |  |  | Sprint 18 | Sprint 18 |  |  |  | RTR | RTR-GL | IC | WESCO - Tax Stories | [12 empty] | N/A
[7 empty] | Record to Report | Manage Intercompany Accounting | Manage Users and Access Rights | As a tax accountant, I need access to all Cornerstone IAP and Teradata tables so that I can access the data needed for tax compliance |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Tax requires access to transactions tables to retrieve required data for analysis, reporting, and compliance from BI/IAP/Teradata | Tax team will have access to query integrated IAP and Terradata tables |  |  |  | Approved | Rita Nanni | 2022-10-03 |  |  | Sprint 18 | Sprint 18 |  |  |  | RTR | RTR-BI | IC | WESCO - Tax Stories | [12 empty] | N/A
[5 empty] | DP-RTR-AHCS-096 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant I need Site rule to be applied against MF Inventory using ST-008 for ICI and AII and IRI and ISI interfaces on specified lines in the business rule. Rule should capture Derive site based on GL location (Ops and non Ops location). |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | ST-008 Site rule to be applied used for MF Inventory for ICI and AII and IRI and ISI interfaces on specified lines in the business rule. Rule should capture Derive site based on GL location (Ops and non Ops location). | Review results in AHCS and BI after Accounting entries have posted. Ensure that COA mapping is as expected and accurate as per 1B business design |  |  |  | Approved | Ian Plummer | 10/5/2022 10/6/2022 10/7/2022 |  |  | Sprint 18 | Sprint 18 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | 1B AHCS : Delivery phase User stories approval Approved on Fri 10/7/2022 2:58 AM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-097 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant I need Site rule to be applied against MF Inventory using ST-004 for IRI interface on specified lines in the business rules. Rule should capture Derive site based on location to site mapping values unless intangible product class then see rule GR-045. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | ST-004 Site rule to be applied against MF Inventory using for IRI interface on specified lines in the business rules. Rule should capture Derive site based on location to site mapping values unless intangible product class then see rule GR-045. | Review results in AHCS and BI after Accounting entries have posted. Ensure that COA mapping is as expected and accurate as per 1B business design |  |  |  | Approved | Ian Plummer | 10/5/2022 10/7/2022 |  |  | Sprint 18 | Sprint 18 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | 1B AHCS : Delivery phase User stories approval Approved on Fri 10/7/2022 2:58 AM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-098 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant I need Site rule to be applied against MF Inventory using ST-003 for IRI,ISI, CQI, IBI, FTI, FII interfaces on specified lines in the business rule. Rule should capture Derive site based on Ops location to site value sets in AHCS received from mapping engine if not available default to zero. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Site rule to be applied against MF Inventory using ST-003 for IRI,ISI, CQI, IBI, FTI, FII interfaces on specified lines in the business rule. Rule should capture Derive site based on Ops location to site value sets in AHCS received from mapping engine if not available default to zero. | Review results in AHCS and BI after Accounting entries have posted. Ensure that COA mapping is as expected and accurate as per 1B business design |  |  |  | Approved | Ian Plummer | 2022-10-05 |  |  | Sprint 18 | Sprint 18 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | 1B AHCS : Delivery phase User stories approval Approved on Fri 10/7/2022 2:58 AM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-099 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant I need Site rule to be applied against MF AR using ST-003 for CRI and SII interfaces on specified lines in the business rule. Rule should capture Derive site based on Ops location to site value sets in AHCS received from mapping engine if not available default to zero. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Site rule to be applied against MF AR using ST-003 for CRI and SII interfaces on specified lines in the business rule. Rule should capture Derive site based on Ops location to site value sets in AHCS received from mapping engine if not available default to zero. | Review results in AHCS and BI after Accounting entries have posted. Ensure that COA mapping is as expected and accurate as per 1B business design |  |  |  | Approved | Ian Plummer | 2022-10-05 |  |  | Sprint 18 | Sprint 18 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | 1B AHCS : Delivery phase User stories approval Approved on Fri 10/7/2022 2:58 AM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-100 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant I need Site rule to be applied against MF Inventory using ST-006 for ISI and FII interfaces on specified lines in the business rules. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Site rule to be applied against MF Inventory using ST-006 for ISI and FII interfaces on specified lines in the business rules. | Review results in AHCS and BI after Accounting entries have posted. Ensure that COA mapping is as expected and accurate as per 1B business design |  |  |  | Approved | Ian Plummer | 10/5/2022 10/6/2022 |  |  | Sprint 18 | Sprint 18 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | 1B AHCS : Delivery phase User stories approval Approved on Fri 10/7/2022 2:58 AM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-101 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant I need Site rule to be applied against MF Inventory to be updated to zeroes for IRI and ISI and CQI interfaces on specified lines in the business rules for Secondary Ledger. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Site rule to be applied against MF Inventory to be updated to zeroes for IRI and ISI and CQI interfaces on specified lines in the business rules for Secondary Ledger. | Review results in AHCS and BI after Accounting entries have posted. Ensure that COA mapping is as expected and accurate as per 1B business design |  |  |  | Approved | Ian Plummer | 2022-10-05 |  |  | Sprint 18 | Sprint 18 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | 1B AHCS : Delivery phase User stories approval Approved on Fri 10/7/2022 2:58 AM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-102 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant I need Department rule to be applied against MF Inventory using DT-003 for FII,ISI, CQI,FTI interfaces on specified lines in the business rule. Rule should capture Derive dept based on GL location to dept value sets in AHCS received from mapping engine if location not found then default to Oracle Dept 8000. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Department rule to be applied against MF Inventory using DT-003 for FII,ISI, CQI,FTI interfaces on specified lines in the business rule. Rule should capture Derive dept based on GL location to dept value sets in AHCS received from mapping engine if location not found then default to Oracle Dept 8000. | Review results in AHCS and BI after Accounting entries have posted. Ensure that COA mapping is as expected and accurate as per 1B business design |  |  |  | Approved | Ian Plummer | 10/5/2022 10/6/2022 |  |  | Sprint 18 | Sprint 18 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | 1B AHCS : Delivery phase User stories approval Approved on Fri 10/7/2022 2:58 AM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-103 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant I need Department rule to be applied against MF AR using DT-003 for CRI and SII interfaces on specified lines in the business rule. Rule should capture Derive dept based on GL location to dept value sets in AHCS received from mapping engine if location not found then default to Oracle Dept 8000. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Department rule to be applied against MF AR using DT-003 for CRI and SII interfaces on specified lines in the business rule. Rule should capture Derive dept based on GL location to dept value sets in AHCS received from mapping engine if location not found then default to Oracle Dept 8000. | Review results in AHCS and BI after Accounting entries have posted. Ensure that COA mapping is as expected and accurate as per 1B business design |  |  |  | Approved | Ian Plummer | 2022-10-05 |  |  | Sprint 18 | Sprint 18 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | 1B AHCS : Delivery phase User stories approval Approved on Fri 10/7/2022 2:58 AM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-104 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant I need Dept rule to be applied against MF Inventory to be updated to zeroes for IRI and ISI and CQI interfaces on specified lines in the business rules for Secondary Ledger. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Dept rule to be applied against MF Inventory to be updated to zeroes for IRI and ISI and CQI interfaces on specified lines in the business rules for Secondary Ledger. | Review results in AHCS and BI after Accounting entries have posted. Ensure that COA mapping is as expected and accurate as per 1B business design |  |  |  | Approved | Ian Plummer | 2022-10-05 |  |  | Sprint 18 | Sprint 18 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | 1B AHCS : Delivery phase User stories approval Approved on Fri 10/7/2022 2:58 AM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-105 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant I need Op Group rule to be applied against MF Inventory to be updated for ISI interface on specified lines in the business rules using OG-004. Lines capturing changes will be identified. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Op Group rule to be applied against MF Inventory to be updated for ISI interface on specified lines in the business rules using OG-004. Lines capturing changes will be identified. | Review results in AHCS and BI after Accounting entries have posted. Ensure that COA mapping is as expected and accurate as per 1B business design |  |  |  | Approved | Ian Plummer | 10/5/2022 10/06/22 |  |  | Sprint 18 | Sprint 18 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | 1B AHCS : Delivery phase User stories approval Approved on Fri 10/7/2022 2:58 AM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-106 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | AS IT Administrator, I want the ability to see Import Accounting Error on OIC dashboard and ability to download import accounting errors |  |  | Phase 1B only | 5-Gap-Build-Extension | Gap | Build | Extension | EXT123 | AS IT Administrator, I want the ability to see Import Accounting Error on OIC dashboard and ability to download import accounting errors | Confirm through validating the correct import status with ability to download import errors | [6 empty] | Sprint 18 |  | Sprint 18 | Sprint 18 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | 1B AHCS : Delivery phase User stories approval Approved on Fri 10/7/2022 2:58 AM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-107 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant I need Op Group rule to be applied against MF Inventory to be updated for IRI and ISI interface on specified lines in the business rules using OG-007. Rule is Derive OG based on GL location . |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Op Group rule to be applied against MF Inventory to be updated for IRI and ISI interface on specified lines in the business rules using OG-007. Rule is Derive OG based on GL location . | Review results in AHCS and BI after Accounting entries have posted. Ensure that COA mapping is as expected and accurate as per 1B business design |  |  |  | Approved | Ian Plummer | 2022-10-06 |  |  | Sprint 18 | Sprint 18 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | 1B AHCS : Delivery phase User stories approval Approved on Fri 10/7/2022 2:58 AM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-108 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As an IT administrator I need to review the records that failed load in Oracle (Import Accounting Error) to be added to the BAD File to identify rejected transactions |  |  | Phase 1B only | 5-Gap-Build-Extension | Gap | Build | Extension | INT218, INT219, INT240, INT216, INT217, INT 240, INT222, INT223, EXT123 | As an IT administrator I need to review the records that failed load in Oracle (Import Accounting Error) to be added to the BAD File to identify rejected transactions | Validate the records that failed during Import Accounting are a part of the BAD file | [25 empty] | 1B AHCS : Delivery phase User stories approval Approved on Fri 10/7/2022 2:58 AM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-109 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant I need Site rule to be applied against MF Inventory using ST-009 for ISI interface on specified lines in the business rules. Rule should capture Derive site based on "ship from" loc based on Ops location to site value sets in AHCS received from mapping engine if not available default to zero. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Site rule to be applied against MF Inventory using ST-009 for ISI interface on specified lines in the business rules. Rule should capture Derive site based on "ship from" loc based on Ops location to site value sets in AHCS received from mapping engine if not available default to zero. | Review results in AHCS and BI after Accounting entries have posted. Ensure that COA mapping is as expected and accurate as per 1B business design |  |  |  | Approved | Ian Plummer | 2022-10-07 |  |  | Sprint 18 | Sprint 18 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | 1B AHCS : Delivery phase User stories approval Approved on Fri 10/7/2022 2:58 AM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-110 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant I need Site rule to be applied against MF Inventory using ST-010 for ISI interface on specified lines in the business rules. Rule should capture Derive site based on "ship from" loc based on (Ops & Non Ops) location to site value sets in AHCS received from mapping engine unless intangible then see rule GR-045. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Site rule to be applied against MF Inventory using ST-010 for ISI interface on specified lines in the business rules. Rule should capture Derive site based on "ship from" loc based on (Ops & Non Ops) location to site value sets in AHCS received from mapping engine unless intangible then see rule GR-045. | Review results in AHCS and BI after Accounting entries have posted. Ensure that COA mapping is as expected and accurate as per 1B business design |  |  |  | Approved | Ian Plummer | 2022-10-07 |  |  | Sprint 18 | Sprint 18 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | 1B AHCS : Delivery phase User stories approval Approved on Fri 10/7/2022 2:58 AM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-111 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant I need Department rule to be applied against MF Inventory using DT-005 for ISI interface on specified lines in the business rule. Rule should capture Derive Dept based on Ship from Location or Receiving Location if location not found then default to Oracle dept 8000. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Department rule to be applied against MF Inventory using DT-005 for ISI interface on specified lines in the business rule. Rule should capture Derive Dept based on Ship from Location or Receiving Location if location not found then default to Oracle dept 8000. | Review results in AHCS and BI after Accounting entries have posted. Ensure that COA mapping is as expected and accurate as per 1B business design |  |  |  | Approved | Ian Plummer | 2022-10-07 |  |  | Sprint 18 | Sprint 18 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | 1B AHCS : Delivery phase User stories approval Approved on Fri 10/7/2022 2:58 AM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-112 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant I need LE rule to be applied against MF Inventory using LE-002 for ISI interface on specified lines in the business rule. Rule should capture Derive LE based on Ship from Loc BU in AHCS |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | LE rule to be applied against MF Inventory using LE-002 for ISI interface on specified lines in the business rule. Rule should capture Derive LE based on Ship from Loc BU in AHCS | Review results in AHCS and BI after Accounting entries have posted. Ensure that COA mapping is as expected and accurate as per 1B business design |  |  |  | Approved | Ian Plummer | 2022-10-07 |  |  | Sprint 18 | Sprint 18 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | 1B AHCS : Delivery phase User stories approval Approved on Fri 10/7/2022 2:58 AM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-113 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant I need Oracle to remove the Debit = Credit amount validation for SXE interfaces and handle unbalanced journal and created a balancing (offset) line using configuration |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT123 | Oracle to remove the Debit = Credit amount validation for SXE interfaces and handle unbalanced journal and created a balancing (offset) line using configuration | Review results in AHCS and BI after Accounting entries have posted. Validate that total lines balance using offset account as per design. |  |  |  | Approved | Ian Plummer | 2022-10-07 | Sprint 18 |  | Sprint 18 | Sprint 18 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | 1B AHCS : Delivery phase User stories approval Approved on Fri 10/7/2022 2:58 AM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-114 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant I need Oracle to remove the Debit = Credit amount validation for Eclipse interfaces and handle unbalanced journal and created a balancing (offset) line using configuration |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT124 | Oracle to remove the Debit = Credit amount validation for Eclipse interfaces and handle unbalanced journal and created a balancing (offset) line using configuration | Review results in AHCS and BI after Accounting entries have posted. Validate that total lines balance using offset account as per design. |  |  |  | Approved | Ian Plummer | 2022-10-07 | Sprint 18 |  | Sprint 18 | Sprint 18 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | 1B AHCS : Delivery phase User stories approval Approved on Fri 10/7/2022 2:58 AM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-115 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant I need Site rule to be applied against MF Inventory using ST-008 for IBI interface on specified lines in the business rule. Rule should capture Derive site based on GL location (Ops and non Ops location). |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Site rule to be applied against MF Inventory using ST-008 for IBI interface on specified lines in the business rule. Rule should capture Derive site based on GL location (Ops and non Ops location). | Review results in AHCS and BI after Accounting entries have posted. Ensure that COA mapping is as expected and accurate as per 1B business design |  |  |  | Approved | Ian Plummer | 2022-10-10 |  |  | Sprint 18 | Sprint 18 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | 1B AHCS : Delivery phase User stories approval Approved on Fri 10/7/2022 2:58 AM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-116 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant I need Op Group rule to be applied against MF Inventory to be updated for IBI interface on specified lines in the business rules using OG-007. Rule is Derive OG based on GL location . |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Op Group rule to be applied against MF Inventory to be updated for IBI interface on specified lines in the business rules using OG-007. Rule is Derive OG based on GL location . | Review results in AHCS and BI after Accounting entries have posted. Ensure that COA mapping is as expected and accurate as per 1B business design |  |  |  | Approved | Ian Plummer | 2022-10-10 |  |  | Sprint 18 | Sprint 18 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | 1B AHCS : Delivery phase User stories approval Approved on Fri 10/7/2022 2:58 AM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-117 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As an IT administrator I need additional columns ERROR_MSG and LEDGER_NAME to be added in BAD File at the end for 1B sources |  |  | Phase 1B only | 5-Gap-Build-Extension | Gap | Build | Extension | EXT123 | As an IT administrator I need additional columns ERROR_MSG and LEDGER_NAME to be added in BAD File at the end for 1B sources | Review additional columns ERROR_MSG and LEDGER_NAME added in BAD File at the end for 1B sources |  |  |  | Approved | Sijo John | 2022-10-12 |  |  | Sprint 18 | Sprint 18 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | 1B AHCS : Delivery phase User stories approval Approved on Wed 10/19/2022 3:06 AM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-118 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant I need updated Account Rule (AC-015) to be applied against MF Inventory to be updated for ISI interface on specified lines in the business rules. See GR-046 updated in rule AC-015. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | updated Account Rule (AC-015) to be applied against MF Inventory to be updated for ISI interface on specified lines in the business rules. See GR-046 updated in rule AC-015. | Review results in AHCS and BI after Accounting entries have posted. Ensure that COA mapping is as expected and accurate as per 1B business design |  |  |  | Approved | Ian Plummer | 2022-10-14 |  |  | Sprint 18 | Sprint 18 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | 1B AHCS : Delivery phase User stories approval Approved on Wed 10/19/2022 3:06 AM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-119 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant I need MF Inventory to be updated for IBI interface for GL35 rules on the specified line in the business rules requirement document. GL35 should be treated as pass through. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | MF Inventory to be updated for IBI interface for GL35 rules on the specified line in the business rules requirement document. GL35 should be treated as pass through. | Review results in AHCS and BI after Accounting entries have posted. Ensure that COA mapping is as expected and accurate as per 1B business design |  |  |  | Approved | Ian Plummer | 2022-10-14 |  |  | Sprint 18 | Sprint 18 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | 1B AHCS : Delivery phase User stories approval Approved on Wed 10/19/2022 3:06 AM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-120 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant I need updated Account Rule (AC-015) to be applied against MF Inventory to be updated for IRI interface on specified lines in the business rules. See GR-045 R(3) rule where site should be derived by ST-008 rule and OG should be OG-007. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | updated Account Rule (AC-015) to be applied against MF Inventory to be updated for IRI interface on specified lines in the business rules. See GR-045 R(3) rule where site should be derived by ST-008 rule and OG should be OG-007. | Review results in AHCS and BI after Accounting entries have posted. Ensure that COA mapping is as expected and accurate as per 1B business design |  |  |  | Approved | Ian Plummer | 2022-10-14 |  |  | Sprint 18 | Sprint 18 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | 1B AHCS : Delivery phase User stories approval Approved on Wed 10/19/2022 3:06 AM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-121 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As an IT Administrator, I want to remove the “SUM Line Debit = SUM Line Credit” validation for CQI interfaces |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT222, INT223 | As an IT Administrator, I want to remove the “SUM Line Debit = SUM Line Credit” validation for CQI interfaces | Records with Dr/Cr mismatch are processed successfully for CQI interface |  |  |  | Approved | Sijo John | 2022-10-14 |  |  | Sprint 18 | Sprint 18 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | 1B AHCS : Delivery phase User stories approval Approved on Wed 10/19/2022 3:06 AM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-122 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant I need MF Inventory for IRI Stat line, amt type STV to have account mapping updated for Spain Secondary ledger. Account should be 6010007 |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | MF Inventory for IRI Stat line, amt type STV to have account mapping updated for Spain Secondary ledger. Account should be 6010007 | Review results in AHCS and BI after Accounting entries have posted. Ensure that COA mapping is as expected and accurate as per 1B business design |  |  |  | Approved | Ian Plummer | 2022-10-14 |  |  | Sprint 18 | Sprint 18 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | 1B AHCS : Delivery phase User stories approval Approved on Wed 10/19/2022 3:06 AM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-123 |  | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As a GL Accountant I need event type field to be added to RPT009 |  |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report | RPT009 | event type field to be added to RPT009 | Review results in RPT009 that able to view event type for each transaction |  |  |  | Approved | Ian Plummer | 2022-10-17 |  |  | Sprint 18 | Sprint 18 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | 1B AHCS : Delivery phase User stories approval Approved on Wed 10/19/2022 3:06 AM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-124 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL accountant I need event type field to be added to INT043 |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT043 | event type field to be added to INT043 | Review results in INT043 that able to view event type for each transaction |  |  |  | Approved | Ian Plummer | 2022-10-17 |  |  | Sprint 18 | Sprint 18 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | 1B AHCS : Delivery phase User stories approval Approved on Wed 10/19/2022 3:06 AM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-125 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As an IT Administrator, I want system to replace double quotes with space from all MF and Cresus data before processing in Oracle |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT218, INT219, INT240, INT216, INT217, INT 240, INT222, INT223 | As an IT Administrator, I want system to replace double quotes with space from all MF and Cresus data before processing in Oracle | Double Quotes are replaced with space for all MF and Cresus transactions |  |  |  | Approved | Ian Plummer | 2022-10-17 |  |  | Sprint 18 | Sprint 18 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | 1B AHCS : Delivery phase User stories approval Approved on Wed 10/19/2022 3:06 AM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-126 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | PS FA uses accounts 312700000 and 127000000 which are same as MF IC accounts. Need to be changed or mapped to Oracle accounts 114006 INTERCOMPANY ACCOUNTS RECEIVABLE - NON INVOICING and 212006 INTERCOMPANY ACCOUNTS PAYABLE - NON INVOICING |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | PS FA uses accounts 312700000 and 127000000 which are same as MF IC accounts. Need to be changed or mapped to Oracle accounts 114006 INTERCOMPANY ACCOUNTS RECEIVABLE - NON INVOICING and 212006 INTERCOMPANY ACCOUNTS PAYABLE - NON INVOICING | Verify PS FA IC results are going to correct accounts as per design |  |  |  | Approved | Ian Plummer | 2022-10-19 |  |  | Sprint 19 | Sprint 19 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | 1B AHCS : Delivery phase User stories approval Approved on Mon 10/31/2022 7:05 PM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-127 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, require MF Inventory subledger for ISI interface to be updated to exclude credit to issue STAT account lines from AHCS configuration for Trade shipments. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | As GL Accountant, require MF Inventory subledger for ISI interface to be updated to exclude credit to issue STAT account lines from AHCS configuration for Trade shipments. | Confirm through review that lines are not being pulled for credit to issue as per design |  |  |  | Approved | Ian Plummer | 2022-10-19 |  |  | Sprint 19 | Sprint 19 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | 1B AHCS : Delivery phase User stories approval Approved on Mon 10/31/2022 7:05 PM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-128 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As an IT Administrator, I want to update the logic to use absolute value of HEADER amount for validation for CAIN (Contra) |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT218, INT219, INT240 | As an IT Administrator, I want to update the logic to use absolute value of HEADER amount for validation for CAIN (Contra) | Confirm the Contra files having Header with negative and Lines with positive are processed successfully |  |  |  | Approved | Sijo John | 2022-10-26 | Sprint 19 |  | Sprint 19 | Sprint 19 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | 1B AHCS : Delivery phase User stories approval Approved on Mon 10/31/2022 7:05 PM |  |  |  | N/A
[5 empty] | DP-RTR-AHCS-129 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant I need Concur grouping logic to be updated to allow posting with correct Accounting date. Grouping should allow for multiple feeds in a day with multiple report dates, assigned to one batch date or one feed with multiple report dates to be posted with correct Accounting date. |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT016 | Concur grouping logic to be updated to allow posting with correct Accounting date. Grouping should allow for multiple feeds in a day with multiple report dates, assigned to one batch date or one feed with multiple report dates to be posted with correct Accounting date. | Confirm after reviewing Concur data that all transaction posted with the correct Accounting Date |  |  |  | Approved | Ian Plummer | 2022-10-27 | Sprint 19 |  | Sprint 19 | Sprint 19 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | 1B AHCS : Delivery phase User stories approval Approved on Mon 10/31/2022 7:05 PM |  |  |  | No
[5 empty] | DP-RTR-IC-108 (for future use) |  | Record to Report | Manage General Ledger Accounting | Process Intercompany Journal Entries | User story to update BPM rules to auto-reject reversal batches where accounting period of reversal batch <> period based on IC batch date of reversal batch Duplicate Story as DP-RTR-IC-112 |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | BPM Config upate | Reversal batches where accounting period of reversal batch <> period based on IC batch date of reversal batch are auto-rejected |  |  |  | Approved | Rita | 2022-10-27 | [7 empty] | RTR | RTR-GL | IC | [13 empty] | Cancelled
[5 empty] | DP-RTR-IC-109 (for future use) |  | Record to Report | Manage General Ledger Accounting | Process Intercompany Journal Entries | User story for new RICE build to identify batches that are reversals of original batches with prior periods and need FX entries in GL. Report will only identify such batches & subsequent user action will be required. Duplicate Story as DP-RTR-IC-113 |  |  | Phase 1B only | 8-TBD (Temporary)-TBD-TBD | TBD (Temporary) | TBD | TBD | RPT213 |  | RPT213 will contain only details for reversals of original batches with prior periods that require FX entries in GL. |  |  |  | Approved | Rita | 2022-10-27 | [7 empty] | RTR | RTR-GL | IC | [13 empty] | Cancelled
[5 empty] | DP-RTR-AHCS-130 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant I need Concur feed to reject if the branch posting to is in a different ledger than the employee is assigned for Legacy ABC Corp. |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT016 | Concur feed to reject if the branch posting to is in a different ledger than the employee is assigned for Legacy ABC Corp. | Confirm after reviewing Concur data that all transaction posted correctly as per business design |  |  |  | Approved | Ian Plummer | 2022-10-28 |  |  | Sprint 19 | Sprint 19 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | 1B AHCS : Delivery phase User stories approval Approved on Mon 10/31/2022 7:05 PM |  |  |  | No
[5 empty] | DP-RTR-IC-110 |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As a Tax Accountant, I require tax lines data to be included in reporting for IC Non Material AR |  |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report | RPT027 | These reports are currently displaying only Line Type "Line" but should also include Line Type "Tax." Per PF: Thanks, although the tax lines are not explicitly called out as an exclusion in the LEAN specs (just the payable/receivable is), it does refer to item and revenue as inclusion, so I believe this is an oversight. | Tax lines are included in report output |  |  |  | Approved | Rita Nanni | 2022-10-28 | [7 empty] | RTR | RTR-GL | IC | [13 empty] | No
[5 empty] | DP-RTR-IC-111 |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As a Tax Accountant, I require tax lines data to be included in reporting for IC Non Material AP |  |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report | RPT028 | These reports are currently displaying only Line Type "Line" but should also include Line Type "Tax." Per PF: Thanks, although the tax lines are not explicitly called out as an exclusion in the LEAN specs (just the payable/receivable is), it does refer to item and revenue as inclusion, so I believe this is an oversight. | Tax lines are included in report output |  |  |  | Approved | Rita Nanni | 2022-10-28 | [7 empty] | RTR | RTR-GL | IC | [13 empty] | No
[5 empty] | DP-RTR-AHCS-131 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a Financial Systems Analyst, I need to fix multiple transactions for mapping errors/source data issues that are created after processing Create Accounting. This functionality will help to fix these multiple errors without manual intervention. |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Extension | EXT123 | As a Financial Systems Analyst, I need to fix multiple transactions for mapping errors/source data issues that are created after processing Create Accounting. This functionality will help to fix these multiple errors without manual intervention. | Confirm that you can run Accounting Error Reprocessing process and multiple errors are fixed. |  |  |  | Approved | Ian Plummer | 2022-11-07 |  |  | Sprint 19 | Sprint 19 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | 1B AHCS : Delivery phase User stories approval Approved on Mon 10/31/2022 7:05 PM |  |  |  | No
[5 empty] | DP-RTR-AHCS-132 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As an IT Administrator, I want to group Treasury (TMI) transactions by Accounting Date and modify the transaction number logic accordingly | Phase 1B only | 3-Gap-Build-Interface | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT045 | As an IT Administrator, I want to group Treasury (TMI) transactions by Accounting Date and modify the transaction number logic accordingly | Treasury file with multiple Accounting Dates are processed as separate transactions | 2022-10-26 |  |  | Approved | Sijo John | 2022-10-31 |  |  | Sprint 19 | Sprint 19 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | 1B AHCS : Delivery phase User stories approval Approved on Mon 10/31/2022 7:05 PM |  |  |  | No
[5 empty] | DP-RTR-AHCS-133 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As an IT Administrator, I want to modify Transaction# logic for MF and Cresus as Interface ID+ HDR SEQ NBR + Static Ledger Number (Based on Ledger Lookup in OIC) | Phase 1B only | 3-Gap-Build-Interface | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT216, INT217, INT 240 INT218, INT219, INT240 INT222, INT223 | As an IT Administrator, I want to modify Transaction# logic for MF and Cresus as Interface ID+ HDR SEQ NBR + Static Ledger Number (Based on Ledger Lookup in OIC) | Transaction number for all Mainframe and Cresus is created with static ledger number |  |  |  | Approved | Sijo John | 2022-10-31 |  |  | Sprint 19 | Sprint 19 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | 1B AHCS : Delivery phase User stories approval Approved on Wed 11/2/2022 10:21 PM |  |  |  | No
[5 empty] | DP-RTR-GL-084 |  | Record to Report | Manage General Ledger Accounting | Perform Allocations | As a GL Accountant, I want to be able to create a monthly worldwide allocation that moves intransit line, cut, and markup charges from BS to IS so that cost of labor is recognized in correct period. This allocation should run at the end of each period and then reverses at the beginning of the following period. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Intransit Expense Allocation (IEA) Without this allocation these balances would remain in intransit (BS) accounts until shipment is received. | Allocated balance in functional currency. Reversal of balance beginning of next period. |  |  |  | Approved | Rita | 2022-10-31 | [7 empty] | RTR | RTR-GL | GL | [13 empty] | No
[5 empty] | DP-RTR-GL-085 |  | Record to Report | Manage General Ledger Accounting | Perform Allocations | As a GL Accountant, I want to be able to create a monthly worldwide allocation that reclasses balances from supply chain revenue accounts to expense accounts so that expenses and revenues are offset in same section of P&L. This allocation should run at the end of each period and then reverses at the beginning of the following period. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Revenue Reclass Allocation (RRA) Without this allocation these internal revenues would be recorded as operating revenue. | Allocated balance in functional currency. Reversal of balance beginning of next period. |  |  |  | Approved | Rita | 2022-10-31 | [7 empty] | RTR | RTR-GL | GL | [13 empty] | No
[5 empty] | DP-RTR-AHCS-134 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As an IT Administrator, I want to use Entered Currency from Header for Sales interface offset lines. This is to follow the logic used in FAH | Phase 1B only | 3-Gap-Build-Interface | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | As an IT Administrator, I want to use Entered Currency from Header for Sales interface offset lines. This is to follow the logic used in FAH | Entered Currency is used from Headers for Sales Interface | 2022-10-26 |  |  | Approved | Sijo John | 2022-11-02 |  |  | Sprint 19 | Sprint 19 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | 1B AHCS : Delivery phase User stories approval Approved on Tue 11/15/2022 2:13 AM |  |  |  | No
[5 empty] | DP-RTR-AHCS-135 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant I need GL Location Field in AHCS populated with configured Legacy Shipped from Location for all event types for the interface ISI. This should be applicable to all created lines in AHCS that fall under ISI where the rules state to use Ship from location to derive site in 1B document. This is only applicable for BSR lines only. | Phase 1B only | 3-Gap-Build-Interface | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | GL Location Field in AHCS populated with configured Legacy Shipped from Location for all event types for the interface ISI. This should be applicable to all created lines in AHCS that fall under ISI where the rules state to use Ship from location to derive site in 1B document. This is only applicable for BSR lines only. | Verified able to view fields as defined per business design | 2022-10-26 |  |  | Approved | Ian Plummer | 11/3/2022 11/28/22 |  |  | Sprint 19 | Sprint 19 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | 1B AHCS : Delivery phase User stories approval Approved on Tue 11/15/2022 2:13 AM |  |  |  | No
[5 empty] | DP-RTR-AHCS-136 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant I need MF AR to capture Source System ~ Document Date~ Sales Order Number~ Memo R: <Memo R Value> ~ User I: <User ID> ~ <Source Description> at header level | Phase 1B only | 3-Gap-Build-Interface | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | MF AR to capture Source System ~ Document Date~ Sales Order Number~ Memo R: <Memo R Value> ~ User I: <User ID> ~ <Source Description> at header level | Verified able to view fields as defined per business design | 2022-10-26 |  |  | Approved | Ian Plummer | 2022-11-04 |  |  | Sprint 19 | Sprint 19 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | 1B AHCS : Delivery phase User stories approval Approved on Tue 11/15/2022 2:13 AM |  |  |  | No
[5 empty] | DP-RTR-AHCS-137 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant I need MF AP to capture Source System~ Document Date~ Purchase Order Number~Memo R: <Memo R Value> ~ User I: <User ID> ~ <Source Description> at the header level | Phase 1B only | 3-Gap-Build-Interface | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | MF AP to capture Source System~ Document Date~ Purchase Order Number~Memo R: <Memo R Value> ~ User I: <User ID> ~ <Source Description> at the header level | Verified able to view fields as defined per business design | 2022-10-26 |  |  | Approved | Ian Plummer | 2022-11-04 |  |  | Sprint 19 | Sprint 19 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | 1B AHCS : Delivery phase User stories approval Approved on Tue 11/15/2022 2:13 AM |  |  |  | No
[5 empty] | DP-RTR-AHCS-138 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant I need MF Inventory to capture Source System~ Invoice Number~Invoice Date~ Trading Partner Number~Customer PO~RA Number~ Receiver Number~ Memo R: <Memo R Value> ~ User I: <User ID> ~ <Source Description> at the header level | Phase 1B only | 3-Gap-Build-Interface | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | MF Inventory to capture Source System~ Invoice Number~Invoice Date~ Trading Partner Number~Customer PO~RA Number~ Receiver Number~ Memo R: <Memo R Value> ~ User I: <User ID> ~ <Source Description> at the header level | Verified able to view fields as defined per business design | 2022-10-26 |  |  | Approved | Ian Plummer | 2022-11-04 |  |  | Sprint 19 | Sprint 19 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | 1B AHCS : Delivery phase User stories approval Approved on Tue 11/15/2022 2:13 AM |  |  |  | No
[5 empty] | DP-RTR-AHCS-139 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant I need MF AR to capture Source System ~ Amount Type Description ~ Legacy Division ~ Export Type ~ Customer PO at the line level | Phase 1B only | 3-Gap-Build-Interface | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | MF AR to capture Source System ~ Amount Type Description ~ Legacy Division ~ Export Type ~ Customer PO at the line level | Verified able to view fields as defined per business design | 2022-10-26 |  |  | Approved | Ian Plummer | 2022-11-04 |  |  | Sprint 19 | Sprint 19 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | 1B AHCS : Delivery phase User stories approval Approved on Tue 11/15/2022 2:13 AM |  |  |  | No
[5 empty] | DP-RTR-AHCS-140 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant I need MF AP to capture Source System ~ Amount Type Description ~ Legacy Division ~ FRT BILL PRO REF NBR at the line level | Phase 1B only | 3-Gap-Build-Interface | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | MF AP to capture Source System ~ Amount Type Description ~ Legacy Division ~ FRT BILL PRO REF NBR at the line level | Verified able to view fields as defined per business design | 2022-10-26 |  |  | Approved | Ian Plummer | 2022-11-04 |  |  | Sprint 19 | Sprint 19 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | 1B AHCS : Delivery phase User stories approval Approved on Tue 11/15/2022 2:13 AM |  |  |  | No
[5 empty] | DP-RTR-AHCS-141 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant I need MF Inventory to capture Source System~Trading Partner Number~ Receiver Number ~ Item Number ~Amount Type Description at the line level | Phase 1B only | 3-Gap-Build-Interface | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | MF Inventory to capture Source System~Trading Partner Number~ Receiver Number ~ Item Number ~Amount Type Description at the line level | Verified able to view fields as defined per business design | 2022-10-26 |  |  | Approved | Ian Plummer | 2022-11-04 |  |  | Sprint 19 | Sprint 19 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | 1B AHCS : Delivery phase User stories approval Approved on Tue 11/15/2022 2:13 AM |  |  |  | No
[5 empty] | DP-RTR-AHCS-142 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant need PURCHASE_ORDER_NUMBER, SALES_ORDER_NUMBER, SHIP_FROM_LOCATION added to the IC lines for ICI and AII interface as part of MF |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | As GL Accountant need PURCHASE_ORDER_NUMBER, SALES_ORDER_NUMBER, SHIP_FROM_LOCATION added to the IC lines for ICI and AII interface as part of MF | Verified able to view fields as defined per business design |  |  |  | Approved | Ian Plummer | 2022-11-04 |  |  | Sprint 19 | Sprint 19 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | 1B AHCS : Delivery phase User stories approval Approved on Tue 11/15/2022 2:13 AM |  |  |  | No
[5 empty] | DP-RTR-AHCS-143 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant need MF Inventory specific to IBI interface to capture PO number from the line level |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT222, INT223 | As GL Accountant need MF Inventory specific to IBI interface to capture PO number from the line level | Verified able to view fields as defined per business design |  |  |  | Approved | Ian Plummer | 2022-11-11 |  |  | Sprint 19 | Sprint 19 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | 1B AHCS : Delivery phase User stories approval Approved on Tue 11/15/2022 2:13 AM |  |  |  | No
[5 empty] | DP-RTR-AHCS-144 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant I need MF Inventory for IRI to be updated to to include WKU and IAK as the same as WST and ISK because they are both Workorders and Kava Intransit the coding should be the same. 1B document updated on sharepoint. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | As GL Accountant I need MF Inventory for IRI to be updated to to include WKU and IAK as the same as WST and ISK because they are both Workorders and Kava Intransit the coding should be the same. 1B document updated on sharepoint. | Verified able to view fields as defined per business design |  |  |  | Approved | Ian Plummer | 2022-11-11 |  |  | Sprint 19 | Sprint 19 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | 1B AHCS : Delivery phase User stories approval Approved on Tue 11/15/2022 2:13 AM |  |  |  | No
[5 empty] | DP-RTR-IC-112 |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As a Tax Accountant, I require that chronological sequencing is aligned with batch date. Intercompany Module should reject transaction if Batch Month and Year is not equal to Month and Year of Accounting Date. This is to prevent approval of a batch if the batch date is not in a current, open period. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | 1) System prevents approval of a reverse any batch with batch date of a closed period (including future) (cfr POC designed and tested by Deloitte) (irrespective of "regional" vs "global") 2) User creates reverse batch with batch date according to the assumption (reverse batch batch date is current during month and last day of month during close) 3) In case invoice was in different entered currency, user adjusts FX (process TBD) based on report (to be built) |  |  |  |  | Approved | Rita Nanni | 2022-11-10 | [7 empty] | RTR | RTR-GL | IC | [13 empty] | No
[5 empty] | DP-RTR-IC-113 |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As a GL Accountant, I require a report that identifies intercompany reverse batch transactions where batch date does not equal batch date of original transaction. This report is to allow the user to identify where there are fx variances due to different rate dates, and allow user to upload a GL journal to correct. This is Day 90 requirement. |  |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report | RPT214 | [5 empty] | Approved | Rita Nanni | 2022-11-10 | [7 empty] | RTR | RTR-GL | IC | [13 empty] | No
[5 empty] | DP-RTR-IC-114 |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As a Tax Accountant, I require an XML file to be created at the time of invoice creation for each transaction to be archived with the PDF. |  |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | [8 empty] | Jessica Ponzo | [24 empty] | No
[5 empty] | DP-RTR-AHCS-145 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant I need 1B requirement business rules to be updated as follows 1. Change rule ST-015 which is the rule about BU 002 deriving site based on location to site value sets in the mapping engine to ST-011. 2. Change rule GR-047 for every intangible line to ST-018 and DT-005. 3. Update rule ST-016 referring to rule GR-047 and DT-004 was changed to refer to GR-047 to be consistent with ST-016 |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | As GL Accountant I need 1B requirement business rules to be updated as follows 1. Change rule ST-015 which is the rule about BU 002 deriving site based on location to site value sets in the mapping engine to ST-011. 2. Change rule GR-047 for every intangible line to ST-018 and DT-005. 3. Update rule ST-016 referring to rule GR-047 and DT-004 was changed to refer to GR-047 to be consistent with ST-016 | Verify results in accordance with updated business design |  |  |  | Approved | Ian Plummer | 2022-11-16 |  |  | Sprint 19 | Sprint 19 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | 1B AHCS : Delivery phase User stories approval Approved on Fri 11/18/2022 7:22 PM |  |  |  | No
[5 empty] | DP-RTR-AHCS-146 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant I need 1B requirement business rules to be added for AR subledger specific to CRI interface for amount types MTA and DIS. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | As GL Accountant I need 1B requirement business rules to be added for AR subledger specific to CRI interface for amount types MTA and DIS. | Verify results in accordance with updated business design |  |  |  | Approved | Ian Plummer | 2022-11-17 |  |  | Sprint 19 | Sprint 19 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | 1B AHCS : Delivery phase User stories approval Approved on Fri 11/18/2022 7:22 PM |  |  |  | No
[5 empty] | DP-RTR-AHCS-147 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant I need PO Receipt Type to be used to populate Legacy Transaction Type in AHCS for IRI interface as part of MF Inventory subledger |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface |  | As GL Accountant I need PO Receipt Type to be used to populate Legacy Transaction Type in AHCS for IRI interface as part of MF Inventory subledger | Verify results in accordance with updated business design |  |  |  | Approved | Ian Plummer | 2022-11-17 |  |  | Sprint 19 | Sprint 19 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | 1B AHCS : Delivery phase User stories approval Approved on Fri 12/2/2022 8:48 PM |  |  |  | No
[5 empty] | DP-RTR-IC-115 |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As GL and Tax Accountant, I require that zero dollar tax lines are suppressed in report output for RPT027 Non Material IC AR Report, since call to tax engine will generate such lines, even if result is zero. This is to eliminate clutter from reporting. |  |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report | RPT027 | From PF email: suppress zero dollar accounting class “TAX” on RPT027 and INT189/190. I also noticed zero dollar lines for accounting class “EXCHANGE_GAIN_LOSS” on INT189/190 which I recommend to suppress. From Omkar email: Suppress of line while importing or displaying will be BI user story For outbounds suppression should be tackled on reporting layer - so BI. Can you please provide these user stories to BI as it pertains to interfaces | Zero dollar tax lines do not appear on report output |  |  |  | Approved | Rita Nanni | 2022-11-18 | [7 empty] | RTR | RTR-GL | AP | [13 empty] | No
[5 empty] | DP-RTR-IC-116 |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As GL and Tax Accountant, I require that zero dollar tax lines are suppressed in report output for RPT028 Non Material IC AP Report, since call to tax engine will generate such lines, even if result is zero. This is to eliminate clutter from reporting. |  |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report | RPT028 | From PF email: zero dollar tax lines, which includes the non-recoverable, where accounting class (XLA_AE_LINES.ACCOUNTING_CLASS_CODE) is equal to "RTAX" and "NRTAX" and both debit/credit are zero From Omkar email: Suppress of line while importing or displaying will be BI user story For outbounds suppression should be tackled on reporting layer - so BI. Can you please provide these user stories to BI as it pertains to interfaces | Zero dollar tax lines do not appear on report output |  |  |  | Approved | Rita Nanni | 2022-11-18 | [7 empty] | RTR | RTR-GL | AP | [13 empty] | No
[5 empty] | DP-RTR-AHCS-148 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant I need rule ST-013 to be updated in 1B requirement document to read "If EMEA LE (Mainframe BU 008* mapped to Oracle LE) – derive site based location to site value set in AHCS received from the mapping engine . Use Sales Loc to derive site |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | As GL Accountant I need rule ST-013 to be updated in 1B requirement document to read "If EMEA LE (Mainframe BU 008* mapped to Oracle LE) – derive site based location to site value set in AHCS received from the mapping engine . Use Sales Loc to derive site | Verify results in accordance with updated business design |  |  |  | Approved | Ian Plummer | 2022-11-18 |  |  | Sprint 19 | Sprint 19 |  |  |  | RTR | RTR-AHCS | AHCS | [6 empty] | 1B AHCS : Delivery phase User stories approval Approved on Fri 11/18/2022 7:22 PM |  |  | 1B AHCS : Delivery phase User stories approval Approved on Fri 12/2/2022 8:48 PM |  |  |  | No
[5 empty] | DP-RTR-IC-114 |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As a Tax Accountant, I require an XML file to be created at the time of invoice creation for each transaction to be archived with the PDF. |  |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report |  | The invoice XML is required to archive the data used at time of invoice creation for Tax compliance & auditing. (RMN 11/28/22) Will this require new RICE, or will it be addressed by third party? Still to be determined. | Both XML and PDF formats are available for archived invoices |  |  |  | Approved | Rita Nanni | 2022-11-18 | [7 empty] | RTR | RTR-GL | IC | [5 empty] | Approved - Jessica Ponzo | [7 empty] | No
[5 empty] | DP-RTR-AHCS-149 | Record to Report | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As an IT Administrator, I want to exclude below off system LEs from Leases files: 00338 - Tri-Ed Puerto Rico 00533 - ABC Corp Atlas Genentech 00532 - ABC Corp Inner Range 00531 - ABC Corp Central Security | 3-Gap-Build-Interface |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT020 | As an IT Administrator, I want to exclude below off system LEs from Leases files: 00338 - Tri-Ed Puerto Rico 00533 - ABC Corp Atlas Genentech 00532 - ABC Corp Inner Range 00531 - ABC Corp Central Security | Off system LEs are excluded from Leases files for processing | 2022-10-31 |  |  | Approved | Sijo John Ian Plummer | 11/28/2022 11/30/2022 |  |  | Sprint 19 | Sprint 19 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | 1B AHCS : Delivery phase User stories approval Approved on Fri 12/2/2022 8:48 PM |  |  |  | No
[5 empty] | DP-RTR-AHCS-150 |  | Record to Report | Manage Subledger Accounting |  | As GL Accountant I need MF AR subledger specific to SPER interface to populate data in the SR field of Freight Terms taken from header of MF source; populate in the SR field of Invoice Due Date taken from header of MF source; populate data in the SR field of Standard Unit cost taken from line of MF source. All three SRs are applicable for all lines in the SPER interface. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | As GL Accountant I need MF AR subledger specific to SPER interface to populate data in the SR field of Freight Terms taken from header of MF source; populate in the SR field of Invoice Due Date taken from header of MF source; populate data in the SR field of Standard Unit cost taken from line of MF source. All three SRs are applicable for all lines in the SPER interface. | Verify results in accordance with updated business design |  |  |  | Approved | Ian Plummer | 2022-11-28 |  |  | Sprint 19 | Sprint 19 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | 1B AHCS : Delivery phase User stories approval Approved on Fri 12/2/2022 8:48 PM |  |  |  | No
[5 empty] | DP-RTR-AHCS-151 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant I need MF Inventory Subledger specific to ISI to populate Document date as a SR on ISI for all lines/event types. This should be derived from the header from MF Source. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | MF Inventory Subledger specific to ISI to populate Document date as a SR on ISI for all lines/event types. This should be derived from the header from MF Source. | Verify results in accordance with updated business design |  |  |  | Approved | Ian Plummer | 2022-11-28 |  |  | Sprint 19 | Sprint 19 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | 1B AHCS : Delivery phase User stories approval Approved on Fri 12/2/2022 8:48 PM |  |  |  | No
[5 empty] | DP-RTR-AHCS-152 | Record to Report | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant I need SR Ship From Location Field in AHCS populated with Legacy Shipped from Location for all lines/event types related to IBI interface. This should be taken from the header from MF source data. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | SR Ship From Location Field in AHCS populated with Legacy Shipped from Location for all lines/event types related to IBI interface. This should be taken from the header from MF source data. | Verify results in accordance with updated business design |  |  |  | Approved | Ian Plummer | 2022-11-28 |  |  | Sprint 19 | Sprint 19 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | 1B AHCS : Delivery phase User stories approval Approved on Fri 12/2/2022 8:48 PM |  |  |  | No
[5 empty] | DP-RTR-AHCS-153 | Record to Report | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant I need the RA concatenating logic 'RA_NBR + RA_LOC field from source file', removed for all source codes and event types that fall under MF Inventory. This should also be updated in lean spec from 'Source System to AHCS Mapping' tab |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT222, INT223 | the RA concatenating logic 'RA_NBR + RA_LOC field from source file', removed for all source codes and event types that fall under MF Inventory. This should also be updated in lean spec from 'Source System to AHCS Mapping' tab | Verify results in accordance with updated business design |  |  |  | Approved | Ian Plummer | 2022-11-28 |  |  | Sprint 19 | Sprint 19 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | 1B AHCS : Delivery phase User stories approval Approved on Fri 12/2/2022 8:48 PM |  |  |  | No
[5 empty] | DP-RTR-AHCS-154 | Record to Report | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant I need MF AP to capture Source System ~ Amount Type Description ~ Legacy Division ~ FRT BILL PRO REF NBR at the line level for Amount type 'DUT' as part of configuration under description rules for MF AP. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | MF AP to capture Source System ~ Amount Type Description ~ Legacy Division ~ FRT BILL PRO REF NBR at the line level for Amount type 'DUT' as part of configuration under description rules for MF AP. | Verify results in accordance with updated business design |  |  |  | Approved | Ian Plummer | 2022-11-28 |  |  | Sprint 19 | Sprint 19 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | 1B AHCS : Delivery phase User stories approval Approved on Fri 12/2/2022 8:48 PM |  |  |  | No
[5 empty] | DP-RTR-AHCS-155 | Record to Report | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant I need MF AP to capture Source System ~ ~ Legacy Division ~ FRT BILL PRO REF NBR at the line level for all AP Conversions as part of configuration under description rules for MF AP. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | MF AP to capture Source System ~ ~ Legacy Division ~ FRT BILL PRO REF NBR at the line level for all AP Conversions as part of configuration under description rules for MF AP. | Verify results in accordance with updated business design |  |  |  | Approved | Ian Plummer | 2022-11-28 |  |  | Sprint 19 | Sprint 19 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | 1B AHCS : Delivery phase User stories approval Approved on Fri 12/2/2022 8:48 PM |  |  |  | No
[5 empty] | DP-RTR-AHCS-156 | Record to Report | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant I need MF AR to capture Source System ~ ~ Legacy Division ~ Export Type ~ Customer PO at line level for all AR Conversions as part of configuration under description rules for MF AR. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | MF AR to capture Source System ~ ~ Legacy Division ~ Export Type ~ Customer PO at line level for all AR Conversions as part of configuration under description rules for MF AR. | Verify results in accordance with updated business design |  |  |  | Approved | Ian Plummer | 2022-11-28 |  |  | Sprint 19 | Sprint 19 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | 1B AHCS : Delivery phase User stories approval Approved on Fri 12/2/2022 8:48 PM |  |  |  | No
[5 empty] | DP-RTR-AHCS-157 | Record to Report | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant I need MF Inventory to capture Source System~Trading Partner Number~ Receiver Number ~ Item Number ~ at line level for all Inventory Conversions as part of configuration under description rules for MF Inventory. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | MF Inventory to capture Source System~Trading Partner Number~ Receiver Number ~ Item Number ~ at line level for all Inventory Conversions as part of configuration under description rules for MF Inventory. | Verify results in accordance with updated business design |  |  |  | Approved | Ian Plummer | 2022-11-28 |  |  | Sprint 19 | Sprint 19 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | 1B AHCS : Delivery phase User stories approval Approved on Fri 12/2/2022 8:48 PM |  |  |  | No
[5 empty] | DP-RTR-AHCS-158 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant I need MF AR to capture Source System ~ Document Date~ Sales Order Number~ Memo R: <Memo R Value> ~ User I: <User ID> ~ <Source Description> at header level for all AR Conversions as part of configuration under description rules for MF AR. | Phase 1B only | 3-Gap-Build-Interface | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | MF AR to capture Source System ~ Document Date~ Sales Order Number~ Memo R: <Memo R Value> ~ User I: <User ID> ~ <Source Description> at header level for all AR Conversions as part of configuration under description rules for MF AR. | Verified able to view fields as defined per business design | 2022-10-26 |  |  | Approved | Ian Plummer | 2022-11-28 |  |  | Sprint 19 | Sprint 19 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | 1B AHCS : Delivery phase User stories approval Approved on Fri 12/2/2022 8:48 PM |  |  |  | No
[5 empty] | DP-RTR-AHCS-159 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant I need MF AP to capture Source System~ Document Date~ Purchase Order Number~Memo R: <Memo R Value> ~ User I: <User ID> ~ <Source Description> at the header level for all AP Conversions as part of configuration under description rules for MF AP. | Phase 1B only | 3-Gap-Build-Interface | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | MF AP to capture Source System~ Document Date~ Purchase Order Number~Memo R: <Memo R Value> ~ User I: <User ID> ~ <Source Description> at the header level for all AP Conversions as part of configuration under description rules for MF AP. | Verified able to view fields as defined per business design | 2022-10-26 |  |  | Approved | Ian Plummer | 2022-11-28 |  |  | Sprint 19 | Sprint 19 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | 1B AHCS : Delivery phase User stories approval Approved on Fri 12/2/2022 8:48 PM |  |  |  | No
[5 empty] | DP-RTR-AHCS-160 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant I need MF Inventory to capture Source System~ Invoice Number~Invoice Date~ Trading Partner Number~Customer PO~RA Number~ Receiver Number~ Memo R: <Memo R Value> ~ User I: <User ID> ~ <Source Description> at the header level for all Inventory Conversions as part of configuration under description rules for MF Inventory | Phase 1B only | 3-Gap-Build-Interface | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | MF Inventory to capture Source System~ Invoice Number~Invoice Date~ Trading Partner Number~Customer PO~RA Number~ Receiver Number~ Memo R: <Memo R Value> ~ User I: <User ID> ~ <Source Description> at the header level for all Inventory Conversions as part of configuration under description rules for MF Inventory | Verified able to view fields as defined per business design | 2022-10-26 |  |  | Approved | Ian Plummer | 2022-11-28 |  |  | Sprint 19 | Sprint 19 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | 1B AHCS : Delivery phase User stories approval Approved on Fri 12/2/2022 8:48 PM |  |  |  | No
[5 empty] | DP-RTR-AHCS-161 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant I need MF Inventory specific to ISI interface where rules ST-020 is applicable to be updated to use Ship location instead of GL location to derive site segment as per defined rules in 1B - Business requirements UAT File document | Phase 1B only | 3-Gap-Build-Interface | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | MF Inventory specific to ISI interface where rules ST-020 is applicable to be updated to use Ship location instead of GL location to derive site segment as per defined rules in 1B - Business requirements UAT File document | Verified able to view fields as defined per business design | 2022-10-26 |  |  | Approved | Ian Plummer | 2022-11-29 |  |  | Sprint 19 | Sprint 20 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | 1B AHCS : Delivery phase User stories approval Approved on Fri 12/2/2022 8:48 PM |  |  |  | No
[5 empty] | DP-RTR-AHCS-162 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant I need MF Inventory to be updated as of November 11, 2022 as per defined rules in 1B - Business requirements UAT File document | Phase 1B only | 3-Gap-Build-Interface | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | MF Inventory to be updated as of November 11, 2022 as per defined rules in 1B - Business requirements UAT File document | Verified able to view fields as defined per business design | 2022-10-26 |  |  | Approved | Ian Plummer | 2022-11-29 |  |  | Sprint 19 | Sprint 20 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | 1B AHCS : Delivery phase User stories approval Approved on Fri 12/2/2022 8:48 PM |  |  |  | No
[5 empty] | DP-RTR-AHCS-163 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant I need MF AP to be updated as of November 11, 2022 as per defined rules in 1B - Business requirements UAT File document | Phase 1B only | 3-Gap-Build-Interface | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | MF AP to be updated as of November 11, 2022 as per defined rules in 1B - Business requirements UAT File document | Verified able to view fields as defined per business design | 2022-10-26 |  |  | Approved | Ian Plummer | 2022-11-29 |  |  | Sprint 19 | Sprint 19 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | 1B AHCS : Delivery phase User stories approval Approved on Fri 12/2/2022 8:48 PM |  |  |  | No
[5 empty] | DP-RTR-AHCS-164 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant I need MF AR to be updated as of November 11, 2022 as per defined rules in 1B - Business requirements UAT File document | Phase 1B only | 3-Gap-Build-Interface | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | MF AR to be updated as of November 11, 2022 as per defined rules in 1B - Business requirements UAT File document | Verified able to view fields as defined per business design | 2022-10-26 |  |  | Approved | Ian Plummer | 2022-11-29 |  |  | Sprint 19 | Sprint 19 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | 1B AHCS : Delivery phase User stories approval Approved on Fri 12/2/2022 8:48 PM |  |  |  | No
[5 empty] | DP-RTR-IC-117 |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As an intercompany accountant, I need the ability to include legacy Wesco entities 1002 (WESCO Distribution, Inc. USD), and 2001 (WESCO Distribution Canada LP) in the in the non-material intercompany processes that leverage the IC module as well as IC AP and AR |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | To allow all entities that transact with Non US and Canada entities to adhere to intercompany invoicing requirements. To also ensure that we follow one global process for managing non-material intercompany transactions. |  |  |  |  | Approved | Rita Nanni | 2022-11-29 | [7 empty] | RTR | RTR-GL | IC | [13 empty] | No
[5 empty] | DP-RTR-AHCS-165 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant, I need rule 47 for France Ledger to be updated for Department rule DT-005 and Site rule ST-018 for all PC Flags in the 1B - Business requirements UAT File. | Phase 1B only | 3-Gap-Build-Interface | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | As a GL Accountant, I need rule 47 for France Ledger to be updated for Department rule DT-005 and Site rule ST-018 for all PC Flags in the 1B - Business requirements UAT File. | Verified able to view fields as defined per business design | 2022-10-26 |  |  | Approved | Ian Plummer | 2022-11-30 |  |  | Sprint 20 | Sprint 20 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | 1B AHCS : Delivery phase User stories approval Approved on Fri 12/2/2022 8:48 PM |  |  |  | No
[5 empty] | DP-RTR-AHCS-166 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant, I need rule 47a for France Ledger to be updated for Project rule PR-005 and Site rule ST-012 for all PC Flags in the 1B - Business requirements UAT File. | Phase 1B only | 3-Gap-Build-Interface | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | As a GL Accountant, I need rule 47a for France Ledger to be updated for Project rule PR-005 and Site rule ST-012 for all PC Flags in the 1B - Business requirements UAT File. | Verified able to view fields as defined per business design | 2022-10-26 |  |  | Approved | Ian Plummer | 2022-11-30 |  |  | Sprint 20 | Sprint 20 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | 1B AHCS : Delivery phase User stories approval Approved on Fri 12/2/2022 8:48 PM |  |  |  | No
[5 empty] | DP-RTR-IC-118 |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As a tax accountant, I require one PDF file for each Intercompany transaction |  |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report | RPT102-RPT103 | This user story is for evaluation/analysis to be performed by Deloitte on existing RICE |  |  |  |  | Approved | Rita Nanni | 2022-11-29 | [7 empty] | RTR | RTR-GL | IC | [13 empty] | No
[5 empty] | DP-RTR-AHCS-167 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant, I need MF AR specific to CRI for events 1. Cash Applications Bank line, IC receivable and payable line; 2 Freight Claims IC receivable and payable line; 3. Late Fees IC receivable and payable line rule to be changed from 00000 to rule ST-011 in the 1B - Business requirements UAT File. | Phase 1B only | 3-Gap-Build-Interface | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | As a GL Accountant, I need rule 47a for France Ledger to be updated for Project rule PR-005 and Site rule ST-012 for all PC Flags in the 1B - Business requirements UAT File. | Verified able to view fields as defined per business design | 2022-10-26 |  |  | Approved | Ian Plummer | 2022-11-30 |  |  | Sprint 20 | Sprint 20 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | 1B AHCS : Delivery phase User stories approval Approved on Fri 12/2/2022 8:48 PM |  |  |  | No
[5 empty] | DP-RTR-IC-119 |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As a tax accountant, I require that the AR line description field is populated in the AR outbound Interfaces (INT189, INT190) |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT189, INT190 | This field is currently blank per Oracle standard functionality, but is required by Tax team. For evaluation by Deloitte team Per SG Email 1/19/2023: As discussed; this Description Rule setup is not required for MVP1, so add the condition in the Description Rule setup to restrict it only for Cornerstone AR Transactions. |  |  |  |  | Approved | Rita Nanni | 2022-12-01 |  |  | Sprint 20 | Sprint 20 |  |  |  | RTR | RTR-GL | IC | [13 empty] | No
[5 empty] | DP-RTR-IC-120 |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As an intercompany accountant I require that APAC off-system entities be excluded from list of Intercompany Organizations (LE's 4008, 4009, 4019) |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | APAC off-system entities should be excluded from intercompany invoicing | APAC LE's 4008, 4009, and 4019 are not available for IC tranactions |  |  |  | Approved | Rita Nanni | 2022-12-01 |  |  | Sprint 20 | Sprint 20 |  |  |  | RTR | RTR-GL | IC | [13 empty] | No
[5 empty] | DP-RTR-AHCS-168 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | AHCS BI outbound interface objects are planned to be converted in ESS job set for placing the file in sequential manner(Data, CTL, Done) . done file to be placed after completion of data and CTL file. INT043 -- AHCS Data to IAP - AHCS Details INT044 -- AHCS Data to IAP - AHCS Reconciliation Balances INT244 -- AHCS Conversion Details To IAP |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface |  | AHCS BI outbound interface objects be converted in ESS job set for placing the file in sequential manner(Data, CTL, Done) . done file to be placed after completion of data and CTL file. INT043 -- AHCS Data to IAP - AHCS Details INT044 -- AHCS Data to IAP - AHCS Reconciliation Balances INT244 -- AHCS Conversion Details To IAP | The files are placed in sequential manner (Data, CTL, Done) |  |  |  | Approved | Sijo John | 2022-12-02 |  |  | Sprint 20 | Sprint 20 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | 1B AHCS : Delivery phase User stories approval Approved on Fri 12/2/2022 8:48 PM |  |  |  | No
[5 empty] | DP-RTR-AHCS-169 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant, I need rule 47 for all Ledgers to be updated for 1. Department rule DT-003 for all PC flags except PC flag M and R should be 0000 2. For Site rule ST-011 for all PC Flags in the 1B - Business requirements UAT File. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Rule to be updated 47 for all Ledgers to be updated for 1. Department rule DT-003 for all PC flags except PC flag M and R should be 0000 2. For Site rule ST-011 for all PC Flags in the 1B - Business requirements UAT File. | Verified able to view fields as defined per business design |  |  |  | Approved | Ian Plummer | 2022-12-02 |  |  | Sprint 20 | Sprint 20 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | 1B AHCS : Delivery phase User stories approval Approved on Mon 12/5/2022 7:29 PM |  |  |  | No
[5 empty] | DP-RTR-AHCS-170 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant, I need rule 47a for all Ledgers to be updated for Department rule DT-005 for all PC flags except PC flag M and R should be 0000 in the 1B - Business requirements UAT File. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Rule to be updated 47a for all Ledgers to be updated for Department rule DT-005 for all PC flags except PC flag M and R should be 0000 in the 1B - Business requirements UAT File. | Verified able to view fields as defined per business design |  |  |  | Approved | Ian Plummer | 2022-12-02 |  |  | Sprint 20 | Sprint 20 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | 1B AHCS : Delivery phase User stories approval Approved on Mon 12/5/2022 7:29 PM |  |  |  | No
[5 empty] | DP-RTR-AHCS-171 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant, I need rule DT-003 verbiage to be updated to remove default 8000 from the rules. This should be applicable against MF AR specific to SII, CRI for all specified events where rules are applicable in the 1B - Business requirements UAT File. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Rule to be updated DT-003 verbiage to remove default 8000 from the rules. This should be applicable against MF AR specific to SII, CRI for all specified events where rules are applicable in the 1B - Business requirements UAT File. | Verified able to view fields as defined per business design |  |  |  | Approved | Ian Plummer | 2022-12-02 |  |  | Sprint 20 | Sprint 20 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | 1B AHCS : Delivery phase User stories approval Approved on Mon 12/5/2022 7:29 PM |  |  |  | No
[5 empty] | DP-RTR-AHCS-172 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant, I need rule DT-003 verbiage to be updated to remove default 8000 from the rules. This should be applicable against MF Inventory specific to ISI, CQI, FII for all specified events where rules are applicable in the 1B - Business requirements UAT File. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Rule to be updated DT-003 verbiage to remove default 8000 from the rules. This should be applicable against MF Inventory specific to ISI, CQI, FII for all specified events where rules are applicable in the 1B - Business requirements UAT File. | Verified able to view fields as defined per business design |  |  |  | Approved | Ian Plummer | 2022-12-02 |  |  | Sprint 20 | Sprint 20 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | 1B AHCS : Delivery phase User stories approval Approved on Mon 12/5/2022 7:29 PM |  |  |  | No
[5 empty] | DP-RTR-AHCS-173 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant, I need rule DT-005 verbiage to be updated to remove default 8000 from the rules. This should be applicable against MF Inventory specific to ISI, FII for all specified events where rules are applicable in the 1B - Business requirements UAT File. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Rule to be updated DT-005 verbiage to remove default 8000 from the rules. This should be applicable against MF Inventory specific to ISI, FII for all specified events where rules are applicable in the 1B - Business requirements UAT File. | Verified able to view fields as defined per business design |  |  |  | Approved | Ian Plummer | 2022-12-02 |  |  | Sprint 20 | Sprint 20 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | 1B AHCS : Delivery phase User stories approval Approved on Mon 12/5/2022 7:29 PM |  |  |  | No
[5 empty] | DP-RTR-AHCS-174 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant, I need Voucher Number to be used to populate Cross Reference Number field in the supporting reference for all AP sources (where currently used). |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Voucher Number to be used to populate Cross Reference Number field in the supporting reference for all AP sources (where currently used). | Verified able to view fields as defined per business design |  |  |  | Approved | Ian Plummer | 2022-12-05 |  |  | Sprint 20 | Sprint 20 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | 1B AHCS : Delivery phase User stories approval Approved on Mon 12/12/2022 9:04 PM |  |  |  | No
[5 empty] | DP-RTR-AHCS-175 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant, I need RPT208 to be updated to capture all code combinations between AHCS and GL for all LEs based on the defined BSR Accounts. |  |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report |  | RPT208 to be updated to capture all code combinations between AHCS and GL for all LEs based on the defined BSR Accounts. | Verified able to view all code combination in the report as per design |  |  |  | Approved | Ian Plummer | 2022-12-08 | Sprint 20 |  | Sprint 20 | Sprint 20 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | 1B AHCS : Delivery phase User stories approval Approved on Mon 12/12/2022 9:04 PM |  |  |  | No
[5 empty] | DP-RTR-AHCS-176 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant, I need the date that the file comes over is that date that should be used for posting to AHCS. Do not subtract 5 days. If file is sent outside of current calendar period, Leases Accountant will send the file manually to IT team (Dave Ramsey) so that the file would be dated the last day of the month. |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface |  | Date that should be used for posting to AHCS. Do not subtract 5 days. If file is sent outside of current calendar period, Leases Accountant will send the file manually to IT team so that the file would be dated the last day of the month. | Verified able to view data with correct Accounting Date |  |  |  | Approved | Ian Plummer | 2022-12-08 | Sprint 20 |  | Sprint 20 | Sprint 20 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | 1B AHCS : Delivery phase User stories approval Approved on Mon 12/12/2022 9:04 PM |  |  |  | No
[5 empty] | DP-RTR-AHCS-177 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant, I need for MF Inventory specific to AII inteface that all lines sent from Mainframe for event type 'AII Intercompany Reversal' should be flipped based on the sign sent by Mainframe. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | MF Inventory specific to AII inteface that all lines sent from Mainframe for event type 'AII Intercompany Reversal' should be flipped based on the sign sent by Mainframe. | Verified able to view fields as defined per business design |  |  |  | Approved | Ian Plummer | 2022-12-09 |  |  | Sprint 20 | Sprint 20 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | 1B AHCS : Delivery phase User stories approval Approved on Mon 12/12/2022 9:04 PM |  |  |  | No
[5 empty] | DP-RTR-IC-121 |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As an intercompany accountant, I would like to remove the following Legal Entities from inclusion in Intercompany module setup and from invoicing: 2023 - Pro Canadian Holdings I, ULC 2024 - WireXpress Ltd. 1054 - ICV GP Inc. 1055 - Signal Capital Projects, Inc. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | This would exclude noted entities from intercompany Customer/Supplier setup, as well as bank accounts. Entities contain no balances/activity, and are not included in mapping, resulting in RVS failures when configuring. | Entities referenced in description will not be available for IC transactions |  |  |  | Approved | Rita Nanni | 2022-12-12 15:13 | [7 empty] | RTR | RTR-GL | IC | [13 empty] | No
[5 empty] | DP-RTR-AHCS-178 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant, I need for MF Inventory specific to IBI interface that for line type TUV sent from Mainframe to override account number segment using rule AC-033 in the 1B Business requirements UAT file. Account to use is 511001. This line should not be included as Balance SR. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | MF Inventory specific to IBI interface that for line type TUV sent from Mainframe to override account number segment using rule AC-033 in the 1B Business requirements UAT file. Account to use is 511001. This line should not be included as Balance SR. | Verified able to view fields as defined per business design |  |  |  | Approved | Ian Plummer | 2022-12-13 |  |  | Sprint 20 | Sprint 20 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | 1B AHCS : Delivery phase User stories approval Approved on Thu 12/15/2022 3:16 AM |  |  |  | No
[5 empty] | DP-RTR-AHCS-179 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant, I need for MF Inventory specific to ISI interface to update project rule segment to PR-005 as per 1B Business requirements UAT file for IB30 Cost Adjustments event |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | MF Inventory specific to ISI interface to update project rule segment to PR-005 as per 1B Business requirements UAT file for IB30 Cost Adjustments event | Verified able to view fields as defined per business design |  |  |  | Approved | Ian Plummer | 2022-12-13 |  |  | Sprint 20 | Sprint 20 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | 1B AHCS : Delivery phase User stories approval Approved on Thu 12/15/2022 3:16 AM |  |  |  | No
[5 empty] | DP-RTR-GL-086 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | As a GL Accountant, I require the reversal of the revaluation entry that is included in the converted GL Balances, to be loaded to the subsequent period |  |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions |  | PS team will load a file into month following conversion period that contains the reversal of the revaluation that was included in the converted balances | Balances in first period post conversion will not include any revaluation in ledger/base currency |  |  |  | Approved | Rita Nanni | 2022-12-13 | [7 empty] | RTR | RTR-GL | GL | [13 empty] | No
[5 empty] | DP-RTR-AHCS-180 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant, I need for MF Inventory specific to IBI interface that for line type TUV sent from Mainframe to override account number segment using rule AC-033 in the 1B Business requirements UAT file. This should be updated for Secondary ledgers with accounts Norway use account 43, France use account 6817120, Poland use account 7050006300 and Spain 6100000. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | MF Inventory specific to IBI interface that for line type TUV sent from Mainframe to override account number segment using rule AC-033 in the 1B Business requirements UAT file. This should be updated for Secondary ledgers with accounts Norway use account 43, France use account 6817120, Poland use account 7050006300 and Spain 6100000. | Verified able to view fields as defined per business design |  |  |  | Approved | Ian Plummer | 2022-12-14 |  |  | Sprint 20 | Sprint 20 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | 1B AHCS : Delivery phase User stories approval Approved on Thu 1/12/2023 7:34 PM |  |  |  | No
[5 empty] | DP-RTR-AHCS-181 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant, I need for MF Inventory specific to IBI interface to remove customer type conditions for all lines so that all lines sent by MF is configured. Customer type field is at the header level. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | MF Inventory specific to IBI interface to remove customer type (from header level.) conditions for all lines so that all lines sent by MF is configured | Verified able to view fields as defined per business design |  |  |  | Approved | Ian Plummer | 2022-12-14 |  |  | Sprint 22 | Sprint 22 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | 1B AHCS : Delivery phase User stories approval Approved on Thu 1/12/2023 7:34 PM |  |  |  | No
[5 empty] | DP-RTR-AHCS-182 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant, I need for MF Inventory specific to ISI interface to use rule LE-003 to determine LE for all lines highlighted in updated 1B-business requirement UAT file under LE rule. Rule says For India Ledger Derive LE based on Ship from Loc BU and Ship from Loc, for everything else use LE-002. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | MF Inventory specific to ISI interface to use rule LE-003 to determine LE for all lines highlighted in updated 1B-business requirement UAT file under LE rule. Rule says For India Ledger Derive LE based on Ship from Loc BU and Ship from Loc, for everything else use LE-002. | Verified able to view fields as defined per business design |  |  |  | Approved | Ian Plummer | 2022-12-16 |  |  | Sprint 20 | Sprint 20 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | 1B AHCS : Delivery phase User stories approval Approved on Thu 1/12/2023 7:34 PM |  |  |  | No
[5 empty] | DP-RTR-AHCS-183 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As an IT Administrator, I want to remove/ stop empty file notification |  |  | Phase 1B only | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope |  | 01/03 : Per RMO decision , this has been marked as a requirement to be implement post go-live. | Verify IT user is not getting email notifications for empty files |  |  |  | Approved | Sijo John | 2022-12-19 |  |  | Sprint 21 | Sprint 21 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | 1B AHCS : Delivery phase User stories approval Approved on Thu 1/12/2023 7:34 PM |  |  |  | No
[5 empty] | DP-RTR-BI-XX |  | Record to Report |  |  | We need beginning balances loaded for Quantity for reporting purposes specific to Trade Inventory. This will be used for reports such as Inventory Roll forward, Inventory Trial Balance, etc. The beginning balances should be captured from Mainframe which will be stored in a separate table and combined with AHCS transactional data and made available for reporting. No quantities will be loaded as part of the Inventory beginning balance file from FAH |  |  | Phase 1B only | [6 empty] | Verified able to view fields as defined per business design |  |  |  | Approved |  | 2022-12-21 | [23 empty] | No
[5 empty] | DP-RTR-GL-087 |  | Record to Report | Manage General Ledger Accounting | Maintain Chart of Accounts | To support GL Accounting, we are required to change the parent legal entity for Anixter India Private Limited from 4014 to 4110 to align with FCCS COA tree, as 4014 is being used for historical data inputs in FCCS. 4014 will be an inactive base member under the new parent. Indian states will then be base members under the new 4110 parent. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | This requires changing the COA tree changes in Oracle GL by Financial Systems team, as well as intercompany document sequencing in UAT1 configuration |  |  |  |  | Approved | Rita Nanni | 2022-12-22 | [7 empty] | RTR | RTR-GL | GL | [13 empty] | No
[5 empty] | DP-RTR-IC-123 |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As an Intercompany Accountant, I require that we modify the Non Material Intercompany AR Report to reference distribution data for Amount fields, and that we derive code combinations from SLA. I also require that this report selects only accounted transactions. To align with this change to amount fields, I request that we change the column heading for "Line Amount" to "Amount in Invoice Currency" and "Line Amount in Ledger Currency" to "Amount in Ledger Currency." |  |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report | RPT027 | Reference Antara De email from 12/9/22 | Amounts for each row will reflect the amounts in the distribution lines of transaction, and chartfields will reflect SLA code combinations to tie to GL output | [13 empty] | RTR | RTR-GL | IC | [13 empty] | No
[5 empty] | DP-RTR-IC-124 |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As an Intercompany Accountant, I require that we modify the Non Material Intercompany AP Report to reference distribution data for Amount fields, and that we derive code combinations from SLA. I also require that this report selects only accounted transactions. To align with this change to amount fields, I request that we change the column heading for "Line Amount" to "Amount in Invoice Currency" and "Line Amount in Ledger Currency" to "Amount in Ledger Currency." |  |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report | RPT028 | Reference Antara De email from 12/9/22 | Amounts for each row will reflect the amounts in the distribution lines of transaction, and chartfields will reflect SLA code combinations to tie to GL output | [13 empty] | RTR | RTR-GL | IC | [13 empty] | No
[5 empty] | DP-RTR-AHCS-184 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | Enable the UKG (Payroll) Integration to support the GL Journals and Accruals Creation Process. |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | TBD | Enable the UKG (Payroll) Integration to support the GL Journal Creation Process. We need the Journals, Accruals and Headcount information. Journals must be at the Sumamry level. | [9 empty] | Sprint 21 | Sprint 21 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | 1B AHCS : Delivery phase User stories approval Approved on Thu 1/12/2023 7:34 PM |  |  |  | No
[5 empty] | DP-RTR-IC-108 |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As a tax accountant, I require that customer and supplier changes be made in the UAT1 instance so that my tax calculations will be accurate and successful. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Changes to customer and supplier address and names were identifed after approval given to load files. Tax calls may fail if data is not corrected. | Review extract of customer and supplier data after changes made into UAT1 environment. | [13 empty] | RTR | RTR-GL | IC | [13 empty] | No
[5 empty] | DP-RTR-IC-109 |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As a tax accountant, I require an extract of legal entity information: including legal entity name, address, registration numbers, etc, from HCM Prodution so that I can validate the information prior to any cloning for new environments. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | In discussion, this would be a query run with extract assigned to Satheesh's team. | Extract of legal entity data provided in an Excel workbook. | [13 empty] | RTR | RTR-GL | IC | [13 empty] | No
[5 empty] | DP-RTR-AHCS-185 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant, I need for MF AR specific to SII interface for event type material RA Credits (returns) to updated rule "If Export Type ‘E’ (GR-002) Others - 412111" . See '1B - Business requirements UAT Delta Change 1-9-23' file. Original rule was "If Export Type ‘E’ (rule GR-002) Others (GR-005a) -412110" |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | For MF AR specific to SII interface for event type material RA Credits (returns) to updated rule "If Export Type ‘E’ (GR-002) Others - 412111" . See '1B - Business requirements UAT Delta Change 1-9-23' file. | Verified able to view fields as defined per business design |  |  |  | Approved | Ian Plummer | 2023-01-09 |  |  | Sprint 21 | Sprint 21 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | 1B AHCS : Delivery phase User stories approval Approved on Thu 1/12/2023 7:34 PM |  |  |  | No
[5 empty] | DP-RTR-AHCS-186 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As an IT Manager, For CAIN (Contra) I want to remove the absolute value logic for the HEADER amount and use Header/Line matching logic as "Header Amount= Sum of Debit - Sum of Credit" |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT218, INT219, INT240 | For CAIN (Contra) I want to remove the absolute value logic for the HEADER amount and add Header/Line matching logic as "Header Amount= Sum of Debit - Sum of Credit" | CAIN files are validated with the new Header/Line Amount mismatch logic |  |  |  | Approved | Sijo John | 2023-01-11 |  |  | Sprint 21 | Sprint 21 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | 1B AHCS : Delivery phase User stories approval Approved on Thu 1/12/2023 7:34 PM |  |  |  | No
[5 empty] | DP-RTR-AHCS-187 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant, I need for MF AR specific to SII interface for event type Freight Billed Line where rule AC-001 is used to be updated to include "For APAC BU 005* and CALA BU 003* if export type = E or D use Sales Freight Adjustment 411322" as addition to the existing rule. See '1B - Business requirements UAT Delta Change 1-9-23' file. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | MF AR specific to SII interface for event type Freight Billed Line where rule AC-001 is used to be updated to include "For APAC BU 005* and CALA BU 003* if export type = E or D use Sales Freight Adjustment 411322" as addition to the existing rule. See '1B - Business requirements UAT Delta Change 1-9-23' file. | Verified able to view fields as defined per business design |  |  |  | Approved | Ian Plummer | 1/9/2023 1/18/2023 |  |  | Sprint 21 | Sprint 21 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | 1B AHCS : Delivery phase User stories approval Approved on Thu 1/12/2023 7:34 PM |  |  |  | No
[5 empty] | DP-RTR-AHCS-188 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant, I need for MF Inventory specific to FTI interface for all lines where PR-004 rule is used to be updated as follows "Derive project based on Sales location to project value sets in mapping engine, if not found default to 0000" . See '1B - Business requirements UAT Delta Change 1-12-23' file. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | MF Inventory specific to FTI interface for all lines where PR-004 rule is used to be updated as follows "Derive project based on Sales location to project value sets in mapping engine, if not found default to 0000" | Verified able to view fields as defined per business design |  |  |  | Approved | Ian Plummer | 2023-01-12 |  |  | Sprint 21 | Sprint 21 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | 1B AHCS : Delivery phase User stories approval Approved on Thu 1/12/2023 7:34 PM |  |  |  | No
[5 empty] | DP-RTR-AHCS-189 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant, I need for MF Inventory specific to ISI and FII interfaces for all lines where PR-005 rule is used to be updated as follows "Derive project based on Ship location to project value sets in mapping engine, if not found default to 0000" . See '1B - Business requirements UAT Delta Change 1-12-23' file. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | MF Inventory specific to ISI and FII interfaces for all lines where PR-005 rule is used to be updated as follows "Derive project based on Ship location to project value sets in mapping engine, if not found default to 0000" . | Verified able to view fields as defined per business design |  |  |  | Approved | Ian Plummer | 2023-01-12 |  |  | Sprint 21 | Sprint 21 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | 1B AHCS : Delivery phase User stories approval Approved on Thu 1/12/2023 7:34 PM |  |  |  | No
[5 empty] | DP-RTR-AHCS-190 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant, I need for MF AR specific to SII interface for all lines where PR-005 rule is used to be updated as follows "Derive project based on Ship location to project value sets in mapping engine, if not found default to 0000" . See '1B - Business requirements UAT Delta Change 1-12-23' file. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | MF AR specific to SII interface for all lines where PR-005 rule is used to be updated as follows "Derive project based on Ship location to project value sets in mapping engine, if not found default to 0000" . | Verified able to view fields as defined per business design |  |  |  | Approved | Ian Plummer | 2023-01-12 |  |  | Sprint 21 | Sprint 21 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | 1B AHCS : Delivery phase User stories approval Approved on Thu 1/12/2023 7:34 PM |  |  |  | No
[5 empty] | DP-RTR-AHCS-191 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant, I need for MF AR specific to SII interface for all lines where PR-006 rule is used to be updated as follows : 1."If US or Canada or CALA LE's (Mainframe BU 00001 – 00299 & BU 00300 – 00399 mapped to Oracle LE) – derive site based location to site value set in AHCS received from the mapping engine . Use BU HQ Loc to derive project otherwise default to 0000" 2. "If APAC LE's (Mainframe BU 00500 – 00599 with exception 00524, mapped to Oracle LE) – derive site based location to site value set in AHCS received from the mapping engine . Use BU HQ Loc to derive project otherwise default to 0000" 3. "If APAC LE (Mainframe BU 00524, mapped to Oracle LE) – derive site based location to site value set in AHCS received from the mapping engine . Use Sales Loc to derive project otherwise default to 0000" See '1B - Business requirements UAT Delta Change 1-12-23' file. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | MF AR specific to SII interface for all lines where PR-006 rule is used to be updated as follows : 1."If US or Canada or CALA LE's (Mainframe BU 00001 – 00299 & BU 00300 – 00399 mapped to Oracle LE) – derive site based location to site value set in AHCS received from the mapping engine . Use BU HQ Loc to derive project otherwise default to 0000" 2. "If APAC LE's (Mainframe BU 00500 – 00599 with exception 00524, mapped to Oracle LE) – derive site based location to site value set in AHCS received from the mapping engine . Use BU HQ Loc to derive project otherwise default to 0000" 3. "If APAC LE (Mainframe BU 00524, mapped to Oracle LE) – derive site based location to site value set in AHCS received from the mapping engine . Use Sales Loc to derive project otherwise default to 0000" See '1B - Business requirements UAT Delta Change 1-12-23' file. | Verified able to view fields as defined per business design |  |  |  | Approved | Ian Plummer | 2023-01-12 |  |  | Sprint 22 | Sprint 22 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | 1B AHCS : Delivery phase User stories approval Approved on Thu 1/12/2023 7:34 PM |  |  |  | No
[5 empty] | DP-RTR-GL-088 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | As a Financial Systems Analyst, I need to see the legacy chart string included in the output of CNV001. I would also like to see the error description included on each row. |  |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions |  | Would allow for easier reconciliation of conversion errors. Deloitte to evaluate feasibility of including such detail | Report displays legacy chart string for each line that went into error |  |  |  | Approved | Rita Nanni | 2023-01-12 | [7 empty] | RTR | RTR-GL | GL | [13 empty] | No
[5 empty] | DP-RTR-IC-125 |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As a Tax Accountant I require Customers and Suppliers to be setup in Oracle corresponding to each BSV for the Indian LE 4014. (BSVs 4111-4116) |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | To allow for correct tax treatment for intercompany transactions with Indian states | Tax is correctly calculated for IC transactions with India |  |  |  | Approved | Rita Nanni | 2023-01-17 13:32 | [7 empty] | RTR | RTR-GL | IC | [13 empty] | No
[5 empty] | DP-RTR-AHCS-192 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As an IT Manager, I want the ability to download Import accounting error records on Subledger Dashboard |  |  | Phase 1B only | 5-Gap-Build-Extension | Gap | Build | Extension | EXT123 | Should be able to download Import accounting error records on Subledger Dashboard | Able to download import accounting errors from Subledger Dashboard |  |  |  | Approved | Sijo John | 2023-01-17 13:32 |  |  | Sprint 22 | Sprint 22 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | RMO approved 01/20 |  |  |  | No
[5 empty] | DP-RTR-AHCS-193 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant I need MF Inventory Subledger to be updated specific to ISI for all event types ISI_INTRA_ADJUSTMENTS, ISI_INTRA_CREDITS and ISI_INTRA_INVOICES to ignore the Intercompany lines sent by Mainframe. These lines are denoted as Amount Type = ITP and ITR. If LE's are not the same use systematic balancing in Oracle to generate IC lines. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | MF Inventory Subledger to be updated specific to ISI for all event types ISI_INTRA_ADJUSTMENTS, ISI_INTRA_CREDITS and ISI_INTRA_INVOICES to ignore the Intercompany lines sent by Mainframe. These lines are denoted as Amount Type = ITP and ITR. If LE's are not the same use systematic balancing in Oracle to generate IC lines. | Verified able to view fields as defined per business design |  |  |  | Approved | Ian Plummer | 2023-01-19 |  |  | Sprint 22 | Sprint 22 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | RMO approved 01/20 |  |  |  | No
[5 empty] | DP-RTR-AHCS-194 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant I need MF Inventory Subledger to be updated specific to ISI for all event types ISI_INTRA_ADJUSTMENTS, ISI_INTRA_CREDITS and ISI_INTRA_INVOICE, IC lines to be updated and removed from the business rules document. Ref delta file '1B - Business requirements UAT Delta Change 1-19-22' on 'Intracompany 20810' tab. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | MF Inventory Subledger to be updated specific to ISI for all event types ISI_INTRA_ADJUSTMENTS, ISI_INTRA_CREDITS and ISI_INTRA_INVOICE, IC lines to be updated and removed from the business rules document. Ref delta file '1B - Business requirements UAT Delta Change 1-19-22' on 'Intracompany 20810' tab. | Verified able to view fields as defined per business design |  |  |  | Approved | Ian Plummer | 2023-01-19 |  |  | Sprint 22 | Sprint 22 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | RMO approved 01/20 |  |  |  | No
[5 empty] | DP-RTR-AHCS-195 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant, I need for MF AR specific to SII interface for all lines where rule AC-005 is used to be updated based on delta file . '1B - Business requirements UAT Delta Change 1-19-22' on 'AC-005 Rule 16799' tab. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | MF AR specific to SII interface for all lines where rule AC-005 is used to be updated based on delta file . '1B - Business requirements UAT Delta Change 1-19-22' on 'AC-005 Rule 16799' tab. | Verified able to view fields as defined per business design |  |  |  | Approved | Ian Plummer | 2023-01-19 |  |  | Sprint 22 | Sprint 22 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | RMO approved 01/20 |  |  |  | No
[5 empty] | DP-RTR-AHCS-196 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant, I need for MF AP for all lines where STAT Rule 13 is used to be updated based on delta file. '1B - Business requirements UAT Delta Change 1-18-22'. VAT R/C Recoverable Domestic account should be mapped to 4456640 and VAT R/C Payable Domestic should be mapped to 4456641 for France only. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | MF AP for all lines where STAT Rule 13 is used to be updated based on delta file. '1B - Business requirements UAT Delta Change 1-18-22'. VAT R/C Recoverable Domestic account should be mapped to 4456640 and VAT R/C Payable Domestic should be mapped to 4456641 for France only. | Verified able to view fields as defined per business design |  |  |  | Approved | Ian Plummer | 2023-01-19 |  |  | Sprint 22 | Sprint 22 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | RMO approved 01/20 |  |  |  | No
[5 empty] | DP-RTR-AHCS-197 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant, I need for MF AP specific to Amount types IAE, FMC, ICC, IRP, GAN, IBP, IBR, IAM, LOS, REP to use description in delta file '1B - Business requirements UAT Delta Change 1-19-22' on 'Amount Type Line Description' tab. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | MF AP specific to Amount types IAE, FMC, ICC, IRP, GAN, IBP, IBR, IAM, LOS, REP to use description in delta file '1B - Business requirements UAT Delta Change 1-19-22' on 'Amount Type Line Description' tab. | Verified able to view fields as defined per business design |  |  |  | Approved | Ian Plummer | 2023-01-19 |  |  | Sprint 22 | Sprint 22 |  |  |  | RTR | RTR-AHCS | AHCS | [9 empty] | RMO approved 01/20 |  |  |  | No
[5 empty] | DP-RTR-IC-126 |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As an Accountant I require a new LE to be setup in Oracle corresponding to a new Irish BU with a Functional Currency of USD. As an Accountant I require the new USD Irish LE to accept MF AP, AR, INV, Third Party, Cresus transactions. As an Accountant I require the New USD Irish LE to accept Oracle Module realted transactions. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Need to add this new entity as we know this LE will be active from March/april and will have payroll, fixed asset, leasing, travel activity. | all functionality works for the new entity. |  |  |  | Submited for Approval | Bhim Chhestir | 2023-01-19 | [7 empty] | RTR | RTR-GL | IC | [13 empty] | No
[5 empty] | DP-RTR-GL-092 |  | Record to Report | Manage General Ledger Accounting | Perform Allocations | As a GL Accountant, I want to be able to create a North American allocation, for Legacy Anixter LE's, that consolodates freight accrual balances at the Head Office operating group for each SBU. This allocation should run at the end of each period and reverse at the beginning of the following period. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Freight Accrual Sweep (FSA) Facilitates accounting and analysis of freight accrual and payments | Balances are swept to the SBU Head Offices |  |  |  |  | Rita Nanni | 2023-01-24 | [7 empty] | RTR | RTR-GL | GL | [13 empty] | No
[5 empty] | DP-RTR-GL-090 |  | Record to Report | Manage General Ledger Accounting | Perform Allocations | As a GL Accountant, I want to be able to create an allocation that consolodates tax accrual balances at the Corporate Head Office operating group for Legacy Anixter Canada and US Power Solutions. This allocation should run at the end of each period and reverse at the beginning of the following period. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Tax Accrual Allocation (TXA) Facilitates accounting and analysis of tax accrual and payments | Balances are swept to the Corporate Head Office |  |  |  |  | Rita Nanni | 2023-01-24 | [7 empty] | RTR | RTR-GL | GL | [13 empty] | No
| #N/A | #N/A | CSTONE-12562 |  | DP-RTR-GL-077 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | User story to retrofit 1A object to have the creator of Inter/Intra journals included in the Created By field in RICE ID:INT021 extracts so that usable data in this field is available for extract. Should also be able to access the correct Approved by data for extract |  |  |  | 3-Gap-Build-Interface | Gap | Build | Interface | INT021 |  | Creator of journal submitted via inter/intra custom data loader is identified in creator field of extract, as opposed to "FIN_INT" |  |  |  | Approved | Rita |  | Sprint 14 |  |  | Sprint 16 |  |  |  | RTR | RTR-GL | GL | [13 empty] | N/A
Cancelled
[5 empty] | DP-RTR-GL-091 |  | Record to Report | Manage General Ledger Accounting | Perform Allocations | As a GL Accountant, I want to be able to create an allocation that allocates depreciation activity from Supply Chain/Operations to regional SBU. This allocation should run at the end of each period. Legacy Allocation name ODA |  |  | Phase 1A + Phase 1B (Post go-live) | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Operations Dep Allocation - ODA To be dispositioned post go live for both legacy AXE and WCC entities | Balances to move from OPS depreacition accounts and Regional Ops/Supply Chain Op Groups to regional SBU |  |  |  |  | Farah Husain | 2023-01-25 | [7 empty] | RTR | RTR-GL | GL | [13 empty] | No
[5 empty] | DP-RTR-IC-127 |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As an Intercompany Accountant I would like to separate the AR Transaction Number and AP Invoice Numbers into two columns, one for AR Trans Number and one for AP Inv Number, in the Subledger Transaction section of the report |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional | RPT036 | This will allow users to more easily identify intercompany transactions where temporary invoice number has been captured into AP before AR transaction is complete. This could occur if tax process takes longer than expected, resulting in invoice numbering mismatch btw AP and AR | [5 empty] | Rita Nanni | 2023-01-26 | [7 empty] | RTR | RTR-GL | IC | [13 empty] | No
[5 empty] | DP-RTR-IC-128 |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As an Intercompany Accountant I would like to change the IC Source Name parameter from Required to Not Required |  |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report | RPT099 | Making this field optional allows user to capture both sources in one report | [5 empty] | Rita Nanni | 2023-01-26 | [7 empty] | RTR | RTR-GL | IC | [13 empty] | No
[5 empty] | DP-RTR-AHCS-198 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant, I want event type ISI_INTRA_ADJUSTMENTS, ISI_INTRA_CREDITS and ISI_INTRA_INVOICES for ISI source system to use Sales Location value as GL Location SR for Intercompany Intransit when Customer type = IA and Amount Type = Avg. |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT222, INT223, EXT121 | Event type ISI_INTRA_ADJUSTMENTS, ISI_INTRA_CREDITS and ISI_INTRA_INVOICES for ISI source system to use Sales Location value as GL Location SR for Intercompany Intransit when Customer type = IA and Amount Type = Avg. | Verified able to view fields as defined per business design |  |  |  | Approved | Ian Plummer | 2023-01-27 |  |  | Sprint 22 | Sprint 22 |  |  |  | RTR | RTR-AHCS | AHCS | [13 empty] | No
[5 empty] | DP-RTR-AHCS-199 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want Intercompany line for ICI & AII sources to use rule GR-031 to populate the GL location SR (should be the same location that is used for site rule) |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT222, INT223, EXT121 | Intercompany line for ICI & AII sources to use rule GR-031 to populate the GL location SR (should be the same location that is used for site rule) | Verified able to view fields as defined per business design |  |  |  | Approved | Ian Plummer | 2023-01-30 |  |  | Sprint 22 | Sprint 22 |  |  |  | RTR | RTR-AHCS | AHCS | [13 empty] | No
[5 empty] | DP-RTR-AHCS-200 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As an IT Manager, I want AHCS Increment outbound program (INT043) to have option to run for selective time/date and mechanism to recover/reset incremental schedule when program errors due to unavoidable situation but not limited to technical glitch, FTP or volume |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT043 | AHCS Increment outbound program (INT043) to have option to run for selective time/date and mechanism to recover/reset incremental schedule when program errors due to unavoidable situation but not limited to technical glitch, FTP or volume | Able to run for selective time/date and mechanism to recover/reset incremental schedule when program errors |  |  |  | Approved | Sijo John | 2023-02-02 |  |  | Sprint 22 | Sprint 22 |  |  |  | RTR | RTR-AHCS | AHCS | [13 empty] | No
[5 empty] | DP-RTR-IC-129 |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As an IT Manager, I want Increment outbound program (INT185, INT186) to have option to run for selective time/date and mechanism to recover/reset incremental schedule when program errors due to unavoidable situation but not limited to technical glitch, FTP or volume |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT185, INT186 | To allow IT to have option to run outbound integration with selective time/date on ad hoc basis. CTPFS-21367 reference defect in UAT1 2/7/23: RMO Rejected User Story for 1B Go-Live; deferred to post Go-Live. Should be taken as enhancement at that time. | Successfully able to run on ad hoc basis with selective time/date |  |  |  | Approved | Rita Nanni | 2023-02-03 |  |  | Sprint 22 | Sprint 22 |  |  |  | RTR | RTR-GL | IC | [13 empty] | No
[5 empty] | DP-RTR-IC-130 |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As an IT Manager, I want Increment outbound program (INT187, INT188) to have option to run for selective time/date and mechanism to recover/reset incremental schedule when program errors due to unavoidable situation but not limited to technical glitch, FTP or volume |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT187, INT188 | To allow IT to have option to run outbound integration with selective time/date on ad hoc basis. CTPFS-21367 reference defect in UAT1 2/7/23: RMO Rejected User Story for 1B Go-Live; deferred to post Go-Live. Should be taken as enhancement at that time. | Successfully able to run on ad hoc basis with selective time/date |  |  |  | Approved | Rita Nanni | 2023-02-03 |  |  | Sprint 22 | Sprint 22 |  |  |  | RTR | RTR-GL | IC | [13 empty] | No
[5 empty] | DP-RTR-IC-131 |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As an IT Manager, I want Increment outbound program (INT189, INT190) to have option to run for selective time/date and mechanism to recover/reset incremental schedule when program errors due to unavoidable situation but not limited to technical glitch, FTP or volume |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT189, INT190 | To allow IT to have option to run outbound integration with selective time/date on ad hoc basis. CTPFS-21368 reference defect in UAT1 2/7/23: RMO Rejected User Story for 1B Go-Live; deferred to post Go-Live. Should be taken as enhancement at that time. | Successfully able to run on ad hoc basis with selective time/date |  |  |  | Approved | Rita Nanni | 2023-02-03 |  |  | Sprint 22 | Sprint 22 |  |  |  | RTR | RTR-GL | IC | [13 empty] | No
[5 empty] | DP-RTR-IC-132 |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As an IT Manager, I want Increment outbound program (INT191, INT192) to have option to run for selective time/date and mechanism to recover/reset incremental schedule when program errors due to unavoidable situation but not limited to technical glitch, FTP or volume |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT191, INT192 | To allow IT to have option to run outbound integration with selective time/date on ad hoc basis. CTPFS-21368 reference defect in UAT1 2/7/23: RMO Rejected User Story for 1B Go-Live; deferred to post Go-Live. Should be taken as enhancement at that time. | Successfully able to run on ad hoc basis with selective time/date |  |  |  | Approved | Rita Nanni | 2023-02-03 |  |  | Sprint 22 | Sprint 22 |  |  |  | RTR | RTR-GL | IC | [13 empty] | No
[5 empty] | DP-RTR-AHCS-201 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant I need to add a conversion upload for North America MF AP Subledger for UAT1 test instance to align with CNV041 for Region NA-EMEA. |  |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV041 | add a conversion upload for North America MF AP Subledger for UAT1 scope to align with CNV041 for Region NA-EMEA. | Successfully able to view conversion data |  |  |  | Approved | Ian Plummer | 2023-02-03 |  |  | Sprint 22 | Sprint 22 |  |  |  | RTR | RTR-AHCS | AHCS | [13 empty] | No
[5 empty] | DP-RTR-AHCS-202 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant I need to add a conversion upload for North America MF AR Subledger for UAT1 test instance to align with CNV042 for Region NA-EMEA. |  |  | Phase 1B only | 4-Gap-Build-Conversions | Gap | Build | Conversions | CNV042 | add a conversion upload for North America MF AR Subledger for UAT1 scope to align with CNV042 for Region NA-EMEA. | Successfully able to view conversion data |  |  |  | Approved | Ian Plummer | 2023-02-03 |  |  | Sprint 22 | Sprint 22 |  |  |  | RTR | RTR-AHCS | AHCS | [13 empty] | No
[5 empty] | DP-RTR-AHCS-203 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant I need MF AR specific to Java Tools to capture Source System ~ No Description ~ Legacy Division ~ Export Type ~ Customer PO at the line level |  |  | Phase 1B only | 10-Not Required-Not Required-Not Required | Not Required | Not Required | Not Required |  | MF AR specific to Java Tools to capture Source System ~ No Description ~ Legacy Division ~ Export Type ~ Customer PO at the line level | Verified able to view fields as defined per business design | 2022-10-26 |  |  | Approved | Ian Plummer | 2023-02-06 | [7 empty] | RTR | RTR-AHCS | AHCS | [13 empty] | Cancelled
[5 empty] | DP-RTR-AHCS-204 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant I need MF AP specific to Java tools to capture Source System ~ No Description ~ Legacy Division ~ FRT BILL PRO REF NBR at the line level |  |  | Phase 1B only | 10-Not Required-Not Required-Not Required | Not Required | Not Required | Not Required |  | MF AP specific to Java tools to capture Source System ~ No Description ~ Legacy Division ~ FRT BILL PRO REF NBR at the line level | Verified able to view fields as defined per business design | 2022-10-26 |  |  | Approved | Ian Plummer | 2023-02-06 | [7 empty] | RTR | RTR-AHCS | AHCS | [13 empty] | Cancelled
[5 empty] | DP-RTR-AHCS-205 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant I need MF Inventory specific to Java Tools to capture Source System~Trading Partner Number~ Receiver Number ~ Item Number ~No Description at the line level |  |  | Phase 1B only | 10-Not Required-Not Required-Not Required | Not Required | Not Required | Not Required |  | MF Inventory specific to Java Tools to capture Source System~Trading Partner Number~ Receiver Number ~ Item Number ~No Description at the line level | Verified able to view fields as defined per business design | 2022-10-26 |  |  | Approved | Ian Plummer | 2023-02-06 | [7 empty] | RTR | RTR-AHCS | AHCS | [13 empty] | Cancelled
[5 empty] | DP-RTR-AHCS-206 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant I need MF Inventory specific to CQI interface, for Trade inventory line (115101) department segment to be updated from DT-003 rule to default 0000 based on 1B - Business requirements UAT Delta 2-6-23 file. See department field higlighted gray. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | MF Inventory specific to CQI interface, for Trade inventory line (115101) department segment to be updated from DT-003 rule to default 0000 based on 1B - Business requirements UAT Delta 2-6-23 file. See department field higlighted gray. | Verified able to view fields as defined per business design | 2022-10-26 |  |  | Approved | Ian Plummer | 2023-02-06 |  |  | Sprint 22 | Sprint 22 |  |  |  | RTR | RTR-AHCS | AHCS | [13 empty] | No
[5 empty] | DP-RTR-AHCS-207 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As an IT Manager, I want to add User ID on RPT006 |  |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report | RPT006 | This is Low priority and not critical for Go Live | User ID is populated on RPT006 report | 2022-10-26 |  |  | Approved | Sijo John | 2023-02-07 |  |  | Sprint 23 | Sprint 23 |  |  |  | RTR | RTR-AHCS | AHCS | [13 empty] | No
[5 empty] | DP-RTR-GL-093 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | As an IT Manager, I want Increment outbound program (INT011, INT021) to have option to run for selective time/date and mechanism to recover/reset incremental schedule when program errors due to unavoidable situation but not limited to technical glitch, FTP or volume |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT011, INT021 | To allow IT to have option to run outbound integration with selective time/date on ad hoc basis. CTPFS-21366 reference defect in UAT1 2/7/23: RMO Rejected User Story for 1B Go-Live; deferred to post Go-Live. Should be taken as enhancement at that time. | Successfully able to run on ad hoc basis with selective time/date |  |  |  | Approved | Rita Nanni | 2023-02-07 |  |  | Sprint 22 | Sprint 22 |  |  |  | RTR | RTR-GL | GL | [13 empty] | No
[5 empty] | DP-RTR-GL-094 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | All transaction data for FEC Reporting must also contain the related master data for CONCUR, LEASES and Oracle LSI. |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Report | RPT026 | Data to be included in extract to be confirmed with AHCS team. | Ensure noted integration data is sent over to BI for subsequent reporting from BI |  |  |  | Approved | Rita Nanni | 2023-02-07 |  |  | Sprint 22 | Sprint 22 |  |  |  | RTR | RTR-GL | GL | [13 empty] | No
[5 empty] | DP-RTR-GL-095 |  | Record to Report | Manage General Ledger Accounting | Maintain Chart of Accounts | COA Engine - Validate Cache Table |  |  | Phase 1A+1B | 3-Gap-Build-Interface | Gap | Build | Report | [32 empty] | No
[5 empty] | DP-RTR-IC-133 |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As an intercompany accountant, I need to include legacy ABC Corp entities 1013 (Carlton-Bates Company), 2005 (Stone Eagle Electrical Supply Limited Partnership), and 2007 (Stone Eagle Electrical Supply GP Inc.) in the in the non-material intercompany processes that leverage the IC module as well as IC AP and AR |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Report |  | To allow all entities that transact with Non US and Canada entities to adhere to intercompany invoicing requirements. To also ensure that we follow one global process for managing non-material intercompany transactions. | Entities are available for intercompany invoicing and non invoicing transactions within the Intercompany Module |  |  |  | Approved | Rita Nanni | 2023-02-08 |  |  | Sprint 22 | Sprint 22 |  |  |  | RTR | RTR-GL | IC | [13 empty] | No
[5 empty] | DP-RTR-AHCS-208 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want Intercompany receivables lines for SII source, for MF AR subledger to use rule ST-014 to populate the GL location SR (should be the same location that is used for site rule) |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT216, INT217, INT 240 | Intercompany receivables lines for SII source, for MF AR subledger to use rule ST-014 to populate the GL location SR (should be the same location that is used for site rule) | Reviewed data and confirm functioning as per business design | 2022-10-26 |  |  | Approved | Ian Plummer | 2023-02-13 |  |  | Sprint 23 | Sprint 23 |  |  |  | RTR | RTR-AHCS | AHCS | [13 empty] | No
[5 empty] | DP-RTR-AHCS-209 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want RPT008 to keep the source transaction number field but only populate for 1A and keep blank for 1B data. |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | INT216, INT217, INT 240 | RPT008 to keep the source transaction number field but only populate for 1A and keep blank for 1B data. | Reviewed data and confirm functioning as per business design | 2022-10-26 |  |  | Approved | Ian Plummer | 2023-02-13 |  |  | Sprint 23 | Sprint 23 |  |  |  | RTR | RTR-AHCS | AHCS | [13 empty] | No
[5 empty] | DP-RTR-IC-134 |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | When we have multiple LE's within same BU and incorrect LE is chosen during payment. For AP, need SLA rule for gain/loss account to derive LE (segment 1) from Cash Clearing. As we see, rate difference causes foreign exchange line to generate auto balancing lines. This rule should reflect in SLAM with local COA as well as in other SLAM's. (Reference Defect - CTPFS-21754) |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | To avoid assignment of incorrect LE to fx lines (and corresponding intercompany balancing lines) that would be generated if user selects incorrect bank account, if more than one legal entity exists within same BU. |  |  |  |  | Approved | Rita Nanni | 2023-02-14 |  |  | Sprint 22 | Sprint 22 |  |  |  | RTR | RTR-GL | IC | [13 empty] | No
[5 empty] | DP-RTR-IC-135 |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | To truncate Batch name on Receivables Standard Receipt Import template to 25 characters so that file does not error during upload. |  |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report | RPT031 | To avoid upload error when Batch name from transaction exceeds 25 character limit on Receivables Standard Reciept Import template. |  |  |  |  | Approved | Rita Nanni | 2023-02-14 |  |  | Sprint 22 | Sprint 22 |  |  |  | RTR | RTR-GL | IC | [13 empty] | No
[5 empty] | DP-RTR-AHCS-210 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want MF AR subledger to be updated specific to SII interface for all tax line where rule AC-004 is used for Canada LE 2021. Rule should be updated to say For Canada GST has a separate account (218815) (Amount type = TX2). For RA Credits, FM09’s and FM09 voids account 218815 must be used for Canada only (Amount Type = TX2). For Canada Accrued sales tax use the sales tax map on this file (Amount type = TX1. Refer '1B - Business requirements UAT Delta Change 2-15-2023' |  |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface |  | MF AR subledger to be updated specific to SII interface for all tax line where rule AC-004 is used for Canada LE 2021. Rule should be updated to say For Canada GST has a separate account (218815) (Amount type = TX2). For RA Credits, FM09’s and FM09 voids account 218815 must be used for Canada only (Amount Type = TX2). For Canada Accrued sales tax use the sales tax map on this file (Amount type = TX1. Refer '1B - Business requirements UAT Delta Change 2-15-2023' | Reviewed data and confirm functioning as per business design | 2022-10-26 |  |  | Approved | Ian Plummer | 2023-02-15 |  |  | Sprint 23 | Sprint 23 |  |  |  | RTR | RTR-AHCS | AHCS | [13 empty] | No
[5 empty] | DP-RTR-IC-136 |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | User story to move company XML tag from outside of Property List to inside Property List for the invoice archiving process associated with RPT102 and RPT103 |  |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report | RPT102, RPT103 | Prevents error upon ingestion process for the archiving of IC Invoices in EDMS. |  |  |  |  | Approved | RMN on behalf of Tax | 2023-02-17 | [7 empty] | RTR | RTR-GL | GL | [13 empty] | No
[5 empty] | DP-RTR-IC-137 |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | User story to replace ‘EInvoiceFnStoreRequest’ with ‘ICTransactionFnStoreRequest’ this is at the top and bottom of the request, because XML files for RPT102 and RPT103 invoice print are new ingestion process for EDMS. |  |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report | RPT102, RPT103 | Change is required for new request to EDMS with new fields, such as COA. Fields being imported are different from existing imports |  |  |  |  | Approved | RMN on behalf of Tax | 2023-02-17 | [7 empty] | RTR | RTR-GL | GL | [13 empty] | No
[5 empty] | DP-RTR-IC-138 |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | User story to align on document naming convention for IC Invoice Print. The date component of the file name for both the PDF document and XML metadata needs to change from MMDDYYYY to YYYYMMDD. (RPT102 and RPT103) |  |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report | RPT102, RPT103 | For consistency in PDF naming convention |  |  |  |  | Approved | RMN on behalf of Tax | 2023-02-17 | [7 empty] | RTR | RTR-GL | GL | [13 empty] | No
[5 empty] | DP-RTR-AHCS-211 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I want Item# is not required as balanced SR for MF AP subledger but should be store as non balancesd SR (Item# Nbsr) |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Item# is not required as balanced SR for MF AP subledger, however should be store as non balancesd SR (Item# Nbsr) | Reviewed data and confirm functioning as per business design | 2022-10-26 |  |  | Approved | Ian Plummer | 2023-02-20 |  |  | Sprint 23 | Sprint 23 |  |  |  | RTR | RTR-AHCS | AHCS | [13 empty] | No
[5 empty] | DP-RTR-AHCS-212 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | Item# is not required as balanced SR for MF AR subledger but should be store as non balancesd SR (Item## Nbsr) |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Item# is not required as balanced SR for MF AR subledger , However should be store as non balancesd SR (Item## Nbsr) | Reviewed data and confirm functioning as per business design | 2022-10-26 |  |  | Approved | Ian Plummer | 2023-02-20 |  |  | Sprint 23 | Sprint 23 |  |  |  | RTR | RTR-AHCS | AHCS | [13 empty] | No
[5 empty] | DP-RTR-AHCS-213 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | Partnert# is not required for balanced SR for MF Inventory subledger except AII & ICI , for all other sources store that non balanced SR (Trading partenr# Nbsr) |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Partnert# is not required for balanced SR for MF Inventory subledger except AII & ICI , for all other sources store that non balanced SR (Trading partenr# Nbsr) | Reviewed data and confirm functioning as per business design | 2022-10-26 |  |  | Approved | Ian Plummer | 2023-02-20 |  |  | Sprint 23 | Sprint 23 |  |  |  | RTR | RTR-AHCS | AHCS | [13 empty] | No
[5 empty] | DP-RTR-GL-089 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | To be consistant with AHCS, required GL Integration Jobs to include 1A and 1B data into Datawarehouse systems. | Phase 1B only |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface |  |  | All GL integration jobs are captured in Data Wharehouse Systems |  |  |  |  | RMN on behalf of Satheesh Gooda | 2023-02-01 |  |  | Sprint 22 | Sprint 22 |  |  |  | RTR | RTR-GL | GL | [13 empty] | No
[5 empty] | DP-RTR-IC-139 |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As part of IC/AP, IC/AR and GL Conversions, various Job sets has been created to reduce the overall effort and time taken to perform conversions. | Phase 1B only |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional | [6 empty] | Approved | Rita Nanni | 2023-02-24 | [7 empty] | RTR | RTR-GL | IC | [13 empty] | No
[5 empty] | DP-RTR-IC-140 |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | Implement Oracle intercompany work-around for Portugal business unit to enable BU IC AR Processing and test - to mitigate risk related to open SR with Oracle, where invoice goes to Frozen status. Defect:CTPFS-20545 | Phase 1B only |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | AGIS invoicing will not be transferred to Receivables, but will be created in Payables. Restricting provider entry for PT BU within intercompany module. Receivables functionality to be liminted to non-invoicing only. AR invoices from PT BU and corresponding AP invoices to be removed from conversion extract/load. |  |  |  |  | Approved | Rita Nanni | 2023-02-24 | [7 empty] | RTR | RTR-GL | IC | [13 empty] | No
[5 empty] | DP-RTR-AHCS-214 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As an IT Manager, I want to develop a report to identify any outbounds & reports errors that have occurred within a 24-hour period and their execution time. This is only for support and Technical/Lean Spec is not required. |  |  | Phase 1A+1B | 3-Gap-Build-Interface | Gap | Build | Interface |  | Need a report to identify any outbounds & reports errors that have occurred within a 24-hour period and their execution time | Able to identify any outbounds & reports errors that have occurred within a 24-hour period and their execution time |  |  |  | Approved | Sijo John | 2023-02-24 |  |  | Sprint 23 | Sprint 23 |  |  |  | RTR | RTR-AHCS | AHCS | [13 empty] | No
[5 empty] | DP-RTR-AHCS-215 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant I need AHCS specific to PSFA subledger to use updated inbound file layout & mapping intercompany from source file to derive future cloud IC segment. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | AHCS specific to PSFA subledger to use updated inbound file layout & mapping intercompany from source file to derive future cloud IC segment. | Reviewed data and confirm functioning as per business design |  |  |  | Approved | Ian Plummer | 2023-03-01 | [7 empty] | RTR | RTR-AHCS | AHCS |  |  |  | Post Go live change | [9 empty] | No
[5 empty] | DP-RTR-IC-141 |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As Intercompany Accountant I require addition of three creation date fields to the RPT036 Intercompany Transaction Details report. Creation Date for IC Batch, Creation Date for AR Invoice, and Creation Date for AP Invoice. | Phase 1B only |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report | RPT036 | Addition of creation date fields to allow user to analyze where there is a delay in processing. | Fields are present in report output |  |  |  | Approved | Rita Nanni | 2023-02-24 | [7 empty] | RTR | RTR-GL | IC | [13 empty] | No
[5 empty] | DP-RTR-IC-142 |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As an Intercompany Accountant I require that the Intercompany Balancing account for all Custom Subledger transactions be changed from 114005 IC AR Invoicing to 114006 IC AR non Invoicing, and 212005 IC AP Invoicing to 212006 IC AR non Invoicing. | Phase 1B only |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | This change will keep the intercompany AR and AP invoicing accounts in line with the intercompany AR and AP subledgers. | All AHCS sources will map to Intercompany Non Invoicing AR (114006) and AP (212006) balancing accounts |  |  |  | Approved | Rita Nanni | 2023-03-10 | [7 empty] | RTR | RTR-GL | IC | [13 empty] | No
[5 empty] | DP-RTR-IC-143 |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As Intercompany Accountant I require a change to the rules of RPT190 AP-AR SLA to GL Reconciliation Report so that there is a new Event to capture activity to the 114005 (IC AR) and 212005 (IC AP) accounts that are generated from Custom Subledger transactions, such as Concur and Java Tools, as well as any expense category lines booked directly to those accounts from IC module transactions. (Day 30) | Phase 1B only |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report | RPT190 | Invoicing event would be from AR SL, Payment event from AP SL, Non SLA from GL, Other Accounting event would be from other transactions that would impact this account. RMN to work with IP to lock accounts from JAVA tools and to add IC invoicing accounts to list of control accounts. | Report would correctly categorize activity according to rules noted in comments |  |  |  | Approved | Rita Nanni | 2023-03-10 | [7 empty] | RTR | RTR-GL | IC | [13 empty] | No
[5 empty] | DP-RTR-AHCS-216 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant I need PPV (Acct# 211048) – Manual Conversion beginning balance event type to be updated from IVB_BEG_BAL to IVB_UNVCH_BEG_BAL specific to North America and CALA |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | PPV (Acct# 211048) – Manual Conversion beginning balance event type to be updated from IVB_BEG_BAL to IVB_UNVCH_BEG_BAL specific to North America and CALA | Reviewed data and confirm functioning as per business design |  |  |  | Approved | Ian Plummer | 2023-03-18 |  |  | Sprint 24 | Sprint 24 |  |  |  | RTR | RTR-AHCS | AHCS | [13 empty] | No
[5 empty] | DP-RTR-AHCS-217 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant I need Reels (Acct# 115118) - Manual Conversion (Only for NA) beginning balance to be updated for Trading Partner Number and Invoice number. These fields should be updated as blank meaning no data will be stored. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Reels (Acct# 115118) - Manual Conversion (Only for NA) beginning balance to be updated for Trading Partner Number and Invoice number. These fields should be updated as blank meaning no data will be stored. | Reviewed data and confirm functioning as per business design |  |  |  | Approved | Ian Plummer | 2023-03-18 |  |  | Sprint 24 | Sprint 24 |  |  |  | RTR | RTR-AHCS | AHCS | [13 empty] | No
[5 empty] | DP-RTR-AHCS-218 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant I need IntraIntransit (Acc# 115153) – Automated conversion beginning balance event type to be updated from IVB_UNVCH_BEG_BAL to IVB_BEG_BAL and Trading Partner Number and Invoice Number fields updated to be blank. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | IntraIntransit (Acc# 115153) – Automated conversion beginning balance event type to be updated from IVB_UNVCH_BEG_BAL to IVB_BEG_BAL and Trading Partner Number and Invoice Number fields updated to be blank. | Reviewed data and confirm functioning as per business design |  |  |  | Approved | Ian Plummer | 2023-03-18 |  |  | Sprint 24 | Sprint 24 |  |  |  | RTR | RTR-AHCS | AHCS | [13 empty] | No
[5 empty] | DP-RTR-AHCS-219 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant I need Intransit (same accounts as AII and ICI Inventory source) – manual conversion beginning balance with event type IVB_BEG_BAL, to have Trading Partner Number assigned as BSR |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Intransit (same accounts as AII and ICI Inventory source) – manual conversion beginning balance with event type IVB_BEG_BAL, to have Trading Partner Number assigned as BSR | Reviewed data and confirm functioning as per business design |  |  |  | Approved | Ian Plummer | 2023-03-18 |  |  | Sprint 24 | Sprint 24 |  |  |  | RTR | RTR-AHCS | AHCS | [13 empty] | No
[5 empty] | DP-RTR-AHCS-220 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant I need Kava (Acc# 115111) to be updated in AHCS configuration to use UBSR logic i.e. only assign Loc SR for Kava account across all Subledgers |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Kava (Acc# 115111) to be updated in AHCS configuration to use UBSR logic i.e. only assign Loc SR for Kava account across all Subledgers | Reviewed data and confirm functioning as per business design |  |  |  | Approved | Ian Plummer | 2023-03-18 |  |  | PGL | PGL |  |  |  | RTR | RTR-AHCS | AHCS |  |  |  | Post Go live change | [9 empty] | No
[5 empty] | DP-RTR-AHCS-221 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant I need to add a conversion upload for CALA MF AP Subledger for UAT2 test instance to align with CNV041. Conversion will be called MF AP Conversion [Manual Accounts - Freight and Duty Unvouchered]. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | add a conversion upload for CALA MF AP Subledger for UAT2 test instance to align with CNV041. Conversion will be called MF AP Conversion [Manual Accounts - Freight and Duty Unvouchered]. | Successfully able to view conversion data |  |  |  | Approved | Ian Plummer | 2023-03-21 | [7 empty] | RTR | RTR-AHCS | AHCS | [13 empty] | No
[5 empty] | DP-RTR-AHCS-222 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant I need to add a conversion upload for CALA MF Inventory Subledger for UAT2 test instance to align with CNV043. Conversion will be called MF Inv Conversion [Manual Accounts - Freight and Duty Unvouchered]. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | add a conversion upload for CALA MF Inventory Subledger for UAT2 test instance to align with CNV043. Conversion will be called MF Inv Conversion [Manual Accounts - Freight and Duty Unvouchered]. | Successfully able to view conversion data |  |  |  | Approved | Ian Plummer | 2023-03-21 | [7 empty] | RTR | RTR-AHCS | AHCS | [13 empty] | No
[5 empty] | DP-RTR-AHCS-223 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant I need MF AR Subledger specific to CRI interface for Late Fees to update the Event Lines Customer Finance Charges from Debit default to Credit default & Finance Allow CR Recoveries from Credit default to Debit default as relates to the acconting entry sign. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | MF AR Subledger specific to CRI interface for Late Fees to update the Event Lines Customer Finance Charges from Debit default to Credit default & Finance Allow CR Recoveries from Credit default to Debit default as relates to the acconting entry sign. | Reviewed data and confirm functioning as per business design |  |  |  | Approved | Ian Plummer | 2023-03-21 | [7 empty] | RTR | RTR-AHCS | AHCS | [13 empty] | No
[5 empty] | DP-RTR-IC-144 |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As a tax accountant, I require "ECM" to be replaced with "EDMS" in the xml so that EDMS will accept the data. (see below) <ICTransactionFnStoreRequest xmlns="http://ABC Corp.com/ECM"> - for this we have to replace ECM with EDMS Also, I require the filename tag of the XML for EDMS needs to contain a capital N in the filename so that EDMS will accept the data. (see below) <filename>5014_IC5027-0000_501423100002_20230201.PDF</filename> - for this the XML Tag of <filename needs to be <fileName, thus we need to capitalize the N in name. <fileName>5014_IC5027-0000_501423100002_20230201.PDF</fileName> |  |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report | RPT102, RPT103 |  | Invoices/CMs are able to be consumed EDM for archiving |  |  |  | Approved | RMN on behalf of Tax | 2023-03-21 | [7 empty] | RTR | RTR-GL | IC | [13 empty] | No
[5 empty] | DP-RTR-IC-145 |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As an Intercompany Accountant, I require the addition of a Created By field to the search paramiters of RPT036 - Intercompany Transaction Details Report to allow me to more easily query journals that I've created |  |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report | RPT036 | While report output can be filterd by user, this enhancement would make reporting more efficient. EMEA requested this to help bridge Oracle process to legacy one where GL04/GL08 report was used to review all IC transactions they created. This is low priority enhancement, 90 day. | I am able to limit report to intercompany transactions that I've created |  |  |  | Approved | Rita Nanni | 2023-03-21 | [7 empty] | RTR | RTR-GL | IC | [13 empty] | No
[5 empty] | DP-RTR-IC-146 |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As a tax accountant, I require the logic of the invoice template process to be updated for the tax currency field so that my invoice data is correct. When transaction currency is different than tax currency, ZXLines table is not being updated with an exchange rate. This is a workaround to an existing bug/SR with Oracle. Logic: When a tax currency rate is null, pull rate from base table of exchange rates (GL Daily Rates). SR 3-32021104991-TAX_CURRENCY_CONVERSION_RATE in ZX_LINES is null for many transactions |  |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report | RPT102, RPT103 | SR 3-32021104991-TAX_CURRENCY_CONVERSION_RATE in ZX_LINES is null for many transactions | Correct FX rate is populated if there is a discrepancy between tax currency and transaction currency |  |  |  | Approved | RMN on behalf of Tax | 2023-03-22 | [7 empty] | RTR | RTR-GL | IC | [13 empty] | No
[5 empty] | DP-RTR-GL-096 |  | Record to Report | Manage General Ledger Accounting | Process Manual Journal Entries | As a GL Accountant, I need to be able to categorize Journal entries by the additional following categories: "Freight" and "Rebates and Ship and Debit". Neither of these should be reversing | Phase 1B only |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Required for go-live | Category is available to select when creating a journal entry |  |  |  | Approved | Heather Bowmil | 2023-03-31 | [7 empty] | RTR | RTR-GL | GL | [13 empty] | No
[5 empty] | DP-RTR-AHCS-224 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a Financial Systems Admin, I require the ability to create a single Mapping set for Primary & Secondary Ledger in MF AP Subledger. This will ensure that mappings are aligned across AP subledger by reducing risk of manual errors while reducing time / effort to make mapping updates across all AP rules. | Phase 1B only |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional | [11 empty] | PGL | PGL |  |  |  | RTR | RTR-AHCS | AHCS | [13 empty] | No
[5 empty] | DP-RTR-AHCS-225 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a Financial Systems Admin, I require the ability to have AHCS dashboards reflect when transactions have been purged so that Import Errors do not continue to show transactions which have already been addressed. This will ensure appropriate controls are in place to manage the dashboard. | Phase 1B only |  | Phase 1A+1B | 5-Gap-Build-Extension | Gap | Build | Extension | [11 empty] | PGL | PGL | ; |  |  | RTR | RTR-AHCS | AHCS | [13 empty] | No
[5 empty] | DP-RTR-AHCS-226 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a Financial Systems Admin, I require the ability to have the AHCS mapping set update through an automated solution | Phase 1B only |  | Phase 1B only | 3-Gap-Build-Interface | Gap | Build | Interface | [11 empty] | PGL | PGL |  |  |  | RTR | RTR-AHCS | AHCS | [13 empty] | No
[5 empty] | DP-RTR-AHCS-227 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a Accountant, I want accounting entries for IBI source posting to GL account as per the revised rules mentioned in the 1B accounting rules |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Accounting entries for IBI source posting to GL account as per the revised rules mentioned in the 1B accounting rules | Reviewed data and confirm functioning as per business design |  |  |  | Approved | Ian Plummer | 2023-04-03 |  |  | PGL | PGL |  |  |  | RTR | RTR-AHCS | AHCS | [13 empty] | No
[5 empty] | DP-RTR-AHCS-228 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As IT Manager, I want to remove Invoice Number as BSR for better system performance (Post Go Live) |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Remove Invoice Number as BSR for better system performance (Post Go Live) | Invoice number is not used as BSR any more |  |  |  | Approved | Sijo John | 2023-04-06 |  |  | PGL | PGL |  |  |  | RTR | RTR-AHCS | AHCS | [13 empty] | No
[5 empty] | DP-RTR-IC-147 |  | Record to Report | Manage General Ledger Accounting | Process Intercompany AR/AP Invoices | As a general accountant, I want validation of Inter/Intra extension to be updated to validate Net of Debit-Credit of provider with Net of Debit-Credit of receiver in Inter Group to allow mixed lines (e.g. Payroll entries) - UAT2 Enhancement defect CTPFS-30157 |  |  | Phase 1B only | 3-Gap-Build-Extension |  |  |  |  | Validation of Inter/Intra extension to be updated to validate Net of Debit-Credit of provider with Net of Debit-Credit of receiver in Inter Group to allow mixed lines (e.g. Payroll entries) - UAT2 Enhancement defect CTPFS-30157 | [30 empty] | No
[5 empty] | DP-RTR-IC-148 |  | Record to Report | Manage General Ledger Accounting | Process Intercompany AR/AP Invoices | As a general accountant, I want Inter/Intra mapping to IC FBDI template to be updated to allow debit and credit lines both on provider and receiver in Inter group (e.g. Payroll entries) - UAT2 Enhancement defect CTPFS-30157 |  |  | Phase 1B only | 5-Gap-Build-Extension | Gap | Build | Extension |  | Inter/Intra mapping to IC FBDI template to be updated to allow debit and credit lines both on provider and receiver in Inter group (e.g. Payroll entries) - UAT2 Enhancement defect CTPFS-30157 | [30 empty] | No
[5 empty] | DP-RTR-GL-097 |  | Record to Report | Manage General Ledger Accounting | Process Manual Journal Entries | As a GL Accountant I need to see a sample of the 1B COA legacy string and mapping on ADFDI template under User COA mapping link. |  |  | Phase 1A+1B | 5-Gap-Build-Extension | Gap | Build | Extension |  | Requested by Manisha Deshpande via email on 4/5/23 | Template includes sample of 1B legacy chartstring |  |  |  | Approved | Rita Nanni | 2023-04-07 | [7 empty] | RTR | RTR-AHCS | GL | [13 empty] | No
[5 empty] | DP-RTR-GL-098 |  | Record to Report | Manage General Ledger Accounting | Process Manual Journal Entries | As a GL Accountant I need to have "Created By" field added to RPT046 Journal Line Detail Report output so that users can identify who created journal lines. |  |  | Phase 1A+1B | 2-Gap-Build-Report | Gap | Build | Report | RPT046 | Requested during UAT2 1A Regression Testing with defect CTPFS-29980 1B users do not use 1A journal naming convention which includes user ID. Note that field should be populated similar to same field in RPT042 "Journal Creator (Journals with source ‘WSC Intra Spreadsheet’ should take ‘Created By’ username from the Batch Description.)" | Report output includes user name of journal creator. |  |  |  | Approved | Rita Nanni | 2023-04-07 | [7 empty] | RTR | RTR-AHCS | GL | [13 empty] | No
[5 empty] | DP-RTR-GL-099 |  | Record to Report | Manage General Ledger Accounting | Process Manual Journal Entries | As a GL Accountant I need to have logic added to Manage Journals Serch Criteria output that includes user names in Created By field for system generated reversing entries. |  |  | Phase 1A+1B | 7-Out of Scope-Out of Scope-Out of Scope | Out of Scope | Out of Scope | Out of Scope |  | Requested during UAT2 1A Regression Testing with defect CTPFS-29972 1B users do not use 1A journal naming convention which includes user ID. OTBI report created by OSS for interim for review RMN to have someone look into IAP or Teradata as possible work-around 5/25 update - Not a delivered functionality in Oracle, logged an Idea # 682599 with Oracle as Enhancement. De-Scoped in user story tracker. | Search output includes user name of journal creator for all sources |  |  |  | Approved | Rita Nanni | 2023-04-07 | [7 empty] | RTR | RTR-AHCS | GL | [13 empty] | No
[5 empty] | DP-RTR-IC-149 |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As an Intercompany Accountant I require the additional LE switching combinations noted below to be added LSI solution: 1036 ABC Corp Inc. & 5054 ABC Corp Eurotwo Holdings B.V. 2021 ABC Corp Canada Inc. & 5054 ABC Corp Eurotwo Holdings B.V. 5054 ABC Corp Eurotwo Holdings B.V. & 1036 ABC Corp Inc. 5054 ABC Corp Eurotwo Holdings B.V. & 2021 ABC Corp Canada Inc. |  |  | Phase 1B only | 5-Gap-Build-Extension | Gap | Build | Extension |  | Issue logged in Defect CTPFS-29796 Notes from OSS: In stabilized phase, I am assuming there would be cadence to review enhancements and their priority. This user story can then be useful to determine based on b/w vs prioritization then For go-live & quarter close remove relationship from LSI & handle manually - Key driver: Low volume of trx, risk of regression on a solution that been pretty stable since SIT2 (when it was released) | US and Canada can switch with LE 5054 which is final netting entity (See Scenarios 5-1 snd 5-2) |  |  |  | Approved | Rita Nanni | 2023-04-07 | [7 empty] | RTR | RTR-GL | IC | [13 empty] | No
[5 empty] | DP-RTR-IC-150 |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | If ZX_LINES.Attribute 1 in (SO,SFO, SOSFO) Pick the Operational Address from Attribute5,Attribute6 of Lookup Table: WSC_LEGAL_ENTITY_MASTER_TAX; If Null or any other value then Pick up registered address from Attribute3,Attribute4 of Lookup Table: WSC_LEGAL_ENTITY_MASTER_TAX Existing condition to be modified to treat SOSFO similar to SO/SFO for Company Information column. |  |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report | RPT102, RPT103 |  | 1) Enter a journal for goods with ABC Corp Limited Spain (LE 5049) as the seller and check that the Spanish address is printing in the company header. This should be triggered by the code SOSFO being populated in ZX_LINES.Attribute1 2) Enter a journal for services with ABC Corp Limited Spain (LE 5049) as the seller and check that the Spanish address is printing in the company header. This should be triggered by the code SOSFO being populated in ZX_LINES.Attribute1 |  |  |  | Approved | RMN on behalf of Tax | 2023-04-10 | [7 empty] | RTR | RTR-GL | IC | [13 empty] | No
[5 empty] | DP-RTR-AHCS-229 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As IT Manager, I want to create and migrate SQL queries to support Hypercare |  |  | Phase 1B only | 5-Gap-Build-Extension | Gap | Build | Extension |  |  | SQL queries are created and moved to Production to support Hypercare |  |  |  | Approved | Sijo John | 2023-04-10 | [7 empty] | RTR | RTR-AHCS
[5 empty] | DP-RTR-IC-151 |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As a specialized user of Intercompany AP and AR, I require the ability to change invoice date on AR Invoices to support the workaround for processing of AR/AP invoices that cannot be processed due to tax issue that cannot be resolved prior to ME Close. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Specialized users only, two per global region. Should be new role that allows only the access required to change date on invoice to avoid SOD conflict | User is able to change accounting date on AR invoice so that "stuck" transactions can be moved to subsequent period. |  |  |  | Approved | Rita Nanni | 2023-04-10 | [7 empty] | RTR | RTR-GL | IC | [13 empty] | No
[5 empty] | DP-RTR-AHCS-230 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As IT Manager, I want to stop sending the error notification emails for Legacy system empty files |  |  | Phase 1B only | 5-Gap-Build-Extension | Gap | Build | Extension |  |  | No email notifications are sent for the files having empty data for Legacy systems |  |  |  | Approved | Sijo John | 2023-04-10 | [7 empty] | RTR | RTR-AHCS
[5 empty] | DP-RTR-IC-152 |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As an intercompany accountant I require that Tri-Ed Puerto Rico off-system entities be excluded from list of Intercompany Organizations (LE 3034) |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | Tri-Ed off-system entity should be excluded from intercompany invoicing | Tri Ed Puerto Rico LE 3034 is not available for IC tranactions |  |  |  | Approved | Rita Nanni | 2023-04-12 | [7 empty] | RTR | RTR-GL | IC | [13 empty] | No
[5 empty] | DP-RTR-AHCS-231 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As IT Manager, I want OIC Dashboard to show the detail status when you drill down on the Batch ID for 3rd party systems - Post Go Live |  |  | Phase 1B only | 5-Gap-Build-Extension | Gap | Build | Extension |  |  | The detail status is displayed on OIC Dashboard for 3rd party systems |  |  |  | Approved | Sijo John | 2023-04-12 | [7 empty] | RTR | RTR-AHCS
[5 empty] | DP-RTR-AHCS-232 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant I need all transactions under late fees as part of CRI interface in MF AR, to only look at Dr/Cr flag provided by Mainframe and ignore negative/positive signs. |  |  | Phase 1B only | 5-Gap-Build-Extension | Gap | Build | Extension |  |  | Verify data is correct as per business design |  |  |  | Approved | Ian Plummer | 2023-04-20 | [7 empty] | RTR | RTR-AHCS |  |  |  |  | Post Go live change
[5 empty] | DP-RTR-AHCS-233 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant I need all transactions specific to event type Customer Finance Charge Paid under late fees as part of CRI interface in MF AR, to use rule AC-34 for account segment as per 1B - Business requirements UAT Delta change 4-20-2023 document |  |  | Phase 1B only | 5-Gap-Build-Extension | Gap | Build | Extension |  |  | Verify data is correct as per business design |  |  |  | Approved | Ian Plummer | 2023-04-20 | [7 empty] | RTR | RTR-AHCS |  |  |  |  | Post Go live change
[5 empty] | DP-RTR-AHCS-234 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant I need for INT043 to be updated to incorporate File Name and sent in the outbound feed for CONCUR source. This is applicable for Concur Subledger. |  |  | Phase 1B only | 5-Gap-Build-Extension | Gap | Build | Extension |  |  | Verify data is correct as per business design |  |  |  | Approved | Ian Plummer | 2023-04-20 | [7 empty] | RTR | RTR-AHCS |  |  |  |  | Post Go live change
[5 empty] | DP-RTR-IC-153 |  | Record to Report | Manage Intercompany Accounting | Perform Intercompany Transactions | As an intercompany Accountant I require that my in-region intercompany transactions get routed for GL Approval based on Manage Journals Approval Rules. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | To remove risk of Intercompany Module transactions not being subject to review, eliminating a preventative control. | Regional transactions are routed for GL approval, using same rules as GL journals. |  |  |  | Approved | Rita Nanni | 2023-04-24 | [7 empty] | RTR | RTR-GL | IC | [13 empty] | No
[5 empty] | DP-RTR-GL-100 |  | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | As a ABC Corp Accountant I would like to remove the ABC Corp abbreviation "AXE_" from all GL, IC, AP, and AR reports custom reports within Reports and Analytics folders. To support a common report naming convention with prefix of "ABC Corp_GBL_". |  |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report |  | To support a common report naming convention. Low priority. | All custom reports consistently use the ABC Corp_GBL_ prefix as part of naming convention |  |  |  | Approved | Rita Nanni | 2023-04-26 | [7 empty] | RTR | RTR-GL | GL | [13 empty] | No
[5 empty] | DP-RTR-IC-154 |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | Missing address on the invoices for the MD entities in the vendor and/or customer and/or ship to fields “For fields 3c and 4b , if ZX_Lines.ATTRIBUTE2 is Null or any other value then pick registered address from WSC_CUSTOMER_TAX” |  |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report | RPT102, RPT103 | [6 empty] | Bharat Kaki on behalf of Tax
[5 empty] | DP-RTR-AHCS-235 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant I need SR Loc for Trade Payables lines to use HQ Location Value for CAI source, Early Pay discount line as part of MF AP. |  |  | Phase 1B only | 5-Gap-Build-Extension | Gap | Build | Extension |  |  | Verify data is correct as per business design |  |  |  | Approved | Ian Plummer | 2023-04-27 | [7 empty] | RTR | RTR-AHCS |  |  |  |  | Post Go live change
[5 empty] | DP-RTR-IC-155 |  | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | Currently we are referring currency_conversion_code from table ZX_lines. Derivation logic needs to be changed for field exchange rate on top of logic provided for user story ‘DP-RTR-IC-146’ |  |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report | RPT102, RPT103 | User story DP-RTR-IC-146 logged earlier to incorporate changes on Tax & Tax regime Currency , Tax Basis & Tax regime Currency and Exchange Rate This new user story is to change logic provided for column Exchange Rate. | [5 empty] | Bharat Kaki on behalf of Tax
[5 empty] | DP-RTR-IC-156 |  | Record to Report | Manage Intercompany Accounting | Perform Intercompany Transactions | As and Intercompany Accountant, I require a new security role that provides access to edit Accounting Date on Accounts Receivable invoice header, for transactions created by Global Intercompany source. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | This access is required for AR intercompany invoices that cannot be processed within the current period and would prevent us from closing AR subledger until error is resolved. This is required as there is no functionality to allow us to sweep AR transactions into the next period. This has been referred to as the Last Resort solution. Access to this specific role would be very limited. |  |  |  |  | Approved | Rita Nanni | 2023-05-01 | [7 empty] | RTR | RTR-GL | IC | [13 empty] | No
[5 empty] | MOVED TO LEG IT |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | Given the recent calendar change from 4-4-5 to the monthly calendar, we need to have invoices created on the weekend especially when the month-end falls on a weekend. As a ABC Corp Accountant we need to be able to account for these invoices in the proper calendar period. |  |  | Post Go-Live | 10-Not Required-Not Required-Not Required | Not Required | Not Required | Not Required |  | This requirement was pushed back since this year we had limited times when this will occur for quarter-end. Recently, we received additional guidance from leadership where this will be a requirement moving forward even on non quarter-end months (as we experienced in April). | Invoices are created on the final day of the month regardless of when that day falls during the week, especially on a weekend. |  |  |  | Approved | Heather Bowmil | 2023-05-05 | [7 empty] | RTR | AXE-Calendar Change | Legacy
[5 empty] | DP-RTR-AHCS-236 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | Modify the Bad File generation program to work for large data |  |  | Phase 1B only | 5-Gap-Build-Extension | Gap | Build | Extension |  |  | Bad file is generated successfully for large data |  |  |  | Approved | Sijo John | 2023-05-21
[5 empty] | DP-RTR-GL-101 |  | Record to Report | Manage General Ledger Accounting | Process Manual Journal Entries | As an Intercompany and GL Accountant, I would like to be able to load journals for more than 38 ledgers through a single file using Inter Intra custom loader |  |  | Phase 1B only | 5-Gap-Build-Extension | Gap | Build | Extension |  | As discovered during non-Prod smoke testing, Inter Intra Custom Loader has limitation in number of ledgers that can be loaded in single file. At max only 38 ledgers can be loaded in one go through a single file. CTPFS-30237 Workaround is to split journal with more than 38 ledgers into multiple journals, therefore this is low priority enhancement. |  |  |  |  | Approved | Rita Nanni | 2023-05-22
[5 empty] | DP-RTR-AHCS-237 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | Enable Ledger Split for Mf Inventory - JTI transactions |  |  | Phase 1B only | 5-Gap-Build-Extension | Gap | Build | Extension |  |  | Java Tools MF Inventory transactions are split into different ledgers based on the LEs |  |  |  | Approved | Sijo John | 2023-06-01 | [7 empty] | RTR | RTR-GL | GL
[5 empty] | DP-RTR-IC-157 |  | Record to Report | Manage Intercompany Accounting | Perform Intercompany Transactions | As an Intercompany Accountant, I require the purging of tables related to the LSI process. Proposal is for the tables to be purged every 60 or 90 days, to be determined after evaluation by IT. |  |  | Phase 1B only | 5-Gap-Build-Extension | Gap | Build | Extension |  | Pending evaluation of timing by IT |  |  |  |  | Approved | Rita Nanni | 2023-06-05 | [7 empty] | RTR | RTR-GL | IC | [13 empty] | N/A
[5 empty] | DP-RTR-IC-158 |  | Record to Report | Manage Intercompany Accounting | Perform Intercompany Transactions | As an Intercompany Accountant, I require the purging of tables related to the use of the Custom Data Loader. Proposal is for the tables to be purged every 60 or 90 days, to be determined after evaluation by IT. |  |  | Phase 1B only | 5-Gap-Build-Extension | Gap | Build | Extension |  | Pending evaluation of timing by IT |  |  |  |  | Approved | Rita Nanni | 2023-06-05 | [7 empty] | RTR | RTR-GL | IC | [13 empty] | N/A
[5 empty] | DP-RTR-IC-159 |  | Record to Report | Manage Intercompany Accounting | Perform Intercompany Transactions | As an Intercompany Accountant, I require an enhancement to the LSI process so that transactions will switch using the actual daily rate as of the LSI date, and not reference the conversion rate type of original invoice. |  |  | Phase 1B only | 5-Gap-Build-Extension | Gap | Build | Extension |  | This will remedy the issue of transactions failing if they were created during month end close using month end rate type. This solution was agreed up during our call with Patrick (Tax) and Geert (Treasury) on 6/12/23. | Eligible IC transactions created during month end close with ME conv rate will process correclty during that eveneng's LSI with that day's actual rate. |  |  |  | Approved | Rita Nanni | 2023-06-12 | [7 empty] | RTR | RTR-GL | IC | [13 empty] | N/A
[5 empty] | DP-RTR-AHCS-238 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant I need source JTI for event type COST_QUANTITY_TRUEUP to ignore GAAP flag lines for Primary Ledger and only post in Secondary Ledger in AHCS. |  |  | Phase 1B only | 5-Gap-Build-Extension | Gap | Build | Extension |  |  | Review results and confirm aligned based on business design |  |  |  | Approved | Ian Plummer | 2023-06-13
[5 empty] | DP-RTR-AHCS-239 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As a GL Accountant I need for MF AR under Transaction type derivation , to be updated for transaction type CRI_CASH_APPLICATIONS. Input data needed for event type under Cashcode should also include RSWO. |  |  | Phase 1B only | 5-Gap-Build-Extension | Gap | Build | Extension |  |  | Review results and confirm aligned based on business design |  |  |  | Approved | Ian Plummer | 2023-06-14
[5 empty] | DP-RTR-GL-102 |  | Record to Report | Manage General Ledger Accounting | Process Manual Journal Entries | For manually reversed journal batches that were created using Inter-Intra Custom Loader we require that system reference the UserID of user that initiates the reversal for purposes of routing for approval. |  |  | Phase 1B only | 5-Gap-Build-Extension | Gap | Build | Extension |  | Look at feasibility of identifying UserID for manually reversed journals for WSC Intra Spreadsheet journals by referencing Created By field. | Manually reversed journals for WSC Intra Spreadsheet journals should be routed for approval |  |  |  | Approved | Rita Nanni | 2023-06-14 | [7 empty] | RTR | RTR-GL | GL | [13 empty] | No
[5 empty] | DP-RTR-GL-103 |  | Record to Report | Manage General Ledger Accounting | Process Manual Journal Entries | As a GL Intercompany Accountant, I require that the accounted invoice balances for JPY and KRW currencies be formatted to zero decimal places in RPT019. |  |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report | RPT019 |  | Report will show zero decimal places for KRW and JPY currency accounted balances. |  |  |  | Approved | Rita Nanni | 2023-06-30 15:03 | [7 empty] | RTR | RTR-GL | GL
[5 empty] | DP-RTR-GL-104 |  | Record to Report | Manage General Ledger Accounting | Process Manual Journal Entries | As a GL Intercompany Accountant, I require that the accounted invoice balances for JPY and KRW currencies be formatted to zero decimal places in RPT020. |  |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report | RPT020 | Request per Boon-Hui email 6/6/23: change the accounted amounts to be precise for JP USGAAP JPY and KR USGAAP KRW ledgers on the below mentioned report | Report will show zero decimal places for KRW and JPY currency accounted balances. |  |  |  | Approved | Rita Nanni | 2023-07-12 | [7 empty] | RTR | RTR-GL | GL
[5 empty] | DP-RTR-GL-105 |  | Record to Report | Manage General Ledger Accounting | Process Manual Journal Entries | As a GL Intercompany Accountant, I require that the accounted invoice balances for JPY and KRW currencies be formatted to zero decimal places in RPT209. |  |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report | RPT209 | Request per Boon-Hui email 6/6/23: change the accounted amounts to be precise for JP USGAAP JPY and KR USGAAP KRW ledgers on the below mentioned report | Report will show zero decimal places for KRW and JPY currency accounted balances. |  |  |  | Approved | Rita Nanni | 2023-07-12 | [7 empty] | RTR | RTR-GL | GL
[5 empty] | DP-RTR-GL-106 |  | Record to Report | Manage General Ledger Accounting | Process Manual Journal Entries | As a GL Intercompany Accountant, I require that the accounted invoice balances for JPY and KRW currencies be formatted to zero decimal places in RPT210. |  |  | Phase 1B only | 2-Gap-Build-Report | Gap | Build | Report | RPT210 | Request per Boon-Hui email 6/6/23: change the accounted amounts to be precise for JP USGAAP JPY and KR USGAAP KRW ledgers on the below mentioned report | Report will show zero decimal places for KRW and JPY currency accounted balances. |  |  |  | Approved | Rita Nanni | 2023-07-12 | [7 empty] | RTR | RTR-GL | GL
[5 empty] | DP-RTR-GL-107 |  | Record to Report | Manage General Ledger Accounting | Process Manual Journal Entries | As a GL accountant I require the disabling of the following LEs from the Oracle setup: 2020 - ABC Corp Canadian Holdings ULC, 5060 - Eurinvest B.V., and 5059 - Eurinvest Cooperatief U.A.. These entities are being eliminated as part of the ongoing LE rationalization process. |  |  | Phase 1B only | 1-Fit-Configuration-Functional | Fit | Configuration | Functional |  | LE's are being eliminated or consolidated as part of LE rationalization | LE's will not be available for processing in Oracle systems |  |  |  | Approved | Rita Nanni | 2023-07-18 10:56 | [7 empty] | RTR | RTR-GL | GL | [13 empty] | No
[5 empty] | DP-RTR-AHCS-240 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I need tax line for India to be sent to sent to AHCS once these tax accounts are created in MF. This will prevent out of balance transactions |  |  | Phase 1B only | 5-Gap-Build-Extension | Gap | Configuration | Functional |  | Sending tax line for India to AHCS | Correct accounts are passed in the tax line for India |  |  |  | Approved | Manisha Deshpande | 2023-09-08
[5 empty] | DP-RTR-AHCS-241 |  | Record to Report | Manage Subledger Accounting | Create Subledger Accounting | As GL Accountant, I need tax accounts are created in MF for India so there are no out of balance transactions. |  |  | Phase 1B only | 5-Gap-Build-Extension | Gap | Configuration | Functional |  | Creating India tax accounts in MF | Correct accounts are created in MF for India |  |  |  | Approved | Manisha Deshpande | 2023-09-08
Note on P222: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This should be a GAP since we use OIC mapping to fulfil this requirement
Note on P224: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Should be a GAP
Note on K230: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Need to confirm
Note on P232: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Should be GAP
Note on T232: Arun, Gheware Nilakanth: Subledger Interface ID Source Transaction Number (Concatenated Value) MF AP NA Invoice Number ~ Vendor Number ~ Invoice Date MF AR NA Invoice Number ~ Customer Number MF INV ISI, IBI, ICI, AII, SSI, FII, FTI Invoice Number ~ Customer Number ~ Invoice Date MF INV IRI Item Number ~ Receiver Location ~ Receiver Number MF INV CQI Part Number ~ PS Location (5digits) MF INV DAI PO Number ~ Vendor Number ~ Invoice Date PS FA PSFA ASSET ID Leases Leases RECORD ID (Asset ID) SXE SXE Blank ECLIPS ECLPS Blank Treasury APS Blank CloudPay CPI Blank
Note on P233: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Should be GAP
Note on T233: Arun, Gheware Nilakanth: Subledger Interface ID Source Transaction Number (Concatenated Value) MF AP NA Invoice Number ~ Vendor Number ~ Invoice Date MF AR NA Invoice Number ~ Customer Number MF INV ISI, IBI, ICI, AII, SSI, FII, FTI Invoice Number ~ Customer Number ~ Invoice Date MF INV IRI Item Number ~ Receiver Location ~ Receiver Number MF INV CQI Part Number ~ PS Location (5digits) MF INV DAI PO Number ~ Vendor Number ~ Invoice Date PS FA PSFA ASSET ID Leases Leases RECORD ID (Asset ID) SXE SXE Blank ECLIPS ECLPS Blank Treasury APS Blank CloudPay CPI Blank
Note on P234: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Should be GAP
Note on T243: Arun, Gheware Nilakanth: Subledger Interface ID Source Transaction Number (Concatenated Value) MF AP NA Invoice Number ~ Vendor Number ~ Invoice Date MF AR NA Invoice Number ~ Customer Number MF INV ISI, IBI, ICI, AII, SSI, FII, FTI Invoice Number ~ Customer Number ~ Invoice Date MF INV IRI Item Number ~ Receiver Location ~ Receiver Number MF INV CQI Part Number ~ PS Location (5digits) MF INV DAI PO Number ~ Vendor Number ~ Invoice Date PS FA PSFA ASSET ID Leases Leases RECORD ID (Asset ID) SXE SXE Blank ECLIPS ECLPS Blank Treasury APS Blank CloudPay CPI Blank
Note on F399: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: changed from 117 Nov 29
Note on Z400: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: updated Tri Ed US to Tri Ed Puerto Rico

## Sprint Plan by RICE Type
RICE View - Lean Spec (L)
Release | (Multiple Items)
L0 | Record to Report
Oracle Module | (Multiple Items)
User Story Disposition | (Multiple Items)
Count of Unique ID |  | Design Sprint [Lean Specs]
SubTrack | RICE type from RICE Tracker | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5
RTR-AHCS | Extension |  | 2
RTR-AHCS | Interface | 4 | 12 | 1
RTR-AHCS | Report | 1 | 1 | 2
RTR-AHCS Total |  | 5 | 15 | 3
RTR-GL | Conversion | 2
RTR-GL | Extension | 4 | 12
RTR-GL | Interface | 5 | 3
RTR-GL | Report |  | 18 | 11 | 5 | 3
RTR-GL Total |  | 11 | 33 | 11 | 5 | 3
RICE View - Build (D)
Release | (Multiple Items)
L0 | Record to Report
Oracle Module | (Multiple Items)
User Story Disposition | (Multiple Items)
Count of Unique ID |  | Build Sprint [Tech Build]
SubTrack | RICE type from RICE Tracker | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5 | Sprint 6 | TBD
RTR-AHCS | Extension |  | 2
RTR-AHCS | Interface | 9 | 3 | 5
RTR-AHCS | Report | 1 |  | 3
RTR-AHCS Total |  | 10 | 5 | 8
RTR-GL | Conversion | 2
RTR-GL | Extension | 4 | 9 | 3
RTR-GL | Interface | 5 | 3
RTR-GL | Report |  | 2 | 12 | 19 | 3 | 1
RTR-GL Total |  | 11 | 14 | 15 | 19 | 3 | 1
RICE View - TUT/FUT (T)
Release | (Multiple Items)
L0 | Record to Report
Oracle Module | (Multiple Items)
User Story Disposition | (Multiple Items)
Count of Unique ID |  | Delivery Sprint [TUT/FUT]
SubTrack | RICE type from RICE Tracker | Sprint 11 | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5 | Sprint 6 | Sprint 68 | Sprint 69 | Sprint 73 | Sprint 76 | Sprint 80 | Sprint 9 | TBD
RTR-AHCS | Extension |  |  | 2
RTR-AHCS | Interface |  |  | 12 | 5
RTR-AHCS | Report |  |  | 1 | 3
RTR-AHCS Total |  |  |  | 15 | 8
RTR-GL | Conversion |  |  | 2
RTR-GL | Extension |  | 3 | 10 | 3
RTR-GL | Interface |  | 5 | 3
RTR-GL | Report | 1 |  | 2 | 3 | 18 | 6 | 1 | 1 | 1 | 1 | 1 | 1 | 1
RTR-GL Total |  | 1 | 8 | 17 | 6 | 18 | 6 | 1 | 1 | 1 | 1 | 1 | 1 | 1
SubTrack | RICE type from RICE Tracker | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5 | Sprint 6 | TBD
RTR-AHCS | Conversion | 0 | 0 | 0 | 0 | 0 | 0 | 0
RTR-AHCS | Extension | 0 | 2 | 4 | 0 | 0 | 0 | 0
RTR-AHCS | Interface | 4 | 21 | 16 | 10 | 0 | 0 | 0
RTR-AHCS | Report | 1 | 2 | 3 | 6 | 0 | 0 | 0
RTR-GL | Conversion | 2 | 2 | 2 | 0 | 0 | 0 | 0
RTR-GL | Extension | 4 | 19 | 19 | 6 | 0 | 0 | 0
RTR-GL | Interface | 5 | 13 | 6 | 0 | 0 | 0 | 0
RTR-GL | Report | 0 | 18 | 15 | 20 | 40 | 9 | 2
RTR-AHCS | Conversion | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Cumulative
RTR-AHCS | Extension | 0 | 2 | 6 | 6 | 6 | 6 | 6 |  | Cumulative
RTR-AHCS | Interface | 4 | 25 | 41 | 51 | 51 | 51 | 51 |  | Cumulative
RTR-AHCS | Report | 1 | 3 | 6 | 12 | 12 | 12 | 12 |  | Cumulative
RTR-GL | Conversion | 2 | 4 | 6 | 6 | 6 | 6 | 6 |  | Cumulative
RTR-GL | Extension | 4 | 23 | 42 | 48 | 48 | 48 | 48 |  | Cumulative
RTR-GL | Interface | 5 | 18 | 24 | 24 | 24 | 24 | 24 |  | Cumulative
RTR-GL | Report | 0 | 18 | 33 | 53 | 93 | 102 | 104 |  | Cumulative
SubTrack | RICE type from RICE Tracker | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5 | Sprint 6 | TBD
RTR-AHCS | Conversion | NA | NA | NA | NA | NA | NA | NA
RTR-AHCS | Extension | 0% | 33.33% | 100% | 100% | 100% | 100% | 100%
RTR-AHCS | Interface | 7.843% | 49.02% | 80.39% | 100% | 100% | 100% | 100%
RTR-AHCS | Report | 8.333% | 25% | 50% | 100% | 100% | 100% | 100%
RTR-GL | Conversion | 33.33% | 66.67% | 100% | 100% | 100% | 100% | 100%
RTR-GL | Extension | 8.333% | 47.92% | 87.5% | 100% | 100% | 100% | 100%
RTR-GL | Interface | 20.83% | 75% | 100% | 100% | 100% | 100% | 100%
RTR-GL | Report | 0% | 17.65% | 32.35% | 51.96% | 91.18% | 100% | 102%

## JIRA
Issue Type | Key | Summary | OSS Key | OSS Functional Key | Technical OSS Key | OSS TUT/FUT | Business Owner Assignee | Assignee | Reporter | Priority | Status | Resolution | Created | Updated | Due date | Sprint | Fix versions | Epic Name | Release | RICE ID | Sub Track | Track | Type | parent
User Story | CSTONE-42 | RTR-AHCS-001 | RTR-AHCS-001 | RTR-AHCS-001 - Functional |  |  |  | Avinash Bandla | Mehul Kumar Patel |  | Done | Fixed | 2021-06-13 14:00 | 2021-10-25 13:27 |  | CSTONE Sprint 1 | 1A+1B |  |  |  | RTR-AHCS | RTR | Configuration
User Story | CSTONE-43 | RTR-AHCS-002 | RTR-AHCS-002 | RTR-AHCS-002 - Functional |  |  |  | Avinash Bandla | Mehul Kumar Patel |  | Done | Fixed | 2021-06-13 14:00 | 2021-10-25 13:27 |  | CSTONE Sprint 1 | 1A+1B |  |  |  | RTR-AHCS | RTR | Configuration
User Story | CSTONE-44 | RTR-AHCS-004 | RTR-AHCS-004 | RTR-AHCS-004 - Functional |  |  |  | Avinash Bandla | Mehul Kumar Patel |  | Done | Fixed | 2021-06-13 14:00 | 2021-10-25 13:27 |  | CSTONE Sprint 1 | 1A |  |  |  | RTR-AHCS | RTR | Configuration
User Story | CSTONE-45 | RTR-AHCS-005 | RTR-AHCS-005 | RTR-AHCS-005 - Functional |  |  |  | Avinash Bandla | Mehul Kumar Patel |  | Done | Fixed | 2021-06-13 14:00 | 2021-10-25 13:27 |  | CSTONE Sprint 1 | 1A+1B |  |  |  | RTR-AHCS | RTR | Configuration
User Story | CSTONE-54 | RTR-AHCS-030 | RTR-AHCS-030 | RTR-AHCS-030 - Functional |  |  |  | Avinash Bandla | Mehul Kumar Patel |  | Done | Fixed | 2021-06-13 14:00 | 2021-10-25 13:27 |  | CSTONE Sprint 1 | 1A+1B |  |  |  | RTR-AHCS | RTR | Configuration
User Story | CSTONE-55 | RTR-AHCS-032 | RTR-AHCS-032 | RTR-AHCS-032 - Functional |  |  |  | Avinash Bandla | Mehul Kumar Patel |  | Done | Fixed | 2021-06-13 14:00 | 2021-10-25 13:27 |  | CSTONE Sprint 1 | 1A+1B |  |  |  | RTR-AHCS | RTR | Configuration
User Story | CSTONE-56 | RTR-AHCS-033 | RTR-AHCS-033 | RTR-AHCS-033 - Functional |  |  |  | Avinash Bandla | Mehul Kumar Patel |  | Done | Fixed | 2021-06-13 14:00 | 2021-10-25 13:27 |  | CSTONE Sprint 1 | 1A+1B |  |  |  | RTR-AHCS | RTR | Configuration
User Story | CSTONE-57 | RTR-AHCS-035 | RTR-AHCS-035 | RTR-AHCS-035 - Functional |  |  |  | Avinash Bandla | Mehul Kumar Patel |  | Done | Fixed | 2021-06-13 14:00 | 2021-10-25 13:27 |  | CSTONE Sprint 1 | 1A+1B |  |  |  | RTR-AHCS | RTR | Configuration
User Story | CSTONE-58 | RTR-AHCS-048 | RTR-AHCS-048 | RTR-AHCS-048 - Functional |  |  |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-06-13 14:00 | 2021-07-08 14:53 |  | CSTONE Sprint 1 | 1A+1B |  |  |  | RTR-AHCS | RTR | Configuration
User Story | CSTONE-59 | RTR-AHCS-049 | RTR-AHCS-049 | RTR-AHCS-049 - Functional |  |  |  | Avinash Bandla | Mehul Kumar Patel |  | Done | Fixed | 2021-06-13 14:00 | 2021-07-13 12:07 |  | CSTONE Sprint 1 | 1A+1B |  |  |  | RTR-AHCS | RTR | Configuration
User Story | CSTONE-62 | RTR-GL-007 | RTR-GL-007 | RTR-GL-007 - Functional |  |  |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-06-13 14:06 | 2021-10-25 13:27 |  | CSTONE Sprint 1 | 1A+1B |  |  |  | RTR-GL | RTR | Configuration
User Story | CSTONE-64 | RTR-GL-009 | RTR-GL-009 | RTR-GL-009 - Functional |  |  |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-06-13 14:06 | 2021-07-08 14:53 |  | CSTONE Sprint 1 | 1A+1B |  |  |  | RTR-GL | RTR | Configuration
User Story | CSTONE-63 | RTR-GL-008 | RTR-GL-008 | RTR-GL-008 - Functional |  |  |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-06-13 14:06 | 2021-10-25 13:27 |  | CSTONE Sprint 1 | 1A+1B |  |  |  | RTR-GL | RTR | Configuration
User Story | CSTONE-67 | RTR-GL-011 | RTR-GL-011 | RTR-GL-011 - Functional |  |  |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-06-13 14:07 | 2021-10-25 13:26 |  | CSTONE Sprint 1 | 1A+1B |  |  |  | RTR-GL | RTR | Configuration
User Story | CSTONE-68 | RTR-GL-012 | RTR-GL-012 | RTR-GL-012 - Functional |  |  |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-06-13 14:07 | 2021-10-25 13:26 |  | CSTONE Sprint 1 | 1A+1B |  |  |  | RTR-GL | RTR | Configuration
User Story | CSTONE-71 | RTR-GL-014 | RTR-GL-014 | RTR-GL-014 - Functional |  |  |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-06-13 14:07 | 2021-10-25 13:26 |  | CSTONE Sprint 2 | 1A+1B |  |  |  | RTR-GL | RTR | Work Around
User Story | CSTONE-72 | RTR-GL-015 | RTR-GL-015 | RTR-GL-015 - Functional |  |  |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-06-13 14:07 | 2021-10-25 13:26 |  | CSTONE Sprint 1 | 1A+1B |  |  |  | RTR-GL | RTR | Configuration
User Story | CSTONE-73 | RTR-GL-016 | RTR-GL-016 | RTR-GL-016 - Functional |  |  |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-06-13 14:07 | 2021-10-25 13:27 |  | CSTONE Sprint 1 | 1A+1B |  |  |  | RTR-GL | RTR | Configuration
User Story | CSTONE-78 | RTR-GL-019 | RTR-GL-019 | RTR-GL-019 - Functional |  |  |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-06-13 14:07 | 2021-10-25 13:26 |  | CSTONE Sprint 1 | 1A+1B |  |  |  | RTR-GL | RTR | Configuration
User Story | CSTONE-79 | RTR-GL-023 | RTR-GL-023 | RTR-GL-023 - Functional |  |  |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-06-13 14:07 | 2021-10-25 13:26 |  | CSTONE Sprint 1 | 1A+1B |  |  |  | RTR-GL | RTR | Configuration
User Story | CSTONE-80 | RTR-GL-025 | RTR-GL-025 | RTR-GL-025 - Functional |  |  |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-06-13 14:07 | 2021-10-25 13:26 |  | CSTONE Sprint 1 | 1A+1B |  |  |  | RTR-GL | RTR | Configuration
User Story | CSTONE-81 | RTR-GL-026 | RTR-GL-026 | RTR-GL-026 - Functional |  |  |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-06-13 14:07 | 2021-10-25 13:26 |  | CSTONE Sprint 1 | 1A+1B |  |  |  | RTR-GL | RTR | Configuration
User Story | CSTONE-82 | RTR-GL-028 | RTR-GL-028 | RTR-GL-028 - Functional |  |  |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-06-13 14:07 | 2021-10-25 13:26 |  | CSTONE Sprint 1 | 1A+1B |  |  |  | RTR-GL | RTR | Configuration
User Story | CSTONE-83 | RTR-GL-029 | RTR-GL-029 | RTR-GL-029 - Functional |  |  |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-06-13 14:07 | 2021-10-25 13:26 |  | CSTONE Sprint 1 | 1A+1B |  |  |  | RTR-GL | RTR | Configuration
User Story | CSTONE-84 | RTR-GL-030 | RTR-GL-030 | RTR-GL-030 - Functional |  |  |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-06-13 14:07 | 2021-10-25 13:26 |  | CSTONE Sprint 1 | 1A+1B |  |  |  | RTR-GL | RTR | Configuration
User Story | CSTONE-85 | RTR-GL-031 | RTR-GL-031 | RTR-GL-031 - Functional |  |  |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-06-13 14:07 | 2021-10-25 13:26 |  | CSTONE Sprint 1 | 1A+1B |  |  |  | RTR-GL | RTR | Configuration
User Story | CSTONE-86 | RTR-GL-032 | RTR-GL-032 | RTR-GL-032 - Functional |  |  |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-06-13 14:07 | 2021-10-25 13:26 |  | CSTONE Sprint 1 | 1A+1B |  |  |  | RTR-GL | RTR | Configuration
User Story | CSTONE-88 | RTR-GL-034 | RTR-GL-034 | RTR-GL-034 - Functional |  |  |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-06-13 14:07 | 2021-07-08 14:57 |  | CSTONE Sprint 1 | 1A+1B |  |  |  | RTR-GL | RTR | Configuration
User Story | CSTONE-89 | RTR-GL-061 | RTR-GL-061 | RTR-GL-061 - Functional |  |  |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-06-13 14:07 | 2021-10-25 13:26 |  | CSTONE Sprint 1 | 1A+1B |  |  |  | RTR-GL | RTR | Configuration
User Story | CSTONE-90 | RTR-GL-067 | RTR-GL-067 | RTR-GL-067 - Functional |  |  |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-06-13 14:07 | 2021-10-25 13:26 |  | CSTONE Sprint 1 | 1A+1B |  |  |  | RTR-GL | RTR | Configuration
User Story | CSTONE-91 | RTR-GL-068 | RTR-GL-068 | RTR-GL-068 - Functional |  |  |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-06-13 14:07 | 2021-10-25 13:26 |  | CSTONE Sprint 1 | 1A+1B |  |  |  | RTR-GL | RTR | Configuration
User Story | CSTONE-92 | RTR-GL-069 | RTR-GL-069 | RTR-GL-069 - Functional |  |  |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-06-13 14:07 | 2021-10-25 13:26 |  | CSTONE Sprint 1 | 1A+1B |  |  |  | RTR-GL | RTR | Configuration
User Story | CSTONE-93 | RTR-GL-070 | RTR-GL-070 | RTR-GL-070 - Functional |  |  |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-06-13 14:07 | 2021-10-25 13:26 |  | CSTONE Sprint 1 | 1A+1B |  |  |  | RTR-GL | RTR | Configuration
User Story | CSTONE-94 | RTR-GL-071 | RTR-GL-071 | RTR-GL-071 - Functional |  |  |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-06-13 14:07 | 2021-07-08 14:52 |  | CSTONE Sprint 1 | 1A+1B |  |  |  | RTR-GL | RTR | Configuration
User Story | CSTONE-95 | RTR-GL-072 | RTR-GL-072 | RTR-GL-072 - Functional |  |  |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-06-13 14:07 | 2021-07-08 14:52 |  | CSTONE Sprint 1 | 1A+1B |  |  |  | RTR-GL | RTR | Configuration
User Story | CSTONE-96 | RTR-GL-073 | RTR-GL-073 | RTR-GL-073 - Functional |  |  |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-06-13 14:07 | 2021-10-25 13:27 |  | CSTONE Sprint 1 | 1A+1B |  |  |  | RTR-GL | RTR | Configuration
User Story | CSTONE-97 | RTR-GL-079 | RTR-GL-079 | RTR-GL-079 - Functional |  |  |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-06-13 14:07 | 2021-10-25 13:27 |  | CSTONE Sprint 1 | 1A+1B |  |  |  | RTR-GL | RTR | Configuration
User Story | CSTONE-98 | RTR-GL-082 | RTR-GL-082 | RTR-GL-082 - Functional |  |  |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-06-13 14:07 | 2021-10-25 13:26 |  | CSTONE Sprint 1 | 1A+1B |  |  |  | RTR-GL | RTR | Configuration
User Story | CSTONE-99 | RTR-GL-083 | RTR-GL-083 | RTR-GL-083 - Functional |  |  |  |  | Mehul Kumar Patel |  | In Progress |  | 2021-06-13 14:07 | 2021-07-08 15:15 |  |  | 1B |  |  |  | RTR-GL | RTR | Configuration
User Story | CSTONE-100 | RTR-GL-085 | RTR-GL-085 | RTR-GL-085 - Functional |  |  |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-06-13 14:07 | 2021-10-25 13:26 |  | CSTONE Sprint 1 | 1A+1B |  |  |  | RTR-GL | RTR | Configuration
User Story | CSTONE-103 | RTR-GL-092 | RTR-GL-092 | RTR-GL-092 - Functional |  |  |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-06-13 14:07 | 2021-10-25 13:27 |  | CSTONE Sprint 1 | 1A+1B |  |  |  | RTR-GL | RTR | Configuration
User Story | CSTONE-104 | RTR-GL-093 | RTR-GL-093 | RTR-GL-093 - Functional |  |  |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-06-13 14:07 | 2021-10-25 16:51 |  | CSTONE Sprint 1 | 1A+1B |  |  |  | RTR-GL | RTR | Configuration
User Story | CSTONE-105 | RTR-GL-094 | RTR-GL-094 | RTR-GL-094 - Functional |  |  |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-06-13 14:07 | 2021-10-25 13:27 |  | CSTONE Sprint 1 | 1A+1B |  |  |  | RTR-GL | RTR | Configuration
User Story | CSTONE-108 | RTR-GL-096 | RTR-GL-096 | RTR-GL-096 - Functional |  |  |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-06-13 14:07 | 2021-10-25 13:26 |  | CSTONE Sprint 1 | 1A+1B |  |  |  | RTR-GL | RTR | Configuration
User Story | CSTONE-109 | RTR-GL-097 | RTR-GL-097 | RTR-GL-097 - Functional |  |  |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-06-13 14:07 | 2021-10-25 13:26 |  | CSTONE Sprint 1 | 1A+1B |  |  |  | RTR-GL | RTR | Configuration
User Story | CSTONE-111 | RTR-GL-099 | RTR-GL-099 | RTR-GL-099 - Functional |  |  |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-06-13 14:07 | 2021-10-25 13:26 |  | CSTONE Sprint 1 | 1A+1B |  |  |  | RTR-GL | RTR | Configuration
User Story | CSTONE-110 | RTR-GL-098 | RTR-GL-098 | RTR-GL-098 - Functional |  |  |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-06-13 14:07 | 2021-10-25 13:26 |  | CSTONE Sprint 1 | 1A+1B |  |  |  | RTR-GL | RTR | Configuration
User Story | CSTONE-116 | RTR-GL-114 | RTR-GL-114 | RTR-GL-114 - Functional |  |  |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-06-13 14:07 | 2021-10-25 13:27 |  | CSTONE Sprint 1 | 1A+1B |  |  |  | RTR-GL | RTR | Configuration
User Story | CSTONE-117 | RTR-GL-116 | RTR-GL-116 | RTR-GL-116 - Functional |  |  |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-06-13 14:07 | 2021-10-25 13:27 |  | CSTONE Sprint 1 | 1A+1B |  |  |  | RTR-GL | RTR | Configuration
User Story | CSTONE-46 | RTR-AHCS-007 - Technical | RTR-AHCS-007 |  | RTR-AHCS-007 - Technical |  |  | Devang Pandya | Mehul Kumar Patel |  | Done | Fixed | 2021-06-13 14:07 | 2021-08-12 20:19 |  | CSTONE Sprint 3 | 1A |  |  | INT005 | RTR-AHCS | RTR | Build
User Story | CSTONE-47 | RTR-AHCS-008 - Technical | RTR-AHCS-008 |  | RTR-AHCS-008 - Technical |  |  | Devang Pandya | Mehul Kumar Patel |  | Done | Fixed | 2021-06-13 14:07 | 2021-08-13 14:18 |  | CSTONE Sprint 3 | 1A |  |  | INT002 | RTR-AHCS | RTR | Build
User Story | CSTONE-48 | RTR-AHCS-009 - Technical | RTR-AHCS-009 |  | RTR-AHCS-009 - Technical |  |  | Devang Pandya | Mehul Kumar Patel |  | Done | Fixed | 2021-06-13 14:07 | 2021-08-10 20:51 |  | CSTONE Sprint 3 | 1A |  |  | INT004 | RTR-AHCS | RTR | Build
User Story | CSTONE-49 | RTR-AHCS-026 - Technical | RTR-AHCS-026 |  | RTR-AHCS-026 - Technical |  |  | Preetansh Singh Thakur | Mehul Kumar Patel |  | Done | Fixed | 2021-06-13 14:07 | 2021-08-13 11:40 |  | CSTONE Sprint 3 | 1A+1B |  |  | RPT006 | RTR-AHCS | RTR | Build
User Story | CSTONE-50 | RTR-GL-119 - Technical | RTR-GL-119 |  | RTR-GL-119 - Technical |  |  | Harshit Gangwar | Mehul Kumar Patel |  | Done | Fixed | 2021-06-13 14:07 | 2021-09-16 17:07 |  | CSTONE Sprint 4 | 1A |  |  | CNV001 | RTR-GL | RTR | Build
User Story | CSTONE-60 | RTR-GL-124 - Technical | RTR-GL-124 |  | RTR-GL-124 - Technical |  |  | Devang Pandya | Mehul Kumar Patel |  | Done | Fixed | 2021-06-13 14:07 | 2021-08-06 19:39 |  | CSTONE Sprint 2 | 1A+1B |  |  | EXT001 | RTR-GL | RTR | Build
User Story | CSTONE-61 | RTR-GL-125 - Technical | RTR-GL-125 |  | RTR-GL-125 - Technical |  |  | Devang Pandya | Mehul Kumar Patel |  | Done | Fixed | 2021-06-13 14:07 | 2021-08-06 19:39 |  | CSTONE Sprint 2 | 1A+1B |  |  | EXT002 | RTR-GL | RTR | Build
User Story | CSTONE-65 | RTR-GL-126 - Technical | RTR-GL-126 |  | RTR-GL-126 - Technical |  |  |  | Mehul Kumar Patel |  | Not Started |  | 2021-06-13 14:07 | 2021-08-12 15:34 |  |  | 1B |  |  |  | RTR-GL | RTR | Build
User Story | CSTONE-66 | RTR-GL-127 - Technical | RTR-GL-127 |  | RTR-GL-127 - Technical |  |  | Omkar Samvatsar | Mehul Kumar Patel |  | Done | Fixed | 2021-06-13 14:07 | 2021-09-03 16:28 |  | CSTONE Sprint 3 | 1A+1B |  |  | INT120 | RTR-GL | RTR | Build
User Story | CSTONE-69 | RTR-GL-128 - Technical | RTR-GL-128 |  | RTR-GL-128 - Technical |  |  | gsansanwal | Mehul Kumar Patel |  | De-scoped |  | 2021-06-13 14:07 | 2021-08-09 19:26 |  | CSTONE Sprint 2 | 1A+1B |  |  | INT121 | RTR-GL | RTR | Build
User Story | CSTONE-70 | RTR-GL-129 - Technical | RTR-GL-129 |  | RTR-GL-129 - Technical |  |  | gsansanwal | Mehul Kumar Patel |  | De-scoped |  | 2021-06-13 14:07 | 2021-09-07 22:49 |  | CSTONE Sprint 3 | 1A+1B |  |  | EXT004 | RTR-GL | RTR | Build
User Story | CSTONE-74 | RTR-GL-137 - Technical | RTR-GL-137 |  | RTR-GL-137 - Technical |  |  | Preetansh Singh Thakur | Mehul Kumar Patel |  | Done | Fixed | 2021-06-13 14:07 | 2021-09-16 17:46 |  | CSTONE Sprint 4 | 1A |  |  | INT010 | RTR-GL | RTR | Build
User Story | CSTONE-75 | RTR-GL-139 - Technical | RTR-GL-139 |  | RTR-GL-139 - Technical |  |  | Preetansh Singh Thakur | Mehul Kumar Patel |  | Done | Fixed | 2021-06-13 14:07 | 2021-09-16 17:47 |  | CSTONE Sprint 4 | 1A |  |  | INT011 | RTR-GL | RTR | Build
User Story | CSTONE-76 | RTR-GL-147 - Technical | RTR-GL-147 |  | RTR-GL-147 - Technical |  |  | Devang Pandya | Mehul Kumar Patel |  | Done | Fixed | 2021-06-13 14:07 | 2021-08-30 17:26 |  | CSTONE Sprint 3 | 1A+1B |  |  | EXT014 | RTR-GL | RTR | Build
User Story | CSTONE-77 | RTR-AHCS-007 - Functional | RTR-AHCS-007 | RTR-AHCS-007 - Functional |  |  |  | Avinash Bandla | Mehul Kumar Patel |  | Done | Fixed | 2021-06-13 14:07 | 2021-07-09 22:28 |  | CSTONE Sprint 1 | 1A |  |  | INT005 | RTR-AHCS | RTR | Build
User Story | CSTONE-101 | RTR-AHCS-008 - Functional | RTR-AHCS-008 | RTR-AHCS-008 - Functional |  |  |  | Avinash Bandla | Mehul Kumar Patel |  | Done | Fixed | 2021-06-13 14:07 | 2021-10-28 16:22 |  | CSTONE Sprint 1 | 1A |  |  | INT002 | RTR-AHCS | RTR | Build
User Story | CSTONE-102 | RTR-AHCS-009 - Functional | RTR-AHCS-009 | RTR-AHCS-009 - Functional |  |  |  | Avinash Bandla | Mehul Kumar Patel |  | Done | Fixed | 2021-06-13 14:07 | 2021-08-05 15:14 |  | CSTONE Sprint 1 | 1A |  |  | INT004 | RTR-AHCS | RTR | Build
User Story | CSTONE-106 | RTR-AHCS-026 - Functional | RTR-AHCS-026 | RTR-AHCS-026 - Functional |  |  |  | Avinash Bandla | Mehul Kumar Patel |  | Done | Fixed | 2021-06-13 14:07 | 2021-07-28 06:36 |  | CSTONE Sprint 1 | 1A+1B |  |  | RPT006 | RTR-AHCS | RTR | Build
User Story | CSTONE-107 | RTR-GL-119 - Functional | RTR-GL-119 | RTR-GL-119 - Functional |  |  |  | Andres Romero | Mehul Kumar Patel |  | Done | Fixed | 2021-06-13 14:07 | 2021-07-13 12:01 |  | CSTONE Sprint 2 | 1A |  |  | CNV001 | RTR-GL | RTR | Build
User Story | CSTONE-115 | RTR-GL-124 - Functional | RTR-GL-124 | RTR-GL-124 - Functional |  |  |  | Omkar Samvatsar | Mehul Kumar Patel |  | Done | Fixed | 2021-06-13 14:07 | 2021-07-08 14:47 |  | CSTONE Sprint 1 | 1A+1B |  |  | EXT001 | RTR-GL | RTR | Build
User Story | CSTONE-118 | RTR-GL-125 - Functional | RTR-GL-125 | RTR-GL-125 - Functional |  |  |  | Omkar Samvatsar | Mehul Kumar Patel |  | Done | Fixed | 2021-06-13 14:07 | 2021-07-14 17:44 |  | CSTONE Sprint 1 | 1A+1B |  |  | EXT002 | RTR-GL | RTR | Build
User Story | CSTONE-119 | RTR-GL-126 - Functional | RTR-GL-126 | RTR-GL-126 - Functional |  |  |  |  | Mehul Kumar Patel |  | De-scoped |  | 2021-06-13 14:07 | 2021-10-11 09:41 |  |  | 1B |  |  | EXT003 | RTR-GL | RTR | Build
User Story | CSTONE-120 | RTR-GL-127 - Functional | RTR-GL-127 | RTR-GL-127 - Functional |  |  |  | Omkar Samvatsar | Mehul Kumar Patel |  | Done | Fixed | 2021-06-13 14:07 | 2021-07-14 17:45 |  | CSTONE Sprint 1 | 1A+1B |  |  | INT120 | RTR-GL | RTR | Build
User Story | CSTONE-121 | RTR-GL-128 - Functional | RTR-GL-128 | RTR-GL-128 - Functional |  |  |  | Omkar Samvatsar | Mehul Kumar Patel |  | De-scoped | Fixed | 2021-06-13 14:07 | 2021-08-09 19:27 |  | CSTONE Sprint 1 | 1A+1B |  |  | INT121 | RTR-GL | RTR | Build
User Story | CSTONE-122 | RTR-GL-129 - Functional | RTR-GL-129 | RTR-GL-129 - Functional |  |  |  | Omkar Samvatsar | Mehul Kumar Patel |  | De-scoped | Fixed | 2021-06-13 14:07 | 2021-08-09 22:15 |  | CSTONE Sprint 1 | 1A+1B |  |  | EXT004 | RTR-GL | RTR | Build
User Story | CSTONE-123 | RTR-GL-137 - Functional | RTR-GL-137 | RTR-GL-137 - Functional |  |  |  | bbinkhalid | Mehul Kumar Patel |  | Done | Fixed | 2021-06-13 14:07 | 2021-07-08 15:53 |  | CSTONE Sprint 1 | 1A |  |  | INT010 | RTR-GL | RTR | Build
User Story | CSTONE-124 | RTR-GL-139 - Functional | RTR-GL-139 | RTR-GL-139 - Functional |  |  |  | yuvs | Mehul Kumar Patel |  | Done | Fixed | 2021-06-13 14:07 | 2021-07-09 17:20 |  | CSTONE Sprint 1 | 1A |  |  | INT011 | RTR-GL | RTR | Build
User Story | CSTONE-125 | RTR-GL-147 - Functional | RTR-GL-147 | RTR-GL-147 - Functional |  |  |  | Omkar Samvatsar | Mehul Kumar Patel |  | Done | Fixed | 2021-06-13 14:07 | 2021-07-08 14:45 |  | CSTONE Sprint 1 | 1A+1B |  |  | EXT014 | RTR-GL | RTR | Build
User Story | CSTONE-431 | RTR-AHCS-043 - Functional | RTR-AHCS-043 | RTR-AHCS-043 - Functional |  |  |  | Omkar Samvatsar | Mehul Kumar Patel | Not yet prioritized | Done | Fixed | 2021-06-30 18:09 | 2021-07-21 17:28 |  | CSTONE Sprint 2 | 1A |  |  | INT120 | RTR-GL | RTR | Build
User Story | CSTONE-434 | RTR-AHCS-065 - Functional | RTR-AHCS-065 | RTR-AHCS-065 - Functional |  |  |  | Avinash Bandla | Mehul Kumar Patel | Not yet prioritized | Done | Fixed | 2021-06-30 18:20 | 2021-07-13 20:31 |  | CSTONE Sprint 1 | 1A |  |  | INT122 | RTR-AHCS | RTR | Build
User Story | CSTONE-511 | RTR-AHCS-043 - Technical | RTR-AHCS-043 |  | RTR-AHCS-043 - Technical |  |  | Omkar Samvatsar | Mehul Kumar Patel | Not yet prioritized | Done | Fixed | 2021-07-09 14:45 | 2021-09-03 16:29 |  | CSTONE Sprint 3 | 1A |  |  | INT120 | RTR-GL | RTR | Build
User Story | CSTONE-517 | RTR-GL-001 | RTR-GL-001 | RTR-GL-001 - Functional |  |  |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-07-12 16:59 | 2021-10-25 13:27 |  | CSTONE Sprint 2 | 1A+1B |  |  |  | RTR-GL | RTR | Configuration
User Story | CSTONE-518 | RTR-GL-002 | RTR-GL-002 | RTR-GL-002 - Functional |  |  |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-07-12 16:59 | 2021-10-25 13:26 |  | CSTONE Sprint 2 | 1A+1B |  |  |  | RTR-GL | RTR | Configuration
User Story | CSTONE-519 | RTR-GL-003 | RTR-GL-003 | RTR-GL-003 - Functional |  |  |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-07-12 16:59 | 2021-07-23 20:40 |  | CSTONE Sprint 2 | 1A+1B |  |  |  | RTR-GL | RTR | Configuration
User Story | CSTONE-520 | RTR-GL-004 | RTR-GL-004 | RTR-GL-004 - Functional |  |  |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-07-12 16:59 | 2021-10-25 13:27 |  | CSTONE Sprint 2 | 1A+1B |  |  |  | RTR-GL | RTR | Configuration
User Story | CSTONE-521 | RTR-GL-027 | RTR-GL-027 | RTR-GL-027 - Functional |  |  |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-07-12 16:59 | 2021-10-25 13:26 |  | CSTONE Sprint 2 | 1A+1B |  |  |  | RTR-GL | RTR | Configuration
User Story | CSTONE-522 | RTR-GL-037 | RTR-GL-037 | RTR-GL-037 - Functional |  |  |  | gsansanwal | Mehul Kumar Patel |  | Done | Approved | 2021-07-12 16:59 | 2021-10-25 13:26 |  | CSTONE Sprint 3 | 1A+1B |  |  |  | RTR-GL | RTR | Configuration
User Story | CSTONE-523 | RTR-GL-038 | RTR-GL-038 | RTR-GL-038 - Functional |  |  |  | gsansanwal | Mehul Kumar Patel |  | Done | Approved | 2021-07-12 16:59 | 2021-10-25 13:26 |  | CSTONE Sprint 3 | 1A+1B |  |  |  | RTR-GL | RTR | Configuration
User Story | CSTONE-524 | RTR-GL-039 | RTR-GL-039 | RTR-GL-039 - Functional |  |  |  | gsansanwal | Mehul Kumar Patel |  | Done | Approved | 2021-07-12 16:59 | 2021-10-25 13:26 |  | CSTONE Sprint 3 | 1A+1B |  |  |  | RTR-GL | RTR | Configuration
User Story | CSTONE-525 | RTR-GL-040 | RTR-GL-040 | RTR-GL-040 - Functional |  |  |  | gsansanwal | Mehul Kumar Patel |  | Done | Approved | 2021-07-12 17:00 | 2021-10-25 13:26 |  | CSTONE Sprint 3 | 1A+1B |  |  |  | RTR-GL | RTR | Configuration
User Story | CSTONE-526 | RTR-GL-041 | RTR-GL-041 | RTR-GL-041 - Functional |  |  |  | gsansanwal | Mehul Kumar Patel |  | Done | Approved | 2021-07-12 17:00 | 2021-10-25 13:26 |  | CSTONE Sprint 3 | 1A+1B |  |  |  | RTR-GL | RTR | Configuration
User Story | CSTONE-527 | RTR-GL-042 | RTR-GL-042 | RTR-GL-042 - Functional |  |  |  | gsansanwal | Mehul Kumar Patel |  | Done | Approved | 2021-07-12 17:00 | 2021-10-25 13:26 |  | CSTONE Sprint 3 | 1A+1B |  |  |  | RTR-GL | RTR | Configuration
User Story | CSTONE-528 | RTR-GL-045 | RTR-GL-045 | RTR-GL-045 - Functional |  |  |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-07-12 17:00 | 2021-10-25 13:26 |  | CSTONE Sprint 2 | 1A+1B |  |  |  | RTR-GL | RTR | Configuration
User Story | CSTONE-529 | RTR-GL-046 | RTR-GL-046 | RTR-GL-046 - Functional |  |  |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-07-12 17:00 | 2021-10-25 13:26 |  | CSTONE Sprint 2 | 1A+1B |  |  |  | RTR-GL | RTR | Configuration
User Story | CSTONE-530 | RTR-GL-048 | RTR-GL-048 | RTR-GL-048 - Functional |  |  |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-07-12 17:00 | 2021-10-25 13:26 |  | CSTONE Sprint 2 | 1A+1B |  |  |  | RTR-GL | RTR | Configuration
User Story | CSTONE-531 | RTR-GL-049 | RTR-GL-049 | RTR-GL-049 - Functional |  |  |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-07-12 17:00 | 2021-10-25 13:26 |  | CSTONE Sprint 2 | 1A+1B |  |  |  | RTR-GL | RTR | Configuration
User Story | CSTONE-532 | RTR-GL-054 | RTR-GL-054 | RTR-GL-054 - Functional |  |  |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-07-12 17:00 | 2021-10-25 13:26 |  | CSTONE Sprint 2 | 1A+1B |  |  |  | RTR-GL | RTR | Configuration
User Story | CSTONE-533 | RTR-GL-055 | RTR-GL-055 | RTR-GL-055 - Functional |  |  |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-07-12 17:00 | 2021-10-25 13:27 |  | CSTONE Sprint 2 | 1A+1B |  |  |  | RTR-GL | RTR | Configuration
User Story | CSTONE-534 | RTR-GL-056 | RTR-GL-056 | RTR-GL-056 - Functional |  |  |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-07-12 17:00 | 2021-10-25 13:26 |  | CSTONE Sprint 2 | 1A+1B |  |  |  | RTR-GL | RTR | Configuration
User Story | CSTONE-535 | RTR-GL-062 | RTR-GL-062 | RTR-GL-062 - Functional |  |  |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-07-12 17:00 | 2021-10-25 13:27 |  | CSTONE Sprint 2 | 1A+1B |  |  |  | RTR-GL | RTR | Configuration
User Story | CSTONE-536 | RTR-GL-063 | RTR-GL-063 | RTR-GL-063 - Functional |  |  |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-07-12 17:00 | 2021-10-25 13:27 |  | CSTONE Sprint 2 | 1A+1B |  |  |  | RTR-GL | RTR | Configuration
User Story | CSTONE-537 | RTR-GL-065 | RTR-GL-065 | RTR-GL-065 - Functional |  |  |  | Omkar Samvatsar | Mehul Kumar Patel |  | Done | Fixed | 2021-07-12 17:00 | 2021-10-25 13:26 |  | CSTONE Sprint 2 | 1A+1B |  |  |  | RTR-GL | RTR | Configuration
User Story | CSTONE-538 | RTR-GL-078 | RTR-GL-078 | RTR-GL-078 - Functional |  |  |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-07-12 17:00 | 2021-10-25 13:27 |  | CSTONE Sprint 2 | 1A+1B |  |  |  | RTR-GL | RTR | Configuration
User Story | CSTONE-539 | RTR-GL-086 | RTR-GL-086 | RTR-GL-086 - Functional |  |  |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-07-12 17:00 | 2021-10-25 13:26 |  | CSTONE Sprint 2 | 1A+1B |  |  |  | RTR-GL | RTR | Configuration
User Story | CSTONE-540 | RTR-GL-087 | RTR-GL-087 | RTR-GL-087 - Functional |  |  |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-07-12 17:00 | 2021-10-25 13:26 |  | CSTONE Sprint 2 | 1A+1B |  |  |  | RTR-GL | RTR | Configuration
User Story | CSTONE-541 | RTR-GL-101 | RTR-GL-101 | RTR-GL-101 - Functional |  |  |  | gsansanwal | Mehul Kumar Patel |  | Done | Approved | 2021-07-12 17:00 | 2021-09-01 23:00 |  | CSTONE Sprint 3 | 1A+1B |  |  |  | RTR-GL | RTR | Configuration
User Story | CSTONE-542 | RTR-GL-103 | RTR-GL-103 | RTR-GL-103 - Functional |  |  |  | gsansanwal | Mehul Kumar Patel |  | Done | Approved | 2021-07-12 17:00 | 2021-10-25 13:27 |  | CSTONE Sprint 3 | 1A+1B |  |  |  | RTR-GL | RTR | Configuration
User Story | CSTONE-543 | RTR-GL-104 | RTR-GL-104 | RTR-GL-104 - Functional |  |  |  | Sindhura Yalamanchili | Mehul Kumar Patel |  | Done | Fixed | 2021-07-12 17:00 | 2021-10-25 13:26 |  | CSTONE Sprint 4 | 1A+1B |  |  |  | Security | S&C | Configuration
User Story | CSTONE-544 | RTR-GL-108 | RTR-GL-108 | RTR-GL-108 - Functional |  |  |  | Sindhura Yalamanchili | Mehul Kumar Patel |  | Done | Fixed | 2021-07-12 17:00 | 2021-10-25 13:26 |  | CSTONE Sprint 5 | 1A+1B |  |  |  | Security | S&C | Configuration
User Story | CSTONE-545 | RTR-GL-109 | RTR-GL-109 | RTR-GL-109 - Functional |  |  |  | Sindhura Yalamanchili | Mehul Kumar Patel |  | In Progress |  | 2021-07-12 17:00 | 2021-10-25 13:26 |  | CSTONE Sprint 5 | 1A+1B |  |  |  | Security | S&C | Configuration
User Story | CSTONE-546 | REP-RTR-GL-61 | REP-RTR-GL-61 | REP-RTR-GL-61 - Functional |  |  |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-07-12 17:00 | 2021-10-25 13:26 |  | CSTONE Sprint 2 | 1A |  |  |  | RTR-GL | RTR | Configuration
User Story | CSTONE-547 | REP-RTR-GL-62 | REP-RTR-GL-62 | REP-RTR-GL-62 - Functional |  |  |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-07-12 17:00 | 2021-10-25 13:27 |  | CSTONE Sprint 2 | 1A |  |  |  | RTR-GL | RTR | Configuration
User Story | CSTONE-548 | REP-RTR-GL-64 | REP-RTR-GL-64 | REP-RTR-GL-64 - Functional |  |  |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-07-12 17:00 | 2021-10-25 13:27 |  | CSTONE Sprint 2 | 1A |  |  |  | RTR-GL | RTR | Configuration
User Story | CSTONE-549 | REP-RTR-GL-80 | REP-RTR-GL-80 | REP-RTR-GL-80 - Functional |  |  |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-07-12 17:00 | 2021-10-25 13:27 |  | CSTONE Sprint 2 | 1A |  |  |  | RTR-GL | RTR | Configuration
User Story | CSTONE-550 | RTR-AHCS-003 | RTR-AHCS-003 | RTR-AHCS-003 - Functional |  |  |  | Avinash Bandla | Mehul Kumar Patel |  | Done | Fixed | 2021-07-12 17:00 | 2021-07-23 20:23 |  | CSTONE Sprint 2 | 1A+1B |  |  |  | RTR-AHCS | RTR | Configuration
User Story | CSTONE-551 | RTR-AHCS-006 | RTR-AHCS-006 | RTR-AHCS-006 - Functional |  |  |  | Manosh Kumar | Mehul Kumar Patel |  | Done | Fixed | 2021-07-12 17:00 | 2021-07-23 20:22 |  | CSTONE Sprint 2 | 1A+1B |  |  |  | RTR-AHCS | RTR | Configuration
User Story | CSTONE-552 | RTR-AHCS-028 | RTR-AHCS-028 | RTR-AHCS-028 - Functional |  |  |  | Avinash Bandla | Mehul Kumar Patel |  | Done | Fixed | 2021-07-12 17:00 | 2021-10-25 13:27 |  | CSTONE Sprint 2 | 1A+1B |  |  |  | RTR-AHCS | RTR | Configuration
User Story | CSTONE-553 | RTR-GL-113 | RTR-GL-113 | RTR-GL-113 - Functional |  |  |  | gsansanwal | Mehul Kumar Patel |  | Done | Approved | 2021-07-12 17:00 | 2021-10-25 13:27 |  | CSTONE Sprint 3 | 1A+1B |  |  |  | RTR-GL | RTR | Configuration
User Story | CSTONE-554 | RTR-AHCS-052 | RTR-AHCS-052 | RTR-AHCS-052 - Functional |  |  |  | Amit Dubey | Mehul Kumar Patel |  | Done | Fixed | 2021-07-12 17:00 | 2021-07-28 02:42 |  | CSTONE Sprint 2 | 1A |  |  |  | RTR-AHCS | RTR | Configuration
User Story | CSTONE-555 | RTR-AHCS-053 | RTR-AHCS-053 | RTR-AHCS-053 - Functional |  |  |  | Amit Dubey | Mehul Kumar Patel |  | Done | Fixed | 2021-07-12 17:00 | 2021-10-25 13:27 |  | CSTONE Sprint 2 | 1A+1B |  |  |  | RTR-AHCS | RTR | Configuration
User Story | CSTONE-556 | RTR-GL-150 | RTR-GL-150 | RTR-GL-150 - Functional |  |  |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-07-12 17:00 | 2021-10-25 13:26 |  | CSTONE Sprint 2 | 1A |  |  |  | RTR-GL | RTR | Configuration
User Story | CSTONE-557 | RTR-AHCS-048 | RTR-AHCS-048 | RTR-AHCS-048 - Functional |  |  |  | Avinash Bandla | Mehul Kumar Patel |  | Done | Fixed | 2021-07-12 17:00 | 2021-07-23 20:22 |  | CSTONE Sprint 2 | 1A+1B |  |  |  | RTR-AHCS | RTR | Configuration
User Story | CSTONE-559 | RTR-GL-035 | RTR-GL-035 | RTR-GL-035 - Functional |  |  |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-07-13 13:45 | 2021-08-05 16:18 |  | CSTONE Sprint 2 | 1A+1B |  |  |  | RTR-GL | RTR | Work Around
User Story | CSTONE-560 | RTR-GL-036 | RTR-GL-036 | RTR-GL-036 - Functional |  |  |  | gsansanwal | Mehul Kumar Patel |  | Done | Done | 2021-07-13 13:45 | 2021-08-05 01:18 |  | CSTONE Sprint 2 | 1A+1B |  |  |  | RTR-GL | RTR | Work Around
User Story | CSTONE-561 | RTR-GL-050 | RTR-GL-050 | RTR-GL-050 - Functional |  |  |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-07-13 13:45 | 2021-08-05 16:13 |  | CSTONE Sprint 2 | 1A+1B |  |  |  | RTR-GL | RTR | Work Around
User Story | CSTONE-562 | RTR-GL-089 - Technical | RTR-GL-089 |  | RTR-GL-089 - Technical |  |  | Harshit Gangwar | Mehul Kumar Patel |  | Done | Fixed | 2021-07-13 13:45 | 2021-09-16 17:06 |  | CSTONE Sprint 4 | 1A+1B |  |  | CNV001 | RTR-GL | RTR | Build
User Story | CSTONE-568 | RTR-AHCS-031 | RTR-AHCS-031 | RTR-AHCS-031 - Functional |  |  |  | Avinash Bandla | Mehul Kumar Patel |  | Done | Fixed | 2021-07-13 13:45 | 2021-07-26 05:57 |  | CSTONE Sprint 2 | 1A+1B |  |  |  | RTR-AHCS | RTR | Work Around
User Story | CSTONE-566 | RTR-AHCS-010 - Functional | RTR-AHCS-010 | RTR-AHCS-010 - Functional |  |  |  | Aashutosh Kumar Upadhyay | Mehul Kumar Patel |  | Done | Fixed | 2021-07-13 13:45 | 2021-08-05 14:42 |  | CSTONE Sprint 2 | 1A |  |  | INT033 | RTR-AHCS | RTR | Build
User Story | CSTONE-623 | RTR-AHCS-010 - Technical | RTR-AHCS-010 |  | RTR-AHCS-010 - Technical |  |  | Devang Pandya | Mehul Kumar Patel |  | Done | Fixed | 2021-07-13 13:46 | 2021-09-24 17:41 |  | CSTONE Sprint 4 | 1A |  |  | INT033 | RTR-AHCS | RTR | Build
User Story | CSTONE-624 | RTR-AHCS-036 - Technical | RTR-AHCS-036 |  | RTR-AHCS-036 - Technical |  |  | Devang Pandya | Mehul Kumar Patel |  | Done | Fixed | 2021-07-13 13:46 | 2021-09-24 17:42 |  | CSTONE Sprint 4 | 1A |  |  | INT033 | RTR-AHCS | RTR | Build
User Story | CSTONE-625 | RTR-AHCS-037 - Technical | RTR-AHCS-037 |  | RTR-AHCS-037 - Technical |  |  |  | Mehul Kumar Patel |  | De-scoped |  | 2021-07-13 13:46 | 2021-09-30 20:17 |  | CSTONE Sprint 2 | 1A |  |  | INT034 | RTR-AHCS | RTR | Build
User Story | CSTONE-569 | RTR-AHCS-036 - Functional | RTR-AHCS-036 | RTR-AHCS-036 - Functional |  |  |  | Avinash Bandla | Mehul Kumar Patel |  | Done | Fixed | 2021-07-13 13:45 | 2021-08-05 14:41 |  | CSTONE Sprint 2 | 1A |  |  | INT033 | RTR-AHCS | RTR | Build
User Story | CSTONE-570 | RTR-AHCS-037 - Functional | RTR-AHCS-037 | RTR-AHCS-037 - Functional |  |  |  | Manpreet Singh | Mehul Kumar Patel |  | De-scoped |  | 2021-07-13 13:45 | 2021-09-07 22:51 |  | CSTONE Sprint 3 | 1A |  |  | INT034 | RTR-AHCS | RTR | Build
User Story | CSTONE-571 | RTR-AHCS-038 - Functional | RTR-AHCS-038 | RTR-AHCS-038 - Functional |  |  |  | Manosh Kumar | Mehul Kumar Patel |  | De-scoped |  | 2021-07-13 13:45 | 2021-09-08 06:20 |  | CSTONE Sprint 3 | 1A |  |  | INT035 | RTR-AHCS | RTR | Build
User Story | CSTONE-572 | RTR-AHCS-039 - Functional | RTR-AHCS-039 | RTR-AHCS-039 - Functional |  |  |  | Aashutosh Kumar Upadhyay | Mehul Kumar Patel |  | De-scoped |  | 2021-07-13 13:45 | 2021-09-07 22:52 |  | CSTONE Sprint 3 | 1A |  |  | INT036 | RTR-AHCS | RTR | Build
User Story | CSTONE-573 | RTR-AHCS-040 - Functional | RTR-AHCS-040 | RTR-AHCS-040 - Functional |  |  |  | Manosh Kumar | Mehul Kumar Patel |  | De-scoped |  | 2021-07-13 13:45 | 2021-09-07 22:53 |  | CSTONE Sprint 3 | 1A |  |  | INT037 | RTR-AHCS | RTR | Build
User Story | CSTONE-626 | RTR-AHCS-038 - Technical | RTR-AHCS-038 |  | RTR-AHCS-038 - Technical |  |  |  | Mehul Kumar Patel |  | De-scoped |  | 2021-07-13 13:46 | 2021-09-30 20:17 |  | CSTONE Sprint 3 | 1A |  |  | INT035 | RTR-AHCS | RTR | Build
User Story | CSTONE-581 | RTR-GL-010 - Functional | RTR-GL-010 | RTR-GL-010 - Functional |  |  |  | bbinkhalid | Mehul Kumar Patel |  | Done | Fixed | 2021-07-13 13:46 | 2021-07-26 08:17 |  | CSTONE Sprint 2 | 1A+1B |  |  | RPT002 | RTR-GL | RTR | Build
User Story | CSTONE-582 | RTR-GL-017 - Functional | RTR-GL-017 | RTR-GL-017 - Functional |  |  |  | Andres Romero | Mehul Kumar Patel |  | Done | Fixed | 2021-07-13 13:46 | 2021-08-03 11:59 |  | CSTONE Sprint 2 | 1A+1B |  |  | RPT004 | RTR-GL | RTR | Build
User Story | CSTONE-583 | RTR-GL-018 - Functional | RTR-GL-018 | RTR-GL-018 - Functional |  |  |  | Andres Romero | Mehul Kumar Patel |  | Done | Fixed | 2021-07-13 13:46 | 2021-08-03 11:59 |  | CSTONE Sprint 2 | 1A+1B |  |  | RPT004 | RTR-GL | RTR | Build
User Story | CSTONE-584 | RTR-GL-077 - Functional | RTR-GL-077 | RTR-GL-077 - Functional |  |  |  | Vishnu M Menon | Mehul Kumar Patel |  | Done | Fixed | 2021-07-13 13:46 | 2021-08-06 18:41 |  | CSTONE Sprint 2 | 1A+1B |  |  | RPT009 | RTR-AHCS | RTR | Build
User Story | CSTONE-585 | RTR-GL-090 - Functional | RTR-GL-090 | RTR-GL-090 - Functional |  |  |  | Andres Romero | Mehul Kumar Patel |  | Done | Fixed | 2021-07-13 13:46 | 2021-08-06 12:27 |  | CSTONE Sprint 2 | 1A+1B |  |  | RPT041 | RTR-GL | RTR | Build
User Story | CSTONE-586 | REP-RTR-GL-63 - Functional | REP-RTR-GL-63 | REP-RTR-GL-63 - Functional |  |  |  | bbinkhalid | Mehul Kumar Patel |  | Done | Fixed | 2021-07-13 13:46 | 2021-07-26 08:08 |  | CSTONE Sprint 2 | 1A |  |  | RPT002 | RTR-GL | RTR | Build
User Story | CSTONE-587 | RTR-AHCS-015 - Functional | RTR-AHCS-015 | RTR-AHCS-015 - Functional |  |  |  | Omkar Samvatsar | Mehul Kumar Patel |  | Done | Fixed | 2021-07-13 13:46 | 2021-07-23 02:51 |  | CSTONE Sprint 2 | 1A |  |  | EXT007 | RTR-GL | RTR | Build
User Story | CSTONE-588 | RTR-AHCS-016 - Functional | RTR-AHCS-016 | RTR-AHCS-016 - Functional |  |  |  | Omkar Samvatsar | Mehul Kumar Patel |  | Done | Fixed | 2021-07-13 13:46 | 2021-07-23 02:53 |  | CSTONE Sprint 2 | 1A |  |  | EXT007 | RTR-GL | RTR | Build
User Story | CSTONE-589 | RTR-AHCS-017 - Functional | RTR-AHCS-017 | RTR-AHCS-017 - Functional |  |  |  | Omkar Samvatsar | Mehul Kumar Patel |  | Done | Fixed | 2021-07-13 13:46 | 2021-07-23 02:54 |  | CSTONE Sprint 2 | 1A+1B |  |  | EXT007 | RTR-GL | RTR | Build
User Story | CSTONE-590 | RTR-AHCS-018 - Functional | RTR-AHCS-018 | RTR-AHCS-018 - Functional |  |  |  | Omkar Samvatsar | Mehul Kumar Patel |  | Done | Fixed | 2021-07-13 13:46 | 2021-07-23 02:54 |  | CSTONE Sprint 2 | 1A |  |  | EXT007 | RTR-GL | RTR | Build
User Story | CSTONE-597 | RTR-GL-117 - Functional | RTR-GL-117 | RTR-GL-117 - Functional |  |  |  | Omkar Samvatsar | Mehul Kumar Patel |  | Done | Fixed | 2021-07-13 13:46 | 2021-07-23 02:54 |  | CSTONE Sprint 2 | 1A+1B |  |  | EXT013 | RTR-GL | RTR | Build
User Story | CSTONE-598 | RTR-AHCS-051 - Functional | RTR-AHCS-051 | RTR-AHCS-051 - Functional |  |  |  | Avinash Bandla | Mehul Kumar Patel |  | Done | Fixed | 2021-07-13 13:46 | 2021-08-03 15:47 |  | CSTONE Sprint 2 | 1A+1B |  |  | EXT010 | RTR-AHCS | RTR | Build
User Story | CSTONE-599 | REP-RTR-GL-1 - Functional | REP-RTR-GL-1 | REP-RTR-GL-1 - Functional |  |  |  | bbinkhalid | Mehul Kumar Patel |  | Done | Fixed | 2021-07-13 13:46 | 2021-07-22 14:54 |  | CSTONE Sprint 2 | 1A+1B |  |  | RPT046 | RTR-GL | RTR | Build
User Story | CSTONE-600 | REP-RTR-GL-2 - Functional | REP-RTR-GL-2 | REP-RTR-GL-2 - Functional |  |  |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-07-13 13:46 | 2021-08-09 13:43 |  | CSTONE Sprint 3 | 1A+1B |  |  | RPT047 | RTR-GL | RTR | Build
User Story | CSTONE-601 | REP-RTR-GL-4 - Functional | REP-RTR-GL-4 | REP-RTR-GL-4 - Functional |  |  |  | Vishnu M Menon | Mehul Kumar Patel |  | Done | Fixed | 2021-07-13 13:46 | 2021-08-06 18:42 |  | CSTONE Sprint 2 | 1A+1B |  |  | RPT009 | RTR-AHCS | RTR | Build
User Story | CSTONE-602 | REP-RTR-GL-7 - Functional | REP-RTR-GL-7 | REP-RTR-GL-7 - Functional |  |  |  | bbinkhalid | Mehul Kumar Patel |  | Done | Fixed | 2021-07-13 13:46 | 2021-07-22 14:54 |  | CSTONE Sprint 2 | 1A+1B |  |  | RPT046 | RTR-GL | RTR | Build
User Story | CSTONE-603 | REP-RTR-GL-8 - Functional | REP-RTR-GL-8 | REP-RTR-GL-8 - Functional |  |  |  | bbinkhalid | Mehul Kumar Patel |  | Done | Fixed | 2021-07-13 13:46 | 2021-07-22 14:54 |  | CSTONE Sprint 2 | 1A+1B |  |  | RPT046 | RTR-GL | RTR | Build
User Story | CSTONE-604 | REP-RTR-GL-9 - Functional | REP-RTR-GL-9 | REP-RTR-GL-9 - Functional |  |  |  | bbinkhalid | Mehul Kumar Patel |  | Done | Fixed | 2021-07-13 13:46 | 2021-07-22 14:55 |  | CSTONE Sprint 2 | 1A+1B |  |  | RPT046 | RTR-GL | RTR | Build
User Story | CSTONE-605 | REP-RTR-GL-10 - Functional | REP-RTR-GL-10 | REP-RTR-GL-10 - Functional |  |  |  | yuvs | Mehul Kumar Patel |  | Done | Fixed | 2021-07-13 13:46 | 2021-07-30 14:55 |  | CSTONE Sprint 2 | 1A+1B |  |  | RPT051 | RTR-GL | RTR | Build
User Story | CSTONE-606 | REP-RTR-GL-12 - Functional | REP-RTR-GL-12 | REP-RTR-GL-12 - Functional |  |  |  | yuvs | Mehul Kumar Patel |  | Done | Fixed | 2021-07-13 13:46 | 2021-07-30 14:37 |  | CSTONE Sprint 2 | 1A+1B |  |  | RPT051 | RTR-GL | RTR | Build
User Story | CSTONE-607 | REP-RTR-GL-14 - Functional | REP-RTR-GL-14 | REP-RTR-GL-14 - Functional |  |  |  | bbinkhalid | Mehul Kumar Patel |  | Done | Fixed | 2021-07-13 13:46 | 2021-10-18 14:27 |  | CSTONE Sprint 2 | 1A+1B |  |  | RPT046 | RTR-GL | RTR | Build
User Story | CSTONE-608 | REP-RTR-GL-15 - Functional | REP-RTR-GL-15 | REP-RTR-GL-15 - Functional |  |  |  | bbinkhalid | Mehul Kumar Patel |  | Done | Fixed | 2021-07-13 13:46 | 2021-07-22 14:55 |  | CSTONE Sprint 2 | 1A+1B |  |  | RPT046 | RTR-GL | RTR | Build
User Story | CSTONE-609 | REP-RTR-GL-67-A - Functional | REP-RTR-GL-67-A | REP-RTR-GL-67-A - Functional |  |  |  | Vishnu M Menon | Mehul Kumar Patel |  | Done | Fixed | 2021-07-13 13:46 | 2021-08-06 15:21 |  | CSTONE Sprint 2 | 1A |  |  | RPT046 | RTR-GL | RTR | Build
User Story | CSTONE-610 | REP-RTR-GL-67-B - Functional | REP-RTR-GL-67-B | REP-RTR-GL-67-B - Functional |  |  |  | Omkar Samvatsar | Mehul Kumar Patel |  | Done | Fixed | 2021-07-13 13:46 | 2021-07-23 02:54 |  | CSTONE Sprint 2 | 1A |  |  | EXT013 | RTR-GL | RTR | Build
User Story | CSTONE-611 | RTR-GL-133 - Functional | RTR-GL-133 | RTR-GL-133 - Functional |  |  |  | Omkar Samvatsar | Mehul Kumar Patel |  | Done | Fixed | 2021-07-13 13:46 | 2021-07-23 02:55 |  | CSTONE Sprint 2 | 1A+1B |  |  | EXT008 | RTR-GL | RTR | Build
User Story | CSTONE-612 | RTR-GL-134 - Functional | RTR-GL-134 | RTR-GL-134 - Functional |  |  |  | Omkar Samvatsar | Mehul Kumar Patel |  | Done | Fixed | 2021-07-13 13:46 | 2021-07-23 02:55 |  | CSTONE Sprint 2 | 1A+1B |  |  | EXT009 | RTR-GL | RTR | Build
User Story | CSTONE-613 | RTR-GL-135 - Functional | RTR-GL-135 | RTR-GL-135 - Functional |  |  |  | Omkar Samvatsar | Mehul Kumar Patel |  | Done | Fixed | 2021-07-13 13:46 | 2021-07-23 02:55 |  | CSTONE Sprint 2 | 1A+1B |  |  | EXT012 | RTR-GL | RTR | Build
User Story | CSTONE-614 | RTR-GL-141 - Functional | RTR-GL-141 | RTR-GL-141 - Functional |  |  |  | Manpreet Singh | Mehul Kumar Patel |  | Done | Fixed | 2021-07-13 13:46 | 2021-08-20 11:12 |  | CSTONE Sprint 3 | 1A |  |  | INT012 | RTR-AHCS | RTR | Build
User Story | CSTONE-615 | RTR-GL-143 - Functional | RTR-GL-143 | RTR-GL-143 - Functional |  |  |  | Manpreet Singh | Mehul Kumar Patel |  | Done | Fixed | 2021-07-13 13:46 | 2021-08-06 18:59 |  | CSTONE Sprint 2 | 1A |  |  | INT041 | RTR-AHCS | RTR | Build
User Story | CSTONE-616 | RTR-GL-145 - Functional | RTR-GL-145 | RTR-GL-145 - Functional |  |  |  | yuvs | Mehul Kumar Patel |  | De-scoped |  | 2021-07-13 13:46 | 2021-08-09 19:30 |  | CSTONE Sprint 2 | 1A |  |  | INT007 | RTR-GL | RTR | Build
User Story | CSTONE-617 | RTR-GL-146 - Functional | RTR-GL-146 | RTR-GL-146 - Functional |  |  |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-07-13 13:46 | 2021-08-27 02:22 |  | CSTONE Sprint 3 | 1A |  |  | INT040 | RTR-GL | RTR | Build
User Story | CSTONE-618 | REP-FSG-RTR-GL-002 - Functional | REP-FSG-RTR-GL-002 | REP-FSG-RTR-GL-002 - Functional |  |  |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-07-13 13:46 | 2021-08-26 02:21 |  | CSTONE Sprint 3 | 1A+1B |  |  | RPT053 | RTR-GL | RTR | Build
User Story | CSTONE-619 | RTR-AHCS-060 - Functional | RTR-AHCS-060 | RTR-AHCS-060 - Functional |  |  |  | Avinash Bandla | Mehul Kumar Patel |  | Done | Fixed | 2021-07-13 13:46 | 2021-07-30 00:32 |  | CSTONE Sprint 2 | 1A+1B |  |  | EXT011 | RTR-AHCS | RTR | Build
User Story | CSTONE-620 | RTR-AHCS-062 - Functional | RTR-AHCS-062 | RTR-AHCS-062 - Functional |  |  |  | shukabra | Mehul Kumar Patel |  | Done | Fixed | 2021-07-13 13:46 | 2021-08-05 17:16 |  | CSTONE Sprint 2 | 1A+1B |  |  | INT041 | RTR-AHCS | RTR | Build
User Story | CSTONE-621 | RTR-AHCS-064 - Functional | RTR-AHCS-064 | RTR-AHCS-064 - Functional |  |  |  | Manpreet Singh | Mehul Kumar Patel |  | Done | Fixed | 2021-07-13 13:46 | 2021-08-06 18:51 |  | CSTONE Sprint 2 | 1A+1B |  |  | RPT009 | RTR-AHCS | RTR | Build
User Story | CSTONE-622 | RTR-GL-151 - Functional | RTR-GL-151 | RTR-GL-151 - Functional |  |  |  | yuvs | Mehul Kumar Patel |  | Done | Fixed | 2021-07-13 13:46 | 2021-08-27 02:23 |  | CSTONE Sprint 3 | 1A |  |  | INT047 | RTR-GL | RTR | Build
User Story | CSTONE-591 | RTR-AHCS-020 - Functional | RTR-AHCS-020 | RTR-AHCS-020 - Functional |  |  |  | Omkar Samvatsar | Mehul Kumar Patel |  | Done | Fixed | 2021-07-13 13:46 | 2021-07-23 02:55 |  | CSTONE Sprint 2 | 1A |  |  | EXT007 | RTR-GL | RTR | Build
User Story | CSTONE-592 | RTR-AHCS-021 - Functional | RTR-AHCS-021 | RTR-AHCS-021 - Functional |  |  |  | Omkar Samvatsar | Mehul Kumar Patel |  | Done | Fixed | 2021-07-13 13:46 | 2021-07-23 02:55 |  | CSTONE Sprint 2 | 1A |  |  | EXT007 | RTR-GL | RTR | Build
User Story | CSTONE-593 | RTR-AHCS-023 - Functional | RTR-AHCS-023 | RTR-AHCS-023 - Functional |  |  |  | Omkar Samvatsar | Mehul Kumar Patel |  | Done | Fixed | 2021-07-13 13:46 | 2021-07-23 02:56 |  | CSTONE Sprint 2 | 1A |  |  | EXT007 | RTR-GL | RTR | Build
User Story | CSTONE-594 | RTR-AHCS-024 - Functional | RTR-AHCS-024 | RTR-AHCS-024 - Functional |  |  |  | Manpreet Singh | Mehul Kumar Patel |  | Done | Fixed | 2021-07-13 13:46 | 2021-08-19 20:39 |  | CSTONE Sprint 3 | 1A+1B |  |  | INT012 | RTR-AHCS | RTR | Build
User Story | CSTONE-595 | RTR-AHCS-041 - Functional | RTR-AHCS-041 | RTR-AHCS-041 - Functional |  |  |  | Aashutosh Kumar Upadhyay | Mehul Kumar Patel |  | Done | Fixed | 2021-07-13 13:46 | 2021-08-05 14:44 |  | CSTONE Sprint 2 | 1A |  |  | INT038 | RTR-AHCS | RTR | Build
User Story | CSTONE-596 | RTR-AHCS-042 - Functional | RTR-AHCS-042 | RTR-AHCS-042 - Functional |  |  |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-07-13 13:46 | 2021-08-05 15:01 |  | CSTONE Sprint 2 | 1A |  |  | INT040 | RTR-AHCS | RTR | Build
User Story | CSTONE-627 | RTR-AHCS-039 - Technical | RTR-AHCS-039 |  | RTR-AHCS-039 - Technical |  |  |  | Mehul Kumar Patel |  | De-scoped |  | 2021-07-13 13:46 | 2021-09-30 20:16 |  | CSTONE Sprint 3 | 1A |  |  | INT036 | RTR-AHCS | RTR | Build
User Story | CSTONE-628 | RTR-AHCS-040 - Technical | RTR-AHCS-040 |  | RTR-AHCS-040 - Technical |  |  |  | Mehul Kumar Patel |  | De-scoped |  | 2021-07-13 13:46 | 2021-09-30 20:16 |  | CSTONE Sprint 3 | 1A |  |  | INT037 | RTR-AHCS | RTR | Build
User Story | CSTONE-633 | RTR-GL-090 - Technical | RTR-GL-090 |  | RTR-GL-090 - Technical |  |  | Ramji Agrawal | Mehul Kumar Patel |  | Done | Fixed | 2021-07-13 13:46 | 2021-10-25 13:27 |  |  | 1A+1B |  |  | RPT041 | RTR-GL | RTR | Build
User Story | CSTONE-640 | RTR-AHCS-021 - Technical | RTR-AHCS-021 |  | RTR-AHCS-021 - Technical |  |  | Devang Pandya | Mehul Kumar Patel |  | Done | Fixed | 2021-07-13 13:46 | 2021-09-03 12:42 |  | CSTONE Sprint 3 | 1A |  |  | EXT007 | RTR-GL | RTR | Build
User Story | CSTONE-647 | REP-RTR-GL-1 - Technical | REP-RTR-GL-1 |  | REP-RTR-GL-1 - Technical |  |  | Mamatha, Tata | Mehul Kumar Patel |  | Done | Fixed | 2021-07-13 13:46 | 2021-10-18 20:53 |  | CSTONE Sprint 3 | 1A+1B |  |  | RPT046 | RTR-GL | RTR | Build
User Story | CSTONE-650 | REP-RTR-GL-7 - Technical | REP-RTR-GL-7 |  | REP-RTR-GL-7 - Technical |  |  | Mamatha, Tata | Mehul Kumar Patel |  | Done | Fixed | 2021-07-13 13:46 | 2021-10-18 20:53 |  | CSTONE Sprint 3 | 1A+1B |  |  | RPT046 | RTR-GL | RTR | Build
User Story | CSTONE-651 | REP-RTR-GL-8 - Technical | REP-RTR-GL-8 |  | REP-RTR-GL-8 - Technical |  |  | Mamatha, Tata | Mehul Kumar Patel |  | Done | Fixed | 2021-07-13 13:46 | 2021-10-18 20:52 |  | CSTONE Sprint 3 | 1A+1B |  |  | RPT046 | RTR-GL | RTR | Build
User Story | CSTONE-652 | REP-RTR-GL-9 - Technical | REP-RTR-GL-9 |  | REP-RTR-GL-9 - Technical |  |  | Mamatha, Tata | Mehul Kumar Patel |  | Done | Fixed | 2021-07-13 13:47 | 2021-10-18 20:52 |  | CSTONE Sprint 3 | 1A+1B |  |  | RPT046 | RTR-GL | RTR | Build
User Story | CSTONE-655 | REP-RTR-GL-14 - Technical | REP-RTR-GL-14 |  | REP-RTR-GL-14 - Technical |  |  | Mamatha, Tata | Mehul Kumar Patel |  | Done | Fixed | 2021-07-13 13:47 | 2021-10-18 20:51 |  | CSTONE Sprint 3 | 1A+1B |  |  | RPT046 | RTR-GL | RTR | Build
User Story | CSTONE-656 | REP-RTR-GL-15 - Technical | REP-RTR-GL-15 |  | REP-RTR-GL-15 - Technical |  |  | Mamatha, Tata | Mehul Kumar Patel |  | Done | Fixed | 2021-07-13 13:47 | 2021-10-18 20:50 |  | CSTONE Sprint 3 | 1A+1B |  |  | RPT046 | RTR-GL | RTR | Build
User Story | CSTONE-657 | REP-RTR-GL-67-A - Technical | REP-RTR-GL-67-A |  | REP-RTR-GL-67-A - Technical |  |  | Mamatha, Tata | Mehul Kumar Patel |  | Done | Fixed | 2021-07-13 13:47 | 2021-10-18 20:50 |  | CSTONE Sprint 3 | 1A |  |  | RPT046 | RTR-GL | RTR | Build
User Story | CSTONE-671 | RTR-AHCS-065 - Technical | RTR-AHCS-065 |  | RTR-AHCS-065 - Technical |  |  | Devang Pandya | Mehul Kumar Patel | Not yet prioritized | Done | Done | 2021-07-13 20:31 | 2021-08-12 20:34 |  | CSTONE Sprint 3 | 1A |  |  | INT122 | RTR-AHCS | RTR | Build
User Story | CSTONE-672 | RTR-GL-043 | RTR-GL-043 | RTR-GL-043 - Functional |  |  |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-07-14 13:59 | 2021-08-05 16:12 |  | CSTONE Sprint 2 | 1A+1B |  |  |  | RTR-GL | RTR | Work Around
User Story | CSTONE-673 | RTR-GL-044 | RTR-GL-044 | RTR-GL-044 - Functional |  |  |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-07-14 13:59 | 2021-08-05 16:11 |  | CSTONE Sprint 2 | 1A+1B |  |  |  | RTR-GL | RTR | Work Around
User Story | CSTONE-1089 | DP-RTR-GL-001 | DP-RTR-GL-001 | DP-RTR-GL-001 - Functional |  |  |  | gsansanwal | Mehul Kumar Patel | Not yet prioritized | Done | Approved | 2021-07-14 16:51 | 2021-08-06 13:33 |  | CSTONE Sprint 2 | 1A+1B |  |  |  | RTR-GL | RTR | Configuration
User Story | CSTONE-1090 | RTR-AHCS-043 - TUT/FUT | RTR-AHCS-043 |  |  | RTR-AHCS-043 - TUT/FUT |  | Omkar Samvatsar | Mehul Kumar Patel | Not yet prioritized | Done | Fixed | 2021-07-14 17:39 | 2021-10-01 18:56 |  | CSTONE Sprint 3 | 1A |  |  | INT120 | RTR-AHCS | RTR | Build
User Story | CSTONE-1091 | RTR-GL-124 - TUT/FUT | RTR-GL-124 |  |  | RTR-GL-124 - TUT/FUT |  | Omkar Samvatsar | Mehul Kumar Patel |  | Done | Fixed | 2021-07-14 17:42 | 2021-08-30 13:45 |  | CSTONE Sprint 3 | 1A+1B |  |  | EXT001 | RTR-GL | RTR | Build
User Story | CSTONE-1092 | RTR-GL-125 - TUT/FUT | RTR-GL-125 |  |  | RTR-GL-125 - TUT/FUT |  | Omkar Samvatsar | Mehul Kumar Patel |  | Done | Fixed | 2021-07-14 17:44 | 2021-08-30 13:46 |  | CSTONE Sprint 3 | 1A+1B |  |  | EXT002 | RTR-GL | RTR | Build
User Story | CSTONE-1093 | RTR-GL-127 - TUT/FUT | RTR-GL-127 |  |  | RTR-GL-127 - TUT/FUT |  | Omkar Samvatsar | Mehul Kumar Patel |  | Done | Fixed | 2021-07-14 17:45 | 2021-08-31 12:58 |  | CSTONE Sprint 3 | 1A+1B |  |  | INT120 | RTR-GL | RTR | Build
User Story | CSTONE-1094 | RTR-GL-128 - TUT/FUT | RTR-GL-128 |  |  | RTR-GL-128 - TUT/FUT |  | Omkar Samvatsar | Mehul Kumar Patel |  | De-scoped |  | 2021-07-14 17:47 | 2021-08-09 19:27 |  | CSTONE Sprint 2 | 1A+1B |  |  | INT121 | RTR-GL | RTR | Build
User Story | CSTONE-1095 | RTR-GL-129 - TUT/FUT | RTR-GL-129 |  |  | RTR-GL-129 - TUT/FUT |  | Omkar Samvatsar | Mehul Kumar Patel |  | De-scoped |  | 2021-07-14 17:48 | 2021-09-07 22:49 |  | CSTONE Sprint 3 | 1A+1B |  |  | EXT004 | RTR-GL | RTR | Build
User Story | CSTONE-1096 | RTR-GL-137 - TUT/FUT | RTR-GL-137 |  |  | RTR-GL-137 - TUT/FUT |  | Omkar Samvatsar | Mehul Kumar Patel |  | Done | Fixed | 2021-07-14 17:49 | 2021-10-25 13:27 |  | CSTONE Sprint 4 | 1A |  |  | INT010 | RTR-GL | RTR | Build
User Story | CSTONE-1097 | RTR-GL-139 - TUT/FUT | RTR-GL-139 |  |  | RTR-GL-139 - TUT/FUT |  | Omkar Samvatsar | Mehul Kumar Patel |  | Done | Fixed | 2021-07-14 17:50 | 2021-10-25 13:27 |  | CSTONE Sprint 4 | 1A |  |  | INT011 | RTR-GL | RTR | Build
User Story | CSTONE-1349 | RTR-AHCS-062 - Legacy to TeraData | RTR-AHCS-062 |  |  |  |  | Satheesh Kumar Gooda | Mehul Kumar Patel |  | Done | Fixed | 2021-08-04 16:58 | 2021-08-05 14:06 |  | CSTONE Sprint 2 | 1A+1B |  |  | INT041 | RTR-AHCS | RTR | Build
User Story | CSTONE-1353 | RTR-AHCS-024 - Legacy to TeraData | RTR-AHCS-024 |  |  |  |  | Satheesh Kumar Gooda | Mehul Kumar Patel |  | Done | Fixed | 2021-08-04 17:05 | 2021-08-05 14:53 |  | CSTONE Sprint 2 | 1A+1B |  |  | INT012 | RTR-AHCS | RTR | Build
User Story | CSTONE-1357 | RTR-GL-013 (Functional) | RTR-GL-013 | RTR-GL-013 - Functional |  |  |  | Andres Romero | Mehul Kumar Patel |  | Done | Fixed | 2021-08-08 15:44 | 2021-08-24 16:45 |  | CSTONE Sprint 3 | 1A+1B |  |  | RPT003 | RTR-GL | RTR | Build
User Story | CSTONE-1358 | RTR-GL-075 (Functional) | RTR-GL-075 | RTR-GL-075 - Functional |  |  |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-08-08 15:44 | 2021-08-24 16:43 |  | CSTONE Sprint 3 | 1A+1B |  |  | RPT005 | RTR-GL | RTR | Build
User Story | CSTONE-1359 | RTR-GL-106 (Functional) | RTR-GL-106 | RTR-GL-106 - Functional |  |  |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-08-08 15:44 | 2021-08-12 00:34 |  | CSTONE Sprint 3 | 1A+1B |  |  | RPT043 | RTR-GL | RTR | Build
User Story | CSTONE-1360 | REP-RTR-GL-69 (Functional) | REP-RTR-GL-69 | REP-RTR-GL-69 - Functional |  |  |  | yuvs | Mehul Kumar Patel |  | Done | Fixed | 2021-08-08 15:44 | 2021-08-24 16:42 |  | CSTONE Sprint 3 | 1A |  |  | RPT044 | RTR-GL | RTR | Build
User Story | CSTONE-1361 | REP-RTR-GL-70 (Functional) | REP-RTR-GL-70 | REP-RTR-GL-70 - Functional |  |  |  | Andres Romero | Mehul Kumar Patel |  | Done | Fixed | 2021-08-08 15:44 | 2021-08-24 16:46 |  | CSTONE Sprint 3 | 1A |  |  | RPT003 | RTR-GL | RTR | Build
User Story | CSTONE-1362 | REP-RTR-GL-79 - Functional | REP-RTR-GL-79 | REP-RTR-GL-79 - Functional |  |  |  | yuvs | Mehul Kumar Patel |  | Done | Fixed | 2021-08-08 15:44 | 2021-08-26 02:21 |  | CSTONE Sprint 3 | 1A+1B |  |  | RPT045 | RTR-GL | RTR | Build
User Story | CSTONE-1363 | RTR-AHCS-025 (Functional) | RTR-AHCS-025 | RTR-AHCS-025 - Functional |  |  |  | Manpreet Singh | Mehul Kumar Patel |  | Done | Fixed | 2021-08-08 15:44 | 2021-08-19 20:43 |  | CSTONE Sprint 3 | 1A+1B |  |  | RPT007 | RTR-AHCS | RTR | Build
User Story | CSTONE-1364 | RTR-AHCS-027 (Functional) | RTR-AHCS-027 | RTR-AHCS-027 - Functional |  |  |  | Manpreet Singh | Mehul Kumar Patel |  | Done | Fixed | 2021-08-08 15:44 | 2021-08-18 22:03 |  | CSTONE Sprint 3 | 1A+1B |  |  | RPT008 | RTR-AHCS | RTR | Build
User Story | CSTONE-1365 | RTR-AHCS-044 (Functional) | RTR-AHCS-044 | RTR-AHCS-044 - Functional |  |  |  | Manpreet Singh | Mehul Kumar Patel |  | Blocked |  | 2021-08-08 15:44 | 2021-10-18 20:53 |  | CSTONE Sprint 3 | 1A |  |  | INT016 | RTR-AHCS | RTR | Build
User Story | CSTONE-1366 | REP-FSG-RTR-GL-001 - Functional | REP-FSG-RTR-GL-001 | REP-FSG-RTR-GL-001 - Functional |  |  |  | yuvs | Mehul Kumar Patel |  | Done | Fixed | 2021-08-08 15:44 | 2021-09-01 23:36 |  | CSTONE Sprint 3 | 1A+1B |  |  | RPT052 | RTR-GL | RTR | Build
User Story | CSTONE-1367 | REP-FSG-RTR-GL-003 - Functional | REP-FSG-RTR-GL-003 | REP-FSG-RTR-GL-003 - Functional |  |  |  | bbinkhalid | Mehul Kumar Patel |  | Done | Fixed | 2021-08-08 15:44 | 2021-09-01 23:37 |  | CSTONE Sprint 3 | 1A+1B |  |  | RPT054 | RTR-GL | RTR | Build
User Story | CSTONE-1368 | REP-FSG-RTR-GL-007 - Functional | REP-FSG-RTR-GL-007 | REP-FSG-RTR-GL-007 - Functional |  |  |  | gsansanwal | Mehul Kumar Patel |  | De-scoped |  | 2021-08-08 15:44 | 2021-09-07 22:47 |  | CSTONE Sprint 3 | 1A+1B |  |  | RPT058 | RTR-GL | RTR | Build
User Story | CSTONE-1369 | REP-FSG-RTR-GL-012 (Functional) | REP-FSG-RTR-GL-012 | REP-FSG-RTR-GL-012 - Functional |  |  |  | gsansanwal | Mehul Kumar Patel |  | De-scoped |  | 2021-08-08 15:44 | 2021-09-07 22:48 |  | CSTONE Sprint 3 | 1A+1B |  |  | RPT063 | RTR-GL | RTR | Build
User Story | CSTONE-1370 | RTR-AHCS-015 (Technical) | RTR-AHCS-015 |  | RTR-AHCS-015 - Technical |  |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-08-08 15:44 | 2021-08-30 17:27 |  | CSTONE Sprint 3 | 1A |  |  | EXT007 | RTR-GL | RTR | Build
User Story | CSTONE-1371 | RTR-AHCS-016 (Technical) | RTR-AHCS-016 |  | RTR-AHCS-016 - Technical |  |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-08-08 15:44 | 2021-08-30 17:27 |  | CSTONE Sprint 3 | 1A |  |  | EXT007 | RTR-GL | RTR | Build
User Story | CSTONE-1372 | RTR-AHCS-017 (Technical) | RTR-AHCS-017 |  | RTR-AHCS-017 - Technical |  |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-08-08 15:44 | 2021-08-30 17:29 |  | CSTONE Sprint 3 | 1A+1B |  |  | EXT007 | RTR-GL | RTR | Build
User Story | CSTONE-1373 | RTR-AHCS-018 (Technical) | RTR-AHCS-018 |  | RTR-AHCS-018 - Technical |  |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-08-08 15:44 | 2021-08-30 17:29 |  | CSTONE Sprint 3 | 1A |  |  | EXT007 | RTR-GL | RTR | Build
User Story | CSTONE-1374 | RTR-AHCS-020 (Technical) | RTR-AHCS-020 |  | RTR-AHCS-020 - Technical |  |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-08-08 15:44 | 2021-08-30 17:30 |  | CSTONE Sprint 3 | 1A |  |  | EXT007 | RTR-GL | RTR | Build
User Story | CSTONE-1375 | RTR-AHCS-021 (Technical) | RTR-AHCS-021 |  | RTR-AHCS-021 - Technical |  |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-08-08 15:44 | 2021-08-30 17:30 |  | CSTONE Sprint 3 | 1A |  |  | EXT007 | RTR-GL | RTR | Build
User Story | CSTONE-1376 | RTR-AHCS-023 (Technical) | RTR-AHCS-023 |  | RTR-AHCS-023 - Technical |  |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-08-08 15:44 | 2021-08-30 17:30 |  | CSTONE Sprint 3 | 1A |  |  | EXT007 | RTR-GL | RTR | Build
User Story | CSTONE-1377 | RTR-AHCS-041 (Technical) | RTR-AHCS-041 |  | RTR-AHCS-041 - Technical |  |  | Abhijit Chakraborty | Mehul Kumar Patel |  | Done | Fixed | 2021-08-08 15:44 | 2021-09-24 17:38 |  | CSTONE Sprint 4 | 1A |  |  | INT038 | RTR-AHCS | RTR | Build
User Story | CSTONE-1378 | RTR-AHCS-042 (Technical) | RTR-AHCS-042 |  | RTR-AHCS-042 - Technical |  |  | Astha Shrivastava | Mehul Kumar Patel |  | Done | Fixed | 2021-08-08 15:44 | 2021-09-16 13:37 |  | CSTONE Sprint 4 | 1A |  |  | INT040 | RTR-AHCS | RTR | Build
User Story | CSTONE-1379 | RTR-AHCS-051 (Technical) | RTR-AHCS-051 |  | RTR-AHCS-051 - Technical |  |  | Abhijit Chakraborty | Mehul Kumar Patel |  | Done | Fixed | 2021-08-08 15:44 | 2021-09-08 12:48 |  | CSTONE Sprint 4 | 1A+1B |  |  | EXT010 | RTR-AHCS | RTR | Build
User Story | CSTONE-1380 | REP-RTR-GL-10 (Technical) | REP-RTR-GL-10 |  | REP-RTR-GL-10 - Technical |  |  | Chowdari, Malapati Monika | Mehul Kumar Patel |  | Done | Fixed | 2021-08-08 15:44 | 2021-08-13 11:13 |  | CSTONE Sprint 3 | 1A+1B |  |  | RPT051 | RTR-GL | RTR | Build
User Story | CSTONE-1381 | REP-RTR-GL-12 (Technical) | REP-RTR-GL-12 |  | REP-RTR-GL-12 - Technical |  |  | Chowdari, Malapati Monika | Mehul Kumar Patel |  | Done | Fixed | 2021-08-08 15:44 | 2021-08-13 11:15 |  | CSTONE Sprint 3 | 1A+1B |  |  | RPT051 | RTR-GL | RTR | Build
User Story | CSTONE-1382 | RTR-GL-133 (Technical) | RTR-GL-133 |  | RTR-GL-133 - Technical |  |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-08-08 15:44 | 2021-08-13 16:20 |  | CSTONE Sprint 3 | 1A+1B |  |  | EXT008 | RTR-GL | RTR | Build
User Story | CSTONE-1383 | RTR-GL-134 (Technical) | RTR-GL-134 |  | RTR-GL-134 - Technical |  |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-08-08 15:44 | 2021-08-13 08:42 |  | CSTONE Sprint 3 | 1A+1B |  |  | EXT009 | RTR-GL | RTR | Build
User Story | CSTONE-1384 | RTR-GL-145 (Technical) | RTR-GL-145 |  | RTR-GL-145 - Technical |  |  | gsansanwal | Mehul Kumar Patel |  | De-scoped |  | 2021-08-08 15:44 | 2021-09-07 22:54 |  | CSTONE Sprint 3 | 1A |  |  | INT007 | RTR-GL | RTR | Build
User Story | CSTONE-1385 | RTR-GL-146 (Technical) | RTR-GL-146 |  | RTR-GL-146 - Technical |  |  | Astha Shrivastava | Mehul Kumar Patel |  | Done | Fixed | 2021-08-08 15:44 | 2021-09-16 13:38 |  | CSTONE Sprint 4 | 1A |  |  | INT040 | RTR-GL | RTR | Build
User Story | CSTONE-1386 | RTR-AHCS-060 (Technical) | RTR-AHCS-060 |  | RTR-AHCS-060 - Technical |  |  | Abhijit Chakraborty | Mehul Kumar Patel |  | Done | Fixed | 2021-08-08 15:44 | 2021-09-08 12:49 |  | CSTONE Sprint 4 | 1A+1B |  |  | EXT011 | RTR-AHCS | RTR | Build
User Story | CSTONE-1388 | RTR-GL-151 (Technical) | RTR-GL-151 |  | RTR-GL-151 - Technical |  |  | Chowdari, Malapati Monika | Mehul Kumar Patel |  | Done | Fixed | 2021-08-08 15:44 | 2021-09-16 13:39 |  | CSTONE Sprint 4 | 1A |  |  | INT047 | RTR-GL | RTR | Build
User Story | CSTONE-1389 | RTR-AHCS-007 (TUT/FUT) | RTR-AHCS-007 |  |  | RTR-AHCS-007 - TUT/FUT |  | Manpreet Singh | Mehul Kumar Patel |  | Done | Fixed | 2021-08-08 15:44 | 2021-10-25 13:27 |  | CSTONE Sprint 4 | 1A |  |  | INT005 | RTR-AHCS | RTR | Build
User Story | CSTONE-1390 | RTR-AHCS-008 (TUT/FUT) | RTR-AHCS-008 |  |  | RTR-AHCS-008 - TUT/FUT |  | Manpreet Singh | Mehul Kumar Patel |  | Done | Fixed | 2021-08-08 15:44 | 2021-10-25 13:27 |  | CSTONE Sprint 3 | 1A |  |  | INT002 | RTR-AHCS | RTR | Build
User Story | CSTONE-1391 | RTR-AHCS-009 (TUT/FUT) | RTR-AHCS-009 |  |  | RTR-AHCS-009 - TUT/FUT |  | Manpreet Singh | Mehul Kumar Patel |  | Done | Fixed | 2021-08-08 15:44 | 2021-10-25 13:27 |  | CSTONE Sprint 3 | 1A |  |  | INT004 | RTR-AHCS | RTR | Build
User Story | CSTONE-1392 | RTR-AHCS-010 (TUT/FUT) | RTR-AHCS-010 |  |  | RTR-AHCS-010 - TUT/FUT |  | Manpreet Singh | Mehul Kumar Patel |  | Done | Fixed | 2021-08-08 15:44 | 2021-10-25 13:27 |  | CSTONE Sprint 4 | 1A |  |  | INT033 | RTR-AHCS | RTR | Build
User Story | CSTONE-1393 | RTR-AHCS-015 (TUT/FUT) | RTR-AHCS-015 |  |  | RTR-AHCS-015 - TUT/FUT |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-08-08 15:44 | 2021-10-25 13:27 |  | CSTONE Sprint 3 | 1A |  |  | EXT007 | RTR-GL | RTR | Build
User Story | CSTONE-1394 | RTR-AHCS-016 (TUT/FUT) | RTR-AHCS-016 |  |  | RTR-AHCS-016 - TUT/FUT |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-08-08 15:44 | 2021-10-25 13:27 |  | CSTONE Sprint 3 | 1A |  |  | EXT007 | RTR-GL | RTR | Build
User Story | CSTONE-1395 | RTR-AHCS-017 (TUT/FUT) | RTR-AHCS-017 |  |  | RTR-AHCS-017 - TUT/FUT |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-08-08 15:44 | 2021-10-25 13:27 |  | CSTONE Sprint 3 | 1A+1B |  |  | EXT007 | RTR-GL | RTR | Build
User Story | CSTONE-1396 | RTR-AHCS-018 (TUT/FUT) | RTR-AHCS-018 |  |  | RTR-AHCS-018 - TUT/FUT |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-08-08 15:44 | 2021-10-25 13:27 |  | CSTONE Sprint 3 | 1A |  |  | EXT007 | RTR-GL | RTR | Build
User Story | CSTONE-1397 | RTR-AHCS-020 (TUT/FUT) | RTR-AHCS-020 |  |  | RTR-AHCS-020 - TUT/FUT |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-08-08 15:44 | 2021-10-25 13:27 |  | CSTONE Sprint 3 | 1A |  |  | EXT007 | RTR-GL | RTR | Build
User Story | CSTONE-1398 | RTR-AHCS-021 (TUT/FUT) | RTR-AHCS-021 |  |  | RTR-AHCS-021 - TUT/FUT |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-08-08 15:44 | 2021-10-25 13:27 |  | CSTONE Sprint 3 | 1A |  |  | EXT007 | RTR-GL | RTR | Build
User Story | CSTONE-1399 | RTR-AHCS-023 (TUT/FUT) | RTR-AHCS-023 |  |  | RTR-AHCS-023 - TUT/FUT |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-08-08 15:44 | 2021-10-25 13:27 |  | CSTONE Sprint 3 | 1A |  |  | EXT007 | RTR-GL | RTR | Build
User Story | CSTONE-1400 | RTR-AHCS-026 (TUT/FUT) | RTR-AHCS-026 |  |  | RTR-AHCS-026 - TUT/FUT |  | Manpreet Singh | Mehul Kumar Patel |  | Done | Fixed | 2021-08-08 15:44 | 2021-10-25 13:27 |  | CSTONE Sprint 3 | 1A+1B |  |  | RPT006 | RTR-AHCS | RTR | Build
User Story | CSTONE-1401 | RTR-AHCS-036 (TUT/FUT) | RTR-AHCS-036 |  |  | RTR-AHCS-036 - TUT/FUT |  | Manpreet Singh | Mehul Kumar Patel |  | Done | Fixed | 2021-08-08 15:44 | 2021-10-25 13:27 |  | CSTONE Sprint 4 | 1A |  |  | INT033 | RTR-AHCS | RTR | Build
User Story | CSTONE-1402 | RTR-AHCS-037 (TUT/FUT) | RTR-AHCS-037 |  |  | RTR-AHCS-037 - TUT/FUT |  | Manpreet Singh | Mehul Kumar Patel |  | De-scoped |  | 2021-08-08 15:44 | 2021-10-25 13:27 |  | CSTONE Sprint 3 | 1A |  |  | INT034 | RTR-AHCS | RTR | Build
User Story | CSTONE-1403 | RTR-AHCS-038 (TUT/FUT) | RTR-AHCS-038 |  |  | RTR-AHCS-038 - TUT/FUT |  | Manpreet Singh | Mehul Kumar Patel |  | De-scoped |  | 2021-08-08 15:44 | 2021-10-25 13:27 |  | CSTONE Sprint 3 | 1A |  |  | INT035 | RTR-AHCS | RTR | Build
User Story | CSTONE-1404 | RTR-AHCS-039 (TUT/FUT) | RTR-AHCS-039 |  |  | RTR-AHCS-039 - TUT/FUT |  | Manpreet Singh | Mehul Kumar Patel |  | De-scoped |  | 2021-08-08 15:44 | 2021-10-25 13:27 |  | CSTONE Sprint 3 | 1A |  |  | INT036 | RTR-AHCS | RTR | Build
User Story | CSTONE-1405 | RTR-AHCS-040 (TUT/FUT) | RTR-AHCS-040 |  |  | RTR-AHCS-040 - TUT/FUT |  | Manpreet Singh | Mehul Kumar Patel |  | De-scoped |  | 2021-08-08 15:44 | 2021-10-25 13:27 |  | CSTONE Sprint 3 | 1A |  |  | INT037 | RTR-AHCS | RTR | Build
User Story | CSTONE-1406 | RTR-AHCS-041 (TUT/FUT) | RTR-AHCS-041 |  |  | RTR-AHCS-041 - TUT/FUT |  | Manpreet Singh | Mehul Kumar Patel |  | Done | Fixed | 2021-08-08 15:44 | 2021-10-25 13:27 |  | CSTONE Sprint 4 | 1A |  |  | INT038 | RTR-AHCS | RTR | Build
User Story | CSTONE-1407 | RTR-AHCS-042 (TUT/FUT) | RTR-AHCS-042 |  |  | RTR-AHCS-042 - TUT/FUT |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-08-08 15:44 | 2021-09-21 00:46 |  | CSTONE Sprint 4 | 1A |  |  | INT040 | RTR-AHCS | RTR | Build
User Story | CSTONE-1408 | RTR-AHCS-051 (TUT/FUT) | RTR-AHCS-051 |  |  | RTR-AHCS-051 - TUT/FUT |  | Manpreet Singh | Mehul Kumar Patel |  | Done | Fixed | 2021-08-08 15:44 | 2021-10-25 13:27 |  | CSTONE Sprint 4 | 1A+1B |  |  | EXT010 | RTR-AHCS | RTR | Build
User Story | CSTONE-1409 | REP-RTR-GL-10 (TUT/FUT) | REP-RTR-GL-10 |  |  | REP-RTR-GL-10 - TUT/FUT |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-08-08 15:44 | 2021-08-30 13:58 |  | CSTONE Sprint 3 | 1A+1B |  |  | RPT051 | RTR-GL | RTR | Build
User Story | CSTONE-1410 | REP-RTR-GL-12 (TUT/FUT) | REP-RTR-GL-12 |  |  | REP-RTR-GL-12 - TUT/FUT |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-08-08 15:44 | 2021-10-25 13:27 |  | CSTONE Sprint 3 | 1A+1B |  |  | RPT051 | RTR-GL | RTR | Build
User Story | CSTONE-1411 | RTR-GL-119 (TUT/FUT) | RTR-GL-119 |  |  | RTR-GL-119 - TUT/FUT |  | Harshit Gangwar | Mehul Kumar Patel |  | Done | Fixed | 2021-08-08 15:44 | 2021-10-25 13:27 |  | CSTONE Sprint 4 | 1A |  |  | CNV001 | RTR-GL | RTR | Build
User Story | CSTONE-1412 | RTR-GL-133 (TUT/FUT) | RTR-GL-133 |  |  | RTR-GL-133 - TUT/FUT |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-08-08 15:44 | 2021-10-25 13:27 |  | CSTONE Sprint 3 | 1A+1B |  |  | EXT008 | RTR-GL | RTR | Build
User Story | CSTONE-1413 | RTR-GL-134 (TUT/FUT) | RTR-GL-134 |  |  | RTR-GL-134 - TUT/FUT |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-08-08 15:44 | 2021-10-25 13:27 |  | CSTONE Sprint 3 | 1A+1B |  |  | EXT009 | RTR-GL | RTR | Build
User Story | CSTONE-1414 | RTR-GL-145 (TUT/FUT) | RTR-GL-145 |  |  | RTR-GL-145 - TUT/FUT |  | gsansanwal | Mehul Kumar Patel |  | De-scoped |  | 2021-08-08 15:44 | 2021-09-07 22:53 |  | CSTONE Sprint 3 | 1A |  |  | INT007 | RTR-GL | RTR | Build
User Story | CSTONE-1415 | RTR-GL-146 (TUT/FUT) | RTR-GL-146 |  |  | RTR-GL-146 - TUT/FUT |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-08-08 15:44 | 2021-09-17 14:21 |  | CSTONE Sprint 4 | 1A |  |  | INT040 | RTR-GL | RTR | Build
User Story | CSTONE-1416 | RTR-GL-147 (TUT/FUT) | RTR-GL-147 |  |  | RTR-GL-147 - TUT/FUT |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-08-08 15:44 | 2021-10-25 13:27 |  | CSTONE Sprint 3 | 1A+1B |  |  | EXT014 | RTR-GL | RTR | Build
User Story | CSTONE-1417 | RTR-AHCS-060 (TUT/FUT) | RTR-AHCS-060 |  |  | RTR-AHCS-060 - TUT/FUT |  | Manpreet Singh | Mehul Kumar Patel |  | Done | Fixed | 2021-08-08 15:44 | 2021-10-25 13:27 |  | CSTONE Sprint 4 | 1A+1B |  |  | EXT011 | RTR-AHCS | RTR | Build
User Story | CSTONE-1418 | RTR-AHCS-065 (TUT/FUT) | RTR-AHCS-065 |  |  | RTR-AHCS-065 - TUT/FUT |  | Manpreet Singh | Mehul Kumar Patel |  | Done | Fixed | 2021-08-08 15:44 | 2021-10-25 13:27 |  | CSTONE Sprint 3 | 1A |  |  | INT122 | RTR-AHCS | RTR | Build
User Story | CSTONE-1419 | RTR-GL-151 (TUT/FUT) | RTR-GL-151 |  |  | RTR-GL-151 - TUT/FUT |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-08-08 15:44 | 2021-09-17 00:51 |  | CSTONE Sprint 4 | 1A |  |  | INT047 | RTR-GL | RTR | Build
User Story | CSTONE-1610 | EPM-FCCS-001 | EPM-FCCS-001 | EPM-FCCS-001 - Functional |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:47 | 2021-09-08 19:48 |  | CSTONE Sprint 4 | 1A |  |  |  | EPM - FCCS | EPM | Configuration
User Story | CSTONE-1611 | EPM-FCCS-002 | EPM-FCCS-002 | EPM-FCCS-002 - Functional |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:47 | 2021-09-07 21:49 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - FCCS | EPM | Configuration
User Story | CSTONE-1612 | EPM-FCCS-003 | EPM-FCCS-003 | EPM-FCCS-003 - Functional |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:47 | 2021-09-07 21:49 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - FCCS | EPM | Configuration
User Story | CSTONE-1613 | EPM-FCCS-004 | EPM-FCCS-004 | EPM-FCCS-004 - Functional |  |  |  | vicmartinez | Mehul Kumar Patel | Major | De-scoped |  | 2021-08-08 16:47 | 2021-09-07 22:50 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - FCCS | EPM | Configuration
User Story | CSTONE-1614 | EPM-FCCS-005 | EPM-FCCS-005 | EPM-FCCS-005 - Functional |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:47 | 2021-09-07 21:49 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - FCCS | EPM | Configuration
User Story | CSTONE-1615 | EPM-FCCS-006 | EPM-FCCS-006 | EPM-FCCS-006 - Functional |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:47 | 2021-09-07 21:49 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - FCCS | EPM | Configuration
User Story | CSTONE-1616 | EPM-FCCS-007 | EPM-FCCS-007 | EPM-FCCS-007 - Functional |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:47 | 2021-09-07 21:49 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - FCCS | EPM | Configuration
User Story | CSTONE-1617 | EPM-FCCS-008 | EPM-FCCS-008 | EPM-FCCS-008 - Functional |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:47 | 2021-09-07 21:49 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - FCCS | EPM | Configuration
User Story | CSTONE-1618 | EPM-FCCS-009 | EPM-FCCS-009 | EPM-FCCS-009 - Functional |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:47 | 2021-09-07 21:49 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - FCCS | EPM | Configuration
User Story | CSTONE-1619 | EPM-FCCS-010 | EPM-FCCS-010 | EPM-FCCS-010 - Functional |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:47 | 2021-09-07 21:49 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - FCCS | EPM | Configuration
User Story | CSTONE-1620 | EPM-FCCS-012 | EPM-FCCS-012 | EPM-FCCS-012 - Functional |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:47 | 2021-09-07 21:49 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - FCCS | EPM | Configuration
User Story | CSTONE-1621 | EPM-FCCS-013 | EPM-FCCS-013 | EPM-FCCS-013 - Functional |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:47 | 2021-09-07 21:49 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - FCCS | EPM | Configuration
User Story | CSTONE-1622 | EPM-FCCS-014 | EPM-FCCS-014 | EPM-FCCS-014 - Functional |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:47 | 2021-09-07 21:49 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - FCCS | EPM | Configuration
User Story | CSTONE-1623 | EPM-FCCS-015 | EPM-FCCS-015 | EPM-FCCS-015 - Functional |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:47 | 2021-09-07 21:49 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - FCCS | EPM | Configuration
User Story | CSTONE-1624 | EPM-FCCS-016 | EPM-FCCS-016 | EPM-FCCS-016 - Functional |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:47 | 2021-09-07 21:49 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - FCCS | EPM | Configuration
User Story | CSTONE-1625 | EPM-FCCS-017 | EPM-FCCS-017 | EPM-FCCS-017 - Functional |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:47 | 2021-09-07 21:49 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - FCCS | EPM | Configuration
User Story | CSTONE-1626 | EPM-FCCS-019 | EPM-FCCS-019 | EPM-FCCS-019 - Functional |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:47 | 2021-09-07 21:49 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - FCCS | EPM | Configuration
User Story | CSTONE-1627 | EPM-FCCS-020 | EPM-FCCS-020 | EPM-FCCS-020 - Functional |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:47 | 2021-09-07 21:49 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - FCCS | EPM | Configuration
User Story | CSTONE-1628 | EPM-FCCS-022 | EPM-FCCS-022 | EPM-FCCS-022 - Functional |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:47 | 2021-09-07 21:49 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - FCCS | EPM | Configuration
User Story | CSTONE-1629 | EPM-FCCS-032 | EPM-FCCS-032 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:47 | 2021-10-02 11:51 |  | CSTONE Sprint 4 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-1630 | EPM-FCCS-033 | EPM-FCCS-033 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:47 | 2021-10-02 11:50 |  | CSTONE Sprint 4 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-1631 | EPM-FCCS-034 | EPM-FCCS-034 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Blocked |  | 2021-08-08 16:47 | 2021-10-15 02:01 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-1632 | EPM-FCCS-035 | EPM-FCCS-035 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | De-scoped |  | 2021-08-08 16:47 | 2021-09-07 22:48 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-1633 | EPM-FCCS-036 | EPM-FCCS-036 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Blocked |  | 2021-08-08 16:47 | 2021-10-15 02:01 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-1634 | EPM-FCCS-037 | EPM-FCCS-037 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:47 | 2021-10-02 11:51 |  | CSTONE Sprint 4 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-1635 | EPM-FCCS-038 | EPM-FCCS-038 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | De-scoped |  | 2021-08-08 16:47 | 2021-10-04 20:50 |  | CSTONE Sprint 4 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-1636 | EPM-FCCS-039 | EPM-FCCS-039 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | De-scoped |  | 2021-08-08 16:47 | 2021-10-04 20:50 |  | CSTONE Sprint 4 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-1637 | EPM-FCCS-040 | EPM-FCCS-040 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Blocked |  | 2021-08-08 16:47 | 2021-10-15 02:01 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-1639 | EPM-FCCS-042 | EPM-FCCS-042 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:47 | 2021-10-05 13:45 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-1638 | EPM-FCCS-041 | EPM-FCCS-041 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:47 | 2021-10-02 11:52 |  | CSTONE Sprint 4 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-1640 | EPM-FCCS-043 | EPM-FCCS-043 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Blocked |  | 2021-08-08 16:47 | 2021-10-15 02:01 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-1641 | EPM-FCCS-046 | EPM-FCCS-046 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:47 | 2021-10-02 11:52 |  | CSTONE Sprint 4 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-1642 | EPM-FCCS-048 | EPM-FCCS-048 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:47 | 2021-10-21 21:36 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-1643 | EPM-FCCS-049 | EPM-FCCS-049 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Blocked |  | 2021-08-08 16:47 | 2021-10-15 02:00 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-1644 | EPM-FCCS-050 | EPM-FCCS-050 |  |  |  |  | Will Dixon | Mehul Kumar Patel | Major | De-scoped |  | 2021-08-08 16:47 | 2021-10-04 20:50 |  | CSTONE Sprint 4 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-1645 | EPM-FCCS-051 | EPM-FCCS-051 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Blocked |  | 2021-08-08 16:47 | 2021-10-15 02:00 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-1646 | EPM-FCCS-053 | EPM-FCCS-053 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | De-scoped |  | 2021-08-08 16:47 | 2021-09-07 22:49 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-1647 | EPM-FCCS-054 | EPM-FCCS-054 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | De-scoped |  | 2021-08-08 16:47 | 2021-10-04 20:50 |  | CSTONE Sprint 4 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-1648 | EPM-FCCS-059 | EPM-FCCS-059 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:48 | 2021-10-27 03:47 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-1649 | EPM-FCCS-062 | EPM-FCCS-062 | EPM-FCCS-062 - Functional |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:48 | 2021-09-07 21:49 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - FCCS | EPM | Configuration
User Story | CSTONE-1650 | EPM-FCCS-065 | EPM-FCCS-065 | EPM-FCCS-065 - Functional |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:48 | 2021-09-07 21:49 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - FCCS | EPM | Configuration
User Story | CSTONE-1651 | EPM-FCCS-066 | EPM-FCCS-066 | EPM-FCCS-066 - Functional |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:48 | 2021-09-07 21:49 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - FCCS | EPM | Configuration
User Story | CSTONE-1652 | EPM-FCCS-067 | EPM-FCCS-067 | EPM-FCCS-067 - Functional |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:48 | 2021-09-07 21:49 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - FCCS | EPM | Configuration
User Story | CSTONE-1653 | EPM-FCCS-069 | EPM-FCCS-069 | EPM-FCCS-069 - Functional |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:48 | 2021-09-07 21:49 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - FCCS | EPM | Configuration
User Story | CSTONE-1654 | EPM-FCCS-070 | EPM-FCCS-070 | EPM-FCCS-070 - Functional |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:48 | 2021-09-07 21:49 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - FCCS | EPM | Configuration
User Story | CSTONE-1655 | EPM-FCCS-071 | EPM-FCCS-071 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:48 | 2021-09-13 21:03 |  | CSTONE Sprint 4 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-1656 | EPM-FCCS-073 | EPM-FCCS-073 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | De-scoped |  | 2021-08-08 16:48 | 2021-09-07 22:54 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-1657 | EPM-FCCS-076 | EPM-FCCS-076 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:48 | 2021-09-07 21:49 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-1658 | EPM-FCCS-077 | EPM-FCCS-077 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:48 | 2021-09-07 21:49 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-1659 | EPM-FCCS-078 | EPM-FCCS-078 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:48 | 2021-09-07 21:49 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-1660 | EPM-FCCS-079 | EPM-FCCS-079 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:48 | 2021-09-07 21:49 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-1661 | EPM-FCCS-080 | EPM-FCCS-080 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:48 | 2021-09-07 21:49 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-1662 | EPM-FCCS-081 | EPM-FCCS-081 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:48 | 2021-09-07 21:49 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-1663 | EPM-FCCS-083 | EPM-FCCS-083 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:48 | 2021-09-07 21:49 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-1664 | EPM-FCCS-084 | EPM-FCCS-084 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:48 | 2021-09-07 21:49 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-1665 | EPM-FCCS-085 | EPM-FCCS-085 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:48 | 2021-09-07 21:49 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-1666 | EPM-FCCS-086 | EPM-FCCS-086 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:48 | 2021-09-07 21:49 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-1667 | EPM-FCCS-087 | EPM-FCCS-087 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:48 | 2021-09-07 21:49 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-1668 | EPM-FCCS-088 | EPM-FCCS-088 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:48 | 2021-09-07 21:49 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-1669 | EPM-FCCS-089 | EPM-FCCS-089 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:48 | 2021-09-07 21:49 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-1670 | EPM-FCCS-090 | EPM-FCCS-090 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:48 | 2021-09-07 21:49 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-1671 | EPM-FCCS-091 | EPM-FCCS-091 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:48 | 2021-09-07 21:49 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-1672 | EPM-FCCS-092 | EPM-FCCS-092 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:48 | 2021-09-07 21:49 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-1673 | EPM-FCCS-093 | EPM-FCCS-093 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:48 | 2021-09-07 21:49 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-1674 | EPM-FCCS-094 | EPM-FCCS-094 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:48 | 2021-09-07 21:49 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-1675 | EPM-FCCS-095 | EPM-FCCS-095 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:48 | 2021-09-07 21:49 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-1676 | EPM-FCCS-096 | EPM-FCCS-096 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:48 | 2021-09-07 21:49 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-1677 | EPM-FCCS-097 | EPM-FCCS-097 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:48 | 2021-09-07 21:49 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-1678 | EPM-FCCS-098 | EPM-FCCS-098 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:48 | 2021-09-07 21:49 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-1679 | EPM-FCCS-099 | EPM-FCCS-099 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:48 | 2021-09-07 21:49 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-1680 | EPM-FCCS-100 | EPM-FCCS-100 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:48 | 2021-09-07 21:49 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-1681 | EPM-FCCS-101 | EPM-FCCS-101 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:48 | 2021-09-07 21:49 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-1682 | EPM-FCCS-102 | EPM-FCCS-102 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:48 | 2021-09-07 21:49 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-1683 | EPM-FCCS-103 | EPM-FCCS-103 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:48 | 2021-09-07 21:49 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-1684 | EPM-FCCS-104 | EPM-FCCS-104 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:48 | 2021-09-07 21:49 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-1685 | EPM-FCCS-105 | EPM-FCCS-105 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:48 | 2021-09-07 21:49 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-1686 | EPM-FCCS-106 | EPM-FCCS-106 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:48 | 2021-09-07 21:49 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-1687 | EPM-FCCS-107 | EPM-FCCS-107 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:48 | 2021-09-07 21:49 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-1688 | EPM-FCCS-108 | EPM-FCCS-108 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:48 | 2021-09-07 21:49 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-1689 | EPM-FCCS-109 | EPM-FCCS-109 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:48 | 2021-09-07 21:49 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-1690 | EPM-FCCS-110 | EPM-FCCS-110 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:48 | 2021-09-07 21:49 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-1691 | EPM-FCCS-111 | EPM-FCCS-111 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:48 | 2021-09-07 21:50 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-1692 | EPM-FCCS-112 | EPM-FCCS-112 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:48 | 2021-09-07 21:50 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-1693 | EPM-FCCS-113 | EPM-FCCS-113 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:48 | 2021-09-07 21:50 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-1694 | EPM-FCCS-114 | EPM-FCCS-114 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:48 | 2021-09-07 21:50 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-1695 | EPM-FCCS-115 | EPM-FCCS-115 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:48 | 2021-09-07 21:50 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-1696 | EPM-FCCS-116 | EPM-FCCS-116 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:48 | 2021-09-07 21:50 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-1697 | EPM-FCCS-117 | EPM-FCCS-117 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:48 | 2021-09-07 21:50 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-1698 | EPM-FCCS-118 | EPM-FCCS-118 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:48 | 2021-09-07 21:50 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-1699 | EPM-FCCS-119 | EPM-FCCS-119 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:48 | 2021-09-07 21:50 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-1700 | EPM-FCCS-120 | EPM-FCCS-120 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:48 | 2021-09-07 21:50 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-1701 | EPM-FCCS-187 | EPM-FCCS-187 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:48 | 2021-09-07 21:50 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-1702 | EPM-FCCS-188 | EPM-FCCS-188 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | De-scoped |  | 2021-08-08 16:48 | 2021-09-07 22:54 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-1703 | EPM-FCCS-121 | EPM-FCCS-121 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:48 | 2021-09-07 21:50 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-1704 | EPM-FCCS-122 | EPM-FCCS-122 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:48 | 2021-09-07 21:50 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-1705 | EPM-FCCS-189 | EPM-FCCS-189 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:48 | 2021-09-07 21:50 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-1706 | EPM-FCCS-123 | EPM-FCCS-123 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:48 | 2021-09-07 21:50 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-1707 | EPM-FCCS-124 | EPM-FCCS-124 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:48 | 2021-09-07 21:50 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-1708 | EPM-FCCS-125 | EPM-FCCS-125 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:48 | 2021-09-07 21:50 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-1709 | EPM-FCCS-126 | EPM-FCCS-126 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:48 | 2021-09-07 21:50 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-1710 | EPM-FCCS-127 | EPM-FCCS-127 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:48 | 2021-09-07 21:50 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-1711 | EPM-FCCS-128 | EPM-FCCS-128 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:48 | 2021-09-07 21:50 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-1712 | EPM-FCCS-129 | EPM-FCCS-129 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:48 | 2021-09-07 21:50 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-1713 | EPM-FCCS-130 | EPM-FCCS-130 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:48 | 2021-09-07 21:50 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-1714 | EPM-FCCS-185 | EPM-FCCS-185 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:48 | 2021-09-07 21:50 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-1715 | EPM-FCCS-186 | EPM-FCCS-186 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:48 | 2021-09-07 21:50 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-1716 | EPM-FCCS-134 | EPM-FCCS-134 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:48 | 2021-09-16 16:11 |  | CSTONE Sprint 4 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-1717 | EPM-FCCS-139 | EPM-FCCS-139 | EPM-FCCS-139 - Functional |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:48 | 2021-10-22 19:31 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - FCCS | EPM | Configuration
User Story | CSTONE-1718 | EPM-FCCS-140 | EPM-FCCS-140 | EPM-FCCS-140 - Functional |  |  |  | vicmartinez | Mehul Kumar Patel | Major | De-scoped |  | 2021-08-08 16:48 | 2021-09-07 22:50 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - FCCS | EPM | Configuration
User Story | CSTONE-1719 | EPM-FCCS-141 | EPM-FCCS-141 | EPM-FCCS-141 - Functional |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:48 | 2021-09-07 21:50 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - FCCS | EPM | Configuration
User Story | CSTONE-1720 | EPM-FCCS-166 | EPM-FCCS-166 | EPM-FCCS-166 - Functional |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:48 | 2021-09-29 00:41 |  | CSTONE Sprint 4 | 1A |  |  |  | EPM - FCCS | EPM | Configuration
User Story | CSTONE-1721 | EPM-FCCS-142 | EPM-FCCS-142 | EPM-FCCS-142 - Functional |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:48 | 2021-09-07 21:49 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - FCCS | EPM | Configuration
User Story | CSTONE-1722 | EPM-FCCS-144 | EPM-FCCS-144 | EPM-FCCS-144 - Functional |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:48 | 2021-09-24 03:20 |  | CSTONE Sprint 4 | 1A |  |  |  | EPM - FCCS | EPM | Configuration
User Story | CSTONE-1723 | EPM-FCCS-145 | EPM-FCCS-145 | EPM-FCCS-145 - Functional |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:48 | 2021-09-24 03:21 |  | CSTONE Sprint 4 | 1A |  |  |  | EPM - FCCS | EPM | Configuration
User Story | CSTONE-1724 | EPM-FCCS-146 | EPM-FCCS-146 | EPM-FCCS-146 - Functional |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:48 | 2021-09-24 03:22 |  | CSTONE Sprint 4 | 1A |  |  |  | EPM - FCCS | EPM | Configuration
User Story | CSTONE-1725 | EPM-FCCS-148 | EPM-FCCS-148 | EPM-FCCS-148 - Functional |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:48 | 2021-09-07 21:49 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - FCCS | EPM | Configuration
User Story | CSTONE-1726 | EPM-FCCS-151 | EPM-FCCS-151 | EPM-FCCS-151 - Functional |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:48 | 2021-09-07 21:49 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - FCCS | EPM | Configuration
User Story | CSTONE-1727 | EPM-FCCS-152 | EPM-FCCS-152 | EPM-FCCS-152 - Functional |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:48 | 2021-09-13 21:02 |  | CSTONE Sprint 4 | 1A |  |  |  | EPM - FCCS | EPM | Configuration
User Story | CSTONE-1728 | EPM-FCCS-156 | EPM-FCCS-156 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:48 | 2021-09-15 19:58 |  | CSTONE Sprint 4 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-1729 | EPM-FCCS-157 | EPM-FCCS-157 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | In Progress |  | 2021-08-08 16:48 | 2021-10-04 18:39 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-1730 | EPM-FCCS-160 | EPM-FCCS-160 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:48 | 2021-09-24 03:22 |  | CSTONE Sprint 4 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-1731 | EPM-FCCS-162 | EPM-FCCS-162 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:48 | 2021-09-15 19:58 |  | CSTONE Sprint 4 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-1732 | EPM-FCCS-163 | EPM-FCCS-163 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:48 | 2021-09-15 19:57 |  | CSTONE Sprint 4 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-1733 | EPM-FCCS-164 | EPM-FCCS-164 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:48 | 2021-09-15 19:57 |  | CSTONE Sprint 4 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-1734 | EPM-ARCS-001 | EPM-ARCS-001 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | In Progress |  | 2021-08-08 16:48 | 2021-10-04 18:40 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-1735 | EPM-ARCS-002 | EPM-ARCS-002 | EPM-ARCS-002 - Functional |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:48 | 2021-09-07 21:49 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - FCCS | EPM | Configuration
User Story | CSTONE-1736 | EPM-ARCS-003 | EPM-ARCS-003 | EPM-ARCS-003 - Functional |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:48 | 2021-09-07 21:49 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - FCCS | EPM | Configuration
User Story | CSTONE-1737 | EPM-ARCS-004 | EPM-ARCS-004 | EPM-ARCS-004 - Functional |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:48 | 2021-09-07 21:49 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - FCCS | EPM | Configuration
User Story | CSTONE-1738 | EPM-ARCS-009 | EPM-ARCS-009 | EPM-ARCS-009 - Functional |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:48 | 2021-09-07 21:49 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - FCCS | EPM | Configuration
User Story | CSTONE-1739 | EPM-ARCS-011 | EPM-ARCS-011 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:48 | 2021-09-07 21:49 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-1740 | EPM-ARCS-015 | EPM-ARCS-015 | EPM-ARCS-015 - Functional |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:48 | 2021-09-07 21:49 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - FCCS | EPM | Configuration
User Story | CSTONE-1741 | EPM-ARCS-016 | EPM-ARCS-016 | EPM-ARCS-016 - Functional |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:48 | 2021-09-07 21:49 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - FCCS | EPM | Configuration
User Story | CSTONE-1742 | EPM-ARCS-019 | EPM-ARCS-019 | EPM-ARCS-019 - Functional |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:48 | 2021-09-07 21:49 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - FCCS | EPM | Configuration
User Story | CSTONE-1743 | EPM-ARCS-033 | EPM-ARCS-033 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:48 | 2021-09-07 21:49 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-1744 | EPM-ARCS-034 | EPM-ARCS-034 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | De-scoped |  | 2021-08-08 16:48 | 2021-09-07 22:55 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-1745 | EPM-ARCS-035 | EPM-ARCS-035 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:48 | 2021-09-07 21:49 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-1746 | EPM-ARCS-036 | EPM-ARCS-036 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:48 | 2021-09-12 18:42 |  | CSTONE Sprint 4 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-1747 | EPM-ARCS-037 | EPM-ARCS-037 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | De-scoped |  | 2021-08-08 16:48 | 2021-09-07 22:55 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-1748 | EPM-ARCS-038 | EPM-ARCS-038 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 16:48 | 2021-09-07 21:49 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-1749 | EPM-ARCS-039 | EPM-ARCS-039 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | De-scoped |  | 2021-08-08 16:48 | 2021-09-07 22:55 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-2538 | EPM-EPBCS-001 | EPM-EPBCS-001 | EPM-EPBCS-001 - Functional |  |  |  |  | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 17:33 | 2021-09-07 21:49 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - PBCS | EPM | Configuration
User Story | CSTONE-2539 | EPM-EPBCS-002 | EPM-EPBCS-002 | EPM-EPBCS-002 - Functional |  |  |  |  | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 17:33 | 2021-09-07 21:49 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - PBCS | EPM | Configuration
User Story | CSTONE-2540 | EPM-EPBCS-003 | EPM-EPBCS-003 | EPM-EPBCS-003 - Functional |  |  |  |  | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 17:33 | 2021-09-13 15:29 |  | CSTONE Sprint 4 | 1A |  |  |  | EPM - PBCS | EPM | Configuration
User Story | CSTONE-2541 | EPM-EPBCS-004 | EPM-EPBCS-004 | [5 empty] | Mehul Kumar Patel | Major | In Progress |  | 2021-08-08 17:33 | 2021-10-04 18:40 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - PBCS | EPM | Build
User Story | CSTONE-2542 | EPM-EPBCS-005 | EPM-EPBCS-005 | [5 empty] | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 17:33 | 2021-09-13 22:43 |  | CSTONE Sprint 4 | 1A |  |  |  | EPM - PBCS | EPM | Build
User Story | CSTONE-2543 | EPM-EPBCS-006 | EPM-EPBCS-006 | [5 empty] | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 17:33 | 2021-10-28 23:10 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - PBCS | EPM | Build
User Story | CSTONE-2544 | EPM-EPBCS-007 | EPM-EPBCS-007 | [5 empty] | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 17:33 | 2021-10-28 23:09 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - PBCS | EPM | Build
User Story | CSTONE-2545 | EPM-EPBCS-008 | EPM-EPBCS-008 | EPM-EPBCS-008 - Functional |  |  |  |  | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 17:33 | 2021-09-07 21:50 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - PBCS | EPM | Configuration
User Story | CSTONE-2546 | EPM-EPBCS-009 | EPM-EPBCS-009 | EPM-EPBCS-009 - Functional |  |  |  |  | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 17:33 | 2021-09-07 21:50 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - PBCS | EPM | Configuration
User Story | CSTONE-2547 | EPM-EPBCS-010 | EPM-EPBCS-010 | [5 empty] | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 17:33 | 2021-09-13 22:42 |  | CSTONE Sprint 4 | 1A |  |  |  | EPM - PBCS | EPM | Build
User Story | CSTONE-2548 | EPM-EPBCS-011 | EPM-EPBCS-011 | EPM-EPBCS-011 - Functional |  |  |  |  | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 17:33 | 2021-10-28 14:28 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - PBCS | EPM | Configuration
User Story | CSTONE-2549 | EPM-EPBCS-012 | EPM-EPBCS-012 | [5 empty] | Mehul Kumar Patel | Major | In Progress |  | 2021-08-08 17:33 | 2021-10-04 18:40 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - PBCS | EPM | Build
User Story | CSTONE-2550 | EPM-EPBCS-013 | EPM-EPBCS-013 | EPM-EPBCS-013 - Functional |  |  |  |  | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 17:33 | 2021-10-07 19:33 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - PBCS | EPM | Configuration
User Story | CSTONE-2551 | EPM-EPBCS-014 | EPM-EPBCS-014 | EPM-EPBCS-014 - Functional |  |  |  |  | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 17:33 | 2021-10-07 19:34 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - PBCS | EPM | Configuration
User Story | CSTONE-2552 | EPM-EPBCS-015 | EPM-EPBCS-015 | EPM-EPBCS-015 - Functional |  |  |  |  | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 17:33 | 2021-09-07 21:50 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - PBCS | EPM | Configuration
User Story | CSTONE-2553 | EPM-EPBCS-016 | EPM-EPBCS-016 | EPM-EPBCS-016 - Functional |  |  |  |  | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 17:33 | 2021-09-07 21:50 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - PBCS | EPM | Configuration
User Story | CSTONE-2554 | EPM-EPBCS-017 | EPM-EPBCS-017 | EPM-EPBCS-017 - Functional |  |  |  |  | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 17:33 | 2021-09-07 21:50 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - PBCS | EPM | Configuration
User Story | CSTONE-2555 | EPM-EPBCS-018 | EPM-EPBCS-018 | EPM-EPBCS-018 - Functional |  |  |  |  | Mehul Kumar Patel | Mid | Done | Fixed | 2021-08-08 17:33 | 2021-09-07 21:46 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - PBCS | EPM | Configuration
User Story | CSTONE-2556 | EPM-EPBCS-019 | EPM-EPBCS-019 | EPM-EPBCS-019 - Functional |  |  |  |  | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 17:33 | 2021-09-07 21:50 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - PBCS | EPM | Configuration
User Story | CSTONE-2557 | EPM-EPBCS-020 | EPM-EPBCS-020 | EPM-EPBCS-020 - Functional |  |  |  |  | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 17:33 | 2021-09-13 15:29 |  | CSTONE Sprint 4 | 1A |  |  |  | EPM - PBCS | EPM | Configuration
User Story | CSTONE-2558 | EPM-EPBCS-021 | EPM-EPBCS-021 | EPM-EPBCS-021 - Functional |  |  |  |  | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 17:33 | 2021-09-07 21:50 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - PBCS | EPM | Configuration
User Story | CSTONE-2559 | EPM-EPBCS-022 | EPM-EPBCS-022 | EPM-EPBCS-022 - Functional |  |  |  |  | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 17:33 | 2021-10-28 23:12 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - PBCS | EPM | Configuration
User Story | CSTONE-2560 | EPM-EPBCS-023 | EPM-EPBCS-023 | EPM-EPBCS-023 - Functional |  |  |  |  | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 17:33 | 2021-10-01 16:37 |  | CSTONE Sprint 4 | 1A |  |  |  | EPM - PBCS | EPM | Configuration
User Story | CSTONE-2561 | EPM-EPBCS-024 | EPM-EPBCS-024 | EPM-EPBCS-024 - Functional |  |  |  |  | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 17:33 | 2021-10-19 17:48 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - PBCS | EPM | Configuration
User Story | CSTONE-2562 | EPM-EPBCS-025 | EPM-EPBCS-025 | EPM-EPBCS-025 - Functional |  |  |  |  | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 17:33 | 2021-10-08 15:54 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - PBCS | EPM | Configuration
User Story | CSTONE-2563 | EPM-EPBCS-026 | EPM-EPBCS-026 | [5 empty] | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 17:33 | 2021-10-01 16:37 |  | CSTONE Sprint 4 | 1A |  |  |  | EPM - PBCS | EPM | Build
User Story | CSTONE-2564 | EPM-EPBCS-027 | EPM-EPBCS-027 | [5 empty] | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 17:33 | 2021-10-01 16:37 |  | CSTONE Sprint 4 | 1A |  |  |  | EPM - PBCS | EPM | Build
User Story | CSTONE-2565 | EPM-EPBCS-028 | EPM-EPBCS-028 | [5 empty] | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 17:33 | 2021-10-08 15:55 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - PBCS | EPM | Build
User Story | CSTONE-2566 | EPM-EPBCS-029 | EPM-EPBCS-029 |  |  |  |  | Will Dixon | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 17:33 | 2021-10-08 15:55 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - PBCS |  | Build
User Story | CSTONE-2567 | EPM-EPBCS-030 | EPM-EPBCS-030 | [5 empty] | Mehul Kumar Patel | Mid | Done | Fixed | 2021-08-08 17:33 | 2021-10-01 17:07 |  | CSTONE Sprint 4 | 1A |  |  |  | EPM - PBCS | EPM | Build
User Story | CSTONE-2568 | EPM-EPBCS-031 | EPM-EPBCS-031 | EPM-EPBCS-031 - Functional |  |  |  |  | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 17:33 | 2021-10-07 17:06 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - PBCS | EPM | Configuration
User Story | CSTONE-2569 | EPM-EPBCS-032 | EPM-EPBCS-032 | [5 empty] | Mehul Kumar Patel | Major | In Progress |  | 2021-08-08 17:33 | 2021-10-04 18:40 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - PBCS | EPM | Build
User Story | CSTONE-2570 | EPM-EPBCS-033 | EPM-EPBCS-033 | [5 empty] | Mehul Kumar Patel | Mid | Done | Fixed | 2021-08-08 17:33 | 2021-10-20 00:39 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - PBCS | EPM | Build
User Story | CSTONE-2571 | EPM-EPBCS-034 | EPM-EPBCS-034 | EPM-EPBCS-034 - Functional |  |  |  |  | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 17:33 | 2021-09-07 21:49 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - PBCS | EPM | Configuration
User Story | CSTONE-2572 | EPM-EPBCS-035 | EPM-EPBCS-035 | EPM-EPBCS-035 - Functional |  |  |  |  | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 17:33 | 2021-10-20 00:35 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - PBCS | EPM | Configuration
User Story | CSTONE-2573 | EPM-EPBCS-036 | EPM-EPBCS-036 | [5 empty] | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 17:33 | 2021-10-01 17:08 |  | CSTONE Sprint 4 | 1A |  |  |  | EPM - PBCS | EPM | Build
User Story | CSTONE-2574 | EPM-EPBCS-037 | EPM-EPBCS-037 | [5 empty] | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 17:33 | 2021-10-01 17:10 |  | CSTONE Sprint 4 | 1A |  |  |  | EPM - PBCS | EPM | Build
User Story | CSTONE-2575 | EPM-EPBCS-038 | EPM-EPBCS-038 | [5 empty] | Mehul Kumar Patel | Mid | Done | Fixed | 2021-08-08 17:34 | 2021-10-07 19:34 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - PBCS | EPM | Build
User Story | CSTONE-2576 | EPM-EPBCS-039 | EPM-EPBCS-039 | [5 empty] | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 17:34 | 2021-10-28 23:09 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - PBCS | EPM | Build
User Story | CSTONE-2577 | EPM-EPBCS-040 | EPM-EPBCS-040 | EPM-EPBCS-040 - Functional |  |  |  |  | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 17:34 | 2021-10-07 17:27 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - PBCS | EPM | Configuration
User Story | CSTONE-2578 | EPM-EPBCS-063 | EPM-EPBCS-063 | [5 empty] | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 17:34 | 2021-09-09 18:51 |  | CSTONE Sprint 4 | 1A |  |  |  | EPM - PBCS | EPM | Build
User Story | CSTONE-2579 | EPM-EPBCS-064 | EPM-EPBCS-064 | [5 empty] | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 17:34 | 2021-09-08 18:13 |  | CSTONE Sprint 4 | 1A |  |  |  | EPM - PBCS | EPM | Build
User Story | CSTONE-2580 | EPM-EPBCS-065 | EPM-EPBCS-065 | [5 empty] | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 17:34 | 2021-09-24 16:19 |  | CSTONE Sprint 4 | 1A |  |  |  | EPM - PBCS | EPM | Build
User Story | CSTONE-2581 | EPM-EPBCS-066 | EPM-EPBCS-066 | [5 empty] | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 17:34 | 2021-09-13 22:40 |  | CSTONE Sprint 4 | 1A |  |  |  | EPM - PBCS | EPM | Build
User Story | CSTONE-2582 | EPM-EPBCS-067 | EPM-EPBCS-067 | [5 empty] | Mehul Kumar Patel | Mid | Done | Fixed | 2021-08-08 17:34 | 2021-10-20 00:39 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - PBCS | EPM | Build
User Story | CSTONE-2583 | EPM-EPBCS-068 | EPM-EPBCS-068 | [5 empty] | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 17:34 | 2021-10-08 16:39 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - PBCS | EPM | Build
User Story | CSTONE-2584 | EPM-EPBCS-069 | EPM-EPBCS-069 | [5 empty] | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 17:34 | 2021-09-17 01:54 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - PBCS | EPM | Build
User Story | CSTONE-2585 | EPM-EPBCS-070 | EPM-EPBCS-070 | [5 empty] | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 17:34 | 2021-09-07 21:49 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - PBCS | EPM | Build
User Story | CSTONE-2586 | EPM-EPBCS-071 | EPM-EPBCS-071 | [5 empty] | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 17:34 | 2021-09-07 21:49 |  | CSTONE Sprint 4 | 1A |  |  |  | EPM - PBCS | EPM | Build
User Story | CSTONE-2587 | EPM-EPBCS-072 | EPM-EPBCS-072 | [5 empty] | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 17:34 | 2021-09-13 15:31 |  | CSTONE Sprint 4 | 1A |  |  |  | EPM - PBCS | EPM | Build
User Story | CSTONE-2588 | EPM-EPBCS-073 | EPM-EPBCS-073 | [5 empty] | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 17:34 | 2021-10-20 00:37 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - PBCS | EPM | Build
User Story | CSTONE-2589 | EPM-EPBCS-074 | EPM-EPBCS-074 | [5 empty] | Mehul Kumar Patel |  | In Progress |  | 2021-08-08 17:34 | 2021-10-04 18:39 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - PBCS | EPM | Build
User Story | CSTONE-2590 | EPM-EPBCS-075 | EPM-EPBCS-075 | [5 empty] | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 17:34 | 2021-09-13 22:42 |  | CSTONE Sprint 4 | 1A |  |  |  | EPM - PBCS | EPM | Build
User Story | CSTONE-2591 | EPM-EPBCS-076 | EPM-EPBCS-076 | [5 empty] | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 17:34 | 2021-09-13 22:41 |  | CSTONE Sprint 4 | 1A |  |  |  | EPM - PBCS | EPM | Build
User Story | CSTONE-2592 | EPM-EPBCS-077 | EPM-EPBCS-077 | [5 empty] | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 17:34 | 2021-10-08 17:09 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - PBCS | EPM | Build
User Story | CSTONE-2593 | EPM-EPBCS-078 | EPM-EPBCS-078 | EPM-EPBCS-078 - Functional |  |  |  |  | Mehul Kumar Patel | Major | In Progress |  | 2021-08-08 17:34 | 2021-10-04 18:39 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - PBCS | EPM | Configuration
User Story | CSTONE-2594 | EPM-EPBCS-079 | EPM-EPBCS-079 | [5 empty] | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 17:34 | 2021-10-28 14:31 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - PBCS | EPM | Build
User Story | CSTONE-2595 | COA-EPM-01 | COA-EPM-01 | COA-EPM-01 - Functional |  |  |  |  | Mehul Kumar Patel |  | Not Started |  | 2021-08-08 17:34 | 2021-10-04 18:39 |  | CSTONE Sprint 5 | Phase 1A+1B |  |  |  |  | EPM | Configuration
User Story | CSTONE-2596 | EPM-EDM-001 | EPM-EDM-001 | EPM-EDM-001 - Functional |  |  |  | Mayank Dargan | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 17:34 | 2021-09-07 21:49 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - Master Data Management | EPM | Configuration
User Story | CSTONE-2597 | EPM-EDM-003 | EPM-EDM-003 | EPM-EDM-003 - Functional |  |  |  | Mayank Dargan | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 17:34 | 2021-10-25 13:26 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - Master Data Management | EPM | Configuration
User Story | CSTONE-2598 | EPM-EDM-005 | EPM-EDM-005 | EPM-EDM-005 - Functional |  |  |  | Mayank Dargan | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 17:34 | 2021-10-13 18:08 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - Master Data Management | EPM | Configuration
User Story | CSTONE-2599 | EPM-EDM-006 | EPM-EDM-006 | EPM-EDM-006 - Functional |  |  |  | Mayank Dargan | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 17:34 | 2021-09-07 21:49 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - Master Data Management | EPM | Configuration
User Story | CSTONE-2600 | EPM-EDM-009 | EPM-EDM-009 | EPM-EDM-009 - Functional |  |  |  | Mayank Dargan | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 17:34 | 2021-10-25 13:26 |  | CSTONE Sprint 4 | 1A |  |  |  | EPM - Master Data Management | EPM | Configuration
User Story | CSTONE-2601 | EPM-EDM-010 | EPM-EDM-010 | EPM-EDM-010 - Functional |  |  |  | Mayank Dargan | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 17:34 | 2021-09-07 21:49 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - Master Data Management | EPM | Configuration
User Story | CSTONE-2602 | EPM-EDM-014 | EPM-EDM-014 | EPM-EDM-014 - Functional |  |  |  | Mayank Dargan | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 17:34 | 2021-09-07 21:49 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - Master Data Management | EPM | Configuration
User Story | CSTONE-2603 | EPM-EDM-015 | EPM-EDM-015 | EPM-EDM-015 - Functional |  |  |  | Mayank Dargan | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 17:34 | 2021-10-25 13:26 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - Master Data Management | EPM | Configuration
User Story | CSTONE-2604 | EPM-EDM-016 | EPM-EDM-016 | EPM-EDM-016 - Functional |  |  |  | Mayank Dargan | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 17:34 | 2021-10-25 13:26 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - Master Data Management | EPM | Configuration
User Story | CSTONE-2605 | EPM-EDM-017 | EPM-EDM-017 | EPM-EDM-017 - Functional |  |  |  | Mayank Dargan | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 17:34 | 2021-09-07 21:49 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - Master Data Management | EPM | Configuration
User Story | CSTONE-2606 | EPM-EDM-021 | EPM-EDM-021 | EPM-EDM-021 - Functional |  |  |  | Mayank Dargan | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 17:34 | 2021-10-25 13:26 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - Master Data Management | EPM | Configuration
User Story | CSTONE-2607 | EPM-EDM-022 | EPM-EDM-022 | EPM-EDM-022 - Functional |  |  |  | Mayank Dargan | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 17:34 | 2021-09-07 21:49 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - Master Data Management | EPM | Configuration
User Story | CSTONE-2608 | EPM-EDM-023 | EPM-EDM-023 | EPM-EDM-023 - Functional |  |  |  | Mayank Dargan | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 17:34 | 2021-09-07 21:49 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - Master Data Management | EPM | Configuration
User Story | CSTONE-2609 | EPM-EDM-024 | EPM-EDM-024 | EPM-EDM-024 - Functional |  |  |  | Mayank Dargan | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 17:34 | 2021-09-07 21:49 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - Master Data Management | EPM | Configuration
User Story | CSTONE-2610 | EPM-EDM-025 | EPM-EDM-025 | EPM-EDM-025 - Functional |  |  |  | Mayank Dargan | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 17:34 | 2021-09-07 21:49 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - Master Data Management | EPM | Configuration
User Story | CSTONE-2611 | EPM-EDM-026 | EPM-EDM-026 | EPM-EDM-026 - Functional |  |  |  | Mayank Dargan | Mehul Kumar Patel | Major | Done | Fixed | 2021-08-08 17:34 | 2021-09-07 21:49 |  | CSTONE Sprint 3 | 1A |  |  |  | EPM - Master Data Management | EPM | Configuration
User Story | CSTONE-2612 | BI-RICE-1_KDD8 Teradata Feed 1 (GL Journals) (Functional) | BI-RICE-1_KDD8 | BI-RICE-1_KDD8 - Functional |  |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Approved | 2021-08-12 00:39 | 2021-10-01 19:25 |  | CSTONE Sprint 3 | 1A |  |  |  | RTR-BI | RTR | Build
User Story | CSTONE-2613 | BI-RICE-2_KDD8 Teradata Feed 2(GL Balances) (Functional) | BI-RICE-2_KDD8 | BI-RICE-2_KDD8 - Functional |  |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Approved | 2021-08-12 00:39 | 2021-10-01 19:25 |  | CSTONE Sprint 3 | 1A |  |  |  | RTR-BI | RTR | Build
User Story | CSTONE-2614 | BI-RICE-17_KDD8 Teradata Feed 1(DSS_TABLES..EXPENSE..) (Functional) | BI-RICE-17_KDD8 | BI-RICE-17_KDD8 - Functional |  |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-12 00:39 | 2021-10-01 19:25 |  | CSTONE Sprint 3 | 1A |  |  |  | RTR-BI | RTR | Build
User Story | CSTONE-2615 | BI-RICE-5_Trial Balance by ODS (Functional) | BI-RICE-5_Trial | BI-RICE-5_Trial - Functional |  |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-12 00:39 | 2021-10-01 19:25 |  | CSTONE Sprint 3 | 1A |  |  |  | RTR-BI | RTR | Build
User Story | CSTONE-2616 | BI-RICE-6_Trial Balance by ODS (Functional) | BI-RICE-6_Trial | BI-RICE-6_Trial - Functional |  |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-12 00:39 | 2021-10-01 19:25 |  | CSTONE Sprint 3 | 1A |  |  |  | RTR-BI | RTR | Build
User Story | CSTONE-2617 | BI-RICE-7_Trial Balance by ODS Trailing (Functional) | BI-RICE-7_Trial | BI-RICE-7_Trial - Functional |  |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-12 00:39 | 2021-10-01 19:25 |  | CSTONE Sprint 3 | 1A |  |  |  | RTR-BI | RTR | Build
User Story | CSTONE-2618 | BI-RICE-8_Trial Balance by ODS Trailing (Functional) | BI-RICE-8_Trial | BI-RICE-8_Trial - Functional |  |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-12 00:39 | 2021-10-01 19:25 |  | CSTONE Sprint 3 | 1A |  |  |  | RTR-BI | RTR | Build
User Story | CSTONE-2619 | BI-RICE-9_Trial Balance by ODS Trailing (Functional) | BI-RICE-9_Trial | BI-RICE-9_Trial - Functional |  |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-12 00:39 | 2021-10-01 19:25 |  | CSTONE Sprint 3 | 1A |  |  |  | RTR-BI | RTR | Build
User Story | CSTONE-2620 | BI-RICE-13_Secured Teradata/P3 Database Files (Functional) | BI-RICE-13_Secured | BI-RICE-13_Secured - Functional |  |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-12 00:39 | 2021-10-01 19:25 |  | CSTONE Sprint 3 | 1A |  |  |  | RTR-BI | RTR | Build
User Story | CSTONE-2621 | BI-RICE-14_Secured Teradata/P3 Database Files (Functional) | BI-RICE-14_Secured | BI-RICE-14_Secured - Functional |  |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-12 00:39 | 2021-10-01 19:25 |  | CSTONE Sprint 3 | 1A |  |  |  | RTR-BI | RTR | Build
User Story | CSTONE-2622 | BI-RICE-15_Unsecured Teradata/P3 Database Files (Functional) | BI-RICE-15_Unsecured | BI-RICE-15_Unsecured - Functional |  |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-12 00:39 | 2021-10-01 19:25 |  | CSTONE Sprint 3 | 1A |  |  |  | RTR-BI | RTR | Build
User Story | CSTONE-2623 | BI-RICE-16_Unsecured Teradata/P3 Database Files (Functional) | BI-RICE-16_Unsecured | BI-RICE-16_Unsecured - Functional |  |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-12 00:39 | 2021-10-01 19:25 |  | CSTONE Sprint 3 | 1A |  |  |  | RTR-BI | RTR | Build
User Story | CSTONE-2624 | BI-RICE-19_Downstream Tables/Views for Operational Reporting (Functional) | BI-RICE-19_Downstream | BI-RICE-19_Downstream - Functional |  |  |  | Jbastidas | Mehul Kumar Patel |  | Done | Fixed | 2021-08-12 00:39 | 2021-10-01 19:25 |  | CSTONE Sprint 3 | 1A |  |  |  | RTR-BI | RTR | Build
User Story | CSTONE-2625 | BI-RICE-20_Downstream Tables/Views for Operational Reporting (Functional) | BI-RICE-20_Downstream | BI-RICE-20_Downstream - Functional |  |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-12 00:39 | 2021-10-01 19:25 |  | CSTONE Sprint 3 | 1A |  |  |  | RTR-BI | RTR | Build
User Story | CSTONE-2626 | BI-RICE-21_Downstream Tables/Views for Operational Reporting (Functional) | BI-RICE-21_Downstream | BI-RICE-21_Downstream - Functional |  |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-12 00:39 | 2021-10-01 19:25 |  | CSTONE Sprint 3 | 1A |  |  |  | RTR-BI | RTR | Build
User Story | CSTONE-2627 | BI-RICE-22_Downstream Tables/Views for Operational Reporting (Functional) | BI-RICE-22_Downstream | BI-RICE-22_Downstream - Functional |  |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-12 00:39 | 2021-10-01 19:25 |  | CSTONE Sprint 3 | 1A |  |  |  | RTR-BI | RTR | Build
User Story | CSTONE-2628 | BI-RICE-23_Downstream Tables/Views for Operational Reporting (Functional) | BI-RICE-23_Downstream | BI-RICE-23_Downstream - Functional |  |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-12 00:39 | 2021-10-01 19:25 |  | CSTONE Sprint 3 | 1A |  |  |  | RTR-BI | RTR | Build
User Story | CSTONE-2629 | BI-RICE-24_Downstream Tables/Views for Operational Reporting (Functional) | BI-RICE-24_Downstream | BI-RICE-24_Downstream - Functional |  |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-12 00:39 | 2021-10-01 19:25 |  | CSTONE Sprint 3 | 1A |  |  |  | RTR-BI | RTR | Build
User Story | CSTONE-2630 | BI-RICE-28_Downstream Tables/Views for Operational Reporting (Functional) | BI-RICE-28_Downstream | BI-RICE-28_Downstream - Functional |  |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-12 00:39 | 2021-10-01 19:25 |  | CSTONE Sprint 3 | 1A |  |  |  | RTR-BI | RTR | Build
User Story | CSTONE-2631 | BI-RICE-29_Downstream Tables/Views for Operational Reporting (Functional) | BI-RICE-29_Downstream | BI-RICE-29_Downstream - Functional |  |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-12 00:39 | 2021-10-01 19:25 |  | CSTONE Sprint 3 | 1A |  |  |  | RTR-BI | RTR | Build
User Story | CSTONE-2632 | BI-RICE-30_Downstream Tables/Views for Operational Reporting (Functional) | BI-RICE-30_Downstream | BI-RICE-30_Downstream - Functional |  |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-12 00:39 | 2021-10-01 19:25 |  | CSTONE Sprint 3 | 1A |  |  |  | RTR-BI | RTR | Build
User Story | CSTONE-2633 | BI-RICE-31_Downstream Tables/Views for Operational Reporting (Functional) | BI-RICE-31_Downstream | BI-RICE-31_Downstream - Functional |  |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-12 00:39 | 2021-10-01 19:25 |  | CSTONE Sprint 3 | 1A |  |  |  | RTR-BI | RTR | Build
User Story | CSTONE-2634 | BI-RICE-32_Downstream Tables/Views for Operational Reporting (Functional) | BI-RICE-32_Downstream | BI-RICE-32_Downstream - Functional |  |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-12 00:39 | 2021-10-01 19:25 |  | CSTONE Sprint 3 | 1A |  |  |  | RTR-BI | RTR | Build
User Story | CSTONE-2635 | BI-RICE-1_KDD8 Teradata Feed 1 (GL Journals) (Technical) | BI-RICE-1_KDD8 |  | BI-RICE-1_KDD8 - Technical |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-12 00:39 | 2021-10-01 19:25 |  | CSTONE Sprint 3 | 1A |  |  |  | RTR-BI | RTR | Build
User Story | CSTONE-2636 | BI-RICE-2_KDD8 Teradata Feed 2(GL Balances) (Technical) | BI-RICE-2_KDD8 |  | BI-RICE-2_KDD8 - Technical |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-12 00:39 | 2021-10-01 19:25 |  | CSTONE Sprint 3 | 1A |  |  |  | RTR-BI | RTR | Build
User Story | CSTONE-2637 | BI-RICE-17_KDD8 Teradata Feed 1(DSS_TABLES..EXPENSE..) (Technical) | BI-RICE-17_KDD8 |  | BI-RICE-17_KDD8 - Technical |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | De-scoped |  | 2021-08-12 00:39 | 2021-10-04 20:49 |  | CSTONE Sprint 4 | 1A |  |  |  | RTR-BI | RTR | Build
User Story | CSTONE-2638 | BI-RICE-5_Trial Balance by ODS (Technical) | BI-RICE-5_Trial |  | BI-RICE-5_Trial - Technical |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-12 00:39 | 2021-10-01 19:25 |  | CSTONE Sprint 4 | 1A |  |  |  | RTR-BI | RTR | Build
User Story | CSTONE-2639 | BI-RICE-6_Trial Balance by ODS (Technical) | BI-RICE-6_Trial |  | BI-RICE-6_Trial - Technical |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-12 00:39 | 2021-10-01 19:25 |  | CSTONE Sprint 4 | 1A |  |  |  | RTR-BI | RTR | Build
User Story | CSTONE-2640 | BI-RICE-7_Trial Balance by ODS Trailing (Technical) | BI-RICE-7_Trial |  | BI-RICE-7_Trial - Technical |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-12 00:39 | 2021-10-01 19:25 |  | CSTONE Sprint 4 | 1A |  |  |  | RTR-BI | RTR | Build
User Story | CSTONE-2641 | BI-RICE-8_Trial Balance by ODS Trailing (Technical) | BI-RICE-8_Trial |  | BI-RICE-8_Trial - Technical |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-12 00:39 | 2021-10-01 19:25 |  | CSTONE Sprint 4 | 1A |  |  |  | RTR-BI | RTR | Build
User Story | CSTONE-2642 | BI-RICE-9_Trial Balance by ODS Trailing (Technical) | BI-RICE-9_Trial |  | BI-RICE-9_Trial - Technical |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-12 00:39 | 2021-10-01 19:25 |  | CSTONE Sprint 4 | 1A |  |  |  | RTR-BI | RTR | Build
User Story | CSTONE-2643 | BI-RICE-13_Secured Teradata/P3 Database Files (Technical) | BI-RICE-13_Secured |  | BI-RICE-13_Secured - Technical |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-12 00:39 | 2021-10-01 19:25 |  | CSTONE Sprint 4 | 1A |  |  |  | RTR-BI | RTR | Build
User Story | CSTONE-2644 | BI-RICE-14_Secured Teradata/P3 Database Files (Technical) | BI-RICE-14_Secured |  | BI-RICE-14_Secured - Technical |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-12 00:39 | 2021-10-01 19:25 |  | CSTONE Sprint 4 | 1A |  |  |  | RTR-BI | RTR | Build
User Story | CSTONE-2645 | BI-RICE-15_Unsecured Teradata/P3 Database Files (Technical) | BI-RICE-15_Unsecured |  | BI-RICE-15_Unsecured - Technical |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-12 00:39 | 2021-10-01 19:25 |  | CSTONE Sprint 4 | 1A |  |  |  | RTR-BI | RTR | Build
User Story | CSTONE-2646 | BI-RICE-16_Unsecured Teradata/P3 Database Files (Technical) | BI-RICE-16_Unsecured |  | BI-RICE-16_Unsecured - Technical |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-12 00:39 | 2021-10-01 19:25 |  | CSTONE Sprint 4 | 1A |  |  |  | RTR-BI | RTR | Build
User Story | CSTONE-2647 | BI-RICE-19_Downstream Tables/Views for Operational Reporting (Technical) | BI-RICE-19_Downstream |  | BI-RICE-19_Downstream - Technical |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-12 00:39 | 2021-10-01 19:25 |  | CSTONE Sprint 4 | 1A |  |  |  | RTR-BI | RTR | Build
User Story | CSTONE-2648 | BI-RICE-20_Downstream Tables/Views for Operational Reporting (Technical) | BI-RICE-20_Downstream |  | BI-RICE-20_Downstream - Technical |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-12 00:39 | 2021-10-01 19:25 |  | CSTONE Sprint 4 | 1A |  |  |  | RTR-BI | RTR | Build
User Story | CSTONE-2649 | BI-RICE-21_Downstream Tables/Views for Operational Reporting (Technical) | BI-RICE-21_Downstream |  | BI-RICE-21_Downstream - Technical |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-12 00:39 | 2021-10-01 19:25 |  | CSTONE Sprint 4 | 1A |  |  |  | RTR-BI | RTR | Build
User Story | CSTONE-2650 | BI-RICE-22_Downstream Tables/Views for Operational Reporting (Technical) | BI-RICE-22_Downstream |  | BI-RICE-22_Downstream - Technical |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-12 00:39 | 2021-10-01 19:25 |  | CSTONE Sprint 4 | 1A |  |  |  | RTR-BI | RTR | Build
User Story | CSTONE-2651 | BI-RICE-23_Downstream Tables/Views for Operational Reporting (Technical) | BI-RICE-23_Downstream |  | BI-RICE-23_Downstream - Technical |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-12 00:39 | 2021-10-01 19:25 |  | CSTONE Sprint 4 | 1A |  |  |  | RTR-BI | RTR | Build
User Story | CSTONE-2652 | BI-RICE-24_Downstream Tables/Views for Operational Reporting (Technical) | BI-RICE-24_Downstream |  | BI-RICE-24_Downstream - Technical |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-12 00:39 | 2021-10-01 19:25 |  | CSTONE Sprint 4 | 1A |  |  |  | RTR-BI | RTR | Build
User Story | CSTONE-2846 | BI-RICE-33_GL hierarchy tables (Functional) | BI-RICE-33_GL | BI-RICE-33_GL - Functional |  |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-19 09:56 | 2021-10-01 19:25 | 2021-08-17 | CSTONE Sprint 3 | 1A |  |  | BI-RICE-33 (Functional) | RTR-BI | RTR | Build
User Story | CSTONE-2847 | BI-RICE-34 _COA mapping table(Functional) | BI-RICE-34 | BI-RICE-34 - Functional |  |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-19 09:56 | 2021-10-01 19:25 | 2021-08-17 | CSTONE Sprint 3 | 1A |  |  | BI-RICE-34 (Functional) | RTR-BI | RTR | Build
User Story | CSTONE-2848 | BI-RICE-35 _Income Statement Detail (Legacy)(Functional) | BI-RICE-35 | BI-RICE-35 - Functional |  |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Not Started | Fixed | 2021-08-19 09:56 | 2021-10-28 18:13 | 2021-08-17 | CSTONE Sprint 6 | 1A |  |  | BI-RICE-35 (Functional) | RTR-BI | RTR | Build
User Story | CSTONE-2849 | BI-RICE-36_Income Statement Summary (Legacy) (Functional) | BI-RICE-36_Income | BI-RICE-36_Income - Functional |  |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Not Started | Fixed | 2021-08-19 09:56 | 2021-10-28 20:28 | 2021-08-17 | CSTONE Sprint 6 | 1A |  |  | BI-RICE-36 (Functional) | RTR-BI | RTR | Build
User Story | CSTONE-2850 | BI-RICE-37_Income Statement Drilldown 1 (Legacy)(Functional) | BI-RICE-37_Income | BI-RICE-37_Income - Functional |  |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Not Started | Fixed | 2021-08-19 09:56 | 2021-10-28 20:18 | 2021-08-17 | CSTONE Sprint 6 | 1A |  |  | BI-RICE-37 (Functional) | RTR-BI | RTR | Build
User Story | CSTONE-2851 | BI-RICE-38_Income Statement Journal Drilldown (Legacy)(Functional) | BI-RICE-38_Income | BI-RICE-38_Income - Functional |  |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-19 09:56 | 2021-10-01 19:25 | 2021-08-17 | CSTONE Sprint 3 | 1A |  |  | BI-RICE-38 (Functional) | RTR-BI | RTR | Build
User Story | CSTONE-2852 | BI-RICE-39_Billing Margin % by Shipment Type (Functional) | BI-RICE-39_Billing | BI-RICE-39_Billing - Functional |  |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-19 09:56 | 2021-10-01 19:25 | 2021-08-17 | CSTONE Sprint 3 | 1A |  |  | BI-RICE-39 (Functional) | RTR-BI | RTR | Build
User Story | CSTONE-2853 | BI-RICE-40_Billing Margin Analysis by Month (Functional) | BI-RICE-40_Billing | BI-RICE-40_Billing - Functional |  |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-19 09:56 | 2021-10-01 19:25 | 2021-08-17 | CSTONE Sprint 3 | 1A |  |  | BI-RICE-40 (Functional) | RTR-BI | RTR | Build
User Story | CSTONE-2854 | BI-RICE-41_Daily Sales by Current Workday (Functional) | BI-RICE-41_Daily | BI-RICE-41_Daily - Functional |  |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-19 09:56 | 2021-10-01 19:25 | 2021-08-17 | CSTONE Sprint 3 | 1A |  |  | BI-RICE-41 (Functional) | RTR-BI | RTR | Build
User Story | CSTONE-2855 | BI-RICE-42_MTD vs Last Year (Functional) | BI-RICE-42_MTD | BI-RICE-42_MTD - Functional |  |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-19 09:56 | 2021-10-01 19:25 | 2021-08-17 | CSTONE Sprint 3 | 1A |  |  | BI-RICE-42 (Functional) | RTR-BI | RTR | Build
User Story | CSTONE-2856 | BI-RICE-43_Sales $ by Shipment Type(Functional) | BI-RICE-43_Sales | BI-RICE-43_Sales - Functional |  |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-19 09:56 | 2021-10-01 19:25 | 2021-08-17 | CSTONE Sprint 3 | 1A |  |  | BI-RICE-43 (Functional) | RTR-BI | RTR | Build
User Story | CSTONE-2857 | BI-RICE-44_YTD vs Last Year (Functional) | BI-RICE-44_YTD | BI-RICE-44_YTD - Functional |  |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-19 09:56 | 2021-10-01 19:25 | 2021-08-17 | CSTONE Sprint 3 | 1A |  |  | BI-RICE-44 (Functional) | RTR-BI | RTR | Build
User Story | CSTONE-2858 | BI-RICE-50_FCCS hierarchy tables (Functional) | BI-RICE-50_FCCS | BI-RICE-50_FCCS - Functional |  |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-19 09:56 | 2021-10-01 19:27 | 2021-08-17 | CSTONE Sprint 3 | 1A |  |  | BI-RICE-50 (Functional) | EPM-BI | EPM | Build
User Story | CSTONE-2859 | BI-RICE-51_EPBCS hierarchy tables (Functional) | BI-RICE-51_EPBCS | BI-RICE-51_EPBCS - Functional |  |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-19 09:56 | 2021-10-01 19:27 | 2021-08-17 | CSTONE Sprint 3 | 1A |  |  | BI-RICE-51 (Functional) | EPM-BI | EPM | Build
User Story | CSTONE-2860 | BI-RICE-52_FCCS Data Target Table (Functional) | BI-RICE-52_FCCS | BI-RICE-52_FCCS - Functional |  |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-19 09:56 | 2021-10-01 19:27 | 2021-08-17 | CSTONE Sprint 3 | 1A |  |  | BI-RICE-52 (Functional) | EPM-BI | EPM | Build
User Story | CSTONE-2861 | BI-RICE-53_EPBCS Data Target Table (Functional) | BI-RICE-53_EPBCS | BI-RICE-53_EPBCS - Functional |  |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-19 09:56 | 2021-10-01 19:27 | 2021-08-17 | CSTONE Sprint 3 | 1A |  |  | BI-RICE-53 (Functional) | EPM-BI | EPM | Build
User Story | CSTONE-2862 | BI-RICE-54_FCCS Reporting Tables (Functional) | BI-RICE-54_FCCS | BI-RICE-54_FCCS - Functional |  |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-19 09:56 | 2021-10-01 19:27 | 2021-08-17 | CSTONE Sprint 3 | 1A |  |  | BI-RICE-54 (Functional) | EPM-BI | EPM | Build
User Story | CSTONE-2863 | BI-RICE-55_EPBCS Reporting Tables (Functional) | BI-RICE-55_EPBCS | BI-RICE-55_EPBCS - Functional |  |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-19 09:56 | 2021-10-01 19:27 |  | CSTONE Sprint 3 | 1A |  |  | BI-RICE-55 (Functional) | EPM-BI | EPM | Build
User Story | CSTONE-2864 | BI-RICE-73_Accounts by Month - Actual (Functional) | BI-RICE-73_Accounts | BI-RICE-73_Accounts - Functional |  |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-19 09:56 | 2021-10-01 19:25 | 2021-08-17 | CSTONE Sprint 3 | 1A |  |  | BI-RICE-73 (Functional) | RTR-BI | RTR | Build
User Story | CSTONE-2865 | BI-RICE-75_Accounts by Quarter - Actual (Functional) | BI-RICE-75_Accounts | BI-RICE-75_Accounts - Functional |  |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-19 09:56 | 2021-10-01 19:25 | 2021-08-17 | CSTONE Sprint 3 | 1A |  |  | BI-RICE-75 (Functional) | RTR-BI | RTR | Build
User Story | CSTONE-2866 | BI-RICE-33_GL hierarchy tables (Technical) | BI-RICE-33_GL |  | BI-RICE-33_GL - Technical |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-19 09:56 | 2021-10-01 19:25 | 2021-08-17 | CSTONE Sprint 3 | 1A |  |  | BI-RICE-33 (Technical) | RTR-BI | RTR | Build
User Story | CSTONE-2867 | BI-RICE-34_COA mapping table (Technical) | BI-RICE-34_COA |  | BI-RICE-34_COA - Technical |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-19 09:56 | 2021-10-19 20:28 | 2021-08-17 | CSTONE Sprint 3 | 1A |  |  | BI-RICE-34 (Technical) | RTR-BI | RTR | Build
User Story | CSTONE-2868 | BI-RICE-35_Income Statement Detail (Legacy) (Technical) | BI-RICE-35_Income |  | BI-RICE-35_Income - Technical |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Not Started | Fixed | 2021-08-19 09:56 | 2021-10-28 18:28 | 2021-08-17 | CSTONE Sprint 6 | 1A |  |  | BI-RICE-35 (Technical) | RTR-BI | RTR | Build
User Story | CSTONE-2869 | BI-RICE-36_Income Statement Summary (Legacy) (Technical) | BI-RICE-36_Income |  | BI-RICE-36_Income - Technical |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-19 09:56 | 2021-10-01 19:25 | 2021-08-17 | CSTONE Sprint 4 | 1A |  |  | BI-RICE-36 (Technical) | RTR-BI | RTR | Build
User Story | CSTONE-2870 | BI-RICE-37_Income Statement Drilldown 1 (Legacy) (Technical) | BI-RICE-37_Income |  | BI-RICE-37_Income - Technical |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Not Started | Fixed | 2021-08-19 09:56 | 2021-10-28 20:17 | 2021-08-17 | CSTONE Sprint 6 | 1A |  |  | BI-RICE-37 (Technical) | RTR-BI | RTR | Build
User Story | CSTONE-2871 | BI-RICE-38_Income Statement Journal Drilldown (Legacy) (Technical) | BI-RICE-38_Income |  | BI-RICE-38_Income - Technical |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-19 09:56 | 2021-10-25 13:27 | 2021-08-17 | CSTONE Sprint 4 | 1A |  |  | BI-RICE-38 (Technical) | RTR-BI | RTR | Build
User Story | CSTONE-3184 | BI-RICE-3_New Recon tables: DSS_TABLES.ORACLE_CLD_AHCS_BAL, DSS_TABLES.EBS_SUBLEDGER_BAL (Functional) | BI-RICE-3_New | BI-RICE-3_New - Functional |  |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-20 17:23 | 2021-10-01 19:25 | 2021-08-17 | CSTONE Sprint 4 | 1A |  |  | BI-RICE-3 | RTR-BI | RTR | Build
User Story | CSTONE-3185 | BI-RICE-4_New tables: DSS_TABLES.ORACLE_CLD_AHCS_DET, DSS_TABLES.EBS_SUBLEDGER_DET (Functional) | BI-RICE-4_New | BI-RICE-4_New - Functional |  |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-20 17:23 | 2021-10-01 19:25 | 2021-08-08 | CSTONE Sprint 4 | 1A |  |  | BI-RICE-4 | RTR-BI | RTR | Build
User Story | CSTONE-3186 | BI-RICE-10_EBS AP to AHCS Recon Report - Detail (Functional) | BI-RICE-10_EBS | BI-RICE-10_EBS - Functional |  |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-20 17:23 | 2021-10-01 19:25 | 2021-08-17 | CSTONE Sprint 4 | 1A |  |  | BI-RICE-10 | RTR-BI | RTR | Build
User Story | CSTONE-3187 | BI-RICE-11_EBS AR to AHCS Recon Report - Detail(Functional) | BI-RICE-11_EBS | BI-RICE-11_EBS - Functional |  |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-20 17:23 | 2021-10-01 19:25 | 2021-08-08 | CSTONE Sprint 4 | 1A |  |  | BI-RICE-11 | RTR-BI | RTR | Build
User Story | CSTONE-3188 | BI-RICE-12_EBS FA to AHCS Recon Report - Detail (Functional) | BI-RICE-12_EBS | BI-RICE-12_EBS - Functional |  |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-20 17:23 | 2021-10-01 19:25 | 2021-08-17 | CSTONE Sprint 4 | 1A |  |  | BI-RICE-12 | RTR-BI | RTR | Build
User Story | CSTONE-3189 | BI-RICE-18_AHCS Spending Per Employee (Functional) | BI-RICE-18_AHCS | BI-RICE-18_AHCS - Functional |  |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Not Started |  | 2021-08-20 17:23 | 2021-10-01 19:25 | 2021-08-08 |  | 1A |  |  | BI-RICE-18 | RTR-BI | RTR | Build
User Story | CSTONE-3190 | BI-RICE-25_dss_tables.wgroup (Functional) | BI-RICE-25_dss_tables.wgroup | BI-RICE-25_dss_tables.wgroup - Functional |  |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Not Started |  | 2021-08-20 17:23 | 2021-10-01 19:25 | 2021-08-17 |  | 1A |  |  | BI-RICE-25 | RTR-BI | RTR | Build
User Story | CSTONE-3191 | BI-RICE-26_dss_tables.region (Functional) | BI-RICE-26_dss_tables.region | BI-RICE-26_dss_tables.region - Functional |  |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Not Started |  | 2021-08-20 17:23 | 2021-10-01 19:25 | 2021-08-17 |  | 1A |  |  | BI-RICE-26 | RTR-BI | RTR | Build
User Story | CSTONE-3192 | BI-RICE-27_dss_tables.district (Functional) | BI-RICE-27_dss_tables.district | BI-RICE-27_dss_tables.district - Functional |  |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Not Started |  | 2021-08-20 17:23 | 2021-10-01 19:25 | 2021-08-17 |  | 1A |  |  | BI-RICE-27 | RTR-BI | RTR | Build
User Story | CSTONE-3193 | BI-RICE-45_EBS AP to AHCS Recon Report - Balances (Functional) | BI-RICE-45_EBS | BI-RICE-45_EBS - Functional |  |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-20 17:23 | 2021-10-01 19:25 | 2021-08-17 | CSTONE Sprint 4 | 1A |  |  | BI-RICE-45 | RTR-BI | RTR | Build
User Story | CSTONE-3194 | BI-RICE-46_EBS AR to AHCS Recon Report - Balances (Functional) | BI-RICE-46_EBS | BI-RICE-46_EBS - Functional |  |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-20 17:23 | 2021-10-01 19:25 | 2021-08-17 | CSTONE Sprint 4 | 1A |  |  | BI-RICE-46 | RTR-BI | RTR | Build
User Story | CSTONE-3195 | BI-RICE-47_EBS FA to AHCS Recon Report - Balances (Functional) | BI-RICE-47_EBS | BI-RICE-47_EBS - Functional |  |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-20 17:23 | 2021-10-01 19:25 | 2021-08-08 | CSTONE Sprint 4 | 1A |  |  | BI-RICE-47 | RTR-BI | RTR | Build
User Story | CSTONE-3196 | BI-RICE-48_ERP POC to AHCS Recon Report - Detail (Functional) | BI-RICE-48_ERP | BI-RICE-48_ERP - Functional |  |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Not Started |  | 2021-08-20 17:23 | 2021-10-25 19:25 | 2021-08-08 |  | 1A |  |  | BI-RICE-48 | RTR-BI | RTR | Build
User Story | CSTONE-3197 | BI-RICE-49_ERP POC to AHCS Recon Report - Balances (Functional) | BI-RICE-49_ERP | BI-RICE-49_ERP - Functional |  |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-20 17:23 | 2021-10-01 19:25 | 2021-08-17 | CSTONE Sprint 4 | 1A |  |  | BI-RICE-49 | RTR-BI | RTR | Build
User Story | CSTONE-3198 | BI-RICE-56_10406 YTD Consol (Functional) | BI-RICE-56_10406 | BI-RICE-56_10406 - Functional |  |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-20 17:23 | 2021-10-01 19:27 | 2021-08-08 | CSTONE Sprint 4 | 1A |  |  | BI-RICE-56 | EPM-BI | EPM | Build
User Story | CSTONE-3199 | BI-RICE-57_Balance Sheet - Diana (Functional) | BI-RICE-57_Balance | BI-RICE-57_Balance - Functional |  |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-20 17:23 | 2021-10-01 19:27 | 2021-08-17 | CSTONE Sprint 4 | 1A |  |  | BI-RICE-57 | EPM-BI | EPM | Build
User Story | CSTONE-3200 | BI-RICE-58_Balance Sheet Invoice - Consolidated (Functional) | BI-RICE-58_Balance | BI-RICE-58_Balance - Functional |  |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-20 17:23 | 2021-10-01 19:27 | 2021-08-08 | CSTONE Sprint 4 | 1A |  |  | BI-RICE-58 | EPM-BI | EPM | Build
User Story | CSTONE-3201 | BI-RICE-59_Branch Header-Oracle (Functional) | BI-RICE-59_Branch | BI-RICE-59_Branch - Functional |  |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Blocked |  | 2021-08-20 17:23 | 2021-10-04 18:40 | 2021-08-17 | CSTONE Sprint 5 | 1A |  |  | BI-RICE-59 | EPM-BI | EPM | Build
User Story | CSTONE-3202 | BI-RICE-60_Karen 24 Month Report - CA (Functional) | BI-RICE-60_Karen | BI-RICE-60_Karen - Functional |  |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-20 17:23 | 2021-10-01 19:27 | 2021-08-17 | CSTONE Sprint 4 | 1A |  |  | BI-RICE-60 | EPM-BI | EPM | Build
User Story | CSTONE-3203 | BI-RICE-61_Karen 24 Month Report Consol (Functional) | BI-RICE-61_Karen | BI-RICE-61_Karen - Functional |  |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-20 17:23 | 2021-10-01 19:27 | 2021-08-17 | CSTONE Sprint 4 | 1A |  |  | BI-RICE-61 | EPM-BI | EPM | Build
User Story | CSTONE-3204 | BI-RICE-62_Oracle-Wesnet Acct Listing (Functional) | BI-RICE-62_Oracle-Wesnet | BI-RICE-62_Oracle-Wesnet - Functional |  |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Blocked |  | 2021-08-20 17:23 | 2021-10-04 18:40 | 2021-08-17 | CSTONE Sprint 5 | 1A |  |  | BI-RICE-62 | EPM-BI | EPM | Build
User Story | CSTONE-3205 | BI-RICE-63_PWC Gross Sales Grp (Functional) | BI-RICE-63_PWC | BI-RICE-63_PWC - Functional |  |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-20 17:23 | 2021-10-01 19:27 | 2021-08-17 | CSTONE Sprint 4 | 1A |  |  | BI-RICE-63 | EPM-BI | EPM | Build
User Story | CSTONE-3206 | BI-RICE-64_Sarah Gross Sales Reduction (Functional) | BI-RICE-64_Sarah | BI-RICE-64_Sarah - Functional |  |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-20 17:23 | 2021-10-01 19:27 | 2021-08-17 | CSTONE Sprint 4 | 1A |  |  | BI-RICE-64 | EPM-BI | EPM | Build
User Story | CSTONE-3207 | BI-RICE-65_Variance Report - Oracle (Functional) | BI-RICE-65_Variance | BI-RICE-65_Variance - Functional |  |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-20 17:23 | 2021-10-01 19:27 | 2021-08-17 | CSTONE Sprint 4 | 1A |  |  | BI-RICE-65 | EPM-BI | EPM | Build
User Story | CSTONE-3208 | BI-RICE-66_z03-I&E-YTD-Grp Report (Functional) | BI-RICE-66_z03-I&E-YTD-Grp | BI-RICE-66_z03-I&E-YTD-Grp - Functional |  |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-20 17:23 | 2021-10-01 19:27 | 2021-08-17 | CSTONE Sprint 4 | 1A |  |  | BI-RICE-66 | EPM-BI | EPM | Build
User Story | CSTONE-3209 | BI-RICE-67_z03-I&E-YTD-GrpBr Report (Functional) | BI-RICE-67_z03-I&E-YTD-GrpBr | BI-RICE-67_z03-I&E-YTD-GrpBr - Functional |  |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-20 17:23 | 2021-10-01 19:27 | 2021-08-17 | CSTONE Sprint 4 | 1A |  |  | BI-RICE-67 | EPM-BI | EPM | Build
User Story | CSTONE-3210 | BI-RICE-68_z03-I&E-YTD-GrpReg Report(Functional) | BI-RICE-68_z03-I&E-YTD-GrpReg | BI-RICE-68_z03-I&E-YTD-GrpReg - Functional |  |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-20 17:23 | 2021-10-01 19:27 | 2021-08-17 | CSTONE Sprint 4 | 1A |  |  | BI-RICE-68 | EPM-BI | EPM | Build
User Story | CSTONE-3211 | BI-RICE-69_z11-PY2selected lines Report (Functional) | BI-RICE-69_z11-PY2selected | BI-RICE-69_z11-PY2selected - Functional |  |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-20 17:23 | 2021-10-01 19:27 | 2021-08-17 | CSTONE Sprint 4 | 1A |  |  | BI-RICE-69 | EPM-BI | EPM | Build
User Story | CSTONE-3212 | BI-RICE-70_z12-PYselected lines Report (Functional) | BI-RICE-70_z12-PYselected | BI-RICE-70_z12-PYselected - Functional |  |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-20 17:23 | 2021-10-01 19:27 | 2021-08-17 | CSTONE Sprint 4 | 1A |  |  | BI-RICE-70 | EPM-BI | EPM | Build
User Story | CSTONE-3213 | BI-RICE-71_z13-CYselected lines Report (Functional) | BI-RICE-71_z13-CYselected | BI-RICE-71_z13-CYselected - Functional |  |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-20 17:23 | 2021-10-01 19:27 | 2021-08-17 | CSTONE Sprint 4 | 1A |  |  | BI-RICE-71 | EPM-BI | EPM | Build
User Story | CSTONE-3214 | BI-RICE-72_z6-Branch Header Report (Functional) | BI-RICE-72_z6-Branch | BI-RICE-72_z6-Branch - Functional |  |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Blocked |  | 2021-08-20 17:23 | 2021-10-04 18:40 | 2021-08-17 | CSTONE Sprint 5 | 1A |  |  | BI-RICE-72 | EPM-BI | EPM | Build
User Story | CSTONE-3215 | BI-RICE-74_Accounts by Month - Actual vs Budget (Functional) | BI-RICE-74_Accounts | BI-RICE-74_Accounts - Functional |  |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-20 17:23 | 2021-10-01 19:27 | 2021-08-17 | CSTONE Sprint 4 | 1A |  |  | BI-RICE-74 | EPM-BI | EPM | Build
User Story | CSTONE-3216 | BI-RICE-76_Accounts by Quarter - Actual vs Budget (Functional) | BI-RICE-76_Accounts | BI-RICE-76_Accounts - Functional |  |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-20 17:23 | 2021-10-01 19:27 | 2021-08-17 | CSTONE Sprint 4 | 1A |  |  | BI-RICE-76 | EPM-BI | EPM | Build
User Story | CSTONE-3217 | BI-RICE-77_Income Statement - Transportation by Month (Functional) | BI-RICE-77_Income | BI-RICE-77_Income - Functional |  |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-20 17:23 | 2021-10-01 19:27 | 2021-08-17 | CSTONE Sprint 4 | 1A |  |  | BI-RICE-77 | EPM-BI | EPM | Build
User Story | CSTONE-3218 | BI-RICE-78_Income Statement - Transportation by Quarter (Functional) | BI-RICE-78_Income | BI-RICE-78_Income - Functional |  |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-20 17:23 | 2021-10-01 19:27 | 2021-08-17 | CSTONE Sprint 4 | 1A |  |  | BI-RICE-78 | EPM-BI | EPM | Build
User Story | CSTONE-3219 | BI-RICE-79_Consolidated Income Statement (Functional) | BI-RICE-79_Consolidated | BI-RICE-79_Consolidated - Functional |  |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-20 17:23 | 2021-10-01 19:27 | 2021-08-17 | CSTONE Sprint 4 | 1A |  |  | BI-RICE-79 | EPM-BI | EPM | Build
User Story | CSTONE-3220 | BI-RICE-80_Corporate Goals by Month (Functional) | BI-RICE-80_Corporate | BI-RICE-80_Corporate - Functional |  |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-20 17:23 | 2021-10-01 19:27 | 2021-08-17 | CSTONE Sprint 4 | 1A |  |  | BI-RICE-80 | EPM-BI | EPM | Build
User Story | CSTONE-3221 | BI-RICE-81_87_z9_Adm_All (Functional) | BI-RICE-81_87_z9_Adm_All | BI-RICE-81_87_z9_Adm_All - Functional |  |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Not Started | Fixed | 2021-08-20 17:23 | 2021-10-28 17:59 | 2021-08-17 | CSTONE Sprint 7 | 1A |  |  | BI-RICE-81 | EPM-BI | EPM | Build
User Story | CSTONE-3222 | BI-RICE-82_88_z9_Adm_Trail (Functional) | BI-RICE-82_88_z9_Adm_Trail | BI-RICE-82_88_z9_Adm_Trail - Functional |  |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Not Started | Fixed | 2021-08-20 17:23 | 2021-10-28 17:59 | 2021-08-17 | CSTONE Sprint 7 | 1A |  |  | BI-RICE-82 | EPM-BI | EPM | Build
User Story | CSTONE-3223 | BI-RICE-83_89_z9_Adm_TrailCAD (Functional) | BI-RICE-83_89_z9_Adm_TrailCAD | BI-RICE-83_89_z9_Adm_TrailCAD - Functional |  |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Not Started | Fixed | 2021-08-20 17:23 | 2021-10-28 18:00 | 2021-08-17 | CSTONE Sprint 7 | 1A |  |  | BI-RICE-83 | EPM-BI | EPM | Build
User Story | CSTONE-3224 | BI-RICE-84_90_z9_VarAnUSD_All (Functional) | BI-RICE-84_90_z9_VarAnUSD_All | BI-RICE-84_90_z9_VarAnUSD_All - Functional |  |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Not Started | Fixed | 2021-08-20 17:23 | 2021-10-28 18:01 | 2021-08-17 | CSTONE Sprint 7 | 1A |  |  | BI-RICE-84 | EPM-BI | EPM | Build
User Story | CSTONE-3225 | BI-RICE-85_91_z9_VarAnUSD_Consol (Functional) | BI-RICE-85_91_z9_VarAnUSD_Consol | BI-RICE-85_91_z9_VarAnUSD_Consol - Functional |  |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Not Started | Fixed | 2021-08-20 17:23 | 2021-10-28 18:02 | 2021-08-17 | CSTONE Sprint 7 | 1A |  |  | BI-RICE-85 | EPM-BI | EPM | Build
User Story | CSTONE-3226 | BI-RICE-86_92_z9_VarAnUSD_Trail_All (Functional) | BI-RICE-86_92_z9_VarAnUSD_Trail_All | BI-RICE-86_92_z9_VarAnUSD_Trail_All - Functional |  |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Not Started | Fixed | 2021-08-20 17:23 | 2021-10-28 18:02 | 2021-08-17 | CSTONE Sprint 7 | 1A |  |  | BI-RICE-86 | EPM-BI | EPM | Build
User Story | CSTONE-3227 | BI-RICE-3_New Recon tables: DSS_TABLES.ORACLE_CLD_AHCS_BAL, DSS_TABLES.EBS_SUBLEDGER_BAL (Technical) | BI-RICE-3_New |  | BI-RICE-3_New - Technical |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-20 17:23 | 2021-10-18 19:30 | 2021-08-17 | CSTONE Sprint 5 | 1A |  |  | BI-RICE-3 | RTR-BI | RTR | Build
User Story | CSTONE-3228 | BI-RICE-4_New tables: DSS_TABLES.ORACLE_CLD_AHCS_DET, DSS_TABLES.EBS_SUBLEDGER_DET (Technical) | BI-RICE-4_New |  | BI-RICE-4_New - Technical |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-20 17:23 | 2021-10-11 19:13 | 2021-08-08 | CSTONE Sprint 5 | 1A |  |  | BI-RICE-4 | RTR-BI | RTR | Build
User Story | CSTONE-3229 | BI-RICE-10_EBS AP to AHCS Recon Report - Detail (Technical) | BI-RICE-10_EBS |  | BI-RICE-10_EBS - Technical |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-20 17:23 | 2021-10-26 18:09 | 2021-08-17 | CSTONE Sprint 5 | 1A |  |  | BI-RICE-10 | RTR-BI | RTR | Build
User Story | CSTONE-3230 | BI-RICE-11_EBS AR to AHCS Recon Report - Detail(Technical) | BI-RICE-11_EBS |  | BI-RICE-11_EBS - Technical |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-20 17:23 | 2021-10-26 18:09 | 2021-08-08 | CSTONE Sprint 5 | 1A |  |  | BI-RICE-11 | RTR-BI | RTR | Build
User Story | CSTONE-3231 | BI-RICE-12_EBS FA to AHCS Recon Report - Detail (Technical) | BI-RICE-12_EBS |  | BI-RICE-12_EBS - Technical |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-20 17:23 | 2021-10-26 18:09 | 2021-08-17 | CSTONE Sprint 5 | 1A |  |  | BI-RICE-12 | RTR-BI | RTR | Build
User Story | CSTONE-3232 | BI-RICE-18_AHCS Spending Per Employee (Technical) | BI-RICE-18_AHCS |  | BI-RICE-18_AHCS - Technical |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Not Started |  | 2021-08-20 17:23 | 2021-10-01 19:25 | 2021-08-08 |  | 1A |  |  | BI-RICE-18 | RTR-BI | RTR | Build
User Story | CSTONE-3233 | BI-RICE-25_dss_tables.wgroup (Technical) | BI-RICE-25_dss_tables.wgroup |  | BI-RICE-25_dss_tables.wgroup - Technical |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Not Started |  | 2021-08-20 17:24 | 2021-10-01 19:25 | 2021-08-17 |  | 1A |  |  | BI-RICE-25 | RTR-BI | RTR | Build
User Story | CSTONE-3234 | BI-RICE-26_dss_tables.region (Technical) | BI-RICE-26_dss_tables.region |  | BI-RICE-26_dss_tables.region - Technical |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Not Started |  | 2021-08-20 17:24 | 2021-10-01 19:25 | 2021-08-17 |  | 1A |  |  | BI-RICE-26 | RTR-BI | RTR | Build
User Story | CSTONE-3235 | BI-RICE-27_dss_tables.district (Technical) | BI-RICE-27_dss_tables.district |  | BI-RICE-27_dss_tables.district - Technical |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Not Started |  | 2021-08-20 17:24 | 2021-10-01 19:25 | 2021-08-17 |  | 1A |  |  | BI-RICE-27 | RTR-BI | RTR | Build
User Story | CSTONE-3236 | BI-RICE-45_EBS AP to AHCS Recon Report - Balances (Technical) | BI-RICE-45_EBS |  | BI-RICE-45_EBS - Technical |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-20 17:24 | 2021-10-26 18:09 | 2021-08-17 | CSTONE Sprint 5 | 1A |  |  | BI-RICE-45 | RTR-BI | RTR | Build
User Story | CSTONE-3237 | BI-RICE-46_EBS AR to AHCS Recon Report - Balances (Technical) | BI-RICE-46_EBS |  | BI-RICE-46_EBS - Technical |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-20 17:24 | 2021-10-26 18:10 | 2021-08-17 | CSTONE Sprint 5 | 1A |  |  | BI-RICE-46 | RTR-BI | RTR | Build
User Story | CSTONE-3238 | BI-RICE-47_EBS FA to AHCS Recon Report - Balances (Technical) | BI-RICE-47_EBS |  | BI-RICE-47_EBS - Technical |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-20 17:24 | 2021-10-26 18:10 | 2021-08-08 | CSTONE Sprint 5 | 1A |  |  | BI-RICE-47 | RTR-BI | RTR | Build
User Story | CSTONE-3239 | BI-RICE-48_ERP POC to AHCS Recon Report - Detail (Technical) | BI-RICE-48_ERP |  | BI-RICE-48_ERP - Technical |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Not Started |  | 2021-08-20 17:24 | 2021-10-25 19:40 | 2021-08-08 |  | 1A |  |  | BI-RICE-48 | RTR-BI | RTR | Build
User Story | CSTONE-3240 | BI-RICE-49_ERP POC to AHCS Recon Report - Balances (Technical) | BI-RICE-49_ERP |  | BI-RICE-49_ERP - Technical |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-20 17:24 | 2021-10-26 18:10 | 2021-08-17 | CSTONE Sprint 5 | 1A |  |  | BI-RICE-49 | RTR-BI | RTR | Build
User Story | CSTONE-3241 | BI-RICE-56_10406 YTD Consol (Technical) | BI-RICE-56_10406 |  | BI-RICE-56_10406 - Technical |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-20 17:24 | 2021-10-26 18:14 | 2021-08-08 | CSTONE Sprint 5 | 1A |  |  | BI-RICE-56 | EPM-BI | EPM | Build
User Story | CSTONE-3242 | BI-RICE-57_Balance Sheet - Diana (Technical) | BI-RICE-57_Balance |  | BI-RICE-57_Balance - Technical |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-20 17:24 | 2021-10-12 15:58 | 2021-08-17 | CSTONE Sprint 5 | 1A |  |  | BI-RICE-57 | EPM-BI | EPM | Build
User Story | CSTONE-3243 | BI-RICE-58_Balance Sheet Invoice - Consolidated(Technical) | BI-RICE-58_Balance |  | BI-RICE-58_Balance - Technical |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-20 17:24 | 2021-10-26 18:15 | 2021-08-08 | CSTONE Sprint 5 | 1A |  |  | BI-RICE-58 | EPM-BI | EPM | Build
User Story | CSTONE-3244 | BI-RICE-59_Branch Header-Oracle (Technical) | BI-RICE-59_Branch |  | BI-RICE-59_Branch - Technical |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Not Started |  | 2021-08-20 17:24 | 2021-10-01 19:27 | 2021-08-17 |  | 1A |  |  | BI-RICE-59 | EPM-BI | EPM | Build
User Story | CSTONE-3245 | BI-RICE-60_Karen 24 Month Report - CA (Technical) | BI-RICE-60_Karen |  | BI-RICE-60_Karen - Technical |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-20 17:24 | 2021-10-26 18:15 | 2021-08-17 | CSTONE Sprint 5 | 1A |  |  | BI-RICE-60 | EPM-BI | EPM | Build
User Story | CSTONE-3246 | BI-RICE-61_Karen 24 Month Report Consol (Technical) | BI-RICE-61_Karen |  | BI-RICE-61_Karen - Technical |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-20 17:24 | 2021-10-26 18:15 | 2021-08-17 | CSTONE Sprint 5 | 1A |  |  | BI-RICE-61 | EPM-BI | EPM | Build
User Story | CSTONE-3247 | BI-RICE-62_Oracle-Wesnet Acct Listing (Technical) | BI-RICE-62_Oracle-Wesnet |  | BI-RICE-62_Oracle-Wesnet - Technical |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Not Started |  | 2021-08-20 17:24 | 2021-10-01 19:27 | 2021-08-17 |  | 1A |  |  | BI-RICE-62 | EPM-BI | EPM | Build
User Story | CSTONE-3248 | BI-RICE-63e EPM-FCCS-BI-11 (Technical) | BI-RICE-63e |  | BI-RICE-63e - Technical |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-20 17:24 | 2021-10-26 18:16 | 2021-08-17 | CSTONE Sprint 5 | 1A |  |  | BI-RICE-63 | EPM-BI | EPM | Build
User Story | CSTONE-3249 | BI-RICE-64_Sarah Gross Sales Reduction (Technical) | BI-RICE-64_Sarah |  | BI-RICE-64_Sarah - Technical |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-20 17:24 | 2021-10-12 16:03 | 2021-08-17 | CSTONE Sprint 5 | 1A |  |  | BI-RICE-64 | EPM-BI | EPM | Build
User Story | CSTONE-3250 | BI-RICE-65_Variance Report - Oracle (Technical) | BI-RICE-65_Variance |  | BI-RICE-65_Variance - Technical |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-20 17:24 | 2021-10-26 18:16 | 2021-08-17 | CSTONE Sprint 5 | 1A |  |  | BI-RICE-65 | EPM-BI | EPM | Build
User Story | CSTONE-3251 | BI-RICE-66_z03-I&E-YTD-Grp Report (Technical) | BI-RICE-66_z03-I&E-YTD-Grp |  | BI-RICE-66_z03-I&E-YTD-Grp - Technical |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-20 17:24 | 2021-10-26 18:12 | 2021-08-17 | CSTONE Sprint 5 | 1A |  |  | BI-RICE-66 | EPM-BI | EPM | Build
User Story | CSTONE-3252 | BI-RICE-67_z03-I&E-YTD-GrpBr Report (Technical) | BI-RICE-67_z03-I&E-YTD-GrpBr |  | BI-RICE-67_z03-I&E-YTD-GrpBr - Technical |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-20 17:24 | 2021-10-26 18:12 | 2021-08-17 | CSTONE Sprint 5 | 1A |  |  | BI-RICE-67 | EPM-BI | EPM | Build
User Story | CSTONE-3253 | BI-RICE-68_z03-I&E-YTD-GrpReg Report (Technical) | BI-RICE-68_z03-I&E-YTD-GrpReg |  | BI-RICE-68_z03-I&E-YTD-GrpReg - Technical |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-20 17:24 | 2021-10-26 18:12 | 2021-08-17 | CSTONE Sprint 5 | 1A |  |  | BI-RICE-68 | EPM-BI | EPM | Build
User Story | CSTONE-3254 | BI-RICE-69_z11-PY2selected lines Report (Technical) | BI-RICE-69_z11-PY2selected |  | BI-RICE-69_z11-PY2selected - Technical |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-20 17:24 | 2021-10-26 18:13 | 2021-08-17 | CSTONE Sprint 5 | 1A |  |  | BI-RICE-69 | EPM-BI | EPM | Build
User Story | CSTONE-3255 | BI-RICE-70_z12-PYselected lines Report (Technical) | BI-RICE-70_z12-PYselected |  | BI-RICE-70_z12-PYselected - Technical |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-20 17:24 | 2021-10-26 18:13 | 2021-08-17 | CSTONE Sprint 5 | 1A |  |  | BI-RICE-70 | EPM-BI | EPM | Build
User Story | CSTONE-3256 | BI-RICE-71_z13-CYselected lines Report (Technical) | BI-RICE-71_z13-CYselected |  | BI-RICE-71_z13-CYselected - Technical |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-20 17:24 | 2021-10-26 18:13 | 2021-08-17 | CSTONE Sprint 5 | 1A |  |  | BI-RICE-71 | EPM-BI | EPM | Build
User Story | CSTONE-3257 | BI-RICE-72_z6-Branch Header Report (Technical) | BI-RICE-72_z6-Branch |  | BI-RICE-72_z6-Branch - Technical |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Not Started |  | 2021-08-20 17:24 | 2021-10-01 19:27 | 2021-08-17 |  | 1A |  |  | BI-RICE-72 | EPM-BI | EPM | Build
User Story | CSTONE-3258 | BI-RICE-74_Accounts by Month - Actual vs Budget (Technical) | BI-RICE-74_Accounts |  | BI-RICE-74_Accounts - Technical |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-20 17:24 | 2021-10-12 15:57 | 2021-08-17 | CSTONE Sprint 5 | 1A |  |  | BI-RICE-74 | EPM-BI | EPM | Build
User Story | CSTONE-3259 | BI-RICE-76_Accounts by Quarter - Actual vs Budget(Technical) | BI-RICE-76_Accounts |  | BI-RICE-76_Accounts - Technical |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-20 17:24 | 2021-10-12 15:57 | 2021-08-17 | CSTONE Sprint 5 | 1A |  |  | BI-RICE-76 | EPM-BI | EPM | Build
User Story | CSTONE-3260 | BI-RICE-77_Income Statement - Transportation by Month (Technical) | BI-RICE-77_Income |  | BI-RICE-77_Income - Technical |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-20 17:24 | 2021-10-12 16:00 | 2021-08-17 | CSTONE Sprint 5 | 1A |  |  | BI-RICE-77 | EPM-BI | EPM | Build
User Story | CSTONE-3261 | BI-RICE-78_Income Statement - Transportation by Quarter (Technical) | BI-RICE-78_Income |  | BI-RICE-78_Income - Technical |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-20 17:24 | 2021-10-12 16:00 | 2021-08-17 | CSTONE Sprint 5 | 1A |  |  | BI-RICE-78 | EPM-BI | EPM | Build
User Story | CSTONE-3262 | BI-RICE-79_Consolidated Income Statement (Technical) | BI-RICE-79_Consolidated |  | BI-RICE-79_Consolidated - Technical |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-20 17:24 | 2021-10-12 15:58 | 2021-08-17 | CSTONE Sprint 5 | 1A |  |  | BI-RICE-79 | EPM-BI | EPM | Build
User Story | CSTONE-3263 | BI-RICE-80_Corporate Goals by Month (Technical) | BI-RICE-80_Corporate |  | BI-RICE-80_Corporate - Technical |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Done | Fixed | 2021-08-20 17:24 | 2021-10-12 15:59 | 2021-08-17 | CSTONE Sprint 5 | 1A |  |  | BI-RICE-80 | EPM-BI | EPM | Build
User Story | CSTONE-3264 | BI-RICE-81_87_z9_Adm_All (Technical) | BI-RICE-81_87_z9_Adm_All |  | BI-RICE-81_87_z9_Adm_All - Technical |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Not Started | Fixed | 2021-08-20 17:24 | 2021-10-28 17:36 | 2021-08-17 | CSTONE Sprint 7 | 1A |  |  | BI-RICE-81 | EPM-BI | EPM | Build
User Story | CSTONE-3265 | BI-RICE-82_88_z9_Adm_Trail (Technical) | BI-RICE-82_88_z9_Adm_Trail |  | BI-RICE-82_88_z9_Adm_Trail - Technical |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Not Started |  | 2021-08-20 17:24 | 2021-10-28 17:30 | 2021-08-17 | CSTONE Sprint 7 | 1A |  |  | BI-RICE-82 | EPM-BI | EPM | Build
User Story | CSTONE-3266 | BI-RICE-83_89_z9_Adm_TrailCAD (Technical) | BI-RICE-83_89_z9_Adm_TrailCAD |  | BI-RICE-83_89_z9_Adm_TrailCAD - Technical |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Not Started | Fixed | 2021-08-20 17:24 | 2021-10-28 17:37 | 2021-08-17 | CSTONE Sprint 7 | 1A |  |  | BI-RICE-83 | EPM-BI | EPM | Build
User Story | CSTONE-3267 | BI-RICE-84_90_z9_VarAnUSD_All (Technical) | BI-RICE-84_90_z9_VarAnUSD_All |  | BI-RICE-84_90_z9_VarAnUSD_All - Technical |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Not Started | Fixed | 2021-08-20 17:24 | 2021-10-28 17:38 | 2021-08-17 | CSTONE Sprint 7 | 1A |  |  | BI-RICE-84 | EPM-BI | EPM | Build
User Story | CSTONE-3268 | BI-RICE-85_91_z9_VarAnUSD_Consol (Technical) | BI-RICE-85_91_z9_VarAnUSD_Consol |  | BI-RICE-85_91_z9_VarAnUSD_Consol - Technical |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Not Started | Fixed | 2021-08-20 17:24 | 2021-10-28 17:40 | 2021-08-17 | CSTONE Sprint 7 | 1A |  |  | BI-RICE-85 | EPM-BI | EPM | Build
User Story | CSTONE-3269 | BI-RICE-86_92_z9_VarAnUSD_Trail_All (Technical) | BI-RICE-86_92_z9_VarAnUSD_Trail_All |  | BI-RICE-86_92_z9_VarAnUSD_Trail_All - Technical |  |  | Jeremy Hornbuckle | Mehul Kumar Patel |  | Not Started |  | 2021-08-20 17:24 | 2021-10-28 17:31 | 2021-08-17 | CSTONE Sprint 7 | 1A |  |  | BI-RICE-86 | EPM-BI | EPM | Build
User Story | CSTONE-3571 | BI-RICE-75_Accounts by Quarter - Actual (Technical) | BI-RICE-75_Accounts |  | BI-RICE-75_Accounts - Technical |  |  | Jeremy Hornbuckle | Jbastidas |  | Done | Fixed | 2021-08-26 21:20 | 2021-10-25 13:27 | 2021-08-17 | CSTONE Sprint 4 | 1A |  |  | BI-RICE-75 (Functional) | RTR-BI | RTR | Build
User Story | CSTONE-3572 | BI-RICE-73_Accounts by Month - Actual (Technical) | BI-RICE-73_Accounts |  | BI-RICE-73_Accounts - Technical |  |  | Jeremy Hornbuckle | Jbastidas |  | Done | Fixed | 2021-08-26 21:22 | 2021-10-25 13:27 | 2021-08-17 | CSTONE Sprint 4 | 1A |  |  | BI-RICE-73 (Functional) | RTR-BI | RTR | Build
User Story | CSTONE-3573 | BI-RICE-55_EPBCS Reporting Tables (Technical) | BI-RICE-55_EPBCS |  | BI-RICE-55_EPBCS - Technical |  |  | Jeremy Hornbuckle | Jbastidas |  | Done | Fixed | 2021-08-26 21:23 | 2021-10-04 18:48 |  | CSTONE Sprint 5 | 1A |  |  | BI-RICE-55 (Functional) | EPM-BI | EPM | Build
User Story | CSTONE-3574 | BI-RICE-54_FCCS Reporting Tables (Technical) | BI-RICE-54_FCCS |  | BI-RICE-54_FCCS - Technical |  |  | Jeremy Hornbuckle | Jbastidas |  | Done | Fixed | 2021-08-26 21:28 | 2021-10-01 19:27 | 2021-08-17 | CSTONE Sprint 4 | 1A |  |  | BI-RICE-54 (Functional) | EPM-BI | EPM | Build
User Story | CSTONE-3575 | BI-RICE-53_EPBCS Data Target Table (Technical) | BI-RICE-53_EPBCS |  | BI-RICE-53_EPBCS - Technical |  |  | Jeremy Hornbuckle | Jbastidas |  | Done | Fixed | 2021-08-26 21:29 | 2021-10-01 19:27 | 2021-08-17 | CSTONE Sprint 4 | 1A |  |  | BI-RICE-53 (Functional) | EPM-BI | EPM | Build
User Story | CSTONE-3576 | BI-RICE-52_FCCS Data Target Table (Technical) | BI-RICE-52_FCCS |  | BI-RICE-52_FCCS - Technical |  |  | Jeremy Hornbuckle | Jbastidas |  | Done | Fixed | 2021-08-26 21:30 | 2021-10-01 19:27 | 2021-08-17 | CSTONE Sprint 4 | 1A |  |  | BI-RICE-52 (Functional) | EPM-BI | EPM | Build
User Story | CSTONE-3577 | BI-RICE-51_EPBCS hierarchy tables (Technical) | BI-RICE-51_EPBCS |  | BI-RICE-51_EPBCS - Technical |  |  | Jeremy Hornbuckle | Jbastidas |  | Done | Fixed | 2021-08-26 21:31 | 2021-10-04 18:50 | 2021-08-17 | CSTONE Sprint 5 | 1A |  |  | BI-RICE-51 (Functional) | EPM-BI | EPM | Build
User Story | CSTONE-3578 | BI-RICE-50_FCCS hierarchy tables (Technical) | BI-RICE-50_FCCS |  | BI-RICE-50_FCCS - Technical |  |  | Jeremy Hornbuckle | Jbastidas |  | Done | Fixed | 2021-08-26 21:31 | 2021-10-01 19:27 | 2021-08-17 | CSTONE Sprint 4 | 1A |  |  | BI-RICE-50 (Functional) | EPM-BI | EPM | Build
User Story | CSTONE-3579 | BI-RICE-44_YTD vs Last Year (Technical) | BI-RICE-44_YTD |  | BI-RICE-44_YTD - Technical |  |  | Jeremy Hornbuckle | Jbastidas |  | Done | Fixed | 2021-08-26 21:35 | 2021-10-25 13:27 | 2021-08-17 | CSTONE Sprint 4 | 1A |  |  | BI-RICE-44 (Functional) | RTR-BI | RTR | Build
User Story | CSTONE-3580 | BI-RICE-43_Sales $ by Shipment Type(Technical) | BI-RICE-43_Sales |  | BI-RICE-43_Sales - Technical |  |  | Jeremy Hornbuckle | Jbastidas |  | Done | Fixed | 2021-08-26 21:36 | 2021-10-25 13:27 | 2021-08-17 | CSTONE Sprint 4 | 1A |  |  | BI-RICE-43 (Functional) | RTR-BI | RTR | Build
User Story | CSTONE-3581 | BI-RICE-42_MTD vs Last Year (Technical) | BI-RICE-42_MTD |  | BI-RICE-42_MTD - Technical |  |  | Jeremy Hornbuckle | Jbastidas |  | Done | Fixed | 2021-08-26 21:37 | 2021-10-25 13:27 | 2021-08-17 | CSTONE Sprint 4 | 1A |  |  | BI-RICE-42 (Functional) | RTR-BI | RTR | Build
User Story | CSTONE-3582 | BI-RICE-41_Daily Sales by Current Workday (Technical) | BI-RICE-41_Daily |  | BI-RICE-41_Daily - Technical |  |  | Jeremy Hornbuckle | Jbastidas |  | Done | Fixed | 2021-08-26 21:38 | 2021-10-25 13:27 | 2021-08-17 | CSTONE Sprint 4 | 1A |  |  | BI-RICE-41 (Functional) | RTR-BI | RTR | Build
User Story | CSTONE-3583 | BI-RICE-40_Billing Margin Analysis by Month (Technical) | BI-RICE-40_Billing |  | BI-RICE-40_Billing - Technical |  |  | Jeremy Hornbuckle | Jbastidas |  | Done | Fixed | 2021-08-26 21:44 | 2021-10-25 13:27 | 2021-08-17 | CSTONE Sprint 4 | 1A |  |  | BI-RICE-40 (Functional) | RTR-BI | RTR | Build
User Story | CSTONE-3584 | BI-RICE-39_Billing Margin % by Shipment Type (Technical) | BI-RICE-39_Billing |  | BI-RICE-39_Billing - Technical |  |  | Jeremy Hornbuckle | Jbastidas |  | Done | Fixed | 2021-08-26 21:45 | 2021-10-25 13:27 | 2021-08-17 | CSTONE Sprint 4 | 1A |  |  | BI-RICE-39 (Functional) | RTR-BI | RTR | Build
User Story | CSTONE-3585 | BI-RICE-32_Downstream Tables/Views for Operational Reporting (Technical) | BI-RICE-32_Downstream |  | BI-RICE-32_Downstream - Technical |  |  | Jeremy Hornbuckle | Jbastidas |  | Done | Fixed | 2021-08-26 21:49 | 2021-10-01 19:25 |  | CSTONE Sprint 4 | 1A |  |  |  | RTR-BI | RTR | Build
User Story | CSTONE-3586 | BI-RICE-31_Downstream Tables/Views for Operational Reporting (Technical) | BI-RICE-31_Downstream |  | BI-RICE-31_Downstream - Technical |  |  | Jeremy Hornbuckle | Jbastidas |  | Done | Fixed | 2021-08-26 21:51 | 2021-10-01 19:25 |  | CSTONE Sprint 4 | 1A |  |  |  | RTR-BI | RTR | Build
User Story | CSTONE-3587 | BI-RICE-30_Downstream Tables/Views for Operational Reporting (Technical) | BI-RICE-30_Downstream |  | BI-RICE-30_Downstream - Technical |  |  | Jeremy Hornbuckle | Jbastidas |  | Done | Fixed | 2021-08-26 21:54 | 2021-10-01 19:25 |  | CSTONE Sprint 4 | 1A |  |  |  | RTR-BI | RTR | Build
User Story | CSTONE-3588 | BI-RICE-29_Downstream Tables/Views for Operational Reporting (Technical) | BI-RICE-29_Downstream |  | BI-RICE-29_Downstream - Technical |  |  | Jeremy Hornbuckle | Jbastidas |  | Done | Fixed | 2021-08-26 21:55 | 2021-10-01 19:25 |  | CSTONE Sprint 4 | 1A |  |  |  | RTR-BI | RTR | Build
User Story | CSTONE-3589 | BI-RICE-28_Downstream Tables/Views for Operational Reporting (Technical) | BI-RICE-28_Downstream |  | BI-RICE-28_Downstream - Technical |  |  | Jeremy Hornbuckle | Jbastidas |  | Done | Fixed | 2021-08-26 21:56 | 2021-10-01 19:25 |  | CSTONE Sprint 4 | 1A |  |  |  | RTR-BI | RTR | Build
User Story | CSTONE-3624 | RTR-GL-006 (Functional) | RTR-GL-006 | RTR-GL-006 - Functional |  |  |  | Satheesh Kumar Gooda | Mehul Kumar Patel |  | Done | Fixed | 2021-09-02 17:57 | 2021-09-24 17:31 |  | CSTONE Sprint 4 | 1A+1B |  |  | RPT001 | RTR-GL | RTR | Build
User Story | CSTONE-3625 | RTR-GL-095 (Functional) | RTR-GL-095 | RTR-GL-095 - Functional |  |  |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-09-02 17:57 | 2021-09-21 12:45 |  | CSTONE Sprint 4 | 1A+1B |  |  | RPT042 | RTR-GL | RTR | Build
User Story | CSTONE-3626 | RTR-GL-010 (Technical) | RTR-GL-010 |  | RTR-GL-010 - Technical |  |  | Chowdari, Malapati Monika | Mehul Kumar Patel |  | Done | Fixed | 2021-09-02 17:57 | 2021-09-15 12:35 |  | CSTONE Sprint 4 | 1A+1B |  |  | RPT002 | RTR-GL | RTR | Build
User Story | CSTONE-3627 | RTR-GL-013 (Technical) | RTR-GL-013 |  | RTR-GL-013 - Technical |  |  | Satheesh Kumar Gooda | Mehul Kumar Patel |  | Done | Fixed | 2021-09-02 17:57 | 2021-10-15 14:38 |  | CSTONE Sprint 5 | 1A+1B |  |  | RPT003 | RTR-GL | RTR | Build
User Story | CSTONE-3628 | RTR-GL-017 (Technical) | RTR-GL-017 |  | RTR-GL-017 - Technical |  |  | Mamatha, Tata | Mehul Kumar Patel |  | Done | Fixed | 2021-09-02 17:57 | 2021-09-15 12:40 |  | CSTONE Sprint 4 | 1A+1B |  |  | RPT004 | RTR-GL | RTR | Build
User Story | CSTONE-3629 | RTR-GL-018 (Technical) | RTR-GL-018 |  | RTR-GL-018 - Technical |  |  | Mamatha, Tata | Mehul Kumar Patel |  | Done | Fixed | 2021-09-02 17:57 | 2021-09-15 12:43 |  | CSTONE Sprint 4 | 1A+1B |  |  | RPT004 | RTR-GL | RTR | Build
User Story | CSTONE-3630 | RTR-GL-075 (Technical) | RTR-GL-075 |  | RTR-GL-075 - Technical |  |  | Satheesh Kumar Gooda | Mehul Kumar Patel |  | Done | Fixed | 2021-09-02 17:57 | 2021-10-15 19:21 |  | CSTONE Sprint 5 | 1A+1B |  |  | RPT005 | RTR-GL | RTR | Build
User Story | CSTONE-3631 | RTR-GL-077 (Technical) | RTR-GL-077 |  | RTR-GL-077 - Technical |  |  | Ramji Agrawal | Mehul Kumar Patel |  | Done | Fixed | 2021-09-02 17:57 | 2021-09-22 12:15 |  | CSTONE Sprint 4 | 1A+1B |  |  | RPT009 | RTR-GL | RTR | Build
User Story | CSTONE-3632 | RTR-GL-106 (Technical) | RTR-GL-106 |  | RTR-GL-106 - Technical |  |  | Astha Shrivastava | Mehul Kumar Patel |  | Done | Fixed | 2021-09-02 17:57 | 2021-10-05 10:14 |  | CSTONE Sprint 5 | 1A+1B |  |  | RPT043 | RTR-GL | RTR | Build
User Story | CSTONE-3633 | REP-RTR-GL-63 (Technical) | REP-RTR-GL-63 |  | REP-RTR-GL-63 - Technical |  |  | Chowdari, Malapati Monika | Mehul Kumar Patel |  | Done | Fixed | 2021-09-02 17:57 | 2021-09-15 12:54 |  | CSTONE Sprint 4 | 1A |  |  | RPT002 | RTR-GL | RTR | Build
User Story | CSTONE-3634 | REP-RTR-GL-69 (Technical) | REP-RTR-GL-69 |  | REP-RTR-GL-69 - Technical |  |  | Satheesh Kumar Gooda | Mehul Kumar Patel |  | In Progress |  | 2021-09-02 17:57 | 2021-10-04 18:39 |  | CSTONE Sprint 5 | 1A |  |  | RPT044 | RTR-GL | RTR | Build
User Story | CSTONE-3635 | REP-RTR-GL-70 (Technical) | REP-RTR-GL-70 |  | REP-RTR-GL-70 - Technical |  |  | Satheesh Kumar Gooda | Mehul Kumar Patel |  | Done | Fixed | 2021-09-02 17:57 | 2021-10-22 15:16 |  | CSTONE Sprint 5 | 1A |  |  | RPT003 | RTR-GL | RTR | Build
User Story | CSTONE-3636 | REP-RTR-GL-79 (Technical) | REP-RTR-GL-79 |  | REP-RTR-GL-79 - Technical |  |  | Harshit Gangwar | Mehul Kumar Patel |  | Done | Fixed | 2021-09-02 17:57 | 2021-10-08 13:48 |  | CSTONE Sprint 5 | 1A+1B |  |  | RPT045 | RTR-GL | RTR | Build
User Story | CSTONE-3637 | RTR-AHCS-024 (Technical) | RTR-AHCS-024 |  | RTR-AHCS-024 - Technical |  |  | Manpreet Singh | Mehul Kumar Patel |  | Done | Fixed | 2021-09-02 17:57 | 2021-10-15 15:29 |  | CSTONE Sprint 5 | 1A+1B |  |  | INT012 | RTR-AHCS | RTR | Build
User Story | CSTONE-3638 | RTR-AHCS-025 (Technical) | RTR-AHCS-025 |  | RTR-AHCS-025 - Technical |  |  | Chowdari, Malapati Monika | Mehul Kumar Patel |  | Done | Fixed | 2021-09-02 17:57 | 2021-09-28 10:58 |  | CSTONE Sprint 4 | 1A+1B |  |  | RPT007 | RTR-AHCS | RTR | Build
User Story | CSTONE-3639 | RTR-AHCS-027 (Technical) | RTR-AHCS-027 |  | RTR-AHCS-027 - Technical |  |  | Manpreet Singh | Mehul Kumar Patel |  | Done | Fixed | 2021-09-02 17:57 | 2021-09-15 19:24 |  | CSTONE Sprint 4 | 1A+1B |  |  | RPT008 | RTR-AHCS | RTR | Build
User Story | CSTONE-3640 | RTR-AHCS-044 (Technical) | RTR-AHCS-044 |  | RTR-AHCS-044 - Technical |  |  | Manpreet Singh | Mehul Kumar Patel |  | Blocked |  | 2021-09-02 17:57 | 2021-10-04 18:39 |  | CSTONE Sprint 5 | 1A |  |  | INT016 | RTR-AHCS | RTR | Build
User Story | CSTONE-3641 | RTR-GL-117 (Technical) | RTR-GL-117 |  | RTR-GL-117 - Technical |  |  | Devang Pandya | Mehul Kumar Patel |  | Done | Fixed | 2021-09-02 17:57 | 2021-09-13 06:50 |  | CSTONE Sprint 4 | 1A+1B |  |  | EXT013 | RTR-GL | RTR | Build
User Story | CSTONE-3642 | REP-RTR-GL-4 (Technical) | REP-RTR-GL-4 |  | REP-RTR-GL-4 - Technical |  |  | Ramji Agrawal | Mehul Kumar Patel |  | Done | Fixed | 2021-09-02 17:57 | 2021-09-23 06:20 |  | CSTONE Sprint 4 | 1A+1B |  |  | RPT009 | RTR-GL | RTR | Build
User Story | CSTONE-3643 | REP-RTR-GL-67-B (Technical) | REP-RTR-GL-67-B |  | REP-RTR-GL-67-B - Technical |  |  | Devang Pandya | Mehul Kumar Patel |  | Done | Fixed | 2021-09-02 17:57 | 2021-09-13 06:50 |  | CSTONE Sprint 4 | 1A |  |  | EXT013 | RTR-GL | RTR | Build
User Story | CSTONE-3644 | RTR-GL-135 (Technical) | RTR-GL-135 |  | RTR-GL-135 - Technical |  |  | Devang Pandya | Mehul Kumar Patel |  | Done | Fixed | 2021-09-02 17:57 | 2021-09-13 06:49 |  | CSTONE Sprint 4 | 1A+1B |  |  | EXT012 | RTR-GL | RTR | Build
User Story | CSTONE-3645 | RTR-GL-141 (Technical) | RTR-GL-141 |  | RTR-GL-141 - Technical |  |  | Mamatha, Tata | Mehul Kumar Patel |  | Done | Fixed | 2021-09-02 17:57 | 2021-10-08 18:56 |  | CSTONE Sprint 5 | 1A |  |  | INT012 | RTR-AHCS | RTR | Build
User Story | CSTONE-3646 | RTR-GL-143 (Technical) | RTR-GL-143 |  | RTR-GL-143 - Technical |  |  | Girish R Acharya | Mehul Kumar Patel |  | Done | Fixed | 2021-09-02 17:57 | 2021-10-08 18:54 |  | CSTONE Sprint 5 | 1A |  |  | INT041 | RTR-AHCS | RTR | Build
User Story | CSTONE-3647 | RTR-AHCS-062 (Technical) | RTR-AHCS-062 |  | RTR-AHCS-062 - Technical |  |  | Girish R Acharya | Mehul Kumar Patel |  | Done | Fixed | 2021-09-02 17:57 | 2021-10-15 15:28 |  | CSTONE Sprint 5 | 1A+1B |  |  | INT041 | RTR-AHCS | RTR | Build
User Story | CSTONE-3648 | RTR-AHCS-064 (Technical) | RTR-AHCS-064 |  | RTR-AHCS-064 - Technical |  |  | Manpreet Singh | Mehul Kumar Patel |  | Done | Fixed | 2021-09-02 17:57 | 2021-09-23 06:19 |  | CSTONE Sprint 4 | 1A+1B |  |  | RPT009 | RTR-AHCS | RTR | Build
User Story | CSTONE-3649 | RTR-GL-010 (TUT/FUT) | RTR-GL-010 |  |  | RTR-GL-010 - TUT/FUT |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-09-02 17:57 | 2021-10-25 13:26 |  | CSTONE Sprint 4 | 1A+1B |  |  | RPT002 | RTR-GL | RTR | Build
User Story | CSTONE-3650 | RTR-GL-013 (TUT/FUT) | RTR-GL-013 |  |  | RTR-GL-013 - TUT/FUT |  | Satheesh Kumar Gooda | Mehul Kumar Patel |  | In Progress |  | 2021-09-02 17:57 | 2021-10-25 13:26 |  | CSTONE Sprint 5 | 1A+1B |  |  | RPT003 | RTR-GL | RTR | Build
User Story | CSTONE-3651 | RTR-GL-017 (TUT/FUT) | RTR-GL-017 |  |  | RTR-GL-017 - TUT/FUT |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-09-02 17:57 | 2021-10-25 13:26 |  | CSTONE Sprint 4 | 1A+1B |  |  | RPT004 | RTR-GL | RTR | Build
User Story | CSTONE-3652 | RTR-GL-018 (TUT/FUT) | RTR-GL-018 |  |  | RTR-GL-018 - TUT/FUT |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-09-02 17:57 | 2021-10-25 13:26 |  | CSTONE Sprint 4 | 1A+1B |  |  | RPT004 | RTR-GL | RTR | Build
User Story | CSTONE-3653 | RTR-GL-075 (TUT/FUT) | RTR-GL-075 |  |  | RTR-GL-075 - TUT/FUT |  | Satheesh Kumar Gooda | Mehul Kumar Patel |  | In Progress |  | 2021-09-02 17:57 | 2021-10-25 19:40 |  | CSTONE Sprint 5 | 1A+1B |  |  | RPT005 | RTR-GL | RTR | Build
User Story | CSTONE-3654 | RTR-GL-077 (TUT/FUT) | RTR-GL-077 |  |  | RTR-GL-077 - TUT/FUT |  | Vishnu M Menon | Mehul Kumar Patel |  | Done | Fixed | 2021-09-02 17:57 | 2021-10-25 13:26 |  | CSTONE Sprint 4 | 1A+1B |  |  | RPT009 | RTR-AHCS | RTR | Build
User Story | CSTONE-3655 | REP-RTR-GL-63 (TUT/FUT) | REP-RTR-GL-63 |  |  | REP-RTR-GL-63 - TUT/FUT |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-09-02 17:57 | 2021-10-25 13:26 |  | CSTONE Sprint 4 | 1A |  |  | RPT002 | RTR-GL | RTR | Build
User Story | CSTONE-3656 | REP-RTR-GL-70 (TUT/FUT) | REP-RTR-GL-70 |  |  | REP-RTR-GL-70 - TUT/FUT |  | Satheesh Kumar Gooda | Mehul Kumar Patel |  | In Progress |  | 2021-09-02 17:57 | 2021-10-25 13:26 |  | CSTONE Sprint 5 | 1A |  |  | RPT003 | RTR-GL | RTR | Build
User Story | CSTONE-3657 | RTR-AHCS-024 (TUT/FUT) | RTR-AHCS-024 |  |  | RTR-AHCS-024 - TUT/FUT |  | Manpreet Singh | Mehul Kumar Patel |  | In Progress |  | 2021-09-02 17:57 | 2021-10-04 18:39 |  | CSTONE Sprint 5 | 1A+1B |  |  | INT012 | RTR-AHCS | RTR | Build
User Story | CSTONE-3658 | RTR-AHCS-025 (TUT/FUT) | RTR-AHCS-025 |  |  | RTR-AHCS-025 - TUT/FUT |  | Manpreet Singh | Mehul Kumar Patel |  | Done | Fixed | 2021-09-02 17:57 | 2021-10-25 13:27 |  | CSTONE Sprint 5 | 1A+1B |  |  | RPT007 | RTR-AHCS | RTR | Build
User Story | CSTONE-3659 | RTR-AHCS-027 (TUT/FUT) | RTR-AHCS-027 |  |  | RTR-AHCS-027 - TUT/FUT |  | Manpreet Singh | Mehul Kumar Patel |  | Done | Fixed | 2021-09-02 17:57 | 2021-10-25 13:27 |  | CSTONE Sprint 4 | 1A+1B |  |  | RPT008 | RTR-AHCS | RTR | Build
User Story | CSTONE-3660 | RTR-AHCS-044 (TUT/FUT) | RTR-AHCS-044 |  |  | RTR-AHCS-044 - TUT/FUT |  | Manpreet Singh | Mehul Kumar Patel |  | Blocked |  | 2021-09-02 17:57 | 2021-10-04 18:39 |  | CSTONE Sprint 5 | 1A |  |  | INT016 | RTR-AHCS | RTR | Build
User Story | CSTONE-3661 | RTR-GL-117 (TUT/FUT) | RTR-GL-117 |  |  | RTR-GL-117 - TUT/FUT |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-09-02 17:57 | 2021-09-09 15:35 |  | CSTONE Sprint 4 | 1A+1B |  |  | EXT013 | RTR-GL | RTR | Build
User Story | CSTONE-3662 | REP-RTR-GL-4 (TUT/FUT) | REP-RTR-GL-4 |  |  | REP-RTR-GL-4 - TUT/FUT |  | Vishnu M Menon | Mehul Kumar Patel |  | Done | Fixed | 2021-09-02 17:57 | 2021-10-25 13:26 |  | CSTONE Sprint 4 | 1A+1B |  |  | RPT009 | RTR-AHCS | RTR | Build
User Story | CSTONE-3663 | REP-RTR-GL-67-B (TUT/FUT) | REP-RTR-GL-67-B |  |  | REP-RTR-GL-67-B - TUT/FUT |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-09-02 17:57 | 2021-09-09 16:38 |  | CSTONE Sprint 4 | 1A |  |  | EXT013 | RTR-GL | RTR | Build
User Story | CSTONE-3664 | RTR-GL-135 (TUT/FUT) | RTR-GL-135 |  |  | RTR-GL-135 - TUT/FUT |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-09-02 17:57 | 2021-10-25 13:27 |  | CSTONE Sprint 4 | 1A+1B |  |  | EXT012 | RTR-GL | RTR | Build
User Story | CSTONE-3665 | RTR-GL-141 (TUT/FUT) | RTR-GL-141 |  |  | RTR-GL-141 - TUT/FUT |  | Manpreet Singh | Mehul Kumar Patel |  | Done | Fixed | 2021-09-02 17:57 | 2021-10-15 15:04 |  | CSTONE Sprint 5 | 1A |  |  | INT012 | RTR-AHCS | RTR | Build
User Story | CSTONE-3666 | RTR-GL-143 (TUT/FUT) | RTR-GL-143 |  |  | RTR-GL-143 - TUT/FUT |  | Manpreet Singh | Mehul Kumar Patel |  | Done | Fixed | 2021-09-02 17:58 | 2021-10-15 15:04 |  | CSTONE Sprint 5 | 1A |  |  | INT041 | RTR-AHCS | RTR | Build
User Story | CSTONE-3667 | RTR-AHCS-062 (TUT/FUT) | RTR-AHCS-062 |  |  | RTR-AHCS-062 - TUT/FUT |  | Manpreet Singh | Mehul Kumar Patel |  | In Progress |  | 2021-09-02 17:58 | 2021-10-25 13:27 |  | CSTONE Sprint 5 | 1A+1B |  |  | INT041 | RTR-AHCS | RTR | Build
User Story | CSTONE-3811 | EPM-EDM-007 | EPM-EDM-007 |  |  |  |  | Mayank Dargan | Mehul Kumar Patel | Major | Done | Fixed | 2021-09-02 18:31 | 2021-10-25 13:26 | 2021-06-25 | CSTONE Sprint 4 | 1A |  |  |  | EPM - Master Data Management
User Story | CSTONE-3809 | EPM-EDM-002 | EPM-EDM-002 |  |  |  |  | Mayank Dargan | Mehul Kumar Patel | Major | Done | Fixed | 2021-09-02 18:31 | 2021-10-20 15:08 | 2021-06-25 | CSTONE Sprint 5 | 1B |  |  |  | EPM - Master Data Management
User Story | CSTONE-3668 | RTR-AHCS-064 (TUT/FUT) | RTR-AHCS-064 |  |  | RTR-AHCS-064 - TUT/FUT |  | Manpreet Singh | Mehul Kumar Patel |  | Done | Fixed | 2021-09-02 17:58 | 2021-09-23 16:01 |  | CSTONE Sprint 4 | 1A+1B |  |  | RPT009 | RTR-AHCS | RTR | Build
User Story | CSTONE-3810 | EPM-EDM-004 | EPM-EDM-004 |  |  |  |  | Mayank Dargan | Mehul Kumar Patel | Major | Done | Fixed | 2021-09-02 18:31 | 2021-10-20 15:08 | 2021-06-25 | CSTONE Sprint 5 | 1B |  |  |  | EPM - Master Data Management
User Story | CSTONE-3812 | EPM-EDM-008 | EPM-EDM-008 |  |  |  |  | Mayank Dargan | Mehul Kumar Patel | Major | Not Started |  | 2021-09-02 18:31 | 2021-10-04 18:40 | 2021-06-25 | CSTONE Sprint 5 | 1A |  |  |  | EPM - Master Data Management
User Story | CSTONE-3813 | EPM-EDM-011 | EPM-EDM-011 |  |  |  |  | Mayank Dargan | Mehul Kumar Patel | Major | Done | Fixed | 2021-09-02 18:31 | 2021-10-29 15:25 | 2021-06-25 | CSTONE Sprint 5 | 1A |  |  |  | EPM - Master Data Management
User Story | CSTONE-3814 | EPM-EDM-012 | EPM-EDM-012 |  |  |  |  | Mayank Dargan | Mehul Kumar Patel | Major | Done | Fixed | 2021-09-02 18:31 | 2021-10-25 13:26 | 2021-06-25 | CSTONE Sprint 4 | 1A |  |  |  | EPM - Master Data Management
User Story | CSTONE-3815 | EPM-EDM-013 | EPM-EDM-013 |  |  |  |  | Mayank Dargan | Mehul Kumar Patel | Major | Done | Fixed | 2021-09-02 18:31 | 2021-10-29 15:04 | 2021-06-25 | CSTONE Sprint 5 | 1A |  |  |  | EPM - Master Data Management
User Story | CSTONE-3816 | EPM-EDM-018 | EPM-EDM-018 |  |  |  |  | Mayank Dargan | Mehul Kumar Patel | Major | Done | Fixed | 2021-09-02 18:31 | 2021-10-25 13:26 | 2021-06-25 | CSTONE Sprint 4 | 1A |  |  |  | EPM - Master Data Management
User Story | CSTONE-3818 | EPM-EDM-020 | EPM-EDM-020 |  |  |  |  | Mayank Dargan | Mehul Kumar Patel | Major | Done | Fixed | 2021-09-02 18:31 | 2021-10-25 13:26 | 2021-06-25 | CSTONE Sprint 4 | 1A |  |  |  | EPM - Master Data Management
User Story | CSTONE-3817 | EPM-EDM-019 | EPM-EDM-019 |  |  |  |  | Mayank Dargan | Mehul Kumar Patel | Major | Done | Fixed | 2021-09-02 18:31 | 2021-10-29 15:25 | 2021-06-25 | CSTONE Sprint 5 | 1A |  |  |  | EPM - Master Data Management
User Story | CSTONE-3819 | EPM-EDM-027 | EPM-EDM-027 |  |  |  |  | Mayank Dargan | Mehul Kumar Patel | Major | Done | Fixed | 2021-09-02 18:31 | 2021-10-25 13:26 | 2021-06-25 | CSTONE Sprint 4 | 1A |  |  |  | EPM - Master Data Management
User Story | CSTONE-3820 | EPM-EDM-028 | EPM-EDM-028 |  |  |  |  | Mayank Dargan | Mehul Kumar Patel | Major | Done | Fixed | 2021-09-02 18:31 | 2021-09-23 15:23 | 2021-06-25 | CSTONE Sprint 4 | 1A |  |  |  | EPM - Master Data Management
User Story | CSTONE-3821 | EPM-EDM-029 | EPM-EDM-029 |  |  |  |  | Mayank Dargan | Mehul Kumar Patel | Major | Done | Fixed | 2021-09-02 18:31 | 2021-09-24 19:32 | 2021-06-25 | CSTONE Sprint 4 | 1A |  |  |  | EPM - Master Data Management
User Story | CSTONE-3861 | EPM-FCCS-011 | EPM-FCCS-011 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-09-02 18:55 | 2021-10-15 17:06 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-3862 | EPM-FCCS-018 | EPM-FCCS-018 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-09-02 18:55 | 2021-10-15 17:05 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-3863 | EPM-FCCS-055 | EPM-FCCS-055 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-09-02 18:55 | 2021-10-27 03:47 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-3864 | EPM-FCCS-184 | EPM-FCCS-184 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-09-02 18:55 | 2021-10-27 03:45 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-3865 | EPM-FCCS-057 | EPM-FCCS-057 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-09-02 18:55 | 2021-10-27 03:45 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-3866 | EPM-FCCS-058 | EPM-FCCS-058 | EPM-FCCS-058 - Functional |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-09-02 18:55 | 2021-10-27 03:41 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - FCCS | EPM | Configuration
User Story | CSTONE-3867 | EPM-FCCS-060 | EPM-FCCS-060 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-09-02 18:55 | 2021-10-27 03:37 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-3868 | EPM-FCCS-061 | EPM-FCCS-061 | EPM-FCCS-061 - Functional |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-09-02 18:55 | 2021-10-27 03:35 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - FCCS | EPM | Configuration
User Story | CSTONE-3869 | EPM-FCCS-063 | EPM-FCCS-063 | EPM-FCCS-063 - Functional |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-09-02 18:55 | 2021-10-27 03:34 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - FCCS | EPM | Configuration
User Story | CSTONE-3870 | EPM-FCCS-064 | EPM-FCCS-064 | EPM-FCCS-064 - Functional |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-09-02 18:55 | 2021-10-27 03:33 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - FCCS | EPM | Configuration
User Story | CSTONE-3871 | EPM-FCCS-074 | EPM-FCCS-074 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-09-02 18:55 | 2021-10-21 13:08 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-3872 | EPM-FCCS-132 | EPM-FCCS-132 | EPM-FCCS-132 - Functional |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-09-02 18:55 | 2021-09-20 15:32 |  | CSTONE Sprint 4 | 1A |  |  |  | EPM - FCCS | EPM | Configuration
User Story | CSTONE-3873 | EPM-FCCS-137 | EPM-FCCS-137 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-09-02 18:55 | 2021-10-01 00:29 |  | CSTONE Sprint 4 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-3874 | EPM-FCCS-138 | EPM-FCCS-138 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-09-02 18:55 | 2021-10-01 00:28 |  | CSTONE Sprint 4 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-3875 | EPM-FCCS-165 | EPM-FCCS-165 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-09-02 18:55 | 2021-09-29 00:37 |  | CSTONE Sprint 4 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-3876 | EPM-FCCS-143 | EPM-FCCS-143 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-09-02 18:55 | 2021-09-29 00:49 |  | CSTONE Sprint 4 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-3877 | EPM-FCCS-147 | EPM-FCCS-147 | EPM-FCCS-147 - Functional |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-09-02 18:55 | 2021-09-13 21:04 |  | CSTONE Sprint 4 | 1A |  |  |  | EPM - FCCS | EPM | Configuration
User Story | CSTONE-3878 | EPM-FCCS-149 | EPM-FCCS-149 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | In Progress |  | 2021-09-02 18:55 | 2021-10-04 18:39 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-3879 | EPM-FCCS-150 | EPM-FCCS-150 | EPM-FCCS-150 - Functional |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-09-02 18:55 | 2021-09-08 22:02 |  | CSTONE Sprint 4 | 1A |  |  |  | EPM - FCCS | EPM | Configuration
User Story | CSTONE-3880 | EPM-ARCS-005 | EPM-ARCS-005 | EPM-ARCS-005 - Functional |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-09-02 18:55 | 2021-10-22 19:30 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - FCCS | EPM | Configuration
User Story | CSTONE-3881 | EPM-ARCS-007 | EPM-ARCS-007 | EPM-ARCS-007 - Functional |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-09-02 18:55 | 2021-09-16 20:18 |  | CSTONE Sprint 4 | 1A |  |  |  | EPM - FCCS | EPM | Configuration
User Story | CSTONE-3882 | EPM-ARCS-008 | EPM-ARCS-008 | EPM-ARCS-008 - Functional |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-09-02 18:55 | 2021-09-16 20:17 |  | CSTONE Sprint 4 | 1A |  |  |  | EPM - FCCS | EPM | Configuration
User Story | CSTONE-3883 | EPM-ARCS-010 | EPM-ARCS-010 | EPM-ARCS-010 - Functional |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-09-02 18:55 | 2021-09-16 20:17 |  | CSTONE Sprint 4 | 1A |  |  |  | EPM - FCCS | EPM | Configuration
User Story | CSTONE-3884 | EPM-ARCS-012 | EPM-ARCS-012 | EPM-ARCS-012 - Functional |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-09-02 18:55 | 2021-09-16 20:15 |  | CSTONE Sprint 4 | 1A |  |  |  | EPM - FCCS | EPM | Configuration
User Story | CSTONE-3885 | EPM-ARCS-014 | EPM-ARCS-014 | EPM-ARCS-014 - Functional |  |  |  | vicmartinez | Mehul Kumar Patel | Major | In Progress |  | 2021-09-02 18:55 | 2021-10-04 18:39 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - FCCS | EPM | Configuration
User Story | CSTONE-3886 | EPM-ARCS-017 | EPM-ARCS-017 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-09-02 18:55 | 2021-09-27 23:51 |  | CSTONE Sprint 4 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-3887 | EPM-ARCS-018 | EPM-ARCS-018 | EPM-ARCS-018 - Functional |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-09-02 18:55 | 2021-09-16 20:16 |  | CSTONE Sprint 4 | 1A |  |  |  | EPM - FCCS | EPM | Configuration
User Story | CSTONE-3888 | EPM-ARCS-021 | EPM-ARCS-021 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-09-02 18:56 | 2021-09-27 23:53 |  | CSTONE Sprint 4 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-3889 | EPM-ARCS-024 | EPM-ARCS-024 | EPM-ARCS-024 - Functional |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-09-02 18:56 | 2021-10-01 04:15 |  | CSTONE Sprint 4 | 1A |  |  |  | EPM - FCCS | EPM | Configuration
User Story | CSTONE-3890 | EPM-ARCS-025 | EPM-ARCS-025 | EPM-ARCS-025 - Functional |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-09-02 18:56 | 2021-09-16 20:13 |  | CSTONE Sprint 4 | 1A |  |  |  | EPM - FCCS | EPM | Configuration
User Story | CSTONE-3891 | EPM-ARCS-026 | EPM-ARCS-026 | EPM-ARCS-026 - Functional |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-09-02 18:56 | 2021-09-16 20:11 |  | CSTONE Sprint 4 | 1A |  |  |  | EPM - FCCS | EPM | Configuration
User Story | CSTONE-3892 | EPM-ARCS-027 | EPM-ARCS-027 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-09-02 18:56 | 2021-09-17 15:37 |  | CSTONE Sprint 4 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-3893 | EPM-ARCS-028 | EPM-ARCS-028 | EPM-ARCS-028 - Functional |  |  |  | vicmartinez | Mehul Kumar Patel | Major | Done | Fixed | 2021-09-02 18:56 | 2021-09-16 20:14 |  | CSTONE Sprint 4 | 1A |  |  |  | EPM - FCCS | EPM | Configuration
User Story | CSTONE-3894 | EPM-ARCS-030 | EPM-ARCS-030 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | De-scoped |  | 2021-09-02 18:56 | 2021-10-15 00:13 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-3895 | EPM-ARCS-031 | EPM-ARCS-031 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | De-scoped | Fixed | 2021-09-02 18:56 | 2021-10-15 00:14 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-3896 | EPM-ARCS-040 | EPM-ARCS-040 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Major | De-scoped |  | 2021-09-02 18:56 | 2021-10-15 00:12 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-4045 | EPM-EPBCS-041 | EPM-EPBCS-041 |  |  |  |  | Will Dixon | Mehul Kumar Patel | Major | Done | Fixed | 2021-09-02 19:50 | 2021-10-12 13:34 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - PBCS | EPM | Build
User Story | CSTONE-4046 | EPM-EPBCS-042 | EPM-EPBCS-042 |  |  |  |  | Will Dixon | Mehul Kumar Patel | Major | Done | Fixed | 2021-09-02 19:50 | 2021-10-12 13:34 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - PBCS | EPM | Build
User Story | CSTONE-4047 | EPM-EPBCS-043 | EPM-EPBCS-043 |  |  |  |  | Will Dixon | Mehul Kumar Patel | Major | Done | Fixed | 2021-09-02 19:50 | 2021-10-12 16:34 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - PBCS | EPM | Build
User Story | CSTONE-4048 | EPM-EPBCS-044 | EPM-EPBCS-044 |  |  |  |  | Will Dixon | Mehul Kumar Patel | Major | In Progress |  | 2021-09-02 19:50 | 2021-10-04 18:39 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - PBCS | EPM | Build
User Story | CSTONE-4049 | EPM-EPBCS-045 | EPM-EPBCS-045 |  |  |  |  | Will Dixon | Mehul Kumar Patel | Major | In Progress |  | 2021-09-02 19:50 | 2021-10-04 18:39 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - PBCS | EPM | Build
User Story | CSTONE-4050 | EPM-EPBCS-048 | EPM-EPBCS-048 | EPM-EPBCS-048 - Functional |  |  |  | Will Dixon | Mehul Kumar Patel | Major | Done | Fixed | 2021-09-02 19:50 | 2021-09-13 15:35 |  | CSTONE Sprint 4 | 1A |  |  |  | EPM - PBCS | EPM | Configuration
User Story | CSTONE-4051 | EPM-EPBCS-049 | EPM-EPBCS-049 | EPM-EPBCS-049 - Functional |  |  |  | Will Dixon | Mehul Kumar Patel | Major | Done | Fixed | 2021-09-02 19:50 | 2021-09-13 15:36 |  | CSTONE Sprint 4 | 1A |  |  |  | EPM - PBCS | EPM | Configuration
User Story | CSTONE-4052 | EPM-EPBCS-050 | EPM-EPBCS-050 | EPM-EPBCS-050 - Functional |  |  |  | Will Dixon | Mehul Kumar Patel |  | Done | Fixed | 2021-09-02 19:50 | 2021-09-17 01:50 |  | CSTONE Sprint 4 | 1A |  |  |  | EPM - PBCS | EPM | Configuration
User Story | CSTONE-4053 | EPM-EPBCS-051 | EPM-EPBCS-051 | EPM-EPBCS-051 - Functional |  |  |  | Will Dixon | Mehul Kumar Patel |  | Done | Fixed | 2021-09-02 19:50 | 2021-09-13 15:36 |  | CSTONE Sprint 4 | 1A |  |  |  | EPM - PBCS | EPM | Configuration
User Story | CSTONE-4054 | EPM-EPBCS-052 | EPM-EPBCS-052 | EPM-EPBCS-052 - Functional |  |  |  | Will Dixon | Mehul Kumar Patel |  | Done | Fixed | 2021-09-02 19:50 | 2021-09-23 13:22 |  | CSTONE Sprint 4 | 1A |  |  |  | EPM - PBCS | EPM | Configuration
User Story | CSTONE-4055 | EPM-EPBCS-053 | EPM-EPBCS-053 | EPM-EPBCS-053 - Functional |  |  |  | Will Dixon | Mehul Kumar Patel |  | Done | Fixed | 2021-09-02 19:50 | 2021-09-23 13:22 |  | CSTONE Sprint 4 | 1A |  |  |  | EPM - PBCS | EPM | Configuration
User Story | CSTONE-4056 | EPM-EPBCS-054 | EPM-EPBCS-054 | EPM-EPBCS-054 - Functional |  |  |  | Will Dixon | Mehul Kumar Patel |  | Done | Fixed | 2021-09-02 19:50 | 2021-09-17 01:51 |  | CSTONE Sprint 4 | 1A |  |  |  | EPM - PBCS | EPM | Configuration
User Story | CSTONE-4057 | EPM-EPBCS-055 | EPM-EPBCS-055 | EPM-EPBCS-055 - Functional |  |  |  | Will Dixon | Mehul Kumar Patel |  | Done | Fixed | 2021-09-02 19:50 | 2021-09-17 01:51 |  | CSTONE Sprint 4 | 1A |  |  |  | EPM - PBCS | EPM | Configuration
User Story | CSTONE-4059 | EPM-EPBCS-057 | EPM-EPBCS-057 |  |  |  |  | Will Dixon | Mehul Kumar Patel |  | Done | Fixed | 2021-09-02 19:50 | 2021-10-28 23:11 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - PBCS | EPM | Build
User Story | CSTONE-4061 | EPM-EPBCS-059 | EPM-EPBCS-059 | EPM-EPBCS-059 - Functional |  |  |  | Will Dixon | Mehul Kumar Patel |  | Done | Fixed | 2021-09-02 19:50 | 2021-10-28 15:55 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - PBCS | EPM | Configuration
User Story | CSTONE-4062 | EPM-EPBCS-060 | EPM-EPBCS-060 | EPM-EPBCS-060 - Functional |  |  |  | Will Dixon | Mehul Kumar Patel |  | In Progress |  | 2021-09-02 19:50 | 2021-10-13 18:27 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - PBCS | EPM | Configuration
User Story | CSTONE-4063 | EPM-EPBCS-061 | EPM-EPBCS-061 | EPM-EPBCS-061 - Functional |  |  |  | Will Dixon | Mehul Kumar Patel |  | Done | Fixed | 2021-09-02 19:50 | 2021-10-07 17:32 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - PBCS | EPM | Configuration
User Story | CSTONE-4064 | EPM-EPBCS-062 | EPM-EPBCS-062 | EPM-EPBCS-062 - Functional |  |  |  | Will Dixon | Mehul Kumar Patel |  | Done | Fixed | 2021-09-02 19:50 | 2021-10-19 18:02 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - PBCS | EPM | Configuration
User Story | CSTONE-4072 | EPM-EPBCS-087 | EPM-EPBCS-087 |  |  |  |  | Will Dixon | Mehul Kumar Patel |  | Not Started |  | 2021-09-02 19:50 | 2021-10-04 18:40 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - PBCS | EPM | Build
User Story | CSTONE-4073 | EPM-EPBCS-088 | EPM-EPBCS-088 |  |  |  |  | Will Dixon | Mehul Kumar Patel |  | Not Started |  | 2021-09-02 19:50 | 2021-10-04 18:40 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - PBCS | EPM | Build
User Story | CSTONE-4074 | EPM-EPBCS-089 | EPM-EPBCS-089 |  |  |  |  | Will Dixon | Mehul Kumar Patel |  | Not Started |  | 2021-09-02 19:50 | 2021-10-04 18:40 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - PBCS | EPM | Build
User Story | CSTONE-4075 | EPM-EPBCS-090 | EPM-EPBCS-090 |  |  |  |  | Will Dixon | Mehul Kumar Patel |  | Not Started |  | 2021-09-02 19:50 | 2021-10-04 18:40 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - PBCS | EPM | Build
User Story | CSTONE-4076 | EPM-EPBCS-091 | EPM-EPBCS-091 |  |  |  |  | Will Dixon | Mehul Kumar Patel |  | Not Started |  | 2021-09-02 19:50 | 2021-10-04 18:40 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - PBCS | EPM | Build
User Story | CSTONE-4077 | EPM-EPBCS-092 | EPM-EPBCS-092 |  |  |  |  | Will Dixon | Mehul Kumar Patel |  | Not Started |  | 2021-09-02 19:50 | 2021-10-04 18:40 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - PBCS | EPM | Build
User Story | CSTONE-4078 | EPM-EPBCS-093 | EPM-EPBCS-093 |  |  |  |  | Will Dixon | Mehul Kumar Patel |  | Not Started |  | 2021-09-02 19:50 | 2021-10-04 18:40 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - PBCS | EPM | Build
User Story | CSTONE-4079 | EPM-EPBCS-094 | EPM-EPBCS-094 |  |  |  |  | Will Dixon | Mehul Kumar Patel |  | Not Started |  | 2021-09-02 19:50 | 2021-10-04 18:40 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - PBCS | EPM | Build
User Story | CSTONE-4087 | EPM-EPBCS-101 | EPM-EPBCS-101 |  |  |  |  | Will Dixon | Mehul Kumar Patel |  | Not Started |  | 2021-09-09 18:50 | 2021-10-04 18:39 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - PBCS | EPM | Build
User Story | CSTONE-4199 | DP-RTR-GL-001 (Functional) | DP-RTR-GL-001 | DP-RTR-GL-001 - Functional |  |  |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-09-13 18:54 | 2021-09-17 23:01 |  | CSTONE Sprint 4 | 1A+1B |  |  |  | RTR-GL | RTR | Configuration
User Story | CSTONE-4200 | DP-RTR-GL-002 (Functional) | DP-RTR-GL-002 | DP-RTR-GL-002 - Functional |  |  |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-09-13 18:54 | 2021-09-17 22:59 | 2021-08-05 | CSTONE Sprint 4 | 1A+1B |  |  |  | RTR-GL | RTR | Configuration
User Story | CSTONE-4201 | DP-RTR-GL-003 (Functional) | DP-RTR-GL-003 | DP-RTR-GL-003 - Functional |  |  |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-09-13 18:54 | 2021-09-17 23:04 | 2021-08-05 | CSTONE Sprint 4 | 1A+1B |  |  |  | RTR-GL | RTR | Configuration
User Story | CSTONE-4202 | DP-RTR-GL-005 | DP-RTR-GL-005 | DP-RTR-GL-005 - Functional |  |  |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-09-13 18:54 | 2021-09-21 00:04 | 2021-08-05 | CSTONE Sprint 4 | 1A+1B |  |  |  | RTR-GL | RTR | Work Around
User Story | CSTONE-4203 | DP-RTR-GL-007 (Functional) | DP-RTR-GL-007 | DP-RTR-GL-007 - Functional |  |  |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-09-13 18:54 | 2021-09-17 23:06 | 2021-08-05 | CSTONE Sprint 4 | 1A+1B |  |  |  | RTR-GL | RTR | Configuration
User Story | CSTONE-4204 | DP-RTR-GL-008A (Technical) | DP-RTR-GL-008A |  | DP-RTR-GL-008A - Technical | DP-RTR-GL-008A - TUT/FUT |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-09-13 18:54 | 2021-10-11 09:43 | 2021-08-05 | CSTONE Sprint 5 | 1A+1B |  |  | RPT047 | RTR-GL | RTR | Build
User Story | CSTONE-4205 | DP-RTR-GL-008B (Technical) | DP-RTR-GL-008B |  | DP-RTR-GL-008B - Technical | DP-RTR-GL-008B - TUT/FUT |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-09-13 18:54 | 2021-10-11 09:44 | 2021-08-05 | CSTONE Sprint 5 | 1A+1B |  |  | RPT047 | RTR-GL | RTR | Build
User Story | CSTONE-4206 | DP-RTR-GL-008C (Technical) | DP-RTR-GL-008C |  | DP-RTR-GL-008C - Technical | DP-RTR-GL-008C - TUT/FUT |  | Preetansh Singh Thakur | Mehul Kumar Patel |  | Done | Fixed | 2021-09-13 18:54 | 2021-10-15 20:29 | 2021-08-05 | CSTONE Sprint 5 | 1A+1B |  |  | RPT047 | RTR-GL | RTR | Build
User Story | CSTONE-4207 | DP-RTR-AHCS-001 (Technical) | DP-RTR-AHCS-001 |  | DP-RTR-AHCS-001 - Technical | DP-RTR-AHCS-001 - TUT/FUT |  | Manpreet Singh | Mehul Kumar Patel |  | Done | Fixed | 2021-09-13 18:54 | 2021-10-01 12:53 | 2021-08-04 | CSTONE Sprint 4 | 1A+1B |  |  | RPT009 | RTR-AHCS | RTR | Build
User Story | CSTONE-4208 | DP-RTR-GL-009 (Functional) | DP-RTR-GL-009 | DP-RTR-GL-009 - Functional |  |  |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-09-13 18:54 | 2021-09-22 11:21 | 2021-08-05 | CSTONE Sprint 4 | 1A+1B |  |  | RPT101 | RTR-GL | RTR | Build
User Story | CSTONE-4209 | DP-RTR-GL-015 (Functional) | DP-RTR-GL-015 | DP-RTR-GL-015 - Functional |  |  |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-09-13 18:54 | 2021-09-22 11:20 | 2021-08-05 | CSTONE Sprint 4 | 1A+1B |  |  | RPT101 | RTR-GL | RTR | Build
User Story | CSTONE-4265 | RTR-GL-090 - TUT/FUT | RTR-GL-090 |  |  | RTR-GL-090 - TUT/FUT |  | Asma Syed | Mehul Kumar Patel |  | Done | Fixed | 2021-09-22 12:56 | 2021-09-23 05:59 |  | CSTONE Sprint 4 | 1A+1B |  |  | RPT041 | RTR-GL | RTR | Build
User Story | CSTONE-4270 | EPM-FCCS-021 | EPM-FCCS-021 | EPM-FCCS-021 - Functional |  |  |  | vicmartinez | Mehul Kumar Patel | Must Have | Done | Fixed | 2021-09-30 17:29 | 2021-10-27 02:56 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - FCCS | EPM | Configuration
User Story | CSTONE-4271 | EPM-FCCS-023 | EPM-FCCS-023 | EPM-FCCS-023 - Functional |  |  |  | vicmartinez | Mehul Kumar Patel | Must Have | Done | Fixed | 2021-09-30 17:29 | 2021-10-27 03:00 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - FCCS | EPM | Configuration
User Story | CSTONE-4272 | EPM-FCCS-024 | EPM-FCCS-024 | EPM-FCCS-024 - Functional |  |  |  | vicmartinez | Mehul Kumar Patel | Must Have | Done | Fixed | 2021-09-30 17:29 | 2021-10-27 03:30 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - FCCS | EPM | Configuration
User Story | CSTONE-4273 | EPM-FCCS-025 | EPM-FCCS-025 | EPM-FCCS-025 - Functional |  |  |  | vicmartinez | Mehul Kumar Patel | Must Have | Done | Fixed | 2021-09-30 17:29 | 2021-10-13 17:58 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - FCCS | EPM | Configuration
User Story | CSTONE-4274 | EPM-FCCS-026 | EPM-FCCS-026 | EPM-FCCS-026 - Functional |  |  |  | vicmartinez | Mehul Kumar Patel | Must Have | Done | Fixed | 2021-09-30 17:29 | 2021-10-13 17:58 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - FCCS | EPM | Configuration
User Story | CSTONE-4275 | EPM-FCCS-027 | EPM-FCCS-027 | EPM-FCCS-027 - Functional |  |  |  | vicmartinez | Mehul Kumar Patel | Must Have | Done | Fixed | 2021-09-30 17:29 | 2021-10-13 17:57 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - FCCS | EPM | Configuration
User Story | CSTONE-4276 | EPM-FCCS-028 | EPM-FCCS-028 | EPM-FCCS-028 - Functional |  |  |  | vicmartinez | Mehul Kumar Patel | Must Have | Done | Fixed | 2021-09-30 17:29 | 2021-10-13 17:59 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - FCCS | EPM | Configuration
User Story | CSTONE-4277 | EPM-FCCS-029 | EPM-FCCS-029 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Must Have | Done | Fixed | 2021-09-30 17:29 | 2021-10-13 17:57 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-4278 | EPM-FCCS-030 | EPM-FCCS-030 | EPM-FCCS-030 - Functional |  |  |  | vicmartinez | Mehul Kumar Patel | Must Have | In Progress |  | 2021-09-30 17:29 | 2021-10-13 20:18 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - FCCS | EPM | Configuration
User Story | CSTONE-4279 | EPM-FCCS-031 | EPM-FCCS-031 | EPM-FCCS-031 - Functional |  |  |  | vicmartinez | Mehul Kumar Patel | Must Have | Done | Fixed | 2021-09-30 17:29 | 2021-10-13 17:59 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - FCCS | EPM | Configuration
User Story | CSTONE-4280 | EPM-FCCS-052 | EPM-FCCS-052 | EPM-FCCS-052 - Functional |  |  |  | vicmartinez | Mehul Kumar Patel | Must Have | Done | Fixed | 2021-09-30 17:29 | 2021-10-22 19:32 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - FCCS | EPM | Configuration
User Story | CSTONE-4281 | EPM-FCCS-068 | EPM-FCCS-068 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Must Have | In Progress |  | 2021-09-30 17:29 | 2021-10-14 01:56 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-4282 | EPM-FCCS-072 | EPM-FCCS-072 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Must Have | In Progress |  | 2021-09-30 17:29 | 2021-10-13 20:17 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-4283 | EPM-FCCS-075 | EPM-FCCS-075 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Must Have | In Progress |  | 2021-09-30 17:29 | 2021-10-08 02:19 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-4284 | EPM-FCCS-131 | EPM-FCCS-131 | EPM-FCCS-131 - Functional |  |  |  | vicmartinez | Mehul Kumar Patel | Must Have | De-scoped |  | 2021-09-30 17:29 | 2021-10-21 12:01 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - FCCS | EPM | Configuration
User Story | CSTONE-4285 | EPM-FCCS-133 | EPM-FCCS-133 |  |  |  |  | vicmartinez | Mehul Kumar Patel | Must Have | In Progress |  | 2021-09-30 17:29 | 2021-10-13 20:17 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - FCCS | EPM | Build
User Story | CSTONE-4286 | EPM-FCCS-135 | EPM-FCCS-135 | EPM-FCCS-135 - Functional |  |  |  | vicmartinez | Mehul Kumar Patel | Must Have | Done | Fixed | 2021-09-30 17:29 | 2021-10-21 12:03 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - FCCS | EPM | Configuration
User Story | CSTONE-4287 | EPM-FCCS-136 | EPM-FCCS-136 | EPM-FCCS-136 - Functional |  |  |  | vicmartinez | Mehul Kumar Patel | Must Have | Done | Fixed | 2021-09-30 17:29 | 2021-10-27 03:31 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - FCCS | EPM | Configuration
User Story | CSTONE-4289 | EPM-FCCS-153 | EPM-FCCS-153 | EPM-FCCS-153 - Functional |  |  |  | vicmartinez | Mehul Kumar Patel | Must Have | Done | Fixed | 2021-09-30 17:29 | 2021-10-13 18:00 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - FCCS | EPM | Configuration
User Story | CSTONE-4290 | EPM-FCCS-154 | EPM-FCCS-154 | EPM-FCCS-154 - Functional |  |  |  | vicmartinez | Mehul Kumar Patel | Must Have | Done | Fixed | 2021-09-30 17:29 | 2021-10-13 18:00 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - FCCS | EPM | Configuration
User Story | CSTONE-4291 | EPM-FCCS-155 | EPM-FCCS-155 | EPM-FCCS-155 - Functional |  |  |  | vicmartinez | Mehul Kumar Patel | Must Have | Done | Fixed | 2021-09-30 17:29 | 2021-10-13 18:00 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - FCCS | EPM | Configuration
User Story | CSTONE-4292 | EPM-ARCS-006 | EPM-ARCS-006 | EPM-ARCS-006 - Functional |  |  |  | vicmartinez | Mehul Kumar Patel | Must Have | Done | Fixed | 2021-09-30 17:29 | 2021-10-29 12:46 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - FCCS | EPM | Configuration
User Story | CSTONE-4293 | EPM-ARCS-020 | EPM-ARCS-020 | EPM-ARCS-020 - Functional |  |  |  | vicmartinez | Mehul Kumar Patel | Must Have | Done | Fixed | 2021-09-30 17:29 | 2021-10-29 12:45 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - FCCS | EPM | Configuration
User Story | CSTONE-4294 | EPM-ARCS-022 | EPM-ARCS-022 | EPM-ARCS-022 - Functional |  |  |  | vicmartinez | Mehul Kumar Patel | Must Have | Done | Fixed | 2021-09-30 17:29 | 2021-10-29 12:45 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - FCCS | EPM | Configuration
User Story | CSTONE-4295 | EPM-ARCS-023 | EPM-ARCS-023 | EPM-ARCS-023 - Functional |  |  |  | vicmartinez | Mehul Kumar Patel | Must Have | Done | Fixed | 2021-09-30 17:29 | 2021-10-29 12:45 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - FCCS | EPM | Configuration
User Story | CSTONE-4296 | EPM-ARCS-032 | EPM-ARCS-032 | EPM-ARCS-032 - Functional |  |  |  | vicmartinez | Mehul Kumar Patel | Must Have | In Progress |  | 2021-09-30 17:29 | 2021-10-13 17:52 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - FCCS | EPM | Configuration
User Story | CSTONE-4390 | REP-FSG-RTR-GL-004 (Functional) | REP-FSG-RTR-GL-004 | REP-FSG-RTR-GL-004 - Functional |  |  |  | gsansanwal | Mehul Kumar Patel |  | De-scoped |  | 2021-09-30 17:53 | 2021-10-11 09:53 |  | CSTONE Sprint 5 |  |  |  | RPT055 | RTR-GL | RTR | Build
User Story | CSTONE-4391 | REP-FSG-RTR-GL-005 (Functional) | REP-FSG-RTR-GL-005 | REP-FSG-RTR-GL-005 - Functional |  |  |  | gsansanwal | Mehul Kumar Patel |  | De-scoped |  | 2021-09-30 17:53 | 2021-10-11 09:54 |  | CSTONE Sprint 5 |  |  |  | RPT056 | RTR-GL | RTR | Build
User Story | CSTONE-4392 | REP-FSG-RTR-GL-006 (Functional) | REP-FSG-RTR-GL-006 | REP-FSG-RTR-GL-006 - Functional |  |  |  | gsansanwal | Mehul Kumar Patel |  | De-scoped |  | 2021-09-30 17:53 | 2021-10-11 09:55 |  | CSTONE Sprint 5 |  |  |  | RPT057 | RTR-GL | RTR | Build
User Story | CSTONE-4393 | RTR-GL-006 (Technical) | RTR-GL-006 |  | RTR-GL-006 - Technical |  |  | Satheesh Kumar Gooda | Mehul Kumar Patel |  | Done | Done | 2021-09-30 17:53 | 2021-10-22 17:29 |  | CSTONE Sprint 5 | 1A+1B |  |  | RPT001 | RTR-GL | RTR | Build
User Story | CSTONE-4394 | RTR-GL-095 (Technical) | RTR-GL-095 |  | RTR-GL-095 - Technical |  |  | Mamatha, Tata | Mehul Kumar Patel |  | Done | Fixed | 2021-09-30 17:53 | 2021-10-15 20:24 |  | CSTONE Sprint 5 | 1A+1B |  |  | RPT042 | RTR-GL | RTR | Build
User Story | CSTONE-4396 | REP-RTR-GL-2 (Technical) | REP-RTR-GL-2 |  | REP-RTR-GL-2 - Technical |  |  | Ramji Agrawal | Mehul Kumar Patel |  | Done | Done | 2021-09-30 17:53 | 2021-10-22 17:29 |  | CSTONE Sprint 5 | 1A+1B |  |  | RPT047 | RTR-GL | RTR | Build
User Story | CSTONE-4403 | REP-FSG-RTR-GL-001 (Technical) | REP-FSG-RTR-GL-001 |  | REP-FSG-RTR-GL-001 - Technical |  |  | Preetansh Singh Thakur | Mehul Kumar Patel |  | In Progress |  | 2021-09-30 17:53 | 2021-10-15 17:53 |  | CSTONE Sprint 5 | 1A+1B |  |  | RPT052 | RTR-GL | RTR | Build
User Story | CSTONE-4404 | REP-FSG-RTR-GL-002 (Technical) | REP-FSG-RTR-GL-002 |  | REP-FSG-RTR-GL-002 - Technical |  |  | Ramji Agrawal | Mehul Kumar Patel |  | Done | Fixed | 2021-09-30 17:53 | 2021-10-15 20:26 |  | CSTONE Sprint 5 | 1A+1B |  |  | RPT053 | RTR-GL | RTR | Build
User Story | CSTONE-4405 | REP-FSG-RTR-GL-003 (Technical) | REP-FSG-RTR-GL-003 |  | REP-FSG-RTR-GL-003 - Technical |  |  | Astha Shrivastava | Mehul Kumar Patel |  | Done | Done | 2021-09-30 17:53 | 2021-10-22 17:30 |  | CSTONE Sprint 5 | 1A+1B |  |  | RPT054 | RTR-GL | RTR | Build
User Story | CSTONE-4406 | REP-FSG-RTR-GL-007 (Technical) | REP-FSG-RTR-GL-007 |  | REP-FSG-RTR-GL-007 - Technical |  |  | gsansanwal | Mehul Kumar Patel |  | De-scoped |  | 2021-09-30 17:53 | 2021-10-12 13:22 |  | CSTONE Sprint 5 | 1A+1B |  |  | RPT058 | RTR-GL | RTR | Build
User Story | CSTONE-4407 | REP-FSG-RTR-GL-009 (Technical) | REP-FSG-RTR-GL-009 |  | REP-FSG-RTR-GL-009 - Technical |  |  | Chowdari, Malapati Monika | Mehul Kumar Patel |  | Done | Done | 2021-09-30 17:53 | 2021-10-25 13:27 |  | CSTONE Sprint 5 | 1A |  |  | RPT060 | RTR-GL | RTR | Build
User Story | CSTONE-4408 | REP-FSG-RTR-GL-010 (Technical) | REP-FSG-RTR-GL-010 |  | REP-FSG-RTR-GL-010 - Technical |  |  | gsansanwal | Mehul Kumar Patel |  | De-scoped |  | 2021-09-30 17:53 | 2021-10-12 13:22 |  | CSTONE Sprint 5 |  |  |  | RPT061 | RTR-GL | RTR | Build
User Story | CSTONE-4409 | REP-FSG-RTR-GL-011 (Technical) | REP-FSG-RTR-GL-011 |  | REP-FSG-RTR-GL-011 - Technical |  |  | gsansanwal | Mehul Kumar Patel |  | De-scoped |  | 2021-09-30 17:53 | 2021-10-12 13:21 |  | CSTONE Sprint 5 |  |  |  | RPT062 | RTR-GL | RTR | Build
User Story | CSTONE-4410 | REP-FSG-RTR-GL-012 (Technical) | REP-FSG-RTR-GL-012 |  | REP-FSG-RTR-GL-012 - Technical |  |  | gsansanwal | Mehul Kumar Patel |  | De-scoped |  | 2021-09-30 17:53 | 2021-10-12 07:24 |  | CSTONE Sprint 5 | 1A+1B |  |  | RPT063 | RTR-GL | RTR | Build
User Story | CSTONE-4411 | RTR-GL-006 (TUT/FUT) | RTR-GL-006 |  |  | RTR-GL-006 - TUT/FUT |  | Satheesh Kumar Gooda | Mehul Kumar Patel |  | In Progress |  | 2021-09-30 17:53 | 2021-10-15 15:08 |  | CSTONE Sprint 5 | 1A+1B |  |  | RPT001 | RTR-GL | RTR | Build
User Story | CSTONE-4412 | RTR-GL-095 (TUT/FUT) | RTR-GL-095 |  |  | RTR-GL-095 - TUT/FUT |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-09-30 17:53 | 2021-10-25 13:27 |  | CSTONE Sprint 5 | 1A+1B |  |  | RPT042 | RTR-GL | RTR | Build
User Story | CSTONE-4413 | RTR-GL-106 (TUT/FUT) | RTR-GL-106 |  |  | RTR-GL-106 - TUT/FUT |  | Asma Syed | Mehul Kumar Patel |  | Done | Fixed | 2021-09-30 17:53 | 2021-10-25 13:27 |  | CSTONE Sprint 5 | 1A+1B |  |  | RPT043 | RTR-GL | RTR | Build
User Story | CSTONE-4414 | REP-RTR-GL-69 (TUT/FUT) | REP-RTR-GL-69 |  |  | REP-RTR-GL-69 - TUT/FUT |  | Satheesh Kumar Gooda | Mehul Kumar Patel |  | Not Started |  | 2021-09-30 17:53 | 2021-10-25 13:27 |  | CSTONE Sprint 5 | 1A |  |  | RPT044 | RTR-GL | RTR | Build
User Story | CSTONE-4415 | REP-RTR-GL-79 (TUT/FUT) | REP-RTR-GL-79 |  |  | REP-RTR-GL-79 - TUT/FUT |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-09-30 17:53 | 2021-10-29 13:03 |  | CSTONE Sprint 5 | 1A+1B |  |  | RPT045 | RTR-GL | RTR | Build
User Story | CSTONE-4416 | REP-RTR-GL-1 (TUT/FUT) | REP-RTR-GL-1 |  |  | REP-RTR-GL-1 - TUT/FUT |  | Asma Syed | Mehul Kumar Patel |  | Done | Fixed | 2021-09-30 17:53 | 2021-10-25 13:27 |  | CSTONE Sprint 5 | 1A+1B |  |  | RPT046 | RTR-GL | RTR | Build
User Story | CSTONE-4417 | REP-RTR-GL-2 (TUT/FUT) | REP-RTR-GL-2 |  |  | REP-RTR-GL-2 - TUT/FUT |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-09-30 17:53 | 2021-10-22 18:54 |  | CSTONE Sprint 5 | 1A+1B |  |  | RPT047 | RTR-GL | RTR | Build
User Story | CSTONE-4418 | REP-RTR-GL-7 (TUT/FUT) | REP-RTR-GL-7 |  |  | REP-RTR-GL-7 - TUT/FUT |  | Asma Syed | Mehul Kumar Patel |  | Done | Fixed | 2021-09-30 17:53 | 2021-10-25 13:27 |  | CSTONE Sprint 5 | 1A+1B |  |  | RPT046 | RTR-GL | RTR | Build
User Story | CSTONE-4419 | REP-RTR-GL-8 (TUT/FUT) | REP-RTR-GL-8 |  |  | REP-RTR-GL-8 - TUT/FUT |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-09-30 17:53 | 2021-10-25 13:27 |  | CSTONE Sprint 5 | 1A+1B |  |  | RPT046 | RTR-GL | RTR | Build
User Story | CSTONE-4420 | REP-RTR-GL-9 (TUT/FUT) | REP-RTR-GL-9 |  |  | REP-RTR-GL-9 - TUT/FUT |  | Asma Syed | Mehul Kumar Patel |  | Done | Fixed | 2021-09-30 17:53 | 2021-10-25 13:27 |  | CSTONE Sprint 5 | 1A+1B |  |  | RPT046 | RTR-GL | RTR | Build
User Story | CSTONE-4421 | REP-RTR-GL-14 (TUT/FUT) | REP-RTR-GL-14 |  |  | REP-RTR-GL-14 - TUT/FUT |  | Asma Syed | Mehul Kumar Patel |  | Done | Fixed | 2021-09-30 17:53 | 2021-10-25 13:27 |  | CSTONE Sprint 5 | 1A+1B |  |  | RPT046 | RTR-GL | RTR | Build
User Story | CSTONE-4422 | REP-RTR-GL-15 (TUT/FUT) | REP-RTR-GL-15 |  |  | REP-RTR-GL-15 - TUT/FUT |  | Asma Syed | Mehul Kumar Patel |  | Done | Fixed | 2021-09-30 17:53 | 2021-10-25 13:27 |  | CSTONE Sprint 5 | 1A+1B |  |  | RPT046 | RTR-GL | RTR | Build
User Story | CSTONE-4423 | REP-RTR-GL-67-A (TUT/FUT) | REP-RTR-GL-67-A |  |  | REP-RTR-GL-67-A - TUT/FUT |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-09-30 17:53 | 2021-10-18 20:57 |  | CSTONE Sprint 5 | 1A |  |  | RPT046 | RTR-GL | RTR | Build
User Story | CSTONE-4424 | REP-FSG-RTR-GL-001 (TUT/FUT) | REP-FSG-RTR-GL-001 |  |  | REP-FSG-RTR-GL-001 - TUT/FUT |  | gsansanwal | Mehul Kumar Patel |  | In Progress |  | 2021-09-30 17:53 | 2021-10-15 16:51 |  | CSTONE Sprint 5 | 1A+1B |  |  | RPT052 | RTR-GL | RTR | Build
User Story | CSTONE-4425 | REP-FSG-RTR-GL-002 (TUT/FUT) | REP-FSG-RTR-GL-002 |  |  | REP-FSG-RTR-GL-002 - TUT/FUT |  | gsansanwal | Mehul Kumar Patel |  | Done | Fixed | 2021-09-30 17:53 | 2021-10-25 16:19 |  | CSTONE Sprint 5 | 1A+1B |  |  | RPT053 | RTR-GL | RTR | Build
User Story | CSTONE-4426 | REP-FSG-RTR-GL-003 (TUT/FUT) | REP-FSG-RTR-GL-003 |  |  | REP-FSG-RTR-GL-003 - TUT/FUT |  | gsansanwal | Mehul Kumar Patel |  | In Progress |  | 2021-09-30 17:53 | 2021-10-15 11:49 |  | CSTONE Sprint 5 | 1A+1B |  |  | RPT054 | RTR-GL | RTR | Build
User Story | CSTONE-4427 | REP-FSG-RTR-GL-007 (TUT/FUT) | REP-FSG-RTR-GL-007 |  |  | REP-FSG-RTR-GL-007 - TUT/FUT |  | gsansanwal | Mehul Kumar Patel |  | De-scoped |  | 2021-09-30 17:53 | 2021-10-25 13:27 |  | CSTONE Sprint 5 | 1A+1B |  |  | RPT058 | RTR-GL | RTR | Build
User Story | CSTONE-4428 | REP-FSG-RTR-GL-012 (TUT/FUT) | REP-FSG-RTR-GL-012 |  |  | REP-FSG-RTR-GL-012 - TUT/FUT |  | gsansanwal | Mehul Kumar Patel |  | De-scoped |  | 2021-09-30 17:53 | 2021-10-12 07:23 |  | CSTONE Sprint 5 | 1A+1B |  |  | RPT063 | RTR-GL | RTR | Build
User Story | CSTONE-4544 | EPM-EPBCS-056 | EPM-EPBCS-056 |  |  |  |  | Will Dixon | Mehul Kumar Patel |  | Not Started |  | 2021-10-07 17:14 | 2021-10-20 13:11 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - PBCS | EPM | Build
User Story | CSTONE-4545 | EPM-EPBCS-080 | EPM-EPBCS-080 |  |  |  |  | Will Dixon | Mehul Kumar Patel |  | Not Started |  | 2021-10-07 17:14 | 2021-10-20 13:11 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - PBCS | EPM | Build
User Story | CSTONE-4546 | EPM-EPBCS-081 | EPM-EPBCS-081 |  |  |  |  | Will Dixon | Mehul Kumar Patel |  | Not Started |  | 2021-10-07 17:14 | 2021-10-20 13:11 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - PBCS | EPM | Build
User Story | CSTONE-4547 | EPM-EPBCS-082 | EPM-EPBCS-082 |  |  |  |  | Will Dixon | Mehul Kumar Patel |  | Not Started |  | 2021-10-07 17:14 | 2021-10-20 13:11 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - PBCS | EPM | Build
User Story | CSTONE-4548 | EPM-EPBCS-083 | EPM-EPBCS-083 |  |  |  |  | Will Dixon | Mehul Kumar Patel |  | Not Started |  | 2021-10-07 17:14 | 2021-10-20 13:11 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - PBCS | EPM | Build
User Story | CSTONE-4549 | EPM-EPBCS-084 | EPM-EPBCS-084 |  |  |  |  | Will Dixon | Mehul Kumar Patel |  | Not Started |  | 2021-10-07 17:14 | 2021-10-20 13:11 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - PBCS | EPM | Build
User Story | CSTONE-4550 | EPM-EPBCS-085 | EPM-EPBCS-085 |  |  |  |  | Will Dixon | Mehul Kumar Patel |  | Not Started |  | 2021-10-07 17:14 | 2021-10-20 13:11 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - PBCS | EPM | Build
User Story | CSTONE-4551 | EPM-EPBCS-086 | EPM-EPBCS-086 |  |  |  |  | Will Dixon | Mehul Kumar Patel |  | Not Started |  | 2021-10-07 17:14 | 2021-10-20 13:11 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - PBCS | EPM | Build
User Story | CSTONE-4552 | EPM-EPBCS-095 | EPM-EPBCS-095 |  |  |  |  | Will Dixon | Mehul Kumar Patel |  | Not Started |  | 2021-10-07 17:14 | 2021-10-20 13:11 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - PBCS | EPM | Build
User Story | CSTONE-4553 | EPM-EPBCS-096 | EPM-EPBCS-096 |  |  |  |  | Will Dixon | Mehul Kumar Patel |  | Not Started |  | 2021-10-07 17:14 | 2021-10-20 13:11 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - PBCS | EPM | Build
User Story | CSTONE-4554 | EPM-EPBCS-097 | EPM-EPBCS-097 |  |  |  |  | Will Dixon | Mehul Kumar Patel |  | Not Started |  | 2021-10-07 17:14 | 2021-10-20 13:11 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - PBCS | EPM | Build
User Story | CSTONE-4555 | EPM-EPBCS-098 | EPM-EPBCS-098 |  |  |  |  | Will Dixon | Mehul Kumar Patel |  | Not Started |  | 2021-10-07 17:14 | 2021-10-20 13:11 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - PBCS | EPM | Build
User Story | CSTONE-4556 | EPM-EPBCS-099 | EPM-EPBCS-099 |  |  |  |  | Will Dixon | Mehul Kumar Patel |  | Not Started |  | 2021-10-07 17:14 | 2021-10-20 13:11 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - PBCS | EPM | Build
User Story | CSTONE-4557 | EPM-EPBCS-100 | EPM-EPBCS-100 |  |  |  |  | Will Dixon | Mehul Kumar Patel |  | Not Started |  | 2021-10-07 17:14 | 2021-10-20 13:11 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - PBCS | EPM | Build
User Story | CSTONE-4558 | EPM-EPBCS-058 | EPM-EPBCS-058 |  |  |  |  | Will Dixon | Mehul Kumar Patel |  | Done | Fixed | 2021-10-07 17:14 | 2021-10-28 23:12 |  | CSTONE Sprint 5 | 1A |  |  |  | EPM - PBCS | EPM | Build
User Story | CSTONE-4634 | EPM-FCCS-200 | EPM-FCCS-200 |  |  |  |  | vicmartinez | Mehul Kumar Patel |  | Not Started |  | 2021-10-07 17:40 | 2021-10-08 15:39 |  | CSTONE Sprint 5 | 1A+1B |  |  |  |  | EPM | Build
User Story | CSTONE-4635 | EPM-FCCS-201 | EPM-FCCS-201 | EPM-FCCS-201 - Functional |  |  |  | vicmartinez | Mehul Kumar Patel |  | Not Started |  | 2021-10-07 17:40 | 2021-10-08 15:39 |  | CSTONE Sprint 5 | 1A+1B |  |  |  |  | EPM | Work Around
User Story | CSTONE-4636 | EPM-FCCS-202 | EPM-FCCS-202 |  |  |  |  | vicmartinez | Mehul Kumar Patel |  | Not Started |  | 2021-10-07 17:40 | 2021-10-19 22:37 |  | CSTONE Sprint 5 | 1B |  |  |  |  | EPM | Build
User Story | CSTONE-4652 | BI-RICE-1_DSS_TABLES.ORACLE_CLD_GL_JE | BI-RICE-1_DSS_TABLES.ORACLE_CLD_GL_JE | [5 empty] | Wassem Sarakbi | Not yet prioritized | Draft In Progress |  | 2021-10-19 16:42 | 2021-10-19 16:42 | 2021-08-08 |  | 1A |  |  | BI-RICE-1 | RTR-BI | RTR | Build
User Story | CSTONE-4653 | BI-RICE-36_Income Statement Summary (Legacy) | BI-RICE-36_Income | [5 empty] | Wassem Sarakbi | Not yet prioritized | Draft In Progress |  | 2021-10-19 16:45 | 2021-10-25 13:27 | 2021-08-08 |  | 1A |  |  | BI-RICE-36 | RTR-BI | RTR | Build
User Story | CSTONE-4654 | BI-RICE-17_DSS_TABLES.ORACLE_EXPENSE_CURRENT_NEW | BI-RICE-17_DSS_TABLES.ORACLE_EXPENSE_CURRENT_NEW | [5 empty] | Wassem Sarakbi | Not yet prioritized | Draft In Progress |  | 2021-10-19 20:59 | 2021-10-19 20:59 | 2021-08-08 |  | 1A |  |  | BI-RICE-17 | RTR-BI | RTR | Build
User Story | CSTONE-4655 | BI-RICE-2_DSS_TABLES.ORACLE_CLD_GL_BAL | BI-RICE-2_DSS_TABLES.ORACLE_CLD_GL_BAL | [5 empty] | Wassem Sarakbi | Not yet prioritized | Draft In Progress |  | 2021-10-19 21:01 | 2021-10-19 21:01 | 2021-08-08 |  | 1A |  |  | BI-RICE-2 | RTR-BI | RTR | Build
User Story | CSTONE-4656 | BI-RICE-33_GL hierarchy tables | BI-RICE-33_GL | [5 empty] | Wassem Sarakbi | Not yet prioritized | Draft In Progress |  | 2021-10-19 21:03 | 2021-10-19 21:03 | 2021-08-13 |  | 1A |  |  | BI-RICE-33 | RTR-BI | RTR | Build

## Summary
Oracle Module | (Multiple Items)
Release | Phase 1B only
SubTrack | RTR-GL
Count of Unique ID | Subtype Status
L2 | Approved | TBD | Grand Total
Maintain Chart of Accounts | 5 | 1 | 6
Perform Allocations | 1 |  | 1
Period-End Closing & Reporting | 22 |  | 22
Process Manual Journal Entries | 2 |  | 2
Process Reversing Journal Entries | 1 |  | 1
Process Intercompany Journal Entries | 6 |  | 6
Process Intercompany AR/AP Invoices | 54 |  | 54
Perform Intercompany Netting & Reconciliation | 1 |  | 1
Process Intercompany Settlements | 1 |  | 1
Perform AR Period Close | 4 |  | 4
Perform AP Period Close | 6 |  | 6
Grand Total | 103 | 1 | 104

## Sprint Plan Summary
Configuration View | [13 empty] | 1. User Stories - RICE View - Lean Specs
Release | (Multiple Items) | [12 empty] | OSS Type for 1B JIRA analysis | (Multiple Items)
L0 | Record to Report | [12 empty] | Subtype Status | Approved
Oracle Module | (Multiple Items) | [12 empty] | Release | Phase 1B only
User Story Disposition | (Multiple Items)
[14 empty] | Count of Unique ID | Column Labels
Count of Unique ID | Column Labels | [12 empty] | Row Labels | Sprint 10 | Sprint 11 | Sprint 12 | Sprint 13 | Sprint 14 | Sprint 9 | Sprint 7 | Sprint 8
Row Labels | Sprint 1 | Sprint 2 | (blank) | [10 empty] | RTR-AHCS | 7 | 63 | 78 | 16 | 4 | 14 | 1 | 12
RTR-AHCS | 10 | 6 | [11 empty] | RTR-GL | 12 | 15 | 14 |  |  | 16 |  | 5
RTR-GL | 37 | 41 | 1 | [10 empty] | Grand Total | 19 | 78 | 92 | 16 | 4 | 30 | 1 | 17
1. User Stories - RICE View - Build Sprint + Fits
RICE View - Lean Spec (L) | [13 empty] | OSS Type for 1B JIRA analysis | (Multiple Items)
Release | (Multiple Items) | [12 empty] | Subtype Status | Approved
L0 | Record to Report | [12 empty] | Release | Phase 1B only
Oracle Module | (Multiple Items)
User Story Disposition | (Multiple Items) | [12 empty] | Count of Unique ID | Column Labels
[14 empty] | Row Labels | Sprint 10 | Sprint 11 | Sprint 12 | Sprint 13 | Sprint 14 | Sprint 15 | Sprint 7 | Sprint 8 | Sprint 9
Count of Unique ID | Design Sprint [Lean Specs] | [12 empty] | RTR-AHCS | 41 | 27 | 74 | 77 | 17 | 4 | 4 | 8 | 20
SubTrack | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5 | [8 empty] | RTR-GL | 6 | 28 | 15 | 14 |  |  | 17 | 32 | 1
RTR-AHCS | 5 | 15 | 3 | [10 empty] | Grand Total | 47 | 55 | 89 | 91 | 17 | 4 | 21 | 40 | 21
RTR-GL | 11 | 33 | 11 | 5 | 3
1. User Stories - RICE View - TUT/FUT
RICE View - Build (D) | [13 empty] | OSS Type for 1B JIRA analysis | (Multiple Items)
Release | (Multiple Items) | [12 empty] | Subtype Status | Approved
L0 | Record to Report | [12 empty] | Release | Phase 1B only
Oracle Module | (Multiple Items)
User Story Disposition | (Multiple Items) | [12 empty] | Count of Unique ID | Column Labels
[14 empty] | Row Labels | Sprint 10 | Sprint 11 | Sprint 12 | Sprint 13 | Sprint 14 | Sprint 15
Count of Unique ID | Build Sprint [Tech Build] | [12 empty] | RTR-AHCS |  | 28 | 6 | 140 | 17 | 4
SubTrack | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5 | Sprint 6 | TBD | [7 empty] | RTR-GL | 5 | 2 | 34 | 21
RTR-AHCS | 10 | 5 | 8 | [10 empty] | Grand Total | 5 | 30 | 40 | 161 | 17 | 4
RTR-GL | 11 | 14 | 15 | 19 | 3 | 1
[14 empty] | 1. User Stories - Total | AHCS | GL
[14 empty] | Sprint 7 | 5 | 17
[14 empty] | Sprint 8 | 20 | 37
[14 empty] | Sprint 9 | 34 | 17
RICE View - TUT/FUT (T) | [13 empty] | Sprint 10 | 48 | 23
Release | (Multiple Items) | [12 empty] | Sprint 11 | 118 | 45
L0 | Record to Report | [12 empty] | Sprint 12 | 158 | 63
Oracle Module | (Multiple Items) | [12 empty] | Sprint 13 | 233 | 35
User Story Disposition | (Multiple Items) | [12 empty] | Sprint 14 | 38 | 0
[14 empty] | Sprint 15 | 8 | 0
Count of Unique ID | Delivery Sprint [TUT/FUT]
SubTrack | Sprint 11 | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5 | Sprint 6 | Sprint 68 | Sprint 69 | Sprint 73 | Sprint 76 | Sprint 80 | Sprint 9 | TBD
RTR-AHCS |  |  | 15 | 8
RTR-GL | 1 | 8 | 17 | 6 | 18 | 6 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2. Deliver phase User Stories - RICE View - Lean Specs
[14 empty] | OSS Type for 1B JIRA analysis | (Multiple Items)
[14 empty] | Release | Phase 1B only
[14 empty] | Subtype Status | Approved
Overall RICE View
| Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5 | Sprint 6 | TBD | [6 empty] | Count of Unique ID | Column Labels
RTR-AHCS | 5 | 25 | 23 | 16 | 0 | 0 | #REF! | [6 empty] | Row Labels | Sprint 10 | Sprint 11 | Sprint 12 | Sprint 8 | Sprint 9
RTR-GL | 11 | 52 | 42 | 26 | 40 | 9 | #REF! | [6 empty] | RTR-GL | 12 | 10 | 15 | 2 | 2
[14 empty] | Grand Total | 12 | 10 | 15 | 2 | 2
Total View | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5 | Sprint 6 | Total
RTR-AHCS | 15 | 31 | 23 | 16 | 0 | 0 | 85 | [6 empty] | 2. Deliver phase User Stories - RICE View - Build + Fits
RTR-GL | 48 | 93 | 43 | 26 | 40 | 9 | 259 | [6 empty] | OSS Type for 1B JIRA analysis | (Multiple Items)
Total View | 63 | 124 | 66 | 42 | 40 | 9 | 344 | [6 empty] | Release | Phase 1B only
RTR-AHCS | 15 | 46 | 69 | 85 | 85 | 85 |  | Cumulative | [5 empty] | Subtype Status | Approved
RTR-GL | 48 | 141 | 184 | 210 | 250 | 259 |  | Cumulative
RTR 1A | 63 | 187 | 253 | 295 | 335 | 344 |  | Cumulative | [5 empty] | Count of Unique ID | Column Labels
RTR-AHCS | 17.65% | 54.12% | 81.18% | 100% | 100% | 100% | [7 empty] | Row Labels | Sprint 10 | Sprint 11 | Sprint 12 | Sprint 13 | Sprint 7 | Sprint 8
RTR-GL | 18.53% | 54.44% | 71.04% | 81.08% | 96.53% | 100% | [7 empty] | RTR-GL | 2 | 14 | 10 | 15 | 4 | 8
RTR 1A % | 18.31% | 54.36% | 73.55% | 85.76% | 97.38% | 100% | [7 empty] | Grand Total | 2 | 14 | 10 | 15 | 4 | 8
2. Deliver phase User Stories - RICE View - Build
[14 empty] | OSS Type for 1B JIRA analysis | (Multiple Items)
[14 empty] | Release | Phase 1B only
[14 empty] | Subtype Status | Approved
[14 empty] | Count of Unique ID | Column Labels
[14 empty] | Row Labels | Sprint 10 | Sprint 11 | Sprint 12 | Sprint 13
[14 empty] | RTR-GL | 2 | 1 | 17 | 21
[14 empty] | Grand Total | 2 | 1 | 17 | 21
[14 empty] | 2. Deliver Phase User Stories - Total | AHCS | GL
[14 empty] | Sprint 7 |  | 4
[14 empty] | Sprint 8 |  | 10
[14 empty] | Sprint 9 |  | 2
[14 empty] | Sprint 10 |  | 16
[14 empty] | Sprint 11 |  | 25
[14 empty] | Sprint 12 |  | 42
[14 empty] | Sprint 13 |  | 36
[14 empty] | Sprint 14 |  | 0
[14 empty] | Sprint 15 |  | 0
[14 empty] | Total User Stories | AHCS | GL | AHCS Cumulative | GL Cumulative | Total | Cumulative %
[14 empty] | Sprint 7 | 5 | 21 | 5 | 21 | 26 | 2.515%
[14 empty] | Sprint 8 | 20 | 47 | 25 | 68 | 93 | 8.994%
[14 empty] | Sprint 9 | 34 | 19 | 59 | 87 | 146 | 14.12%
[14 empty] | Sprint 10 | 48 | 39 | 107 | 126 | 233 | 22.53%
[14 empty] | Sprint 11 | 118 | 70 | 225 | 196 | 421 | 40.72%
[14 empty] | Sprint 12 | 158 | 105 | 383 | 301 | 684 | 66.15%
[14 empty] | Sprint 13 | 233 | 71 | 616 | 372 | 988 | 95.55%
[14 empty] | Sprint 14 | 38 | 0 | 654 | 372 | 1026 | 99.23%
[14 empty] | Sprint 15 | 8 | 0 | 662 | 372 | 1034 | 100%

## WESCO RICE Listing 1B
[24 empty] | Functional Specs | [10 empty] | Technical Design & Build (including TUT) | [8 empty] | Legacy Build
Sr. No. | Business | Release | Product | Sub-Track | Module | RICEW Type | RICEW ID | RICEW Name / Description | Functional Track Lead | Legacy / 3rd Party Build Needed (Y/N)? | Source System | Target System | KDD | Comments / Notes | Approved ? | Object Type | Sprint Cycle | In SOW? | CO # | Complexity | Original Complexity | Frequency | Concatenated String | Functional Spec Delivery Cycle | Functional Spec Author | Process Owner | Product Owner | Functional Spec Start Date | Functional Spec End Date | Process Owner Approval Status | Product Owner Approval Status | Functional Spec Status | Functional Spec Actual Start date | Functional Spec Actual End date | Tech Des & Bld Delivery Cycle | Tech TUT/FUT Cycle | Tech Des & Bld Author | Tech Des & Bld Start Date | Tech Des & Bld End Date | Tech Des & Bld Status | Tech Des & Bld Actual Start Date | Tech Des & Bld Actual End Date | Functional Testing | Legacy Build Delivery Cycle | Legacy Build Author | Legacy Build Start Date | Legacy Build End Date | Legacy Build Status | Legacy Build Actual Start Date | Legacy Build Actual End Date | End-To-End Testing Start Date | End-To-End Testing End Date | E2E Status | Lean Specs Link | Comments | Business Case Grouping | Functional Lean Spec Owner | Rest of Activities - Build & Support Owner | Daily Sync call notes - OSS | Daily Sync Call Notes - AC | Week for SIT1 Readiness | Migration status - SIT1 | Week for SIT2 Readiness | Migration status - SIT2 | Migration Status UAT | Comments | User Story ID | User Story ID Count | Deliver Phase User Story ID | Deliver User Story ID Count | Link to User Story ID | Out of Scope | Report Priority | Link to Original Report RICEW ID
20 | ABC Corp | 1b | ERP | RTR-GL | GL | Report | RPT011 | Confirm relevant manual journals copied to secondary | David |  |  |  |  | Abhijit - Devang - How to recognize if the secondary ledger balances has been copied from primary ledger ?? | Yes | Report (BI Publisher) |  | Y |  | Complex | Complex |  | Report (BI Publisher) - Complex | Sprint 11 | [7 empty] | Not Started |  |  | Sprint 12 | Sprint 12 |  |  |  | Not Started |  |  | Not Started |  |  |  |  | Not Applicable | [18 empty] | RTR-GL-110 DP-RTR-GL-053 DP-RTR-GL-012 | 1 | DP-RTR-GL-012 DP-RTR-GL-053 | 2 | TRUE |  | P1 |  | 0
21 | ABC Corp | 1b | ERP | RTR-GL | GL | Conversion | CNV003 | GL Open Balances (YTD plus Current Fiscal Year period balances) - Secondary Ledger | David | Y | Fusion FAH | Oracle ERP Cloud |  | 6/3 VL : ABC Corp | Yes | Conversion (Using ADFDi and FBDI) |  | Y |  | Complex | Medium |  | Conversion (Using ADFDi and FBDI) - Complex | Sprint 8 | [7 empty] | Not Started |  |  | Sprint 10 | Sprint 10 | Afsheen, Quershi | 2021-01-31 | 2021-02-11 | Not Started | 2021-02-14 | 2021-02-25 | Not Started | [16 empty] | 02/14/2022 - Lean spec still under review and not released for development. Moving this by one sprint to Sprint-10. 12/23 - Assumption is that secondary ledgers will follow the same COA structure but will have different accounting convention. No tweaking necessary in the COA engine to accommodate COA translations. | [6 empty] | RTR-GL-089, RTR-GL-121 | 2 |  | 0 | TRUE |  |  |  | 0
22 | ABC Corp | 1b | ERP | RTR-GL | GL | Conversion | CNV004 | GL Open Balances (YTD plus Current Fiscal Year period balances) - Primary Ledger | David | Y | PeopleSoft | Oracle ERP Cloud |  | 6/3 VL : ABC Corp | Yes | Conversion (Using ADFDi and FBDI) |  | Y |  | Complex | Complex |  | Conversion (Using ADFDi and FBDI) - Complex | Sprint 8 | [7 empty] | Not Started |  |  | Sprint 9 | Sprint 10 | Afsheen, Quershi | 2021-01-17 | 2021-01-28 | Not Started | 2021-01-24 | 2021-02-11 | Not Started | [16 empty] | 02/14/2022 - Lean specs targetted to complete this week. 1A solution is completely reusable for 1B, not net new build required. Sample file expected to complete the unit testing. 12/23 - Assumption is that mocked up/ test COA combination values will be used for unit-testing. Do we get the real file for select Bus/ ledgers with COA mapping during the functional unit testing ? | [6 empty] | RTR-GL-089, RTR-GL-122 | 2 |  | 0 | TRUE |  |  |  | 0
24 | ABC Corp | 1b | ERP | RTR-GL | GL | Interface | INT021 | GL Data to IAP - Journals | David | Y | Oracle ERP Cloud | IAP | KDD 8 | This Component is part of KDD8 - Layout for IAP is same as the TeraData & can be re-used. Based on above assumption regarding no changes in Layout, changing complexity to Simple | Yes | Interface - Outbound (Using BI Report) |  | Y |  | Medium | Medium |  | Interface - Outbound (Using BI Report) - Medium | Sprint 8 |  |  |  |  | 2021-10-01 |  |  | Not Started |  |  | Sprint 10 | Sprint 10 | Preetansh | 2021-01-24 | 2021-02-04 | Not Started | 2021-02-09 |  | Not Started | [16 empty] | 02/14/2022 - Reusable from 1A solution with BI as the tool. 02/11/22 - FS Delayed. Received final approval on 02/09 02/23 - Assuming IAP will expect data from ERP Cloud in the same format as in Teradata. Currently assuming BI Publisher as the extract tool. Need an understanding of data volumes which will drive the design. | [6 empty] | RTR-GL-140 | 1 | DP-RTR-GL-014F | 1 | TRUE |  |  |  | 0
25 | ABC Corp | 1b | ERP | RTR-GL | GL | Report | RPT016 | Flag incorrect exchange rates on Journal report | David | [6 empty] | Report (BI Publisher) |  | Y |  | Medium |  |  | Report (BI Publisher) - Medium | Sprint 12 | [7 empty] | Not Started |  |  | Sprint 13 | Sprint 13 |  |  |  | Not Started |  |  | Not Started |  |  |  |  | Not Applicable | [18 empty] | RTR-GL-107 DP-RTR-GL-054 | 1 | DP-RTR-GL-054 | 1 | TRUE |  | P1 |  | 0
26 | ABC Corp | 1b | ERP | RTR-GL | GL | Report | RPT017 | IC Approval Notification Customization Report | David | [6 empty] | Report (BI Publisher) |  | Y |  | Medium |  |  | Report (BI Publisher) - Medium | Sprint 11 | [7 empty] | Not Started |  |  | Sprint 12 | Sprint 12 |  |  |  | Not Started |  |  | Not Started |  |  |  |  | Not Applicable | [18 empty] | RTR-IC-005 | 1 |  | 0 | TRUE |  | P0 |  | 0
27 | ABC Corp | 1b | ERP | RTR-GL | GL | Report | RPT018 | TB with Dr/Cr report for Tax | David |  |  |  |  | As per call with Ankush/Asma/Nilkanth : We need this report As per Userstory : 12/23 NG: Removed as per latest report rationalization master document Required for International reporting. Accounting would not want planned TB report to show Dr/Cr & hence a new custom report |  | Report (BI Publisher) |  | Y |  | Medium |  |  | Report (BI Publisher) - Medium | Sprint 12 | [7 empty] | Not Started |  |  | Sprint 13 | Sprint 13 |  |  |  | Not Started |  |  | Not Started |  |  |  |  | Not Applicable | [18 empty] | RTR-GL-148 RTR-GL-165 | 1 |  | 5 | TRUE |  | P1 |  | 0
28 | ABC Corp | 1b | ERP | RTR-GL | GL | Report | RPT019 | Non-material IC TB report by LE [Invoice level details] | David | [6 empty] | Report (BI Publisher) |  | Y |  | Complex |  |  | Report (BI Publisher) - Complex | Sprint 12 | [7 empty] | Not Started |  |  | Sprint 13 | Sprint 13 |  |  |  | Not Started |  |  | Not Started |  |  |  |  | Not Applicable | [18 empty] | RTR-IC-012 | 1 |  | 5 | TRUE |  | P1 |  | 0
29 | ABC Corp | 1b | ERP | RTR-GL | GL | Report | RPT020 | Non-material IC TB report by LE [summarize at account level] | David | [6 empty] | Report (BI Publisher) |  | Y |  | Medium |  |  | Report (BI Publisher) - Medium | Sprint 12 | [7 empty] | Not Started |  |  | Sprint 13 | Sprint 13 |  |  |  | Not Started |  |  | Not Started |  |  |  |  | Not Applicable | [18 empty] | RTR-IC-013 | 1 |  | 0 | TRUE |  | P1 |  | 0
30 | ABC Corp | 1b | ERP | RTR-GL | GL | Report | RPT026 | France FEC Report | David |  |  |  |  | Abhijit - Devang - Need to check the standard report availability |  | Report (BI Publisher) |  | Y |  | Very Complex |  |  | Report (BI Publisher) - Very Complex | Sprint 12 |  |  |  |  | 2021-10-01 |  |  | Not Started |  |  | Sprint 13 | Sprint 13 |  |  |  | Not Started |  |  | Not Started |  |  |  |  | Not Applicable | [18 empty] | RTR-GL-076 DP-RTR-GL-014A DP-RTR-GL-058 | 1 | DP-RTR-GL-014A DP-RTR-GL-058 | 3 | TRUE |  | P4 |  | 0
31 | ABC Corp | 1b | ERP | RTR-GL | GL | Report | RPT027 | Non-material IC AR Report | David | [6 empty] | Report (BI Publisher) |  | Y |  | Medium |  |  | Report (BI Publisher) - Medium | Sprint 11 | [7 empty] | Not Started |  |  | Sprint 12 | Sprint 12 |  |  |  | Not Started |  |  | Not Started |  |  |  |  | Not Applicable | [18 empty] | RTR-IC-014A | 1 |  | 5 | TRUE |  | P0 |  | 0
32 | ABC Corp | 1b | ERP | RTR-GL | GL | Report | RPT028 | Non-material IC AP Report | David | [6 empty] | Report (BI Publisher) |  | Y |  | Medium |  |  | Report (BI Publisher) - Medium | Sprint 11 | [7 empty] | Not Started |  |  | Sprint 12 | Sprint 12 |  |  |  | Not Started |  |  | Not Started |  |  |  |  | Not Applicable | [18 empty] | RTR-IC-014B | 1 |  | 5 | TRUE |  | P0 |  | 0
33 | ABC Corp | 1b | ERP | RTR-GL | GL | Report | RPT029 | Non-material IC AR Report with receipts created in selected range | David | [6 empty] | Report (BI Publisher) |  | Y |  | Complex | Medium |  | Report (BI Publisher) - Complex | Sprint 11 | [7 empty] | Not Started |  |  | Sprint 12 | Sprint 12 |  |  |  | Not Started |  |  | Not Started |  |  |  |  | Not Applicable | [18 empty] | RTR-IC-024A | 1 |  | 0 | TRUE |  | P1 |  | 0
34 | ABC Corp | 1b | ERP | RTR-GL | GL | Report | RPT030 | Non-material IC AP Report with payments created in selected range | David | [6 empty] | Report (BI Publisher) |  | Y |  | Complex | Medium |  | Report (BI Publisher) - Complex | Sprint 11 | [7 empty] | Not Started |  |  | Sprint 12 | Sprint 12 |  |  |  | Not Started |  |  | Not Started |  |  |  |  | Not Applicable | [18 empty] | RTR-IC-024B | 1 |  | 0 | TRUE |  | P1 |  | 0
35 | ABC Corp | 1b | ERP | RTR-GL | GL | Report | RPT031 | Non-material IC AP Invoices selected for payment report with associated AR invoice details | David | [6 empty] | Report (BI Publisher) |  | Y |  | Complex | Medium |  | Report (BI Publisher) - Complex | Sprint 11 | [7 empty] | Not Started |  |  | Sprint 12 | Sprint 12 |  |  |  | Not Started |  |  | Not Started |  |  |  |  | Not Applicable | [18 empty] | RTR-IC-028 | 1 |  | 0 | TRUE |  | P1 |  | 0
36 | ABC Corp | 1b | ERP | RTR-GL | GL | Report | RPT032 | Non-material IC AR Invoice Aging [Invoice level] | David | [6 empty] | Report (BI Publisher) |  | Y |  | Complex | Medium |  | Report (BI Publisher) - Complex | Sprint 12 | [7 empty] | Not Started |  |  | Sprint 13 | Sprint 13 |  |  |  | Not Started |  |  | Not Started |  |  |  |  | Not Applicable | [18 empty] | RTR-IC-035A | 1 |  | 5 | TRUE |  | P1 |  | 0
37 | ABC Corp | 1b | ERP | RTR-GL | GL | Report | RPT033 | Non-material IC AP Invoice Aging [Invoice level] | David | [6 empty] | Report (BI Publisher) |  | Y |  | Complex |  |  | Report (BI Publisher) - Complex | Sprint 12 | [7 empty] | Not Started |  |  | Sprint 13 | Sprint 13 |  |  |  | Not Started |  |  | Not Started |  |  |  |  | Not Applicable | [18 empty] | RTR-IC-035B | 1 |  | 5 | TRUE |  | P1 |  | 0
38 | ABC Corp | 1b | ERP | RTR-GL | GL | Report | RPT034 | Non-material IC AR Invoice Aging [Account level] | David | [6 empty] | Report (BI Publisher) |  | Y |  | Complex |  |  | Report (BI Publisher) - Complex | Sprint 12 | [7 empty] | Not Started |  |  | Sprint 13 | Sprint 13 |  |  |  | Not Started |  |  | Not Started |  |  |  |  | Not Applicable | [18 empty] | RTR-IC-036A | 1 |  | 5 | TRUE |  | P1 |  | 0
39 | ABC Corp | 1b | ERP | RTR-GL | GL | Report | RPT035 | Non-material IC AP Invoice Aging [Account level] | David | [6 empty] | Report (BI Publisher) |  | Y |  | Complex | Very Complex |  | Report (BI Publisher) - Complex | Sprint 12 | [7 empty] | Not Started |  |  | Sprint 13 | Sprint 13 |  |  |  | Not Started |  |  | Not Started |  |  |  |  | Not Applicable | [18 empty] | RTR-IC-036B | 1 |  | 5 | TRUE |  | P1 |  | 0
40 | ABC Corp | 1b | ERP | RTR-GL | GL | Report | RPT036 | IC Transaction Detail Report | David | [6 empty] | Report (BI Publisher) |  | Y |  | Very Complex | Very Complex |  | Report (BI Publisher) - Very Complex | Sprint 11 | [7 empty] | Not Started |  |  | Sprint 12 | Sprint 13 |  |  |  | Not Started |  |  | Not Started |  |  |  |  | Not Applicable | [18 empty] | RTR-IC-037 RTR-IC-039 RTR-GL-164 | 2 |  | 5 | TRUE |  | P0 |  | 0
41 | ABC Corp | 1b | ERP | RTR-GL | GL | Conversion | CNV010 | GL Open Balances (YTD plus Current Fiscal Year period balances) - Reporting Ledgers (Extraction & Conversion Required) | David | Y | PeopleSoft | Oracle ERP Cloud |  |  |  | Conversion (Using ADFDi and FBDI) |  | N |  | Medium |  |  | Conversion (Using ADFDi and FBDI) - Medium | Sprint 8 | [7 empty] | Not Started |  |  | Sprint 10 | Sprint 10 | Afsheen, Quershi | 2021-01-24 | 2021-01-28 | Not Started | 2021-01-31 | 2021-02-18 | Not Started | [16 empty] | 02/14/2022 - Lean spec still under review and not released for development. Moving this by one sprint to Sprint-10. 12/23 - Assuming this won't need a new file but triggering additional recon reports to tie back the reporting currency balances associated with the primary ledger posts. | [6 empty] | RTR-GL-089, RTR-GL-123 | 2 |  | 0 | TRUE |  |  |  | 0
42 | ABC Corp | 1b | ERP | RTR-GL | GL | Interface | INT042 | GL Data to IAP - Balances | David | Y | Oracle ERP Cloud | IAP | KDD 8 | This Component is part of KDD8 - Layout for IAP is same as the TeraData & can be re-used Based on above assumption regarding no changes in Layout, changing complexity to Simple | Yes | Interface - Outbound (Using BI Report) |  | N |  | Medium | Medium |  | Interface - Outbound (Using BI Report) - Medium | Sprint 8 |  |  |  |  | 2021-10-01 |  |  | Not Started |  |  | Sprint 10 | Sprint 10 | Preetansh | 2021-01-31 | 2021-02-09 | Not Started | 2021-02-14 | 2021-02-18 | Not Started | [16 empty] | 02/14/2022 - Reusable from 1A with BI as the tool. 02/11/22 - FS Delayed. Received final approval on 02/09 02/23 - Assuming IAP will expect data from ERP Cloud in the same format as in Teradata. Currently assuming BI Publisher as the extract tool. Need an understanding of data volumes which will drive the design. | [6 empty] | RTR-GL-138 | 1 | DP-RTR-GL-014G | 1 | TRUE |  |  |  | 0
43 | ABC Corp | 1b | ERP | RTR-GL | GL | Report | RPT048 | IC Balance Matrix: IC Balance report by GL balances | David | [6 empty] | FRS / SmartView |  | N |  | Medium | Simple |  | FRS / SmartView - Medium | Sprint 11 | [7 empty] | Not Started |  |  | Sprint 12 | Sprint 12 |  |  |  | Not Started |  |  | Not Started |  |  |  |  | Not Applicable | [18 empty] | REP-RTR-GL-3 | 1 |  | 0 | TRUE |  | P0 |  | 0
44 | ABC Corp | 1b | ERP | RTR-GL | GL | Report | RPT049 | Reval Summary Report - all COA Segments | David | [6 empty] | Report (BI Publisher) |  | N |  | Complex |  |  | Report (BI Publisher) - Complex | Sprint 12 |  | Erica | Satheesh | 2021-10-04 | 2021-10-29 |  |  | Not Started |  |  | Sprint 13 | Sprint 13 |  |  |  | Not Started |  |  | Not Started |  |  |  |  | Not Applicable | [6 empty] | P3 | [11 empty] | REP-RTR-GL-5 | 1 |  | 0 | TRUE |  | P1 |  | 0
45 | ABC Corp | 1b | ERP | RTR-GL | GL | Report | RPT050 | Reval Summary Report - only LE & Account | David | [6 empty] | Report (BI Publisher) |  | N |  | Complex |  |  | Report (BI Publisher) - Complex | Sprint 12 |  | Erica | Satheesh | 2021-10-04 | 2021-10-29 |  |  | Not Started |  |  | Sprint 13 | Sprint 13 |  |  |  | Not Started |  |  | Not Started |  |  |  |  | Not Applicable | [6 empty] | P3 | [11 empty] | REP-RTR-GL-6 | 1 |  | 0 | TRUE |  | P1 |  | 0
48 | ABC Corp | 1b | ERP | RTR-GL | GL | Conversion | CNV015 | Intercompany AR Invoices Conversion (non-material) - North America | David | Y | PeopleSoft | Oracle ERP Cloud |  |  |  | Conversion (Using ADFDi and FBDI) |  | N |  | Complex |  |  | Conversion (Using ADFDi and FBDI) - Complex | Sprint 10 | [10 empty] | Sprint 11 | Sprint 12 | [28 empty] | Completed |  | RTR-IC-056 | 1 |  | 0 | TRUE |  |  |  | 0
49 | ABC Corp | 1b | ERP | RTR-GL | GL | Conversion | CNV016 | Intercompany AP Invoices Conversion (non-material) - North America | David | Y | PeopleSoft | Oracle ERP Cloud |  |  |  | Conversion (Using ADFDi and FBDI) |  | N |  | Complex |  |  | Conversion (Using ADFDi and FBDI) - Complex | Sprint 10 | [10 empty] | Sprint 11 | Sprint 12 | [30 empty] | RTR-IC-057 | 1 |  | 0 | TRUE |  |  |  | 0
50 | ABC Corp | 1b | ERP | RTR-GL | GL | Conversion | CNV017 | Intercompany AR Invoices Conversion (non-material) - EMEA | David | Y | PeopleSoft | Oracle ERP Cloud |  |  |  | Conversion (Using ADFDi and FBDI) |  | N |  | Medium |  |  | Conversion (Using ADFDi and FBDI) - Medium | Sprint 10 | [10 empty] | Sprint 11 | Sprint 12 | [28 empty] | Completed |  | RTR-IC-058 | 1 |  | 0 | TRUE |  |  |  | 0
51 | ABC Corp | 1b | ERP | RTR-GL | GL | Conversion | CNV018 | Intercompany AP Invoices Conversion (non-material) - EMEA | David | Y | PeopleSoft | Oracle ERP Cloud |  |  |  | Conversion (Using ADFDi and FBDI) |  | N |  | Medium |  |  | Conversion (Using ADFDi and FBDI) - Medium | Sprint 10 | [10 empty] | Sprint 11 | Sprint 12 | [28 empty] | Completed |  | RTR-IC-059 | 1 |  | 0 | TRUE |  |  |  | 0
52 | ABC Corp | 1b | ERP | RTR-GL | GL | Conversion | CNV019 | Intercompany AR Invoices Conversion (non-material) - APAC | David | Y | PeopleSoft | Oracle ERP Cloud |  |  |  | Conversion (Using ADFDi and FBDI) |  | N |  | Medium |  |  | Conversion (Using ADFDi and FBDI) - Medium | Sprint 10 | [10 empty] | Sprint 11 | Sprint 12 | [28 empty] | Completed |  | RTR-IC-060 | 1 |  | 0 | TRUE |  |  |  | 0
53 | ABC Corp | 1b | ERP | RTR-GL | GL | Conversion | CNV020 | Intercompany AP Invoices Conversion (non-material) - APAC | David | Y | PeopleSoft | Oracle ERP Cloud |  |  |  | Conversion (Using ADFDi and FBDI) |  | N |  | Medium |  |  | Conversion (Using ADFDi and FBDI) - Medium | Sprint 10 | [10 empty] | Sprint 11 | Sprint 12 | [28 empty] | Completed |  | RTR-IC-061 | 1 |  | 0 | TRUE |  |  |  | 0
54 | ABC Corp | 1b | ERP | RTR-GL | GL | Conversion | CNV021 | Intercompany AR Invoices Conversion (non-material) - CALA | David | Y | PeopleSoft | Oracle ERP Cloud |  |  |  | Conversion (Using ADFDi and FBDI) |  | N |  | Medium |  |  | Conversion (Using ADFDi and FBDI) - Medium | Sprint 10 | [10 empty] | Sprint 11 | Sprint 12 | [28 empty] | Completed |  | RTR-IC-062 | 1 |  | 0 | TRUE |  |  |  | 0
55 | ABC Corp | 1b | ERP | RTR-GL | GL | Conversion | CNV022 | Intercompany AP Invoices Conversion (non-material) - CALA | David | Y | PeopleSoft | Oracle ERP Cloud |  |  |  | Conversion (Using ADFDi and FBDI) |  | N |  | Medium |  |  | Conversion (Using ADFDi and FBDI) - Medium | Sprint 10 | [10 empty] | Sprint 11 | Sprint 12 | [28 empty] | Completed |  | RTR-IC-063 | 1 |  | 0 | TRUE |  |  |  | 0
58 | ABC Corp | 1b | ERP | RTR-AHCS | AHCS | Interface | INT125 | Journal Import - Concur | Manpreet | Y | Concur | Oracle AHCS |  | Retro Fit, Need to check if we code change needed to handle multiple files for different regions or we will receive a single file |  | Interface - Inbound (Using Middleware) |  | Y |  | Complex | Complex |  | Interface - Inbound (Using Middleware) - Complex | Sprint 11 | [7 empty] | Not Started |  |  | Sprint 12 | Sprint 13 |  |  |  | Not Started |  |  | Not Started | [23 empty] | RTR-AHCS-175 | 1 |  | 0 | TRUE |  |  |  | 0
60 | ABC Corp | 1b | ERP | RTR-AHCS | AHCS | Interface | INT018 | Journal Import - Payroll (CloudPay) | Manpreet | Y | CloudPay | Oracle AHCS |  | For UK only |  | Interface - Inbound (Using Middleware) |  | Y |  | Complex | Complex |  | Interface - Inbound (Using Middleware) - Complex | Sprint 10 | [7 empty] | Not Started |  |  | Sprint 11 | Sprint 12 |  |  |  | Not Started |  |  | Not Started | [23 empty] | RTR-AHCS-067 | 0 |  | 0 | FALSE |  |  |  | 0
69 | ABC Corp | 1b | ERP | RTR-AHCS | AHCS | Interface | INT020 | Journal Import - Lease Harbor | Manpreet | Y | Lease Harbor | Oracle AHCS |  | Retro-Fit changes may be needed on what was built for Step 1.0 |  | Interface - Inbound (Using Middleware) |  | Y |  | Complex | Complex |  | Interface - Inbound (Using Middleware) - Complex | Sprint 8 | [7 empty] | Not Started |  |  | Sprint 11 | Sprint 12 |  |  |  | Not Started |  |  | Not Started | [23 empty] | RTR-AHCS-183,RTR-AHCS-473 | 0 |  | 0 | FALSE |  |  |  | 0
77 | ABC Corp | 1b | ERP | RTR-AHCS | AHCS | Interface | INT123 | GL Feed from SXE US to AHCS | Manpreet | Y | SXE US | Oracle AHCS | KDD 6B |  |  | Interface - Inbound (Using Middleware) |  |  |  | Complex |  |  | Interface - Inbound (Using Middleware) - Complex | Sprint 9 | [7 empty] | Not Started |  |  | Sprint 10 | Sprint 11 |  |  |  | Not Started |  |  | Not Started | [23 empty] | RTR-AHCS-148,RTR-AHCS-474 | 0 |  | 0 | FALSE |  |  |  | 0
79 | ABC Corp | 1b | ERP | RTR-AHCS | AHCS | Interface | INT124 | GL Feed from Eclipse to AHCS | Manpreet | Y | Eclipse | Oracle AHCS | KDD 6B |  |  | Interface - Inbound (Using Middleware) |  |  |  | Complex |  |  | Interface - Inbound (Using Middleware) - Complex | Sprint 9 | [7 empty] | Not Started |  |  | Sprint 10 | Sprint 11 |  |  |  | Not Started |  |  | Not Started | [23 empty] | RTR-AHCS-149,RTR-AHCS-470 | 0 |  | 0 | FALSE |  |  |  | 0
80 | ABC Corp | 1b | ERP | RTR-AHCS | AHCS | Interface | INT045 | GL Feed from Treasury to AHCS | Manpreet | Y | Treasury | Oracle AHCS | KDD 6B |  |  | Interface - Inbound (Using Middleware) |  |  |  | Complex |  |  | Interface - Inbound (Using Middleware) - Complex | Sprint 10 | [7 empty] | Not Started |  |  | Sprint 11 | Sprint 12 |  |  |  | Not Started |  |  | Not Started | [23 empty] | RTR-AHCS-250,RTR-AHCS-472 | 0 |  | 0 | FALSE |  |  |  | 0
203 | ABC Corp | 1b | ERP | RTR-AHCS | AHCS | Interface | INT184 | Fixed Assets to AHCS | Manpreet | Y | PeopleSoft | Oracle AHCS | KDD 6B2 |  |  | Interface - Inbound (Using Middleware) |  |  |  | Complex |  |  | Interface - Inbound (Using Middleware) - Complex | Sprint 8 | [10 empty] | Sprint 10 | Sprint 11 | Indrenu Misra | 2022-02-08 | 2022-03-25 | Lean spec in progress | 2022-02-08 | [25 empty] | RTR-AHCS-150,RTR-AHCS-471 | 0 |  | 0 | FALSE |  |  |  | 0
214 | ABC Corp | 1b New | ERP | RTR-AHCS | AHCS | Interface | INT216 | MF AR Transactions Load to staging table | Manpreet |  | MF AR | Oracle AHCS |  |  |  | Interface - Inbound (Using Middleware) |  | New (1B Assesment) |  | Medium |  |  | Interface - Inbound (Using Middleware) - Medium | Sprint 7 | [10 empty] | Sprint 10 | Sprint 11 | Syed | 2022-01-31 | 2022-03-11 | Lean spec in progress | 2022-01-31 | [13 empty] | AC - Assumed that all mainframe applications for AR will be able to send a normalized file structure that can be commonly processed. | [11 empty] | RTR-AHCS-088 RTR-AHCS-093 RTR-AHCS-101 RTR-AHCS-094 RTR-AHCS-103 RTR-AHCS-123 RTR-AHCS-124 | 0 |  | 0 | FALSE |  |  |  | 0
215 | ABC Corp | 1b New | ERP | RTR-AHCS | AHCS | Interface | INT217 | MF AR Transaction AHCS Processing | Manpreet |  | MF AR | Oracle AHCS |  |  |  | Interface - Inbound (Using Middleware) |  | New (1B Assesment) |  | Very Complex |  |  | Interface - Inbound (Using Middleware) - Very Complex | Sprint 7 | [10 empty] | Sprint 10 | Sprint 11 | Syed | 2022-01-31 | 2022-03-11 | Lean spec in progress | 2022-01-31 | [25 empty] | RTR-AHCS-088 RTR-AHCS-093 RTR-AHCS-101 RTR-AHCS-094 RTR-AHCS-103 RTR-AHCS-123 RTR-AHCS-124 | 0 |  | 0 | FALSE |  |  |  | 0
216 | ABC Corp | 1b New | ERP | RTR-AHCS | AHCS | Interface | INT218 | MF AP Transactions Load to staging table | Manpreet |  | MF AP | Oracle AHCS |  |  |  | Interface - Inbound (Using Middleware) |  | New (1B Assesment) |  | Medium |  |  | Interface - Inbound (Using Middleware) - Medium | Sprint 8 | [10 empty] | Sprint 10 | Sprint 11 | Jigyasa | 2022-01-31 | 2022-03-11 | Lean spec in progress | 2022-01-31 | [25 empty] | RTR-AHCS-089 RTR-AHCS-091 RTR-AHCS-092 RTR-AHCS-094 RTR-AHCS-093 RTR-AHCS-096 RTR-AHCS-123 RTR-AHCS-124 | 0 |  | 0 | FALSE |  |  |  | 0
217 | ABC Corp | 1b New | ERP | RTR-AHCS | AHCS | Interface | INT219 | MF AP Transaction AHCS Processing | Manpreet |  | MF AP | Oracle AHCS |  |  |  | Interface - Inbound (Using Middleware) |  | New (1B Assesment) |  | Very Complex |  |  | Interface - Inbound (Using Middleware) - Very Complex | Sprint 8 | [10 empty] | Sprint 10 | Sprint 11 | Jigyasa | 2022-01-31 | 2022-03-11 | Lean spec in progress | 2022-01-31 | [25 empty] | RTR-AHCS-089 RTR-AHCS-091 RTR-AHCS-092 RTR-AHCS-094 RTR-AHCS-093 RTR-AHCS-096 RTR-AHCS-123 RTR-AHCS-124 | 0 |  | 0 | FALSE |  |  |  | 0
220 | ABC Corp | 1b New | ERP | RTR-AHCS | AHCS | Interface | INT222 | MF Inventory Transactions Load to staging table | Manpreet |  | MF Inventory | Oracle AHCS |  |  |  | Interface - Inbound (Using Middleware) |  | New (1B Assesment) |  | Medium |  |  | Interface - Inbound (Using Middleware) - Medium | Sprint 9 | [10 empty] | Sprint 10 | Sprint 11 | [30 empty] | RTR-AHCS-090 RTR-AHCS-095 RTR-AHCS-097 RTR-AHCS-098 RTR-AHCS-099 RTR-AHCS-100 RTR-AHCS-102 RTR-AHCS-104 RTR-AHCS-105 RTR-AHCS-106 | 0 |  | 0 | FALSE |  |  |  | 0
221 | ABC Corp | 1b New | ERP | RTR-AHCS | AHCS | Interface | INT223 | MF Inventory Transaction AHCS Process | Manpreet |  | MF Inventory | Oracle AHCS |  |  |  | Interface - Inbound (Using Middleware) |  | New (1B Assesment) |  | Very Complex | Very Complex |  | Interface - Inbound (Using Middleware) - Very Complex | Sprint 9 | [10 empty] | Sprint 10 | Sprint 11 | [30 empty] | RTR-AHCS-090 RTR-AHCS-095 RTR-AHCS-097 RTR-AHCS-098 RTR-AHCS-099 RTR-AHCS-100 RTR-AHCS-102 RTR-AHCS-104 RTR-AHCS-105 RTR-AHCS-106 | 0 |  | 0 | FALSE |  |  |  | 0
222 | ABC Corp | 1b New | ERP | RTR-AHCS | AHCS | Extension | EXT118 | MF AR Data Massaging DB Object | Manpreet | [6 empty] | PaaS Extension |  | New (1B Assesment) |  | Very Complex | Very Complex |  | PaaS Extension - Very Complex | Sprint 7 | [10 empty] | Sprint 10 | Sprint 11 | Syed | 2022-01-31 | 2022-03-11 | Lean spec in progress | 2022-01-31 | [25 empty] | RTR-AHCS-088 RTR-AHCS-093 RTR-AHCS-101 RTR-AHCS-094 RTR-AHCS-094 RTR-AHCS-103 RTR-AHCS-123 RTR-AHCS-124 | 0 |  | 0 | FALSE |  |  |  | 0
223 | ABC Corp | 1b New | ERP | RTR-AHCS | AHCS | Extension | EXT119 | MF AP Data Massaging DB Object | Manpreet | [6 empty] | PaaS Extension |  | New (1B Assesment) |  | Very Complex | Very Complex |  | PaaS Extension - Very Complex | Sprint 7 | [10 empty] | Sprint 10 | Sprint 11 | Jigyasa | 2022-01-31 | 2022-03-11 | Lean spec in progress | 2022-01-31 | [25 empty] | RTR-AHCS-089 RTR-AHCS-091 RTR-AHCS-092 RTR-AHCS-093 RTR-AHCS-096 RTR-AHCS-123 RTR-AHCS-124 | 0 |  | 0 | FALSE |  |  |  | 0
225 | ABC Corp | 1b New | ERP | RTR-AHCS | AHCS | Extension | EXT121 | MF INV Data Massaging DB Object | Manpreet | [6 empty] | PaaS Extension |  | New (1B Assesment) |  | Very Complex | Very Complex |  | PaaS Extension - Very Complex | Sprint 9 | [10 empty] | Sprint 10 | Sprint 11 | [30 empty] | RTR-AHCS-090 RTR-AHCS-095 RTR-AHCS-097 RTR-AHCS-100 RTR-AHCS-099 RTR-AHCS-098 RTR-AHCS-099 RTR-AHCS-100 RTR-AHCS-102 RTR-AHCS-104 RTR-AHCS-105 RTR-AHCS-106 | 0 |  | 0 | FALSE |  |  |  | 0
227 | ABC Corp | 1b New | ERP | RTR-AHCS | AHCS | Extension | EXT123 | Apex Page - Enhancement for additional system and file controlling | Manpreet |  |  |  |  | DP : Placeholder for 1B specific changes |  | PaaS Extension |  | New (1B Assesment) |  | Very Complex |  |  | PaaS Extension - Very Complex | Sprint 12 | [10 empty] | Sprint 13 | Sprint 13 | [30 empty] | RTR-AHCS-166,RTR-AHCS-177 | 0 |  | 0 | FALSE |  |  |  | 0
229 | ABC Corp | 1b New | ERP | RTR-AHCS | AHCS | Interface | INT224 | LSI Cross Reference Table (Netting Maintain) | Manpreet |  |  |  |  | As per Neha's confirmation removing |  | Interface - Outbound (Using BI Report) |  | New (1B Assesment) |  | Medium |  |  | Interface - Outbound (Using BI Report) - Medium | [43 empty] | RTR-AHCS-094 | 0 |  | 0 | FALSE | TBD |  |  | 1
232 | ABC Corp | 1b New | ERP | RTR-AHCS | AHCS | Report | RPT006_R | AHCS Error Report (RPT006 Retrofit) | Manpreet | [6 empty] | Report (BI Publisher) |  | New (1B Assesment) |  | Complex |  |  | Report (BI Publisher) - Complex | Sprint 12 | [10 empty] | Sprint 13 | Sprint 13 | [30 empty] | RTR-AHCS-026 | 2 |  | 0 | TRUE |  | P0 | RPT006 | 0
233 | ABC Corp | 1b | ERP | RTR-AHCS | AHCS | Interface | INT043 | AHCS Data to IAP - AHCS Details | Manpreet | Y | Oracle AHCS | IAP | KDD 8 | Updated the complexity to "Complex" from "Medium" because of the information about the ABC Corp Volume is not known currently and it may require a different integration pattern to handle higher volume . Data Model of AHCS is complex. - This Component is part of KDD8 | Yes | Interface - Outbound (Using BI Report) |  | N |  | Complex | Complex |  | Interface - Outbound (Using BI Report) - Complex | Sprint 12 | [7 empty] | Not Started |  |  | Sprint 13 | Sprint 13 |  |  |  | Not Started |  |  | Not Started | [23 empty] | RTR-AHCS-178 | 1 |  |  | TRUE |  |  |  | 0
234 | ABC Corp | 1b | ERP | RTR-AHCS | AHCS | Interface | INT044 | AHCS Data to IAP - AHCS Reconciliation Balances | Manpreet | Y | Oracle AHCS | IAP | KDD 8 | DP/AC : 02/03 : Updated the complexity to "Complex" from "Medium" because of the information about the ABC Corp Volume is not known currently and it may require a different integration pattern to handle higher volume . Data Model of AHCS is complex. - This Component is part of KDD8 This Component is part of KDD8 - Layout for IAP is same as the TeraData & can be re-used | Yes | Interface - Outbound (Using BI Report) |  | N |  | Complex | Complex |  | Interface - Outbound (Using BI Report) - Complex | Sprint 12 | [7 empty] | Not Started |  |  | Sprint 13 | Sprint 13 |  |  |  | Not Started |  |  | Not Started | [23 empty] | RTR-AHCS-179 | 1 |  |  | TRUE |  |  |  | 0
235 | ABC Corp | 1b | ERP | RTR-Intercompany | Intercompany | Interface | INT185 | Intercompany AP Invoice Feed to IAP | David | Y | Oracle ERP Cloud | IAP | Not in KDD but during IC workshops |  |  | Interface - Outbound (Using BI Report) |  | N |  | Complex |  |  | Interface - Outbound (Using BI Report) - Complex | Sprint 10 | [10 empty] | Sprint 11 | Sprint 12 | [30 empty] | DP-RTR-IC-013A DP-RTR-GL-014B DP-RTR-IC-018A DP-RTR-IC-084 | 0 | DP-RTR-IC-013A DP-RTR-GL-014B DP-RTR-IC-018A DP-RTR-IC-084 | 4 | TRUE |  |  |  | 0
236 | ABC Corp | 1b | ERP | RTR-Intercompany | Intercompany | Interface | INT186 | Intercompany AP Invoice Feed to Teradata | David | Y | Oracle ERP Cloud | Teradata | Not in KDD but during IC workshops |  |  | Interface - Outbound (Using BI Report) |  | N |  | Complex |  |  | Interface - Outbound (Using BI Report) - Complex | Sprint 10 | [10 empty] | Sprint 11 | Sprint 12 | [30 empty] | RTR-IC-064 | 1 |  | 0 | TRUE |  |  |  | 0
237 | ABC Corp | 1b | ERP | RTR-Intercompany | Intercompany | Interface | INT187 | Intercompany AP Payment Feed to IAP (Netting, Settlement, LSI) | David | Y | Oracle ERP Cloud | IAP | Not in KDD but during IC workshops | Payment report requires multiple datasets including Payment,Invoice,Supplier,Bank Details etc |  | Interface - Outbound (Using BI Report) |  | N |  | Very Complex |  |  | Interface - Outbound (Using BI Report) - Very Complex | Sprint 10 | [10 empty] | Sprint 11 | Sprint 12 | [30 empty] | DP-RTR-IC-013B DP-RTR-GL-014C DP-RTR-IC-018B DP-RTR-IC-084 | 0 | DP-RTR-IC-013B DP-RTR-GL-014C DP-RTR-IC-018B DP-RTR-IC-084 | 4 | TRUE |  |  |  | 0
238 | ABC Corp | 1b | ERP | RTR-Intercompany | Intercompany | Interface | INT188 | Intercompany AP Payment Feed to Teradata (Netting, Settlement, LSI) | David | Y | Oracle ERP Cloud | Teradata | Not in KDD but during IC workshops |  |  | Interface - Outbound (Using BI Report) |  | N |  | Very Complex |  |  | Interface - Outbound (Using BI Report) - Very Complex | Sprint 10 | [10 empty] | Sprint 11 | Sprint 12 | [30 empty] | RTR-IC-065 | 1 |  | 0 | TRUE |  |  |  | 0
244 | ABC Corp | 1b | ERP | RTR-Intercompany | Intercompany | Interface | INT189 | Intercompany AR invoice feed to IAP | David | Y | Oracle ERP Cloud | IAP | Not in KDD but during IC workshops |  |  | Interface - Outbound (Using BI Report) |  | N |  | Complex |  |  | Interface - Outbound (Using BI Report) - Complex | Sprint 10 | [10 empty] | Sprint 11 | Sprint 12 | [30 empty] | DP-RTR-IC-013C DP-RTR-GL-014D DP-RTR-IC-018C DP-RTR-IC-084 | 0 | DP-RTR-IC-013C DP-RTR-GL-014D DP-RTR-IC-018C DP-RTR-IC-084 | 4 | TRUE |  |  |  | 0
245 | ABC Corp | 1b | ERP | RTR-Intercompany | Intercompany | Interface | INT190 | Intercompany AR invoice feed to Teradata | David | Y | Oracle ERP Cloud | Teradata | Not in KDD but during IC workshops |  |  | Interface - Outbound (Using BI Report) |  | N |  | Complex |  |  | Interface - Outbound (Using BI Report) - Complex | Sprint 10 | [10 empty] | Sprint 11 | Sprint 12 | [30 empty] | RTR-IC-066 | 1 |  | 0 | TRUE |  |  |  | 0
246 | ABC Corp | 1b | ERP | RTR-Intercompany | Intercompany | Interface | INT191 | Intercompany AR Receipt Feed to IAP (Netting, Settlement, LSI) | David | Y | Oracle ERP Cloud | IAP | Not in KDD but during IC workshops |  |  | Interface - Outbound (Using BI Report) |  | N |  | Complex |  |  | Interface - Outbound (Using BI Report) - Complex | Sprint 10 | [10 empty] | Sprint 11 | Sprint 12 | [30 empty] | DP-RTR-IC-013D DP-RTR-GL-014E DP-RTR-IC-018D DP-RTR-IC-084 | 0 | DP-RTR-IC-013D DP-RTR-GL-014E DP-RTR-IC-018D DP-RTR-IC-084 | 4 | TRUE |  |  |  | 0
247 | ABC Corp | 1b | ERP | RTR-Intercompany | Intercompany | Interface | INT192 | Intercompany AR Receipt Feed to Teradata (Netting, Settlement, LSI) | David | Y | Oracle ERP Cloud | Teradata | Not in KDD but during IC workshops |  |  | Interface - Outbound (Using BI Report) |  | N |  | Complex |  |  | Interface - Outbound (Using BI Report) - Complex | Sprint 10 | [10 empty] | Sprint 11 | Sprint 12 | [30 empty] | RTR-IC-067 | 1 |  | 0 | TRUE |  |  |  | 0
248 | ABC Corp | 1b | ERP | RTR-Intercompany | Intercompany | Extension | EXT036 | Inter/ Intra company custom data loader - Upload data file [UI] | David | Y |  |  | Not in KDD but during User Story Conversion | Apex UI to upload csv data file comprising GL journals & intercompany transactions into staging database. Legacy build might be required, if the file is generated through some automation. |  | PaaS Extension |  | N |  | Complex |  |  | PaaS Extension - Complex | Sprint 9 | [10 empty] | Sprint 11 | Sprint 12 |  | 2021-02-21 | 2021-03-04 |  | 2021-03-07 | 2021-03-25 | [24 empty] | RTR-IC-034A | 1 |  | 0 | TRUE |  |  |  | 0
249 | ABC Corp | 1b | ERP | RTR-Intercompany | Intercompany | Extension | EXT037 | Inter/ Intra company custom data loader - Pre-processor: Split file into journals & intercompany transactions, assign unique ID | David |  |  |  | Not in KDD but during User Story Conversion | Pre-processor program that would validate the batch that will be imported, split the file into intercompany & intracompany batches and assign unique ID. If file size is huge, will split it into smaller batches with optimal import batch size. Might involve legacy to Oracle Code combination translation. |  | PaaS Extension |  | N |  | Very Complex |  |  | PaaS Extension - Very Complex | Sprint 9 | [10 empty] | Sprint 11 | Sprint 12 |  | 2021-02-21 | 2021-03-04 |  | 2021-03-07 | 2021-03-25 | [24 empty] | RTR-IC-034B | 1 |  | 0 | TRUE |  |  |  | 0
250 | ABC Corp | 1b | ERP | RTR-Intercompany | Intercompany | Interface | INT193 | Inter/ Intra company custom data loader custom data loader - Import Journals | David |  |  | Oracle AHCS | Not in KDD but during User Story Conversion | Invoke FBDI to import journals for intra-company transactions. (OIC integration) |  | Interface - Inbound (Using Middleware) |  | N |  | Complex |  |  | Interface - Inbound (Using Middleware) - Complex | Sprint 9 | [10 empty] | Sprint 11 | Sprint 12 |  | 2021-03-07 | 2021-03-18 |  | 2021-03-21 | 2021-04-15 | [24 empty] | RTR-IC-034C | 1 |  | 0 | TRUE |  |  |  | 0
251 | ABC Corp | 1b | ERP | RTR-Intercompany | Intercompany | Interface | INT194 | Inter/ Intra company custom data loader custom data loader - Import Intercompany Transactions | David |  |  | Oracle AHCS | Not in KDD but during User Story Conversion | Import FBDI to import intercompany transactions. (OIC integration) |  | Interface - Inbound (Using Middleware) |  | N |  | Very Complex |  |  | Interface - Inbound (Using Middleware) - Very Complex | Sprint 9 | [10 empty] | Sprint 11 | Sprint 12 |  | 2021-03-07 | 2021-03-18 |  | 2021-03-21 | 2021-04-15 | [24 empty] | RTR-IC-034D | 1 |  | 0 | TRUE |  |  |  | 0
252 | ABC Corp | 1b | ERP | RTR-Intercompany | Intercompany | Extension | EXT038 | Inter/ Intra company custom data loader custom data loader - Loaded batch inquiry [UI] | David |  |  |  | Not in KDD but during User Story Conversion | Inquiry screen to query the status of the uploaded file. |  | PaaS Extension |  | N |  | Medium |  |  | PaaS Extension - Medium | Sprint 9 | [10 empty] | Sprint 11 | Sprint 12 |  | 2021-03-21 | 2021-04-01 |  | 2021-04-04 | 2021-04-28 | [24 empty] | RTR-IC-034E | 1 |  | 0 | TRUE |  |  |  | 0
253 | ABC Corp | 1b | ERP | RTR-Intercompany | Intercompany | Extension | EXT039 | Inter/Intra company - Sync SaaS master data with PaaS for Validations Inter/ Intra company custom data loader custom data loader - Tie back data load status into staging tables for reporting. | David |  | PaaS DB | Oracle ERP Cloud | Not in KDD but during User Story Conversion | Syncing master data from SaaS to PaaS for validation purpose |  | PaaS Extension |  | N |  | Complex |  |  | PaaS Extension - Complex | Sprint 9 | [10 empty] | Sprint 11 | Sprint 12 |  | 2021-03-21 | 2021-04-01 |  | 2021-04-04 | 2021-04-15 | [24 empty] | RTR-IC-034F | 1 |  | 0 | TRUE |  |  |  | 0
255 | ABC Corp | 1b | ERP | RTR-Intercompany | Intercompany | Report | RPT099 | Inter/ Intra company custom data loader custom data loader - Transaction import Error Report | David |  |  |  | Not in KDD but during User Story Conversion | Custom BI report to extract data that has failed import due to intercompany or GL journal transaction import failure. Reporting ability based on file name or batch ID. |  | Report (BI Publisher) |  | N |  | Complex |  |  | Report (BI Publisher) - Complex | Sprint 9 | [10 empty] | Sprint 11 | Sprint 11 |  | 2021-03-21 | 2021-04-01 |  | 2021-04-04 | 2021-04-28 | [24 empty] | RTR-IC-034H | 1 |  | 0 | TRUE |  | P0 |  | 0
256 | ABC Corp | 1b | ERP | RTR-Intercompany | Intercompany | Interface | INT195 | Intercompany Netting / LSI Processor - Extract dependent intercompany transactions (AP/AR) data from ERP Cloud | David |  | ERP Cloud | PaaS DB | KDD22 | Schedule extract program. Data under consideration - Open intercompany AP/ AR invoices between entities eligible for LSI. |  | Interface - Outbound (Using BI Report) |  | N |  | Very Complex |  |  | Interface - Outbound (Using BI Report) - Very Complex | Sprint 9 | [10 empty] | Sprint 11 | Sprint 12 |  | 2021-02-21 | 2021-03-04 |  | 2021-03-07 | 2021-03-18 | [12 empty] | Part of the extract program to extract all the intercompany transactions between applicable intercompany organizations within the enterprise. | [11 empty] | RTR-IC-033A | 1 |  | 0 | TRUE |  |  |  | 0
257 | ABC Corp | 1b | ERP | RTR-Intercompany | Intercompany | Interface | INT196 | Intercompany Netting / LSI Processor - Extract dependent master data from ERP Cloud | David |  | ERP Cloud | PaaS DB | KDD22 | Schedule extract program. Data under consideration - intercompany organizations, supplier, customer, COA values, entity to treasury org mapping. |  | Interface - Outbound (Using BI Report) |  | N |  | Complex |  |  | Interface - Outbound (Using BI Report) - Complex | Sprint 9 | [10 empty] | Sprint 11 | Sprint 12 |  | 2021-02-21 | 2021-02-25 |  | 2021-02-28 | 2021-03-18 | [12 empty] | Identify and extract dependent master data required for Oracle processing of LSI data. Examples - exchange rates, COA values to generate reversal entries, mapping relationship between enterprise orgs and LSI entities.. | [11 empty] | RTR-IC-033B | 1 |  | 0 | TRUE |  |  |  | 0
258 | ABC Corp | 1b | ERP | RTR-Intercompany | Intercompany | Interface | INT197 | Intercompany Netting / LSI Processor - Extract intercompany journals from ERP Cloud | David |  | ERP Cloud | PaaS DB | KDD22 | Schedule extract program. Data under consideration - Intercompany journals eligible for LSI |  | Interface - Outbound (Using BI Report) |  | N |  | Medium |  |  | Interface - Outbound (Using BI Report) - Medium | Sprint 9 | [10 empty] | Sprint 11 | Sprint 12 |  | 2021-02-21 | 2021-03-04 |  | 2021-03-07 | 2021-03-18 | [12 empty] | Extract program to identify and extract intercompany journals between intercompany orgs within the enterprise. | [11 empty] | RTR-IC-033C | 1 |  | 0 | TRUE |  |  |  | 0
259 | ABC Corp | 1b | ERP | RTR-Intercompany | Intercompany | Interface | INT198 | Intercompany Netting / LSI Processor - Generate Dummy receipts & Payments | David |  | PaaS DB | ERP Cloud | KDD22 | Web services for payments & AR receipts. Need to be fine tuned for performance given higher volumes. |  | Interface - Inbound (Using Middleware) |  | N |  | Very Complex |  |  | Interface - Inbound (Using Middleware) - Very Complex | Sprint 9 | [10 empty] | Sprint 11 | Sprint 12 |  | 2021-02-28 | 2021-03-11 |  | 2021-03-14 | 2021-04-01 | [12 empty] | Generate dummy receipts and payments to knock off existing intercompany trading transactions (non-material) between intercompany orgs within the enterprise. | [11 empty] | RTR-IC-033D | 1 |  | 0 | TRUE |  |  |  | 0
260 | ABC Corp | 1b | ERP | RTR-Intercompany | Intercompany | Interface | INT199 | Intercompany Netting / LSI Processor - Create reversal journal entries to knock-off intercompany journals between entities | David |  | PaaS DB | ERP Cloud | KDD22 | Applicable if the intercompany journals are created instead of AP/AR. |  | Interface - Inbound (Using Middleware) |  | N |  | Complex |  |  | Interface - Inbound (Using Middleware) - Complex | Sprint 9 | [10 empty] | Sprint 11 | Sprint 12 |  | 2021-02-28 | 2021-03-11 |  | 2021-03-14 | 2021-04-01 | [12 empty] | For applicable organization entities that do not have AP-AR relationship but instead have I/C journals, create reversal journals to knock off direct I/C trading between these entities. | [11 empty] | RTR-IC-033E | 1 |  | 0 | TRUE |  |  |  | 0
261 | ABC Corp | 1b | ERP | RTR-Intercompany | Intercompany | Extension | EXT041 | Intercompany Netting / LSI Processor - Generate Accounting entries between legal entities & treasury orgs. | David |  |  |  | KDD22 | Generate accounting entries for the different LSI entities. Compute FX gain/losses and books them to respective treasury org. |  | PaaS Extension |  | N |  | Very Complex |  |  | PaaS Extension - Very Complex | Sprint 9 | [10 empty] | Sprint 11 | Sprint 12 |  | 2021-02-28 | 2021-03-11 |  | 2021-03-14 | 2021-04-01 | [12 empty] | Generate accounting entries between legal entities and treasury (LSI) orgs based on LSI rules. | [11 empty] | DP-RTR-IC-003 RTR-IC-010 | 0 | DP-RTR-IC-003 | 1 | TRUE |  |  |  | 0
262 | ABC Corp | 1b | ERP | RTR-Intercompany | Intercompany | Interface | INT200 | Intercompany Netting / LSI Processor - Import LSI accounting transactions to AHCS | David |  | PaaS DB | AHCS | KDD22 | Create GL journals in Oracle ERP Cloud |  | Interface - Inbound (Using Middleware) |  | N |  | Complex |  |  | Interface - Inbound (Using Middleware) - Complex | Sprint 9 | [10 empty] | Sprint 11 | Sprint 12 |  | 2021-03-14 | 2021-03-25 |  | 2021-03-28 | 2021-04-15 | [12 empty] | Import integration push AHCS file from UCM and trigger import accounting. | [11 empty] | RTR-IC-033F | 1 |  | 0 | TRUE |  |  |  | 0
263 | ABC Corp | 1b | ERP | RTR-Intercompany | Intercompany | Report | RPT100 | Intercompany Netting / LSI Processor - LSI Reconciliation/ Error report | David |  |  |  | KDD22 | Reconciliation report show reconciliation - Eligible intercompany invoices/ journals, Knocked of payments/ receipts & journals representing LSI switch between legal entities & treasury operations. |  | Report (BI Publisher) |  | N |  | Very Complex |  |  | Report (BI Publisher) - Very Complex | Sprint 9 | [10 empty] | Sprint 11 | Sprint 11 |  | 2021-03-14 | 2021-03-25 |  | 2021-04-04 | 2021-04-15 | [24 empty] | RTR-IC-033G DP-RTR-IC-079 | 1 | DP-RTR-IC-079 | 0 | TRUE |  | P0 |  | 0
264 | ABC Corp | 1b | ERP | RTR-Intercompany | Intercompany | Extension | EXT042 | Intercompany Netting / LSI Processor - Kick off LSI processor | David |  |  |  | KDD22 | Wrapper interface (scheduled) / UI to kick-off LSI processor. Schedule wrapper OIC program |  | PaaS Extension |  | N |  | Medium |  |  | PaaS Extension - Medium | Sprint 9 | [10 empty] | Sprint 11 | Sprint 12 |  | 2021-03-21 | 2021-04-01 |  | 2021-04-04 | 2021-04-29 | [12 empty] | Generate FBDI file to import LSI transactions into AHCS. | [11 empty] | RTR-IC-033H RTR-IC-010 | 1 |  | 0 | TRUE |  |  |  | 0
265 | ABC Corp | 1b | ERP | RTR-Intercompany | Intercompany | Report | RPT102 | AR Invoice Print | David | [6 empty] | Report (BI Publisher) |  |  |  | Very Complex |  |  | Report (BI Publisher) - Very Complex | Sprint 11 | [10 empty] | Sprint 12 | Sprint 13 | [30 empty] | RTR-IC-008A RTR-IC-015A DP-RTR-IC-001A DP-RTR-IC-002A DP-RTR-IC-088 | 2 | DP-RTR-IC-001A DP-RTR-IC-002A | 2 | TRUE |  | P0 |  | 0
266 | ABC Corp | 1b | ERP | RTR-Intercompany | Intercompany | Report | RPT103 | AR Credit Memo Print | David | [6 empty] | Report (BI Publisher) |  |  |  | Very Complex |  |  | Report (BI Publisher) - Very Complex | Sprint 11 | [10 empty] | Sprint 12 | Sprint 13 | [30 empty] | RTR-IC-008B RTR-IC-015B DP-RTR-IC-001B DP-RTR-IC-002B DP-RTR-IC-089 | 2 | DP-RTR-IC-001B DP-RTR-IC-002B | 2 | TRUE |  | P0 |  | 0
267 | ABC Corp | 1b | ERP | RTR-GL | GL | Report | RPT104 | TB report for MDR entities based on reporting ledger | David | [6 empty] | Report (BI Publisher) |  |  |  | Complex |  |  | Report (BI Publisher) - Complex | Sprint 12 | [10 empty] | Sprint 13 | Sprint 13 | [30 empty] | DP-RTR-GL-004 | 0 | DP-RTR-GL-004 | 1 | TRUE |  | P1 |  | 0
368 | ABC Corp | 1b New Addition | ERP | RTR-AHCS | AHCS | Report | RPT129 | AHCS Subledger Transaction report by Receipt / PO / Vendor / Customer Invoices-Close out report | [7 empty] | Report (BI Publisher) |  |  |  | Complex |  |  | Report (BI Publisher) - Complex | Sprint 12 | [10 empty] | Sprint 13 | Sprint 13 | [30 empty] | RTR-AHCS-197,RTR-AHCS-117,RTR-AHCS-169,RTR-AHCS-171 |  |  |  |  | TBD | P0 |  | 0
369 | ABC Corp | 1b New Addition | ERP | RTR-AHCS | AHCS | Report | RPT131 | Open AP Transaction details Aging report | [7 empty] | Report (BI Publisher) |  |  |  | Very Complex |  |  | Report (BI Publisher) - Very Complex | Sprint 13 | [10 empty] | Sprint 14 | Sprint 14 | [30 empty] | RTR-AHCS-199 | [5 empty] | P1 |  | 0
370 | ABC Corp | 1b New Addition | ERP | RTR-AHCS | AHCS | Report | RPT132 | Detail report breakdown for AP Cash Clearing Aging Details | [7 empty] | Report (BI Publisher) |  |  |  | Very Complex |  |  | Report (BI Publisher) - Very Complex | Sprint 13 | [10 empty] | Sprint 14 | Sprint 14 | [30 empty] | RTR-AHCS-200 | [5 empty] | P0 |  | 0
371 | ABC Corp | 1b New Addition | ERP | RTR-AHCS | AHCS | Report | RPT133 | Movement by AP Intercompany invoices details month wise report - (AHCS Data Only) | [7 empty] | Report (BI Publisher) |  |  |  | Complex |  |  | Report (BI Publisher) - Complex | Sprint 13 | [10 empty] | Sprint 14 | Sprint 14 | [30 empty] | RTR-AHCS-201 | [5 empty] | P1 |  | 0
372 | ABC Corp | 1b New Addition | ERP | RTR-AHCS | AHCS | Report | RPT134 | Movement by AP invoices details month wise report | [7 empty] | Report (BI Publisher) |  |  |  | Complex |  |  | Report (BI Publisher) - Complex | Sprint 13 | [10 empty] | Sprint 14 | Sprint 14 | [30 empty] | RTR-AHCS-202 | [5 empty] | P1 |  | 0
373 | ABC Corp | 1b New Addition | ERP | RTR-AHCS | AHCS | Report | RPT135 | Open AR Transaction details Aging report | [7 empty] | Report (BI Publisher) |  |  |  | Very Complex |  |  | Report (BI Publisher) - Very Complex | Sprint 13 | [10 empty] | Sprint 14 | Sprint 14 | [30 empty] | RTR-AHCS-203 | [5 empty] | P1 |  | 0
374 | ABC Corp | 1b New Addition | ERP | RTR-AHCS | AHCS | Report | RPT136 | Detail report breakdown for AR Cash Clearing Aging Details | [7 empty] | Report (BI Publisher) |  |  |  | Very Complex |  |  | Report (BI Publisher) - Very Complex | Sprint 13 | [10 empty] | Sprint 14 | Sprint 14 | [30 empty] | RTR-AHCS-204 | [5 empty] | P0 |  | 0
375 | ABC Corp | 1b New Addition | ERP | RTR-AHCS | AHCS | Report | RPT137 | Movement by AR Intercompany invoices details month wise report - (AHCS Data Only) | [7 empty] | Report (BI Publisher) |  |  |  | Complex |  |  | Report (BI Publisher) - Complex | Sprint 13 | [10 empty] | Sprint 14 | Sprint 14 | [30 empty] | RTR-AHCS-205 | [5 empty] | P1 |  | 0
376 | ABC Corp | 1b New Addition | ERP | RTR-AHCS | AHCS | Report | RPT138 | Open transactions for different Cash Clearing Accounts Report | [7 empty] | Report (BI Publisher) |  |  |  | Medium |  |  | Report (BI Publisher) - Medium | Sprint 12 | [10 empty] | Sprint 13 | Sprint 13 | [30 empty] | RTR-AHCS-206 | [5 empty] | P0 |  | 0
377 | ABC Corp | 1b New Addition | ERP | RTR-AHCS | AHCS | Report | RPT139 | Movement by AR invoices details month wise report | [7 empty] | Report (BI Publisher) |  |  |  | Complex |  |  | Report (BI Publisher) - Complex | Sprint 13 | [10 empty] | Sprint 14 | Sprint 14 | [30 empty] | RTR-AHCS-207 | [5 empty] | P1 |  | 0
378 | ABC Corp | 1b New Addition | ERP | RTR-AHCS | AHCS | Report | RPT140 | Bank Roll Forward detail - Bank Account Transaction movement report by legal entity | [7 empty] | Report (BI Publisher) |  |  |  | Medium |  |  | Report (BI Publisher) - Medium | Sprint 14 | [10 empty] | Sprint 15 | Sprint 15 | [30 empty] | RTR-AHCS-208 | [5 empty] | P2 |  | 0
379 | ABC Corp | 1b New Addition | ERP | RTR-AHCS | AHCS | Report | RPT141 | Special Sales aging Report by customer/invoice number/date | [7 empty] | Report (BI Publisher) |  |  |  | Very Complex |  |  | Report (BI Publisher) - Very Complex | Sprint 13 | [10 empty] | Sprint 14 | Sprint 14 | [30 empty] | RTR-AHCS-209 | [5 empty] | P1 |  | 0
380 | ABC Corp | 1b New Addition | ERP | RTR-AHCS | AHCS | Report | RPT142 | Intercompany AP Aging (material & non material) process - (AHCS Data Only) | [7 empty] | Report (BI Publisher) |  |  |  | Very Complex |  |  | Report (BI Publisher) - Very Complex | Sprint 13 | [10 empty] | Sprint 14 | Sprint 14 | [30 empty] | RTR-AHCS-210 | [5 empty] | P1 |  | 0
381 | ABC Corp | 1b New Addition | ERP | RTR-AHCS | AHCS | Report | RPT143 | Intercompany AP Trail balance (material & no material) details - (AHCS Data Only) | [7 empty] | Report (BI Publisher) |  |  |  | Complex |  |  | Report (BI Publisher) - Complex | Sprint 13 | [10 empty] | Sprint 14 | Sprint 14 | [30 empty] | RTR-AHCS-211 | [5 empty] | P1 |  | 0
382 | ABC Corp | 1b New Addition | ERP | RTR-AHCS | AHCS | Report | RPT144 | AP Aging Without Invoices Report hitting Trade Payables and Intercompany Payables - (AHCS Data Only) | [7 empty] | Report (BI Publisher) |  |  |  | Very Complex |  |  | Report (BI Publisher) - Very Complex | Sprint 12 | [10 empty] | Sprint 13 | Sprint 13 | [30 empty] | RTR-AHCS-212 | [5 empty] | P0 |  | 0
383 | ABC Corp | 1b New Addition | ERP | RTR-AHCS | AHCS | Report | RPT146 | Inventory in transit by location and invoices | [7 empty] | Report (BI Publisher) |  |  |  | Medium |  |  | Report (BI Publisher) - Medium | Sprint 12 | [10 empty] | Sprint 13 | Sprint 13 | [30 empty] | RTR-AHCS-214 | [5 empty] | P0 |  | 0
384 | ABC Corp | 1b New Addition | ERP | RTR-AHCS | AHCS | Report | RPT147 | Inventory Detailed Trial Balance by BU , Loc ,Item# | [7 empty] | Report (BI Publisher) |  |  |  | Medium |  |  | Report (BI Publisher) - Medium | Sprint 13 | [10 empty] | Sprint 14 | Sprint 14 | [30 empty] | RTR-AHCS-215 | [5 empty] | P1 |  | 0
385 | ABC Corp | 1b New Addition | ERP | RTR-AHCS | AHCS | Report | RPT149 | PTD and YTD sales, payments, and adj for MF AR transactions | [7 empty] | Report (BI Publisher) |  |  |  | Complex |  |  | Report (BI Publisher) - Complex | Sprint 14 | [10 empty] | Sprint 15 | Sprint 15 | [30 empty] | RTR-AHCS-218 | [5 empty] | P2 |  | 0
386 | ABC Corp | 1b New Addition | ERP | RTR-AHCS | AHCS | Report | RPT150 | PTD and YTD invoices, payments, and adj for MF AP transactions | [7 empty] | Report (BI Publisher) |  |  |  | Complex |  |  | Report (BI Publisher) - Complex | Sprint 14 | [10 empty] | Sprint 15 | Sprint 15 | [30 empty] | RTR-AHCS-219 | [5 empty] | P2 |  | 0
387 | ABC Corp | 1b New Addition | ERP | RTR-AHCS | AHCS | Report | RPT151 | PTD and YTD receipts, shipments, adj, and returns split between trade and I/C for MF INV transactions | [7 empty] | Report (BI Publisher) |  |  |  | Complex |  |  | Report (BI Publisher) - Complex | Sprint 14 | [10 empty] | Sprint 15 | Sprint 15 | [30 empty] | RTR-AHCS-220 | [5 empty] | P2 |  | 0
388 | ABC Corp | 1b New Addition | ERP | RTR-AHCS | AHCS | Report | RPT154 | GL Account balance Report by Location or Range of Location for date range or given period | [7 empty] | Report (BI Publisher) |  |  |  | Medium |  |  | Report (BI Publisher) - Medium | Sprint 12 | [10 empty] | Sprint 13 | Sprint 13 | [30 empty] | RTR-AHCS-223 | [5 empty] | P0 |  | 0
407 | ABC Corp | 1b New Addition | ERP | RTR-Intercompany | Intercompany | Interface | INT232 | Open AP Invoice Balance to IAP |  |  | Oracle GL | IAP |  |  |  | Interface - Outbound (Using BI Report) |  |  |  | Complex |  |  | Interface - Outbound (Using BI Report) - Complex | Sprint 12 | [10 empty] | Sprint 13 | Sprint 13 | [30 empty] | DP-RTR-IC-080 |  | DP-RTR-IC-080 | 1 | TRUE |  |  |  | 0
408 | ABC Corp | 1b New Addition | ERP | RTR-Intercompany | Intercompany | Interface | INT233 | Open AP Invoice Balance to TeraData |  |  | Oracle GL | TeraData |  |  |  | Interface - Outbound (Using BI Report) |  |  |  | Complex |  |  | Interface - Outbound (Using BI Report) - Complex | Sprint 12 | [10 empty] | Sprint 13 | Sprint 13 | [30 empty] | DP-RTR-IC-081 |  | DP-RTR-IC-081 | 1 | TRUE |  |  |  | 0
409 | ABC Corp | 1b New Addition | ERP | RTR-Intercompany | Intercompany | Interface | INT234 | Open AR Invoice Balance to IAP |  |  | Oracle GL | IAP |  |  |  | Interface - Outbound (Using BI Report) |  |  |  | Complex |  |  | Interface - Outbound (Using BI Report) - Complex | Sprint 12 | [10 empty] | Sprint 13 | Sprint 13 | [30 empty] | DP-RTR-IC-082 |  | DP-RTR-IC-082 | 1 | TRUE |  |  |  | 0
410 | ABC Corp | 1b New Addition | ERP | RTR-Intercompany | Intercompany | Interface | INT235 | Open AR Invoice Balance to TeraData |  |  | Oracle GL | TeraData |  |  |  | Interface - Outbound (Using BI Report) |  |  |  | Complex |  |  | Interface - Outbound (Using BI Report) - Complex | Sprint 12 | [10 empty] | Sprint 13 | Sprint 13 | [30 empty] | DP-RTR-IC-083 |  | DP-RTR-IC-083 | 1 | TRUE |  |  |  | 0
411 | ABC Corp | 1b New Addition | ERP | RTR-AHCS | AHCS | Language Translation | RPT159 | Inventory Detailed Trial Balance by BU , Loc ,Item# - 5 Language Translation | [7 empty] | Report (BI Publisher) |  |  |  | Simple |  |  | Report (BI Publisher) - Simple | Sprint 13 | [10 empty] | Sprint 14 | Sprint 14 | [30 empty] | RTR-AHCS-259 RTR-AHCS-260 RTR-AHCS-261 RTR-AHCS-262 RTR-AHCS-263 | [5 empty] | P4 | RPT147 | 0
412 | ABC Corp | 1b New Addition | ERP | RTR-AHCS | AHCS | Language Translation | RPT164 | Open AP Transaction details Aging report - 5 Language Translation | [7 empty] | Report (BI Publisher) |  |  |  | Simple |  |  | Report (BI Publisher) - Simple | Sprint 13 | [10 empty] | Sprint 14 | Sprint 14 | [30 empty] | RTR-AHCS-264 RTR-AHCS-265 RTR-AHCS-266 RTR-AHCS-267 RTR-AHCS-268 | [5 empty] | P4 | RPT131 | 0
413 | ABC Corp | 1b New Addition | ERP | RTR-AHCS | AHCS | Language Translation | RPT165 | Detail report breakdown for AP Cash Clearing Aging Details - 5 Language Translation | [7 empty] | Report (BI Publisher) |  |  |  | Simple |  |  | Report (BI Publisher) - Simple | Sprint 13 | [10 empty] | Sprint 14 | Sprint 14 | [30 empty] | RTR-AHCS-269 RTR-AHCS-270 RTR-AHCS-271 RTR-AHCS-272 RTR-AHCS-273 | [5 empty] | P4 | RPT132 | 0
414 | ABC Corp | 1b New Addition | ERP | RTR-AHCS | AHCS | Language Translation | RPT166 | Movement by AP Intercompany invoices details month wise report - (AHCS Data Only) - 5 Language Translation | [7 empty] | Report (BI Publisher) |  |  |  | Simple |  |  | Report (BI Publisher) - Simple | Sprint 13 | [10 empty] | Sprint 14 | Sprint 14 | [30 empty] | RTR-AHCS-274 RTR-AHCS-275 RTR-AHCS-276 RTR-AHCS-277 RTR-AHCS-278 | [5 empty] | P4 | RPT133 | 0
415 | ABC Corp | 1b New Addition | ERP | RTR-AHCS | AHCS | Language Translation | RPT167 | Movement by AP invoices details month wise report- 5 Language Translation | [7 empty] | Report (BI Publisher) |  |  |  | Simple |  |  | Report (BI Publisher) - Simple | Sprint 13 | [10 empty] | Sprint 14 | Sprint 14 | [30 empty] | RTR-AHCS-279 RTR-AHCS-280 RTR-AHCS-281 RTR-AHCS-282 RTR-AHCS-283 | [5 empty] | P4 | RPT134 | 0
416 | ABC Corp | 1b New Addition | ERP | RTR-AHCS | AHCS | Language Translation | RPT168 | Open AR Transaction details Aging report- 5 Language Translation | [7 empty] | Report (BI Publisher) |  |  |  | Simple |  |  | Report (BI Publisher) - Simple | Sprint 13 | [10 empty] | Sprint 14 | Sprint 14 | [30 empty] | RTR-AHCS-284 RTR-AHCS-285 RTR-AHCS-286 RTR-AHCS-287 RTR-AHCS-288 | [5 empty] | P4 | RPT135 | 0
417 | ABC Corp | 1b New Addition | ERP | RTR-AHCS | AHCS | Language Translation | RPT169 | Detail report breakdown for AR Cash Clearing Aging Details- 5 Language Translation | [7 empty] | Report (BI Publisher) |  |  |  | Simple |  |  | Report (BI Publisher) - Simple | Sprint 13 | [10 empty] | Sprint 14 | Sprint 14 | [30 empty] | RTR-AHCS-289 RTR-AHCS-290 RTR-AHCS-291 RTR-AHCS-292 RTR-AHCS-293 | [5 empty] | P4 | RPT136 | 0
418 | ABC Corp | 1b New Addition | ERP | RTR-AHCS | AHCS | Language Translation | RPT170 | Movement by AR Intercompany invoices details month wise report - (AHCS Data Only) - 5 Language Translation | [7 empty] | Report (BI Publisher) |  |  |  | Simple |  |  | Report (BI Publisher) - Simple | Sprint 13 | [10 empty] | Sprint 14 | Sprint 14 | [30 empty] | RTR-AHCS-294 RTR-AHCS-295 RTR-AHCS-296 RTR-AHCS-297 RTR-AHCS-298 | [5 empty] | P4 | RPT137 | 0
419 | ABC Corp | 1b New Addition | ERP | RTR-AHCS | AHCS | Language Translation | RPT171 | Movement by AR invoices details month wise report - 5 Language Translation | [7 empty] | Report (BI Publisher) |  |  |  | Simple |  |  | Report (BI Publisher) - Simple | Sprint 13 | [10 empty] | Sprint 14 | Sprint 14 | [30 empty] | RTR-AHCS-299 RTR-AHCS-300 RTR-AHCS-301 RTR-AHCS-302 RTR-AHCS-303 | [5 empty] | P4 | RPT139 | 0
420 | ABC Corp | 1b New Addition | ERP | RTR-AHCS | AHCS | Language Translation | RPT172 | Open transactions for different Cash Clearing Accounts Report - 5 Language Translation | [7 empty] | Report (BI Publisher) |  |  |  | Simple |  |  | Report (BI Publisher) - Simple | Sprint 12 | [10 empty] | Sprint 13 | Sprint 13 | [30 empty] | RTR-AHCS-304 RTR-AHCS-305 RTR-AHCS-306 RTR-AHCS-307 RTR-AHCS-308 | [5 empty] | P4 | RPT138 | 0
421 | ABC Corp | 1b New Addition | ERP | RTR-AHCS | AHCS | Language Translation | RPT173 | Bank Roll Forward detail - Bank Account Transaction movement report by legal entity - 5 Language Translation | [7 empty] | Report (BI Publisher) |  |  |  | Simple |  |  | Report (BI Publisher) - Simple | Sprint 14 | [10 empty] | Sprint 15 | Sprint 15 | [30 empty] | RTR-AHCS-309 RTR-AHCS-310 RTR-AHCS-311 RTR-AHCS-312 RTR-AHCS-313 | [5 empty] | P4 | RPT140 | 0
422 | ABC Corp | 1b New Addition | ERP | RTR-AHCS | AHCS | Language Translation | RPT175 | Special Sales aging Report by customer/invoice number/date - 5 Language Translation | [7 empty] | Report (BI Publisher) |  |  |  | Simple |  |  | Report (BI Publisher) - Simple | Sprint 13 | [10 empty] | Sprint 14 | Sprint 14 | [30 empty] | RTR-AHCS-314 RTR-AHCS-315 RTR-AHCS-316 RTR-AHCS-317 RTR-AHCS-318 | [5 empty] | P4 | RPT141 | 0
423 | ABC Corp | 1b New Addition | ERP | RTR-AHCS | AHCS | Language Translation | RPT176 | Intercompany AP Aging (material & non material) process - (AHCS Data Only) - 5 Language Translation | [7 empty] | Report (BI Publisher) |  |  |  | Simple |  |  | Report (BI Publisher) - Simple | Sprint 13 | [10 empty] | Sprint 14 | Sprint 14 | [30 empty] | RTR-AHCS-319 RTR-AHCS-320 RTR-AHCS-321 RTR-AHCS-322 RTR-AHCS-323 | [5 empty] | P4 | RPT142 | 0
424 | ABC Corp | 1b New Addition | ERP | RTR-AHCS | AHCS | Language Translation | RPT177 | Intercompany AP Trail balance (material & no material) details - (AHCS Data Only) - 5 Language Translation | [7 empty] | Report (BI Publisher) |  |  |  | Simple |  |  | Report (BI Publisher) - Simple | Sprint 13 | [10 empty] | Sprint 14 | Sprint 14 | [30 empty] | RTR-AHCS-324 RTR-AHCS-325 RTR-AHCS-326 RTR-AHCS-327 RTR-AHCS-328 | [5 empty] | P4 | RPT143 | 0
425 | ABC Corp | 1b New Addition | ERP | RTR-AHCS | AHCS | Language Translation | RPT183 | Intercompany AR Aging (material & non material) process - (AHCS Data Only) - 5 Language Translation | [7 empty] | Report (BI Publisher) |  |  |  | Simple |  |  | Report (BI Publisher) - Simple | Sprint 13 | [10 empty] | Sprint 14 | Sprint 14 | [30 empty] | RTR-AHCS-337 RTR-AHCS-338 RTR-AHCS-339 RTR-AHCS-340 RTR-AHCS-342 | [5 empty] | P4 | RPT179 | 0
426 | ABC Corp | 1b New Addition | ERP | RTR-AHCS | AHCS | Language Translation | RPT184 | Intercompany AR Trail balance (material & no material) details - (AHCS Data Only) - 5 Language Translation | [7 empty] | Report (BI Publisher) |  |  |  | Simple |  |  | Report (BI Publisher) - Simple | Sprint 13 | [10 empty] | Sprint 14 | Sprint 14 | [30 empty] | RTR-AHCS-330 RTR-AHCS-331 RTR-AHCS-332 RTR-AHCS-333 RTR-AHCS-334 RTR-AHCS-335 | [5 empty] | P4 | RPT180 | 0
428 | ABC Corp | 1b New Addition | ERP | RTR-AHCS | AHCS | Report | RPT179 | Intercompany AR Aging (material & non material) - (AHCS Data Only) | [7 empty] | Report (BI Publisher) |  |  |  | Very Complex |  |  | Report (BI Publisher) - Very Complex | Sprint 13 | [10 empty] | Sprint 14 | Sprint 14 | [30 empty] | RTR-AHCS-210 | [5 empty] | P1 |  | 0
429 | ABC Corp | 1b New Addition | ERP | RTR-AHCS | AHCS | Report | RPT180 | Intercompany AR Trail balance (material & no material) - (AHCS Data Only) | [7 empty] | Report (BI Publisher) |  |  |  | Complex |  |  | Report (BI Publisher) - Complex | Sprint 13 | [10 empty] | Sprint 14 | Sprint 14 | [30 empty] | RTR-AHCS-330 | [5 empty] | P1 |  | 0
430 | ABC Corp | 1b New Addition | ERP | RTR-AHCS | AHCS | Report | RPT181 | Intercompany AP Invoice Statement Summary (Material) For the Year Only - (AHCS Data Only) | [5 empty] | Expecting huge volumn considering report needs to extract Yearly data |  | Report (BI Publisher) |  |  |  | Very Complex |  |  | Report (BI Publisher) - Very Complex | Sprint 13 | [10 empty] | Sprint 14 | Sprint 14 | [30 empty] | RTR-AHCS-253 | [5 empty] | P0 |  | 0
431 | ABC Corp | 1b New Addition | ERP | RTR-AHCS | AHCS | Report | RPT182 | Intercompany AR Invoice Statement Summary (Material) For the Year Only - (AHCS Data Only) | [5 empty] | Expecting huge volumn considering report needs to extract Yearly data |  | Report (BI Publisher) |  |  |  | Very Complex |  |  | Report (BI Publisher) - Very Complex | Sprint 13 | [10 empty] | Sprint 14 | Sprint 14 | [30 empty] | RTR-AHCS-341 | [5 empty] | P0 |  | 0
432 | ABC Corp | 1b New Addition | ERP | RTR-AHCS | AHCS | Language Translation | RPT185 | Intercompany AP Invoice Statement Summary (Material) For the Year Only - (AHCS Data Only) - 5 Language Translation | [7 empty] | Report (BI Publisher) |  |  |  | Simple |  |  | Report (BI Publisher) - Simple | Sprint 13 | [10 empty] | Sprint 14 | Sprint 14 | [30 empty] | RTR-AHCS-254 RTR-AHCS-255 RTR-AHCS-256 RTR-AHCS-257 RTR-AHCS-258 | [5 empty] | P4 | RPT181 | 0
433 | ABC Corp | 1b New Addition | ERP | RTR-AHCS | AHCS | Language Translation | RPT186 | Intercompany AR Invoice Statement Summary (Material) For the Year Only - (AHCS Data Only) - 5 Language Translation | [7 empty] | Report (BI Publisher) |  |  |  | Simple |  |  | Report (BI Publisher) - Simple | Sprint 13 | [10 empty] | Sprint 14 | Sprint 14 | [30 empty] | RTR-AHCS-476 RTR-AHCS-477 RTR-AHCS-478 RTR-AHCS-479 RTR-AHCS-480 | [5 empty] | P4 | RPT182 | 0
| ABC Corp | 1b New Addition | ERP | RTR-AHCS | AHCS | Interface | INT237 | Good file OIC Outbound for multiple system |  |  | PAAS DB | Multiple(MFs) |  |  |  | Outbound Interface (Middleware) |  |  |  | Medium |  |  | Outbound Interface (Middleware) - Medium | Sprint 10 | [10 empty] | Sprint 11 | Sprint 12 | [30 empty] | RTR-AHCS-343 | [7 empty] | 0
| ABC Corp | 1b New Addition | ERP | RTR-AHCS | AHCS | Interface | INT238 | Integrity file outbound from Oracle AHCS |  |  | Oracle AHCS | Cresus |  |  |  | Interface - Outbound (Using BI Report) |  |  |  | Complex |  |  | Interface - Outbound (Using BI Report) - Complex | Sprint 12 | [10 empty] | Sprint 13 | Sprint 13 | [30 empty] | RTR-AHCS-329 | [7 empty] | 0
| ABC Corp | 1b New Addition | ERP | RTR-AHCS | AHCS | Interface | INT240 | Cresus to AHCS inbound interface - Preprocessor (AP/AR Data splitter) |  |  | Cresus | Oracle AHCS |  | There is extra efforts involved in separating AP/AR data from one single Cresus file |  | Interface - Inbound (Using Middleware) |  |  |  | Complex |  |  | Interface - Inbound (Using Middleware) - Complex | Sprint 10 | [10 empty] | Sprint 11 | Sprint 11 | [30 empty] | RTR-AHCS-123 RTR-AHCS-124 RTR-AHCS-475 | [7 empty] | 0
| ABC Corp | 1b New Addition | ERP | RTR-AHCS | AHCS | Conversion | CNV041 | Import Subledger balance for MF AP |  | Oracle AHCS | MF AP | Oracle AHCS | Medium |  |  | Conversion (Using ADFDi and FBDI) |  |  |  | Very Complex |  |  | Conversion (Using ADFDi and FBDI) - Very Complex | Sprint 11 | [10 empty] | Sprint 12 | Sprint 13 | [30 empty] | RTR-AHCS-344 RTR-AHCS-345 RTR-AHCS-346 RTR-AHCS-347 RTR-AHCS-348 RTR-AHCS-349 RTR-AHCS-350 RTR-AHCS-364 RTR-AHCS-365 RTR-AHCS-367 RTR-AHCS-371 RTR-AHCS-372 RTR-AHCS-373 RTR-AHCS-377 RTR-AHCS-379 RTR-AHCS-393 RTR-AHCS-394 RTR-AHCS-395 RTR-AHCS-397 RTR-AHCS-400 RTR-AHCS-401 RTR-AHCS-407 RTR-AHCS-419 RTR-AHCS-420 RTR-AHCS-421 RTR-AHCS-423 RTR-AHCS-427 RTR-AHCS-428 RTR-AHCS-442 RTR-AHCS-443 RTR-AHCS-444 RTR-AHCS-445 RTR-AHCS-446 RTR-AHCS-447 RTR-AHCS-448 RTR-AHCS-449 RTR-AHCS-450 RTR-AHCS-464 RTR-AHCS-465 RTR-AHCS-466 RTR-AHCS-468 RTR-AHCS-230 RTR-AHCS-234 | [7 empty] | 0
| ABC Corp | 1b New Addition | ERP | RTR-AHCS | AHCS | Conversion | CNV042 | Import Subledger balance for MF AR |  | Oracle AHCS | MF AR | Oracle AHCS | Medium |  |  | Conversion (Using ADFDi and FBDI) |  |  |  | Very Complex |  |  | Conversion (Using ADFDi and FBDI) - Very Complex | Sprint 11 | [10 empty] | Sprint 12 | Sprint 13 | [30 empty] | RTR-AHCS-351 RTR-AHCS-352 RTR-AHCS-353 RTR-AHCS-224 RTR-AHCS-380 RTR-AHCS-381 RTR-AHCS-382 RTR-AHCS-383 RTR-AHCS-408 RTR-AHCS-409 RTR-AHCS-430 RTR-AHCS-431 RTR-AHCS-451 RTR-AHCS-452 RTR-AHCS-453 RTR-AHCS-454 RTR-AHCS-226 RTR-AHCS-236 | [7 empty] | 0
| ABC Corp | 1b New Addition | ERP | RTR-AHCS | AHCS | Conversion | CNV043 | Import Subledger balance for MF INV |  | Oracle AHCS | MF INV | Oracle AHCS | Medium |  |  | Conversion (Using ADFDi and FBDI) |  |  |  | Very Complex |  |  | Conversion (Using ADFDi and FBDI) - Very Complex | Sprint 12 | [10 empty] | Sprint 13 | Sprint 13 | [30 empty] | RTR-AHCS-354 RTR-AHCS-355 RTR-AHCS-356 RTR-AHCS-357 RTR-AHCS-358 RTR-AHCS-359 RTR-AHCS-360 RTR-AHCS-361 RTR-AHCS-362 RTR-AHCS-363 RTR-AHCS-366 RTR-AHCS-368 RTR-AHCS-369 RTR-AHCS-370 RTR-AHCS-384 RTR-AHCS-385 RTR-AHCS-386 RTR-AHCS-387 RTR-AHCS-388 RTR-AHCS-389 RTR-AHCS-390 RTR-AHCS-391 RTR-AHCS-392 RTR-AHCS-396 RTR-AHCS-398 RTR-AHCS-399 RTR-AHCS-410 RTR-AHCS-411 RTR-AHCS-412 RTR-AHCS-413 RTR-AHCS-414 RTR-AHCS-415 RTR-AHCS-416 RTR-AHCS-417 RTR-AHCS-418 RTR-AHCS-422 RTR-AHCS-424 RTR-AHCS-425 RTR-AHCS-426 RTR-AHCS-432 RTR-AHCS-433 RTR-AHCS-434 RTR-AHCS-435 RTR-AHCS-436 RTR-AHCS-437 RTR-AHCS-438 RTR-AHCS-439 RTR-AHCS-440 RTR-AHCS-441 RTR-AHCS-455 RTR-AHCS-456 RTR-AHCS-457 RTR-AHCS-458 RTR-AHCS-459 RTR-AHCS-460 RTR-AHCS-461 RTR-AHCS-462 RTR-AHCS-463 RTR-AHCS-467 RTR-AHCS-469 RTR-AHCS-228 RTR-AHCS-232 RTR-AHCS-252 | [7 empty] | 0
| ABC Corp | 1b New Addition | ERP | RTR-AHCS | AHCS | Report | RPT009_R | Subledger Account Analysis Report- (RPT009 Retrofit) | Manpreet |  |  |  |  | Existing report is having performance issue so there is less room for leverage 1A Report itself was underestimated considering leverage from other project |  | Report (BI Publisher) |  |  |  | Medium |  |  | Report (BI Publisher) - Medium | Sprint 12 | [10 empty] | Sprint 13 | Sprint 13 | [30 empty] | RTR-AHCS-172 RTR-AHCS-173 | [5 empty] | P0 | RPT009 | 0
| ABC Corp | 1b New Addition | ERP | RTR-AHCS | AHCS | Interface | INT241 | Close out Transactions Load to staging table | Manpreet |  | Close out | Oracle AHCS |  | Different file and logic due to new COA |  | Interface - Inbound (Using Middleware) |  | New (1B Assesment) |  | Medium |  |  | Interface - Inbound (Using Middleware) - Medium | Sprint 12 | [10 empty] | Sprint 14 | Sprint 14 | [30 empty] | RTR-AHCS-482 | 0 |  | 0 | FALSE |  |  |  | 0
| ABC Corp | 1b New Addition | ERP | RTR-AHCS | AHCS | Interface | INT242 | Close out Transaction AHCS Processing | Manpreet |  | Close out | Oracle AHCS |  | Making it medium since we are going to leverage the Individual AHCS Processing Integration. Need to have parent-child file relation between Main Close-out file & corrosponding split file |  | Interface - Inbound (Using Middleware) |  | New (1B Assesment) |  | Complex |  |  | Interface - Inbound (Using Middleware) - Complex | Sprint 12 | [10 empty] | Sprint 14 | Sprint 14 | [30 empty] | RTR-AHCS-482 | 0 |  | 0 | FALSE |  |  |  | 0
| ABC Corp | 1b New Addition | ERP | RTR-AHCS | AHCS | Extension | EXT127 | Close out Data Massaging DB Object | Manpreet |  |  |  |  | Spliting data of different MF systems into individual tables which requires extra efforts from DB side |  | PaaS Extension |  | New (1B Assesment) |  | Very Complex |  |  | PaaS Extension - Very Complex | Sprint 12 | [10 empty] | Sprint 14 | Sprint 14 | [30 empty] | RTR-AHCS-482 | 0 |  | 0 | FALSE |  |  |  | 0
| ABC Corp | 1b New Addition | ERP | RTR-GL | GL | Report | RPT101_R | Journal Batches with no attachments- (RPT101 Retrofit) | Manpreet |  |  |  |  | Adding new sequence column include Secondary ledger journals |  | Report (BI Publisher) |  |  |  | Simple |  |  | Report (BI Publisher) - Simple | Sprint 12 | [10 empty] | Sprint 13 | Sprint 13 | [30 empty] | DP-RTR-IC-087 |  | DP-RTR-IC-087 |  |  |  | P4 | RPT101 | 0
| ABC Corp | 1b New Addition | ERP | RTR-Intercompany | Intercompany | Report | RPT190 | AP/AR SLA to GL Reconciliation Report | David |  |  |  |  | As per Omkar's email on 02/03 |  | Report (BI Publisher) |  |  |  | Complex |  |  | Report (BI Publisher) - Complex | Sprint 11 | [10 empty] | Sprint 12 | Sprint 12 | [30 empty] | DP-RTR-IC-085 DP-RTR-IC-086 |  | DP-RTR-IC-085 DP-RTR-IC-086 |  |  |  | P1 |  | 0
| ABC Corp | 1b New Addition | ERP | RTR-GL | GL | Language Translation | RPT191 | GL Journal Line Detail Report - 5 Language Translation | [5 empty] | GL Delivered phase user stories |  | Report (BI Publisher) |  |  |  | Simple |  |  | Report (BI Publisher) - Simple | Sprint 15 | [10 empty] | Sprint 16 | Sprint 16 | [30 empty] | DP-RTR-GL-023 DP-RTR-GL-029 DP-RTR-GL-035 DP-RTR-GL-041 DP-RTR-GL-047 |  | DP-RTR-GL-023 DP-RTR-GL-029 DP-RTR-GL-035 DP-RTR-GL-041 DP-RTR-GL-047 |  |  |  | P4 | RPT046 | 0
| ABC Corp | 1b New Addition | ERP | RTR-GL | GL | Report | RPT046_R | GL Journal Line Detail Report - (RPT046 Retrofit) | [5 empty] | Adding new sequence column |  | Report (BI Publisher) |  |  |  | Simple |  |  | Report (BI Publisher) - Simple | Sprint 12 | [10 empty] | Sprint 13 | Sprint 13 | [30 empty] | DP-RTR-GL-059 |  | DP-RTR-GL-059 |  |  |  | P1 | RPT046 | 0
| ABC Corp | 1b New Addition | ERP | RTR-GL | GL | Language Translation | RPT192 | Trial Balance by Entered & Accounted Amounts - 5 Language Translation | [5 empty] | GL Delivered phase user stories |  | Report (BI Publisher) |  |  |  | Simple |  |  | Report (BI Publisher) - Simple | Sprint 15 | [10 empty] | Sprint 16 | Sprint 16 | [30 empty] | DP-RTR-GL-024 DP-RTR-GL-030 DP-RTR-GL-036 DP-RTR-GL-042 DP-RTR-GL-048 |  | DP-RTR-GL-024 DP-RTR-GL-030 DP-RTR-GL-036 DP-RTR-GL-042 DP-RTR-GL-048 |  |  |  | P4 | RPT047 | 0
| ABC Corp | 1b New Addition | ERP | RTR-GL | GL | Language Translation | RPT193 | Balance Sheet Trended (GAAP) - 5 Language Translation | [5 empty] | GL Delivered phase user stories |  | Report (BI Publisher) |  |  |  | Simple |  |  | Report (BI Publisher) - Simple | Sprint 15 | [10 empty] | Sprint 16 | Sprint 16 | [30 empty] | DP-RTR-GL-026 DP-RTR-GL-032 DP-RTR-GL-038 DP-RTR-GL-044 DP-RTR-GL-050 |  | DP-RTR-GL-026 DP-RTR-GL-032 DP-RTR-GL-038 DP-RTR-GL-044 DP-RTR-GL-050 |  |  |  | P4 | RPT052 | 0
| ABC Corp | 1b New Addition | ERP | RTR-GL | GL | Language Translation | RPT194 | Income Statement Trailing By Month (GAAP) - 5 Language Translation | [5 empty] | GL Delivered phase user stories |  | Report (BI Publisher) |  |  |  | Simple |  |  | Report (BI Publisher) - Simple | Sprint 15 | [10 empty] | Sprint 16 | Sprint 16 | [30 empty] | DP-RTR-GL-027 DP-RTR-GL-033 DP-RTR-GL-039 DP-RTR-GL-045 DP-RTR-GL-051 |  | DP-RTR-GL-027 DP-RTR-GL-033 DP-RTR-GL-039 DP-RTR-GL-045 DP-RTR-GL-051 |  |  |  | P4 | RPT054 | 0
| ABC Corp | 1b New Addition | ERP | RTR-GL | GL | Report | RPT042_R | Control Accounts Manual Entry Review Report - (RPT042 Retrofit) | [5 empty] | Adding new sequence column |  | Report (BI Publisher) |  |  |  | Simple |  |  | Report (BI Publisher) - Simple | Sprint 12 | [10 empty] | Sprint 13 | Sprint 13 | [30 empty] | DP-RTR-GL-055 |  | DP-RTR-GL-055 |  |  |  | P0 | RPT042 | 0
| ABC Corp | 1b New Addition | ERP | RTR-GL | GL | Report | RPT043_R | GL Journal Report for Journals Missed Reversing - (RPT043 Retrofit) | [5 empty] | Adding new sequence column |  | Report (BI Publisher) |  |  |  | Simple |  |  | Report (BI Publisher) - Simple | Sprint 12 | [10 empty] | Sprint 13 | Sprint 13 | [30 empty] | DP-RTR-GL-056 |  | DP-RTR-GL-056 |  |  |  | P1 | RPT043 | 0
| ABC Corp | 1b New Addition | ERP | RTR-GL | GL | Report | RPT002_R | Journal Batch + Journal Header Report - (RPT002 Retrofit) | [5 empty] | Adding new sequence column |  | Report (BI Publisher) |  |  |  | Simple |  |  | Report (BI Publisher) - Simple | Sprint 12 | [10 empty] | Sprint 13 | Sprint 13 | [30 empty] | DP-RTR-GL-052 |  | DP-RTR-GL-052 |  |  |  | P0 | RPT002 | 0
| ABC Corp | 1b New Addition | ERP | RTR-GL | GL | Language Translation | RPT195 | France FEC Report - 1 Language Translation | [5 empty] | GL Delivered phase user stories |  | Report (BI Publisher) |  |  |  | Simple |  |  | Report (BI Publisher) - Simple | Sprint 12 | [10 empty] | Sprint 13 | Sprint 13 | [30 empty] | DP-RTR-GL-021 |  | DP-RTR-GL-021 |  |  |  | P4 | RPT026 | 0
| ABC Corp | 1b New Addition | ERP | RTR-GL | GL | Language Translation | RPT196 | Reval Summary Report - all COA Segments - 5 Language Translation | [5 empty] | GL Delivered phase user stories |  | Report (BI Publisher) |  |  |  | Simple |  |  | Report (BI Publisher) - Simple | Sprint 12 | [10 empty] | Sprint 13 | Sprint 13 | [30 empty] | DP-RTR-GL-025 DP-RTR-GL-031 DP-RTR-GL-037 DP-RTR-GL-043 DP-RTR-GL-049 |  | DP-RTR-GL-025 DP-RTR-GL-031 DP-RTR-GL-037 DP-RTR-GL-043 DP-RTR-GL-049 |  |  |  | P4 | RPT049 | 0
| ABC Corp | 1b New Addition | ERP | RTR-GL | GL | Language Translation | RPT197 | Non-material IC TB report by LE [Invoice level details] - 5 Language Translation | [5 empty] | GL Delivered phase user stories |  | Report (BI Publisher) |  |  |  | Simple |  |  | Report (BI Publisher) - Simple | Sprint 12 | [10 empty] | Sprint 13 | Sprint 13 | [30 empty] | DP-RTR-IC-019 DP-RTR-IC-031 DP-RTR-IC-043 DP-RTR-IC-055 DP-RTR-IC-067 |  | DP-RTR-IC-019 DP-RTR-IC-031 DP-RTR-IC-043 DP-RTR-IC-055 DP-RTR-IC-067 |  |  |  | P4 | RPT019 | 0
| ABC Corp | 1b New Addition | ERP | RTR-GL | GL | Language Translation | RPT198 | Non-material IC AR Report - 5 Language Translation | [5 empty] | GL Delivered phase user stories |  | Report (BI Publisher) |  |  |  | Simple |  |  | Report (BI Publisher) - Simple | Sprint 11 | [10 empty] | Sprint 12 | Sprint 12 | [30 empty] | DP-RTR-IC-020 DP-RTR-IC-033 DP-RTR-IC-045 DP-RTR-IC-057 DP-RTR-IC-069 |  | DP-RTR-IC-020 DP-RTR-IC-033 DP-RTR-IC-045 DP-RTR-IC-057 DP-RTR-IC-069 |  |  |  | P4 | RPT027 | 0
| ABC Corp | 1b New Addition | ERP | RTR-GL | GL | Language Translation | RPT199 | Non-material IC AP Report - 5 Language Translation | [5 empty] | GL Delivered phase user stories |  | Report (BI Publisher) |  |  |  | Simple |  |  | Report (BI Publisher) - Simple | Sprint 11 | [10 empty] | Sprint 12 | Sprint 12 | [30 empty] | DP-RTR-IC-021 DP-RTR-IC-034 DP-RTR-IC-046 DP-RTR-IC-058 DP-RTR-IC-070 |  | DP-RTR-IC-021 DP-RTR-IC-034 DP-RTR-IC-046 DP-RTR-IC-058 DP-RTR-IC-070 |  |  |  | P4 | RPT028 | 0
| ABC Corp | 1b New Addition | ERP | RTR-GL | GL | Language Translation | RPT200 | Non-material IC AP Invoice Aging [Invoice level] - 5 Language Translation | [5 empty] | GL Delivered phase user stories |  | Report (BI Publisher) |  |  |  | Simple |  |  | Report (BI Publisher) - Simple | Sprint 12 | [10 empty] | Sprint 13 | Sprint 13 | [30 empty] | DP-RTR-IC-026 DP-RTR-IC-038 DP-RTR-IC-050 DP-RTR-IC-062 DP-RTR-IC-074 |  | DP-RTR-IC-026 DP-RTR-IC-038 DP-RTR-IC-050 DP-RTR-IC-062 DP-RTR-IC-074 |  |  |  | P4 | RPT033 | 0
| ABC Corp | 1b New Addition | ERP | RTR-GL | GL | Language Translation | RPT201 | Non-material IC AR Invoice Aging [Account level] - 5 Language Translation | [5 empty] | GL Delivered phase user stories |  | Report (BI Publisher) |  |  |  | Simple |  |  | Report (BI Publisher) - Simple | Sprint 12 | [10 empty] | Sprint 13 | Sprint 13 | [30 empty] | DP-RTR-IC-027 DP-RTR-IC-039 DP-RTR-IC-051 DP-RTR-IC-063 DP-RTR-IC-075 |  | DP-RTR-IC-027 DP-RTR-IC-039 DP-RTR-IC-051 DP-RTR-IC-063 DP-RTR-IC-075 |  |  |  | P4 | RPT034 | 0
| ABC Corp | 1b New Addition | ERP | RTR-GL | GL | Language Translation | RPT202 | Non-material IC AP Invoice Aging [Account level] - 5 Language Translation | [5 empty] | GL Delivered phase user stories |  | Report (BI Publisher) |  |  |  | Simple |  |  | Report (BI Publisher) - Simple | Sprint 12 | [10 empty] | Sprint 13 | Sprint 13 | [30 empty] | DP-RTR-IC-028 DP-RTR-IC-040 DP-RTR-IC-052 DP-RTR-IC-064 DP-RTR-IC-076 |  | DP-RTR-IC-028 DP-RTR-IC-040 DP-RTR-IC-052 DP-RTR-IC-064 DP-RTR-IC-076 |  |  |  | P4 | RPT035 | 0
| ABC Corp | 1b New Addition | ERP | RTR-GL | GL | Language Translation | RPT203 | IC Transaction Detail Report - 5 Language Translation | [5 empty] | GL Delivered phase user stories |  | Report (BI Publisher) |  |  |  | Simple |  |  | Report (BI Publisher) - Simple | Sprint 11 | [10 empty] | Sprint 12 | Sprint 13 | [30 empty] | DP-RTR-IC-029 DP-RTR-IC-041 DP-RTR-IC-053 DP-RTR-IC-065 DP-RTR-IC-077 |  | DP-RTR-IC-029 DP-RTR-IC-041 DP-RTR-IC-053 DP-RTR-IC-065 DP-RTR-IC-077 |  |  |  | P4 | RPT036 | 0
| ABC Corp | 1b New Addition | ERP | RTR-GL | GL | Language Translation | RPT204 | TB with Dr/Cr report for Tax - 5 Language Translation | [5 empty] | GL Delivered phase user stories |  | Report (BI Publisher) |  |  |  | Simple |  |  | Report (BI Publisher) - Simple | Sprint 12 | [10 empty] | Sprint 13 | Sprint 13 | [30 empty] | DP-RTR-GL-022 DP-RTR-GL-028 DP-RTR-GL-034 DP-RTR-GL-040 DP-RTR-GL-046 |  | DP-RTR-GL-022 DP-RTR-GL-028 DP-RTR-GL-034 DP-RTR-GL-040 DP-RTR-GL-046 |  |  |  | P4 | RPT018 | 0
| ABC Corp | 1b New Addition | ERP | RTR-GL | GL | Language Translation | RPT205 | Non-material IC AR Invoice Aging [Invoice level] - 5 Language Translation | [5 empty] | GL Delivered phase user stories |  | Report (BI Publisher) |  |  |  | Simple |  |  | Report (BI Publisher) - Simple | Sprint 12 | [10 empty] | Sprint 13 | Sprint 13 | [30 empty] | DP-RTR-IC-025 DP-RTR-IC-037 DP-RTR-IC-049 DP-RTR-IC-061 DP-RTR-IC-073 |  | DP-RTR-IC-025 DP-RTR-IC-037 DP-RTR-IC-049 DP-RTR-IC-061 DP-RTR-IC-073 |  |  |  | P4 | RPT032 | 0
Note on K2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Development on the legacy - boundary application

## GL Rep. User Story RICE Ration
Unique ID | L0 | L1 | L2 | User Story | Comments / High-level Approach Notes | Acceptance Criteria 1 | Acceptance Criteria 2 | Release | OSS Temp RICE description | OSS RICE ID | Report Release | Actual RICE ID
RTR-GL-006 | Record to Report | Manage General Ledger Accounting | Maintain Chart of Accounts | As GL Manager Financial Systems Analyst, I need to confirm that the system supports viewing the chart of accounts segment, value, description online (COA screen) and through reports (COA report) so that account review and analysis is supported. | COA value Details can be viewed from Manage Chart of Accounts Value set values. Seeded Enterprise Structure report pulls too many details as compared to COA only. If COA report is required from ERP, custom report needs to be built. Report should pull in WHO columns [Created by, creation date, updated by, update date] to enable review with EDMCS For acceptance criteria 1: Use Setup and Maintenance - Manage Chart of Account Values | View COA in real time on screen | Validate report | Phase 1A+1B | COA Value extract report | GL-TEMP-001 | Phase 1A+1B | RPT001
RTR-GL-010 | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As a GL Accountant, I want to be able to review journal entries so that I am aware of what has been entered and posted in the system | Go to Manage Journal Entries task --> search the journals and extract the data in Excel. You may additionally run standard Journal details report to review the journals that are posted Discuss: Build a custom flat excel journal extract report with custom parameters for review. Report output should inlcude columns like posting status, approval status, reversed yes/no, WHO columns etc. Ensure report parameter includes Created By [Journal Batch + Journal Header report] | Run real time data as part of my analysis when reviewing entered and posted entries. Review entered and posted journals via report. | Validate Journals>Enter query (Manage Journal) | Phase 1A+1B | Journal Batch + Journal Header Report | GL-TEMP-002 | Phase 1A+1B | RPT002
RTR-GL-013 | Record to Report | Manage General Ledger Accounting | Approve and Post Journal Entries | As a GL Accountant, I need the ability to inform my manager to approve journal entries, so that they can be posted | Journal can be sent for approval by requesting for approval as per Journal approval KDD For acceptance creieria 2, need to build a new report that shows journals and action history log for journals pending approval | There should be email notification and a flag in cloud as well to alert approver that an approval is needed. Ensure notification includes all the criterias per business design. | Requirement to build a report that identifies all unposted journals and current level of approval. | Phase 1A+1B | Details of unposted journals including details available in Action Log | GL-TEMP-003 | Phase 1A+1B | RPT003
RTR-GL-017 | Record to Report | Manage General Ledger Accounting | Approve and Post Journal Entries | As a GL Manager Financial System Analyst, I want to be able to modify approval notifications template for GL workflows so that the predefined template can be updated to display information based on specific business requirements and policies. | Approval notification template can be updated as per requirement. Requirement to have code combination string added to output For acceptance criteria 1: Customization of notification template to be discussed in RICE lean spec once user story is approved & RICE build is scheduled | Notification contains all the required information previously defined by users. |  | Phase 1A+1B | GL Journal notification update | GL-TEMP-004 | Phase 1A+1B | RPT004
RTR-GL-018 | Record to Report | Manage General Ledger Accounting | Approve and Post Journal Entries | As a GL Manager (an approver of journal) like to know the Journal created creator and submitter so that I know who is creating and submitting the batch for approval | Submitted by details (with time and date stamp) are captured in the standard approval workflow. Customize template to add Created by | Review Journal creator and submitter including date and time stamp at time of approval. |  | Phase 1A+1B | GL Journal notification update | GL-TEMP-004 | Phase 1A+1B | RPT004
RTR-GL-075 | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | As an accountant, I need a Journal approval audit compliance report that pulls 1. Journals with negative dr or cr 2. Journals where created by = final approver 3. Journals where first stage and 2nd stage approver are same | Custom report based GL_JE_ACTION_LOG & GL_JE_BATCHES table | Review results of report to ensure accuracy. | KDD4 Report to identify (1) batches with negative DR and negative CR, (2) journals whose created by = final approver, (3) journals where step 1 approver = step 2 approver. Validate report by testing all three scenarios. | Phase 1A+1B | Journal Approval report for audit compliance | GL-TEMP-005 | Phase 1A+1B | RPT005
RTR-GL-076 | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | As an accountant, I need to be able to create FEC reporting | Custom report to be built for FEC report. Confirm if standard report does not meet requirement as part of lean spec design | Review results of report to ensure accuracy. |  | Phase 1B only | France FEC Report | GL-TEMP-006 | Phase 1B only | RPT026
RTR-GL-077 | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | As an accountant, I need a report which can bring GL journal and SLA journal line details together in a single output | Custom report to bring GL and SLA details together. This report will not go to seeded subledger tables, but will only pull details avaiable in GL and SLA tables | Review results of report to ensure accuracy. |  | Phase 1A+1B | ABC Corp GL & Subleger Account Analysis Report | GL-TEMP-007 | Phase 1A+1B | RPT040
RTR-GL-090 | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | As a GL Accountant, I need a GL Trial Balance from which I can drill down to a report that shows GL and Subledger lines together | Will develop a report that pulls TB in excel. When clicking on amount, it will drill down to GL/SLA report to be built as part of user story RTR-GL-077 | Review results of report to ensure accuracy. |  | Phase 1A+1B | ABC Corp TB with dril-down/link to ABC Corp Subledger Account Analysis Report | GL-TEMP-008 | Phase 1A+1B | RPT041
RTR-GL-095 | Record to Report | Manage General Ledger Accounting | Process Manual Journal Entries | As a GL Accountant, I want to be able to prevent the posting of manual journal entries to control accounts as a means of ensuring that control accounts reconcile to the applicable subledger | Oracle cloud allows ability to define COA natural account values as control accounts. These accounts then cannot be posted to from front end in GL. But when using spreadsheet [ADFDI] approach Oracle allows users to select "delay validation" option. In this case Control account validaiton is not performed in spreadsheet. At this point in time Journal Import process does not perform Control account validation i.e. this validaiton will not be performed. Currently ORacle does not allow ability to take away this ability to "delay validations" from users. Hence a custom reprot needs to be built to reivew non subledger source entries hitting control accounts | Entered journal in restricted account. Ensure journal cannot be posted. |  | Phase 1A+1B | Control Accounts Manual Entry Review Report | GL-TEMP-009 | Phase 1A+1B | RPT042
RTR-GL-106 | Record to Report | Manage General Ledger Accounting | Process Reversing Journal Entries | As a GL Accountant, I need a report that shows journal entries that have reversal period captured but is not reversed or journal entries that have categories that are marked for autoreversal but are not yet reversed even when relevant period has been opened | Create a new custom report to pull journal details satisfying relevant criteria Related to user story RTR-GL-026 | Validate journals in the report. |  | Phase 1A+1B | GL Journal report for journals missed reversing | GL-TEMP-010 | Phase 1A+1B | RPT043
RTR-GL-107 | Record to Report | Manage General Ledger Accounting | Process Manual Journal Entries | As a GL Accountant, I need a report which shows exchange rates used to convert entered currency to functional currency of more than 10% based on daily rate. | Build a custom report based on effective rate computed from entered and accounted amounts which can be compared against configured threshold in lookup | Entered journal where exchange rate is significantly different from the daily rate. Validate journal after posted. Have the ability to select specific percentages or multiple predetermined percentages in the report. |  | Phase 1B only | Flag incorrect exchange rates on Journal report | GL-TEMP-011 | Phase 1B only | RPT016
RTR-GL-110 | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | As a GL Accountant, I need a report that shows all balances from Primary Ledger has been copied to the Secondary Ledger. |  | Verified that balances in Primary Ledger copied over to Secondary Ledger. |  | Phase 1B only | Confirm relevant manual journals copied to secondary | GL-TEMP-012 | Phase 1B only | RPT011
REP-RTR-GL-63 | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | Legacy Report Name:WES_JOURNAL_DETAIL_EXTRACT CP Legacy Report Description:Description is contained within each concurrent request name. Prior to GL Wand, this was the only method to extract data from the GL by branch, account, periods, mgt rollups, journal detail, etc. Users continue to use reports today. | Journal Details report (Journal Batch + Journal Header). Merge RICE with user story RTR-GL-010 |  |  | Phase 1A only | Journal Batch + Journal Header Report | GL-TEMP-002 | Phase 1A only | RPT002
REP-RTR-GL-69 | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | Legacy Report Name:ABC Corp GL Balance Corruption Report Legacy Report Description:Identifies GL table data corruption | Build new report to compare GL balances vs GL journals |  |  | Phase 1A only | Compare GL Balances and GL Journals for Data Corruption | GL-TEMP-013 | Phase 1A only | RPT044
REP-RTR-GL-70 | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | Legacy Report Name:ABC Corp GL Journal Approval Status Report Legacy Report Description:Provides status of journals in approval hierarchy | Journal Batch / Journal Header level report. Provides details where the journal is waiting for approval [Different that other Journal report & journal line report. This is more about where is journal in approval currently so that it can be followed up] [As part of lean spec design finalize information that can be pulled from GL tables for reporting] |  |  | Phase 1A only | Details of unposted journals including details available in Action Log | GL-TEMP-003 | Phase 1A only | RPT003
REP-RTR-GL-79 | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | Legacy Report Name:GL Period Status Query Legacy Report Description: | This is period status report showing 1. Who columns 2. Run for entire year 3. Run for ledger Set 4. Shows period status for GL 5. Shows period status for AR & AP [Phase 1B] |  |  | Phase 1A only | GL/AR/AP Period Status Report | GL-TEMP-014 | Phase 1A only | RPT045
REP-RTR-GL-1 | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | Legacy Report Name:GL Activity Legacy Report Description:As an Accountant, I need a report of GL activity by LE, GL Account, trans currency, functional currency, and all other charfield values. Capability to filter by any chartfield value and date ranges. This report is used to analyze GL activity. Reference ID:AXE-GL-1 | GL Journal Line detail report [Merge AXE-GL-1, AXE-GL-7, , AXE-GL-8, AXE-GL-9, AXE-GL-12, AXE-GL-13]. Ensure there is filter criteria by Period status |  |  | Phase 1A+1B | GL Journal Line detail report | GL-TEMP-015 | Phase 1A+1B | RPT046
REP-RTR-GL-2 | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | Legacy Report Name:GL Balances Legacy Report Description:As an Accountant, I need a report of GL balances by LE, GL Account, trans currency, functional currency, and all other charfield values. Capability to filter by any chartfield value and date ranges. This report is used to analyze GL activity. Reference ID:AXE-GL-2 | New balance report by entered and accounted Note: Why SmartView is not useful - Many people will use it |  |  | Phase 1A+1B | Trial Balance by Entered & Accounted Amounts | GL-TEMP-016 | Phase 1A+1B | RPT047
REP-RTR-GL-3 | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | Legacy Report Name:GL I/C Balances Legacy Report Description:As an Accountant, I need a report of I/C Payables and Receivables balances by LE, account, affiliate (or GL cloud equivalent), cost center, and other chartfield values. Capability to filter by LE, Affliate, account, and other chartfield values. This report is used to analyze I/C balances Reference ID:AXE-GL-3 | IC Balance Matrix: IC Balance report by GL balances [based on IC segment and specific natural accounts] Note: Why SmartView is not useful - Many people will use it |  |  | Phase 1A+1B | IC Balance Matrix: IC Balance report by GL balances | GL-TEMP-017 | Phase 1A+1B | RPT048
REP-RTR-GL-4 | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | Legacy Report Name:GL I/C Activity Legacy Report Description:As an Accountant, I need a report of I/C Payables and Receivables activity by LE, account, affiliate (or GL cloud equivalent), cost center, and other chartfield values. Capability to filter by LE, Affliate, account, and other chartfield values. This report is used to analyze I/C activity. Reference ID:AXE-GL-4 | Merge with GL Drill down report - User story RTR-GL-077 |  |  | Phase 1A+1B | ABC Corp GL & Subleger Account Analysis Report | GL-TEMP-007 | Phase 1A+1B | RPT040
REP-RTR-GL-5 | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | Legacy Report Name:GL Revaluation Legacy Report Description:As an Accountant, I need a report of FX revaluation (using month-end rate) by account, LE, location and other chartfield values. This report is used to analyze current period FX exposure (currently GL 36) Reference ID:AXE-GL-5 | Revaluation summary at COA level [all COA segments]. Run report after reval is executed in system |  |  | Phase 1A+1B | Reval Summary Report - all COA Segments | GL-TEMP-018 | Phase 1A+1B | RPT049
REP-RTR-GL-6 | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | Legacy Report Name:GL Revaluation by account Legacy Report Description:As an accountant, I need a report which shows the monthly revaluation amount for each account for a particular LE. This report is used for FX analysis Reference ID:AXE-GL-6 | Revaluation summary at COA level [only LE & Account]. Run report after reval is executed in system |  |  | Phase 1A+1B | Reval Summary Report - only LE & Account | GL-TEMP-019 | Phase 1A+1B | RPT050
REP-RTR-GL-7 | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | Legacy Report Name:GL Activity by journal enter and post date Legacy Report Description:As an Accountant, I need a report of GL activity by LE, GL Account, trans currency, functional currency, and all other charfield values. Capability to filter by any chartfield value, Journal entered date, journal posted data or date ranges. This report is used to analyze GL activity by posted date. Reference ID:AXE-GL-7 | GL Journal Line detail report [Merge AXE-GL-1, AXE-GL-7, , AXE-GL-8, AXE-GL-9, AXE-GL-12, AXE-GL-13]. Ensure there is filter criteria by Period status |  |  | Phase 1A+1B | GL Journal Line detail report | GL-TEMP-015 | Phase 1A+1B | RPT046
REP-RTR-GL-8 | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | Legacy Report Name:GL Journal detail Legacy Report Description:As an accountant, I need a report which shows all journal lines for the specific JE (JE ID and period is the input data). Currently in PS GL 28 Reference ID:AXE-GL-8 | GL Journal Line detail report [Merge AXE-GL-1, AXE-GL-7, , AXE-GL-8, AXE-GL-9, AXE-GL-12, AXE-GL-13]. Ensure there is filter criteria by Period status |  |  | Phase 1A+1B | GL Journal Line detail report | GL-TEMP-015 | Phase 1A+1B | RPT046
REP-RTR-GL-9 | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | Legacy Report Name:Journal activity by status Legacy Report Description:As an accountant, I need a report of all journals processed by status foe example: posted, entered, validated, deleted…. (JE status and period is the input data). Currently in PS GL 08 Reference ID:AXE-GL-9 | GL Journal Line detail report [Merge AXE-GL-1, AXE-GL-7, , AXE-GL-8, AXE-GL-9, AXE-GL-12, AXE-GL-13]. Ensure there is filter criteria by Period status |  |  | Phase 1A+1B | GL Journal Line detail report | GL-TEMP-015 | Phase 1A+1B | RPT046
REP-RTR-GL-10 | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | Legacy Report Name:Current month FX rates Legacy Report Description:As an accountant, I need a report of all current FX rates loaded in GL by currency and rate type (budget, month end, average, daily). Currently in PS GL 35 Reference ID:AXE-GL-10 | FX Rates loaded in ERP to be pulled out for reporting [Create date range and period as parameters]. Created separate EPM line for budget rates |  |  | Phase 1A+1B | Exchange Rate Export Report | GL-TEMP-020 | Phase 1A+1B | RPT051
REP-RTR-GL-12 | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | Legacy Report Name:Historical FX rates by date Legacy Report Description:As an accountant, I need a report of all historical FX rates loaded in GL by date, currency and rate type (budget, month end, average, daily). Ability to filter by date and currency and geography (if loaded multiple times per day). Currently in PS GL 60 Reference ID:AXE-GL-11 | FX Rates loaded in ERP to be pulled out for reporting [Create date range and period as parameters]. Created separate EPM line for budget rates |  |  | Phase 1A+1B | Exchange Rate Export Report | GL-TEMP-020 | Phase 1A+1B | RPT051
REP-RTR-GL-14 | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | Legacy Report Name:Report of journals which failed CVR Legacy Report Description:I need a report that Lists all accounting events and journal entries that fail period close validation. Groups report by ledger, period, journal source, journal category, and event class at submission. Reference ID:AXE-GL-12 | GL Journal Line detail report [Merge AXE-GL-1, AXE-GL-7, , AXE-GL-8, AXE-GL-9, AXE-GL-12, AXE-GL-13]. Ensure there is filter criteria by Period status |  |  | Phase 1A+1B | GL Journal Line detail report | GL-TEMP-015 | Phase 1A+1B | RPT046
REP-RTR-GL-15 | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | Legacy Report Name:Journals entered not posted Legacy Report Description:I need a report that Lists journal entries that have been entered not posted. Reference ID:AXE-GL-13 | GL Journal Line detail report [Merge AXE-GL-1, AXE-GL-7, , AXE-GL-8, AXE-GL-9, AXE-GL-12, AXE-GL-13]. Ensure there is filter criteria by Period status |  |  | Phase 1A+1B | GL Journal Line detail report | GL-TEMP-015 | Phase 1A+1B | RPT046
REP-FSG-RTR-GL-001 | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | Current Type: FSG PROD NAME: GA_BS (GAAP)_TRENDED_YTD PROD Report Title: BALANCE SHEET TRENDED (GAAP) | Build GL ERP balance based report based on LE actuals only [does not include consolidated/eliminated/budget/forecast etc.] |  |  | Phase 1A+1B | BALANCE SHEET TRENDED (GAAP) | GL-TEMP-021 | Phase 1A+1B | RPT052
REP-FSG-RTR-GL-002 | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | Current Type: FSG PROD NAME: GA_TB (ACCOUNT)_LE_YTD PROD Report Title: TRIAL BALANCE BY LEGAL ENTITY (ACCOUNT) | Build GL ERP balance based report based on LE actuals only [does not include consolidated/eliminated/budget/forecast etc.] |  |  | Phase 1A+1B | TRIAL BALANCE BY LEGAL ENTITY (ACCOUNT) | GL-TEMP-022 | Phase 1A+1B | RPT053
REP-FSG-RTR-GL-003 | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | Current Type: FSG PROD NAME: GA_IS (GAAP)_MONTHLY_PTD PROD Report Title: INCOME STATEMENT TRAILING BY MONTH (GAAP) | Build GL ERP balance based report based on LE actuals only [does not include consolidated/eliminated/budget/forecast etc.] |  |  | Phase 1A+1B | INCOME STATEMENT TRAILING BY MONTH (GAAP) | GL-TEMP-023 | Phase 1A+1B | RPT054
REP-FSG-RTR-GL-004 | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | Current Type: FSG PROD NAME: GA_BS (GAAP)_COUNTRY_YTD PROD Report Title: BALANCE SHEET BY COUNTRY (GAAP) | Build GL ERP balance based report based on LE actuals only [does not include consolidated/eliminated/budget/forecast etc.] |  |  | Phase 1A+1B | BALANCE SHEET BY COUNTRY (GAAP) | GL-TEMP-024 | Phase 1A+1B | RPT055
REP-FSG-RTR-GL-005 | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | Current Type: FSG PROD NAME: GA_IS (GAAP)_COUNTRY_YTD PROD Report Title: INCOME STATEMENT BY COUNTRY (GAAP) | Build GL ERP balance based report based on LE actuals only [does not include consolidated/eliminated/budget/forecast etc.] |  |  | Phase 1A+1B | INCOME STATEMENT BY COUNTRY (GAAP) | GL-TEMP-025 | Phase 1A+1B | RPT056
REP-FSG-RTR-GL-006 | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | Current Type: FSG PROD NAME: GA_IS (OPER)_TRAILING_QTD PROD Report Title: Income Statement Trailing by Quarter (Operating) with % | Build GL ERP balance based report based on LE actuals only [does not include consolidated/eliminated/budget/forecast etc.] |  |  | Phase 1A+1B | Income Statement Trailing by Quarter (Operating) with % | GL-TEMP-026 | Phase 1A+1B | RPT057
REP-FSG-RTR-GL-007 | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | Current Type: FSG PROD NAME: GA_TB_BRANCH_ACTUAL PROD Report Title: Trial Balance by Branch - Actual | Build GL ERP balance based report based on LE actuals only [does not include consolidated/eliminated/budget/forecast etc.] |  |  | Phase 1A+1B | Trial Balance by Branch - Actual | GL-TEMP-027 | Phase 1A+1B | RPT058
REP-FSG-RTR-GL-008 | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | Current Type: FSG PROD NAME: GA_TB_BRANCH_STAT PROD Report Title: Trial Balance by Branch - STAT | Build GL ERP balance based report based on LE actuals only [does not include consolidated/eliminated/budget/forecast etc.] |  |  | Phase 1A+1B | Trial Balance by Branch - STAT | GL-TEMP-028 | Phase 1A+1B | RPT059
REP-FSG-RTR-GL-009 | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | Current Type: FSG PROD NAME: GA_TB_BRANCH_TRAILING_YTD_ACTUAL PROD Report Title: Trial Balance by Branch Trailing YTD - Actual | Build GL ERP balance based report based on LE actuals only [does not include consolidated/eliminated/budget/forecast etc.] |  |  | Phase 1A+1B | Trial Balance by Branch Trailing YTD - Actual | GL-TEMP-029 | Phase 1A+1B | RPT060
REP-FSG-RTR-GL-010 | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | Current Type: FSG PROD NAME: GA_TB_BRANCH_TRAILING_PTD_ACTUAL PROD Report Title: Trial Balance by Branch Trailing PTD - Actual | Build GL ERP balance based report based on LE actuals only [does not include consolidated/eliminated/budget/forecast etc.] |  |  | Phase 1A+1B | Trial Balance by Branch Trailing PTD - Actual | GL-TEMP-030 | Phase 1A+1B | RPT061
REP-FSG-RTR-GL-011 | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | Current Type: FSG PROD NAME: GA_TB_BRANCH_TRAILING_PTD_STAT PROD Report Title: Trial Balance by Branch Trailing PTD - STAT | Build GL ERP balance based report based on LE actuals only [does not include consolidated/eliminated/budget/forecast etc.] |  |  | Phase 1A+1B | Trial Balance by Branch Trailing PTD - STAT | GL-TEMP-031 | Phase 1A+1B | RPT062
REP-FSG-RTR-GL-012 | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | Current Type: FSG PROD NAME: GA_IS(STDCST)_MONTHLY_PTD PROD Report Title: Income Statement Trailing by Month (Standard Cost Operating) | Build GL ERP balance based report based on LE actuals only [does not include consolidated/eliminated/budget/forecast etc.] |  |  | Phase 1A+1B | Income Statement Trailing by Month (Standard Cost Operating) | GL-TEMP-032 | Phase 1A+1B | RPT063
RTR-IC-005 | Record to Report | Manage Intercompany Accounting | Process Intercompany Journal Entries | As an Intercompany Accountant, I want my journal entries to route for approvals if necessary | GL Journals will follow approvals as per KDD4. Autopost will initiate approvals for complete journals which are not yet routed for approvals IC Batches will need to be submitted for users for approvals. Need update to IC approval notificaiton to include "submitted by" details to meet acceptance criteria 1 comment on formats [Discussed with Vitaliy] | Validate that IC journals routed correctly for approval per business design. Validate the format of the approval request matches the business design and contains all the required information. Ensure reviewers have the ability to open attachments and reject journals if required. |  | Phase 1B only | IC Approval Notification Customization Report | OSS-BATCH2-REP14 | Phase 1B only | RPT017
RTR-GL-148 | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | As an accountant, I will need a Gl trial balance by LE which shows the Debit and Credit in separate columns. Balances should be accumulated separately by debit and credit column. | Required for International reporting. Accounting would not want planned TB report to show Dr/Cr & hence a new custom report | Reviewed TB for completeness and accuracy. Valid balances in Debit and Credit columns. |  | Phase 1B only | TB with Dr/Cr report for Tax | OSS-BATCH2-REP13 | Phase 1B only | RPT018
RTR-IC-012 | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As a GL accountant, I need a non-material I/C TB report by legal entity. Report should provide a detail at invoice level. | non-material I/C TB report by legal entity. Report should provide a detail at invoice level. | Reviewed detailed non-material I/C TB report |  | Phase 1B only | Non-material IC TB report by LE [Invoice level details] | OSS-BATCH2-REP1 | Phase 1B only | RPT019
RTR-IC-013 | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As a GL accountant, I need a non-material I/C TB report by legal entity. Report should provide a summary at account level. | need a non-material I/C TB report by legal entity. Report should provide a summary at account level. | Reviewed summarized non-material I/C TB report |  | Phase 1B only | Non-material IC TB report by LE [summarize at account level] | OSS-BATCH2-REP2 | Phase 1B only | RPT020
RTR-IC-014A | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As a I/C GL accountant, I need a report of all non-material I/C AR invoices created by LE and period. | Need a report of all non-material I/C AR invoices created by LE and period. | Reviewed non-material I/C AR invoices report. Ensure all AR invoices generated by period is captured in the report. Ensure format of report matches business design. |  | Phase 1B only | Non-material IC AR Report | OSS-BATCH2-REP3 | Phase 1B only | RPT027
RTR-IC-014B | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As a I/C GL accountant, I need a report of all non-material I/C AP invoices created by LE and period. | need a report of all non-material I/C AP invoices created by LE and period. | Reviewed non-material I/C AP invoices report. Ensure all AP invoices generated by period is captured in the report. Ensure format of report matches business design. |  | Phase 1B only | Non-material IC AP Report | OSS-BATCH2-REP4 | Phase 1B only | RPT028
RTR-IC-024A | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As an I/C GL accountant, I will need a report of I/C AR invoices that have been settled by period and legal entity | Split user story into A & B. RTR-IC-024A: New report to pull IC related AR invoices based on receipts created & invoice open amount. RTR-IC-024B: New report to pull IC related AP invoices based on payments created & invoice open amount | Validate accuracy of the report. Ensure all settled AR invoices are captured. Ensure format of report matches business design |  | Phase 1B only | Non-material IC AR Report with receipts created in selected range | OSS-BATCH2-REP5 | Phase 1B only | RPT029
RTR-IC-024B | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As a I/C GL accountant, I will need a report of I/C AP invoices that have been settled by period and legal entity | Split user story into A & B. RTR-IC-024A: New report to pull IC related AR invoices based on receipts created & invoice open amount. RTR-IC-024B: New report to pull IC related AP invoices based on payments created & invoice open amount | Validate accuracy of the report. Ensure all settled AP invoices are captured. Ensure format of report matches business design. |  | Phase 1B only | Non-material IC AP Report with payments created in selected range | OSS-BATCH2-REP6 | Phase 1B only | RPT030
RTR-IC-028 | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As a I/C GL Accountant, I will need a report of I/C AP invoices that have been selected (not yet settled) for settlement. Report should show I/C AR and AP invoices side by side. This report will be used to approve the settlement of I/C invoices. | Create new custom report that pulls AP invoices that are selected for payment, but not yet paid. Report would then show side by side corresponding AR invoice details | Review format of report to ensure matches business design. Ensure AP invoices selected for settlement from the report have not been settled in the subledger. Validate that invoices selected for settlement cannot be settled on another batch. |  | Phase 1B only | Non-material IC AP Invoices selected for payment report with associated AR invoice details | OSS-BATCH2-REP7 | Phase 1B only | RPT031
RTR-IC-035A | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As a GL accountant, I need a non-material I/C Aging report by legal entity. Report should provide a detail at invoice level. | User story split into A & B. RTR-IC-035A is AR Aging at invoice level. RTR-IC-035B is AP Aging at Invoice level |  |  | Phase 1B only | Non-material IC AR Invoice Aging [Invoice level] | OSS-BATCH2-REP8 | Phase 1B only | RPT032
RTR-IC-035B | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As a GL accountant, I need a non-material I/C Aging report by legal entity. Report should provide a detail at invoice level. | User story split into A & B. RTR-IC-035A is AR Aging at invoice level. RTR-IC-035B is AP Aging at Invoice level |  |  | Phase 1B only | Non-material IC AP Invoice Aging [Invoice level] | OSS-BATCH2-REP9 | Phase 1B only | RPT033
RTR-IC-036A | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As a GL accountant, I need a non-material I/C Aging report by legal entity. Report should provide a summary at account level. | User story split into A & B. RTR-IC-036A is AR Aging at account level. RTR-IC-036B is AP Aging at account level |  |  | Phase 1B only | Non-material IC AR Invoice Aging [Account level] | OSS-BATCH2-REP10 | Phase 1B only | RPT034
RTR-IC-036B | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As a GL accountant, I need a non-material I/C Aging report by legal entity. Report should provide a summary at account level. | User story split into A & B. RTR-IC-036A is AR Aging at account level. RTR-IC-036B is AP Aging at account level |  |  | Phase 1B only | Non-material IC AP Invoice Aging [Account level] | OSS-BATCH2-REP11 | Phase 1B only | RPT035
RTR-IC-037 | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As a GL accountant, I need a report of all IC transactions entered but not approved. | IC Transaction Detail report to be built - similar to workshop layout |  |  | Phase 1B only | IC Transaction Detail Report | OSS-BATCH2-REP12 | Phase 1B only | RPT036
RTR-IC-039 | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | As a GL accountant, I need a report of all IC AR invoices recorded but not yet transferred to AP. | IC Transaction Detail report to be built - similar to workshop layout |  |  | Phase 1B only | IC Transaction Detail Report | OSS-BATCH2-REP12 | Phase 1B only | RPT036
DP-RTR-IC-001 | Record to Report | Manage General Ledger Accounting | Process Manual Journal Entries | As a tax analyst, I would like all I/C invoices to be archived monthly. Invoices must show the historical data on the invoice. (if address for entity changes, historical invoices should still show the old address). [For invoice template bursting to SFTP by invoice template] | Invoice template can be bursted to SFTP folders. ABC Corp IT may pick from SFTP folders and move to required archiving tools like FileNet etc. 2 invoice templates to be built as per assumptions and alignment via email "Non material Intercompany Invoice Template from PeopleSoft" | Ensure all I/C invoices have been archived. Ensure historical data is captured on the invoices. |  | Phase 1B only | AR Invoice Print AR Credit Memo Print | OSS-DP-BATCH1-REP-001 OSS-DP-BATCH1-REP-002 | Phase 1B only | RPT102 RPT103
DP-RTR-IC-002 | Record to Report | Manage Intercompany Accounting | Process Intercompany AR/AP Invoices | (IC Transactions) Oracle GL must have sufficient fields to capture Legal Entity attributes which require printing on an invoice template, such as Registered address, VAT number, Tax and/or Company registration number, Share capital, Directors, the label "Tax invoice", etc... | PF 7/13: A question to the team is whether Oracle foresees fields to store (and maintain) certain data, or whether this is hard coded on every invoice template? OSS Notes: Alignment on tax team call not all fields will be in Oracle tables, some will be in templates. User story DP-RTR-IC-001 will be used to track archiving requirement on reports Vitaliy to work with Patrick for 1B to finalize Intercompany transaction types that are required 7/28 email sent:Note: As mentioned on call, tax computation and related field population is currently not in scope for IC currently in 1B – irrespective as a Tax engine OR as Oracle tax module config. Seems recently a KDD has been created for this which Nanda/Farnaz are working on. Invoice template assumes that data required for template is there on invoice – static [E.g. LE Name], user entered [E.g. Amount ] OR tax related [E.g Tax Code] which is derived either by Tax engine OR Tax configs [both currently not in scope for Release 1] OR user entered. 7/29: As per email "Non material Intercompany Invoice Template from PeopleSoft" 2 invoice print templates planned based on noted assumptions. Expectation based on noted assumptions is it should address local requirements | Ensure required attributes for local country requirements are included and maintained for Intercompany Invoice Templates |  | Phase 1B only | AR Invoice Print AR Credit Memo Print | OSS-DP-BATCH1-REP-001 OSS-DP-BATCH1-REP-002 | Phase 1B only | RPT102 RPT103
DP-RTR-GL-004 | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | FX rates will be at the legal entity level (not BU level). | This story pertains to reporting ledgers required for UK entity having MD-LRD sturcture in EMEA. For example "a BU is in Euro, but the LE is GBP. If Oracle could provide the LE GBP trial balance and US trial balance this would eliminate the manual manipulation of data."- PW Reporting Ledgers will be setup as per approved KDD2. Primary ledgers [USGAAP] will be setup as per approved KDD2 Acceptance criteria 1: Reporting ledger accounted balances will be will currency of reporting ledger Add a new TB report for MDR entities based on reporting ledger restricting it to specific entities [ignore non relevant entities in reporting ledger which will get copied over from primary as they co-exist in same ledger but are not part of MD-LRD structure] | This will be captured at the reporting ledger, per tax user story review session. Tax will ensure reports provided are in the correct functional currency for legal entity. |  | Phase 1B only | TB report for MDR entities based on reporting ledger | OSS-DP-BATCH1-REP-003 | Phase 1B only | RPT104
DP-RTR-GL-009 | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | Documentation/Substantiation is required to be attached to journal entries and other postings. [ERP Component] | Not sure what "other postings" in user story mean Journals cannot be stopped from getting created, approved or posted if attachment is not there. Oracle Cloud ERP supports uploading attachment at Journal level and also at Journal batch level 7/28: Confirmed by Tax team that "other postings" means journals. New custom report to be created that will flag journal batches where there is no attachment at both journal batch and header level Confirmed by JEss this is needed for 1A as well | If Oracle Cloud does not have a mechanism to stop journal entries posting without documentation, per tax user story review, tax will ensure training process addresses attachments in journal entry review process and review report structure for journal entries posted without attachment. |  | Phase 1A+1B | Journal Batches with no attachments | OSS-DP-BATCH1-REP-004 | Phase 1A+1B | RPT101
DP-RTR-GL-015 | Record to Report | Manage General Ledger Accounting | Period-End Closing & Reporting | The financial accounting system shall provide a report of journal entries that do not have supporting documentation or attachments. | Journals cannot be stopped from getting created, approved or posted if attachment is not there. Oracle Cloud ERP supports uploading attachment at Journal level and also at Journal batch level 7/28: New custom report to be created that will flag journal batches where there is no attachment at both journal batch and header level Confirmed by JEss this is needed for 1A as well | If Oracle Cloud does not have a mechanism to stop journal entries posting without documentation, per tax user story review, tax will ensure training process addresses attachments in journal entry review process and review report structure for journal entries posted without attachment. |  | Phase 1A+1B | Journal Batches with no attachments | OSS-DP-BATCH1-REP-004 | Phase 1A+1B | RPT101

## Tax Story Summary
Reference ID | (Multiple Items)
Count of User Story | Column Labels
Row Labels | Phase 1A+1B | Phase 1B only | Grand Total
RTR-GL | 8 | 27 | 35
EPM - CCR | 14 | 4 | 18
COA | 4 | 10 | 14
EPM - COA MDM | 3 | 9 | 12
BI |  | 3 | 3
TECH | 2 |  | 2
LEGACY |  | 1 | 1
RTR-AHCS | 1 |  | 1
Grand Total | 32 | 54 | 86
Reference ID | (Multiple Items)
Count of User Story | Column Labels
Row Labels | Phase 1A+1B | Phase 1B only | Grand Total
RTR-GL | 8 | 27 | 35
Submitted for Approval |  | 6 | 6
TBD |  | 1 | 1
Approved | 8 | 20 | 28
RTR-AHCS | 1 |  | 1
Approved | 1 |  | 1
Grand Total | 9 | 27 | 36
Reference ID | (Multiple Items)
Subtype Status | (Multiple Items)
Count of User Story | Column Labels
Row Labels | RTR-GL | Grand Total
Tax engine decision | 6 | 6
Awaiting alignment with legacy FAH local solution proposed from Incorta | 1 | 1
Grand Total | 7 | 7
Oracle Module | (Multiple Items)
Release | Phase 1A+1B
SubTrack | RTR-GL
Deliver Phase User Stories | Column Labels
L2 | Approved | Initial Fit/Gap Complete | Grand Total
Period-End Closing & Reporting | 8 |  | 8
Process Manual Journal Entries | 1 | 1 | 2
Grand Total | 9 | 1 | 10
Reference ID | (Multiple Items)
Subtype Status | Approved
Count of User Story | Column Labels
Row Labels | RTR-GL | RTR-AHCS | Grand Total
Phase 1A+1B | 8 | 1 | 9
1-Fit-Configuration-Functional | 2 |  | 2
2-Gap-Build-Report | 5 | 1 | 6
6-Gap-Work Around-Work Around | 1 |  | 1
Phase 1B only | 20 |  | 20
1-Fit-Configuration-Functional | 11 |  | 11
2-Gap-Build-Report | 4 |  | 4
3-Gap-Build-Interface | 3 |  | 3
5-Gap-Build-Extension | 1 |  | 1
6-Gap-Work Around-Work Around | 1 |  | 1
Grand Total | 28 | 1 | 29

## WESCO RICE Listing
[24 empty] | Functional Specs | [10 empty] | Technical Design & Build (including TUT) | [8 empty] | Legacy Build
Sr. No. | Business | Release | Product | Sub-Track | Module | RICEW Type | RICEW ID | RICEW Name / Description | Functional Track Lead | Legacy / 3rd Party Build Needed (Y/N)? | Source System | Target System | KDD | Comments / Notes | Approved ? | Object Type | Sprint Cycle | In SOW? | CO # | Complexity | Original Complexity | Frequency | Concatenated String | Functional Spec Delivery Cycle | Functional Spec Author | Process Owner | Product Owner | Functional Spec Start Date | Functional Spec End Date | Process Owner Approval Status | Product Owner Approval Staatus | Functional Spec Status | Functional Spec Acutal Start date | Functional Spec Acutal End date | Tech Des & Bld Delivery Cycle | Tech TUT/FUT Cycle | Tech Des & Bld Author | Tech Des & Bld Start Date | Tech Des & Bld End Date | Tech Des & Bld Status | Tech Des & Bld Acutal Start Date | Tech Des & Bld Acutal End Date | Functional Testing | Legacy Build Delivery Cycle | Legacy Build Author | Legacy Build Start Date | Legacy Build End Date | Legacy Build Status | Legacy Build Acutal Start Date | Legacy Build Actual End Date | Lean Specs Link | Comments | Business Case Grouping | Daily Sync call notes - OSS
1 | ABC Corp | 1a | ERP | RTR-GL | GL | Conversion | CNV001 | GL Open Balances (YTD plus Current Fiscal Year period balances) | Andres | Y | EBS | Oracle ERP Cloud | KDD 7 |  | Yes | Conversion (Using ADFDi and FBDI) |  | Y |  | Complex | Complex |  | Conversion (Using ADFDi and FBDI) - Complex | Sprint 1 | Andres | Erica | Satheesh | 2021-06-07 | 2021-07-09 |  |  | Under Process Owner Review |  |  | Sprint 2 | Sprint 3 | Harshit Gangwar | 2021-06-14 | 2021-07-16 | Not Started |  |  | Not Started | Sprint 2 |  |  |  | Not Started |  |  |  | Dependency on COA mapping to do a full blown TUT/ FUT. |  | 6/30: Waiting for Erica. Satheesh to provide product owner approval today
3 | ABC Corp | 1a | ERP | RTR-AHCS | AHCS | Interface | INT002 | ABC Corp EBS Payables Inbound to AHCS | Manpreet | Y | EBS Payables | Oracle AHCS | KDD 6A | Throwaway interface required until ABC Corp moves AP to cloud from EBS | Yes | Interface - Inbound (Using Middleware) |  | Y |  | Complex | Complex |  | Interface - Inbound (Using Middleware) - Complex | Sprint 1 | Manosh | Erica | Satheesh | 2021-06-14 | 2021-07-09 | Approved | Approved | Under GPO Review |  |  | Sprint 2 | Sprint 3 | Jigyasa | 2021-07-12 | 2021-08-11 | Not Started |  |  | Not Started | Sprint 2 |  |  |  | Not Started | [5 empty] | 6/30: Next meeting on Friday, expect update then
4 | ABC Corp | 1a | ERP | RTR-AHCS | AHCS | Interface | INT004 | ABC Corp EBS Fixed Assets Inbound to AHCS | Manpreet | Y | EBS Fixed Assets | Oracle AHCS | KDD 6A | Throwaway interface required until ABC Corp moves FA to cloud from EBS | Yes | Interface - Inbound (Using Middleware) |  | Y |  | Complex | Complex |  | Interface - Inbound (Using Middleware) - Complex | Sprint 1 | Shubham | Erica | Satheesh | 2021-06-14 | 2021-07-09 | Approved | Approved | Under GPO Review |  |  | Sprint 2 | Sprint 3 | Snehal Shirke | 2021-08-06 | 2021-08-31 | Not Started |  |  | Not Started | Sprint 2 |  |  |  | Not Started | [5 empty] | 6/30: Next meeting on Friday, expect update then
5 | ABC Corp | 1a | ERP | RTR-AHCS | AHCS | Interface | INT005 | ABC Corp EBS Receivables Inbound to AHCS | Manpreet | Y | EBS Receivables | Oracle AHCS | KDD 6A | Throwaway interface required until ABC Corp moves AR to cloud from EBS | Yes | Interface - Inbound (Using Middleware) |  | Y |  | Complex | Complex |  | Interface - Inbound (Using Middleware) - Complex | Sprint 1 | Shubham | Erica | Satheesh | 2021-06-14 | 2021-07-09 | Approved | Approved | Under GPO Review |  |  | Sprint 2 | Sprint 3 | Harman Datta | 2021-07-12 | 2021-08-11 | Not Started |  |  | Not Started | Sprint 2 |  |  |  | Not Started | [5 empty] | 6/30: Next meeting on Friday, expect update then
6 | ABC Corp | 1a | ERP | RTR-GL | GL | Interface | INT007 | GL Data to OnDemand for end user reporting - GL Balances & Daily Journal summary [specific accounts] | Amit | Y | Oracle ERP Cloud | OnDemand | KDD 8 | This is a placeholder and will need further discussion during design to understand if the requirement can be handled with any other tool. - This component is part of KDD8 | Yes | Interface - Outbound (Using BI Report) |  | Y |  | Complex | Complex |  | Interface - Outbound (Using BI Report) - Complex | Sprint 2 | Yuvaraj | Erica | Satheesh | 2021-07-12 | 2021-08-06 |  |  | Not Started |  |  | Sprint 3 | Sprint 3 |  | 2021-08-09 | 2021-08-31 | Not Started |  |  | Not Started | Sprint 3 |  |  |  | Not Started
8 | ABC Corp | 1a | ERP | RTR-AHCS | AHCS | Interface | INT033 | Central Inbound to AHCS - GL Actuals (Inventory/COGS) cs_nightly_feed (Daily feed for sales and cost of goods sold entries.) | Manpreet | Y | Central System | Oracle AHCS | KDD 25 |  | Yes | Interface - Inbound (Using Middleware) |  | N |  | Complex | Complex |  | Interface - Inbound (Using Middleware) - Complex | Sprint 2 | Avinash | Erica | Satheesh | 2021-07-12 | 2021-08-06 |  |  | Not Started |  |  | Sprint 2 | Sprint 3 | Jigyasa | 2021-08-12 | 2021-09-03 | Not Started |  |  | Not Started
9 | ABC Corp | 1a | ERP | RTR-AHCS | AHCS | Interface | INT034 | Central Inbound to AHCS - GL Statistical (MFC Stock) cs_in3912_mfc_37_STAT (Statistical feed for finance charge data for Stock items.) | Manpreet | Y | Central System | Oracle AHCS | KDD 25 |  | Yes | Interface - Inbound (Using Middleware) |  | N |  | Complex | Complex |  | Interface - Inbound (Using Middleware) - Complex | Sprint 2 | Avinash | Erica | Satheesh | 2021-07-12 | 2021-08-06 |  |  | Not Started |  |  | Sprint 2 | Sprint 3 | Harman Datta | 2021-08-12 | 2021-09-03 | Not Started |  |  | Not Started
10 | ABC Corp | 1a | ERP | RTR-AHCS | AHCS | Interface | INT035 | Central Inbound to AHCS - GL Statistical (MFC SO/DS) cs_in0140_mfc_37_STAT (Statistical feed for finance charge data for SO/DS items.) | Manpreet | Y | Central System | Oracle AHCS | KDD 25 |  | Yes | Interface - Inbound (Using Middleware) |  | N |  | Complex | Complex |  | Interface - Inbound (Using Middleware) - Complex | Sprint 2 | Avinash | Erica | Satheesh | 2021-07-12 | 2021-08-06 |  |  | Not Started |  |  | Sprint 2 | Sprint 3 | TBD1 | 2021-08-09 | 2021-09-03 | Not Started |  |  | Not Started
11 | ABC Corp | 1a | ERP | RTR-AHCS | AHCS | Interface | INT036 | Central Inbound to AHCS - GL Statistical (MFC ) cs_cos_mfc_48-49-50_STAT (Monthly finance charge - statistical accounts feed.) | Manpreet | Y | Central System | Oracle AHCS | KDD 25 |  | Yes | Interface - Inbound (Using Middleware) |  | N |  | Complex | Complex |  | Interface - Inbound (Using Middleware) - Complex | Sprint 2 | Avinash | Erica | Satheesh | 2021-07-12 | 2021-08-06 |  |  | Not Started |  |  | Sprint 2 | Sprint 3 | TBD2 | 2021-08-09 | 2021-09-03 | Not Started |  |  | Not Started
12 | ABC Corp | 1a | ERP | RTR-AHCS | AHCS | Interface | INT037 | Central Inbound to AHCS - GL Statistical (Missing Inventory) cs_on_order_inventory_mis_STAT (Feed for counts of inventory items that are on order.) | Manpreet | Y | Central System | Oracle AHCS | KDD 25 |  | Yes | Interface - Inbound (Using Middleware) |  | N |  | Complex | Complex |  | Interface - Inbound (Using Middleware) - Complex | Sprint 2 | Avinash | Erica | Satheesh | 2021-07-12 | 2021-08-06 |  |  | Not Started |  |  | Sprint 2 | Sprint 3 | TBD3 | 2021-08-09 | 2021-09-03 | Not Started |  |  | Not Started
13 | ABC Corp | 1a | ERP | RTR-AHCS | AHCS | Interface | INT038 | Central Inbound to AHCS - GL Actuals (Sales Comission & Accruals) cs_monthly_sales_inactive (This contains journal entries from sales commission processing and sales accruals.) | Manpreet | Y | Central System | Oracle AHCS | KDD 25 |  | Yes | Interface - Inbound (Using Middleware) |  | N |  | Complex | Complex |  | Interface - Inbound (Using Middleware) - Complex | Sprint 2 | Avinash | Erica | Satheesh | 2021-07-12 | 2021-08-06 |  |  | Not Started |  |  | Sprint 3 | Sprint 3 |  | 2021-08-09 | 2021-09-03 | Not Started |  |  | Not Started
14 | ABC Corp | 1a | ERP | RTR-GL | GL | Interface | INT040 | GL to Central Outbound Balances en_consol_gl (Oracle GL Account Conversion to Central System Account) | Amit | Y | Oracle GL | Central System | KDD 25 | 6/3 - VL : discussed with Abhijit - need to understand the volume and current soln if file based i/f is required or can leverage the WS(low volume) | Yes | Interface - Outbound (Using BI Report) |  | N |  | Very Complex | Complex |  | Interface - Outbound (Using BI Report) - Very Complex | Sprint 2 | Gaurav | Erica | Satheesh | 2021-07-12 | 2021-08-06 |  |  | Not Started |  |  | Sprint 3 | Sprint 3 | Girish Acharya | 2021-08-09 | 2021-09-03 | Not Started |  |  | Not Started | [8 empty] | Complexity increased to Very Complex new requirement was to perform a reverse mapping from New COA to Old COA
15 | ABC Corp | 1a | ERP | RTR-GL | GL | Interface | INT010 | GL Data to TeraData for reporting - GL Balances | Badar | Y | Oracle ERP Cloud | TeraData | KDD 8 | This Component is part of KDD8 | Yes | Interface - Outbound (Using BI Report) |  | Y |  | Medium | Medium |  | Interface - Outbound (Using BI Report) - Medium | Sprint 1 | Badar | Erica | Satheesh | 2021-06-14 | 2021-07-09 |  |  | Under Process Owner Review |  |  | Sprint 2 | Sprint 2 | Harshit Gangwar | 2021-07-12 | 2021-07-31 | Not Started |  |  | Not Started | Sprint 2 | [9 empty] | 6/30: Amit to send for approval today
16 | ABC Corp | 1a | ERP | RTR-GL | GL | Interface | INT011 | GL Data to TeraData for reporting - GL Journals | Yuvraj | Y | Oracle ERP Cloud | TeraData | KDD 8 | PlaceHolder to cater to different data being sent to TeraData for reporting - This Component is part of KDD8 | Yes | Interface - Outbound (Using BI Report) |  | Y |  | Medium | Medium |  | Interface - Outbound (Using BI Report) - Medium | Sprint 1 | Yuvaraj | Erica | Satheesh | 2021-06-14 | 2021-07-09 | Approved | Approved | Under GPO Review |  |  | Sprint 2 | Sprint 2 | Devang Pandya | 2021-07-31 | 2021-08-06 | Not Started |  |  | Not Started | Sprint 2 | [9 empty] | 6/30: Updates to be made to specs - Amit to send for approval today: 1. Created by 2. Include journal id of original journal that it reversed 3. Approval Required Yes/No 4. COA Order 5. Length of COA segments
17 | ABC Corp | 1a | ERP | RTR-AHCS | AHCS | Interface | INT012 | AHCS Data to TeraData - AHCS Details | Viji | Y | Oracle AHCS | TeraData | KDD 8 | Updated the complexity to "Complex" from "Medium" because of the inclusion of AHCS as a Source Data. Data Model of AHCS is complex. - This Component is part of KDD8 | Yes | Interface - Outbound (Using BI Report) |  | Y |  | Complex | Medium |  | Interface - Outbound (Using BI Report) - Complex | Sprint 2 | Shubham | Erica | Satheesh | 2021-07-12 | 2021-08-06 |  |  | Not Started |  |  | Sprint 4 | Sprint 4 | TBD1 | 2021-09-06 | 2021-09-24 | Not Started |  |  | Not Started | Sprint 2
18 | ABC Corp | 1a | ERP | RTR-GL | GL | Report | RPT001 | COA Value extract report | Viji | [5 empty] | Yes | Report (BI Publisher) |  | Y |  | Medium | Complex |  | Report (BI Publisher) - Medium | Sprint 4 | [7 empty] | Not Started |  |  | Sprint 5 | Sprint 5 |  |  |  | Not Started |  |  | Not Started |  |  |  |  | Not Applicable |  |  |  | P3
19 | ABC Corp | 1a | ERP | RTR-GL | GL | Report | RPT002 | Journal Batch + Journal Header Report | Amit | [5 empty] | Yes | Report (BI Publisher) |  | Y |  | Medium | Complex |  | Report (BI Publisher) - Medium | Sprint 2 | Badar | Erica | Satheesh |  |  |  |  | Not Started |  |  | Sprint 4 | Sprint 4 | Snehal Shirke |  |  | Not Started |  |  | Not Started |  |  |  |  | Not Applicable |  |  |  | P0
20 | ABC Corp | 1a | ERP | RTR-GL | GL | Report | RPT003 | Details of unposted journals including details available in Action Log | Viji | [5 empty] | Yes | Report (BI Publisher) |  | Y |  | Medium | Medium |  | Report (BI Publisher) - Medium | Sprint 3 | [7 empty] | Not Started |  |  | Sprint 4 | Sprint 4 | TBD2 |  |  | Not Started |  |  | Not Started |  |  |  |  | Not Applicable |  |  |  | P1
21 | ABC Corp | 1a | ERP | RTR-GL | GL | Report | RPT004 | GL Journal notification update | Amit |  |  |  |  | Abhijit / Devang - Need to check whether Notification template can be modified or not | Yes | Report (BI Publisher) |  | Y |  | Medium | Medium |  | Report (BI Publisher) - Medium | Sprint 2 | Andres | Erica | Satheesh |  |  |  |  | Not Started |  |  | Sprint 4 | Sprint 4 | Mamatha Tata |  |  | Not Started |  |  | Not Started |  |  |  |  | Not Applicable |  |  |  | P0
22 | ABC Corp | 1a | ERP | RTR-GL | GL | Report | RPT005 | Journal Approval report for audit compliance | Viji | [5 empty] | Yes | Report (BI Publisher) |  | Y |  | Medium | Medium |  | Report (BI Publisher) - Medium | Sprint 3 | [7 empty] | Not Started |  |  | Sprint 4 | Sprint 4 | TBD3 |  |  | Not Started |  |  | Not Started |  |  |  |  | Not Applicable |  |  |  | P1
23 | ABC Corp | 1a | ERP | RTR-AHCS | AHCS | Report | RPT006 | AHCS Error Report | Manpreet | N | N/A |  |  |  | Yes | Report (BI Publisher) |  | Y |  | Complex | Complex |  | Report (BI Publisher) - Complex | Sprint 1 | Vishnu | Erica | Satheesh | 2021-06-14 | 2021-07-09 |  |  | Under Process Owner Review |  |  | Sprint 2 | Sprint 3 | Girish Acharya | 2021-07-12 | 2021-08-06 | Not Started |  |  | Not Started |  |  |  |  | Not Applicable |  |  |  | P0 This will cover the functionality of the report. Other features such as testing this with AHCS integrations must be tested in Sprint 3 |  | 6/30: Satheesh to approve but waiting on Erica
24 | ABC Corp | 1a | ERP | RTR-AHCS | AHCS | Report | RPT007 | AHCS to GL Reconciliation Report | Manpreet | N | N/A |  |  |  | Yes | Report (BI Publisher) |  | Y |  | Complex | Complex |  | Report (BI Publisher) - Complex | Sprint 3 | Manosh |  |  | 2021-08-08 | 2021-09-03 |  |  | Not Started |  |  | Sprint 4 | Sprint 4 | TBD4 | 2021-09-06 | 2021-09-24 | Not Started |  |  | Not Started |  |  |  |  | Not Applicable |  |  |  | P1
25 | ABC Corp | 1a | ERP | RTR-AHCS | AHCS | Report | RPT008 | Subledger Period Close Exception Report by Ledger Set | Manpreet |  |  |  |  | Assuming that this will involve the copying the seeded report query and layout to accommodate the ledger wise grouping & summary. We may also require to implement data security in the report. | Yes | Report (BI Publisher) |  | Y |  | Complex | Medium |  | Report (BI Publisher) - Complex | Sprint 3 | Shubham |  |  | 2021-08-08 | 2021-09-03 |  |  | Not Started |  |  | Sprint 4 | Sprint 4 | Dhrumil | 2021-09-06 | 2021-09-24 | Not Started |  |  | Not Started |  |  |  |  | Not Applicable |  |  |  | P0
26 | ABC Corp | 1a | ERP | RTR-AHCS | AHCS | Report | RPT009 | Subledger Account Analysis Report | Manpreet | [5 empty] | Yes | Report (BI Publisher) |  | Y |  | Medium | Medium |  | Report (BI Publisher) - Medium | Sprint 2 | Vishnu | Erica | Satheesh | 2021-08-08 | 2021-09-03 |  |  | Not Started |  |  | Sprint 4 | Sprint 4 | Girish Acharya | 2021-09-06 | 2021-09-24 | Not Started |  |  | Not Started |  |  |  |  | Not Applicable |  |  |  | P0
27 | ABC Corp | 1b | ERP | RTR-GL | GL | Report | RPT011 | Confirm relevant manual journals copied to secondary | Viji |  |  |  |  | Abhijit - Devang - How to recognize if the secondary ledger balances has been copied from primary ledger ?? | Yes | Report (BI Publisher) |  | Y |  |  | Complex |  | Report (BI Publisher) - | [8 empty] | Not Started |  |  | Sprint 5 |  |  |  |  | Not Started |  |  | Not Started |  |  |  |  | Not Applicable
28 | ABC Corp | 1b | ERP | RTR-GL | GL | Conversion | CNV003 | GL Open Balances (YTD plus Current Fiscal Year period balances) - Secondary Ledger |  | Y | Fusion FAH | Oracle ERP Cloud |  | 6/3 VL : ABC Corp | Yes | Conversion (Using ADFDi and FBDI) |  | Y |  | Complex | Medium |  | Conversion (Using ADFDi and FBDI) - Complex | [8 empty] | Not Started | [7 empty] | Not Started |  |  | Not Started
29 | ABC Corp | 1b | ERP | RTR-GL | GL | Conversion | CNV004 | GL Open Balances (YTD plus Current Fiscal Year period balances) - Primary Ledger |  | Y | PeopleSoft | Oracle ERP Cloud |  | 6/3 VL : ABC Corp | Yes | Conversion (Using ADFDi and FBDI) |  | Y |  | Complex | Complex |  | Conversion (Using ADFDi and FBDI) - Complex | [8 empty] | Not Started | [7 empty] | Not Started |  |  | Not Started
30 | ABC Corp | 1b | ERP | RTR-GL | GL | Interface | INT015 | GL to Concur - COA interface |  | Y | Oracle AHCS | Concur |  | Retro Fit, Need to check if we can have EPM push it to Concur rather than ERP Cloud |  | Interface - Outbound (Using BI Report) |  | Y |  | Medium | Very complex |  | Interface - Outbound (Using BI Report) - Medium | [8 empty] | Not Started | [7 empty] | Not Started |  |  | Not Started
31 | ABC Corp | 1a | ERP | RTR-AHCS | AHCS | Interface | INT016 | Concur Inbound to AHCS | Manpreet | Y | Concur | Oracle AHCS | KDD 10A | Retro Fit, Need to check if we code change needed to handle multiple files for different regions or we will receive a single file |  | Interface - Inbound (Using Middleware) |  |  |  | Complex | Very complex |  | Interface - Inbound (Using Middleware) - Complex | Sprint 3 | Manosh |  |  | 2021-08-08 | 2021-09-03 |  |  | Not Started |  |  | Sprint 4 | Sprint 4 | Jigyasa | 2021-09-06 | 2021-09-24 | Not Started |  |  | Not Started
32 | ABC Corp | 1b | ERP | RTR-AHCS | AHCS | Interface | INT125 | Journal Import - Concur | Manpreet | Y | Concur | Oracle AHCS |  | Retro Fit, Need to check if we code change needed to handle multiple files for different regions or we will receive a single file |  | Interface - Inbound (Using Middleware) |  | Y |  | Medium | Complex |  | Interface - Inbound (Using Middleware) - Medium | [8 empty] | Not Started | [7 empty] | Not Started |  |  | Not Started
33 | ABC Corp | 1b | ERP | RTR-AHCS | AHCS | Interface | INT017 | Journal Import - Payroll (ADP) When going live, it can include ABC Corp also in addition to ADP | Manpreet | Y | ADP | Oracle AHCS |  | New and retrofit. US and 1 country in EMEA. |  | Interface - Inbound (Using Middleware) |  | Y |  | Medium | Very complex |  | Interface - Inbound (Using Middleware) - Medium | [8 empty] | Not Started | [7 empty] | Not Started |  |  | Not Started
34 | ABC Corp | 1b | ERP | RTR-AHCS | AHCS | Interface | INT018 | Journal Import - Payroll (CloudPay) | Manpreet | Y | CloudPay | Oracle AHCS |  | For UK only |  | Interface - Inbound (Using Middleware) |  | Y |  | Complex | Complex |  | Interface - Inbound (Using Middleware) - Complex | [8 empty] | Not Started | [7 empty] | Not Started |  |  | Not Started
35 | ABC Corp | 1b | ERP | RTR-AHCS | AHCS | Interface | INT019 | Journal Import - PCard transaction | Manpreet | Y | Pcard Transaction | Oracle AHCS |  | Need to check if we need for other Payroll applications |  | Interface - Inbound (Using Middleware) |  | Y |  | Complex | Complex |  | Interface - Inbound (Using Middleware) - Complex | [8 empty] | Not Started | [7 empty] | Not Started |  |  | Not Started
36 | ABC Corp | 1b | ERP | RTR-AHCS | AHCS | Interface | INT020 | Journal Import - Lease Harbor | Manpreet | Y | Lease Harbor | Oracle AHCS |  | Retro-Fit changes may be needed on what was built for Step 1.0 |  | Interface - Inbound (Using Middleware) |  | Y |  | Complex | Complex |  | Interface - Inbound (Using Middleware) - Complex | [8 empty] | Not Started | [7 empty] | Not Started |  |  | Not Started
37 | ABC Corp | 1b | ERP | RTR-GL | GL | Interface | INT021 | GL Data to IAP - Journals |  | Y | Oracle ERP Cloud | IAP | KDD 8 | This Component is part of KDD8 - Layout for IAP is same as the TeraData & can be re-used | Yes | Interface - Outbound (Using BI Report) |  | Y |  | Medium | Medium |  | Interface - Outbound (Using BI Report) - Medium | [5 empty] | 2021-10-01 |  |  | Not Started | [7 empty] | Not Started |  |  | Not Started
38 | ABC Corp | 1b | ERP | RTR-AHCS | AHCS | Interface | INT022 | Intercompany accounting Europe - Belgium Co-ordination Center (BCC) | Manpreet | Y | Belgium Co-ordination Center (BCC) | Oracle AHCS |  | Anticipating an integration to generate accounting entries for the Belgium entity, and then clearing them through elimination entries. |  | Interface - Inbound (Using Middleware) |  | Y |  | Very Complex | Medium |  | Interface - Inbound (Using Middleware) - Very Complex | [8 empty] | Not Started | [7 empty] | Not Started |  |  | Not Started
39 | ABC Corp | 1b | ERP | RTR-AHCS | AHCS | Interface | INT023 | GL Feed from FAH to AHCS | Manpreet | Y | FAH Fusion | Oracle AHCS |  |  |  | Interface - Inbound (Using Middleware) |  | Y |  | Complex | Medium |  | Interface - Inbound (Using Middleware) - Complex | [8 empty] | Not Started | [7 empty] | Not Started |  |  | Not Started
40 | ABC Corp | 1b | ERP | RTR-GL | GL | Interface | INT024 | GL Data from Rubicon (Legacy ERP) |  | Y | Rubicon | Oracle ERP Cloud |  |  |  | Interface - Inbound (Using Middleware) |  | Y |  | Complex | Medium |  | Interface - Inbound (Using Middleware) - Complex | [8 empty] | Not Started | [7 empty] | Not Started |  |  | Not Started
41 | ABC Corp | 1b | ERP | RTR-GL | GL | Interface | INT026 | Outbound to Essbase for ABC Corp Reporting (multiple entities) |  |  | Oracle ERP Cloud | Essbase |  | If there are multiple entities going beyond 180 hours then additional interface needs to be factores in |  | Interface - Outbound (Using BI Report) |  | Y |  | Medium | Medium |  | Interface - Outbound (Using BI Report) - Medium | [8 empty] | Not Started | [7 empty] | Not Started |  |  | Not Started |  |  |  |  | Not Applicable
42 | ABC Corp | 1b | ERP | RTR-AHCS | AHCS | Interface | INT027 | GL Feed from Fusion FAH to AHCS | Manpreet | Y | FAH Fusion | Oracle AHCS |  |  |  | Interface - Inbound (Using Middleware) |  | Y |  | Complex | Medium |  | Interface - Inbound (Using Middleware) - Complex | [8 empty] | Not Started | [7 empty] | Not Started |  |  | Not Started
43 | ABC Corp | 1b | ERP | RTR-AHCS | AHCS | Interface | INT028 | AP Feed from FAH to AHCS | Manpreet | Y | FAH Fusion | Oracle AHCS |  |  |  | Interface - Inbound (Using Middleware) |  | Y |  | Very Complex | Complex |  | Interface - Inbound (Using Middleware) - Very Complex | [8 empty] | Not Started | [7 empty] | Not Started |  |  | Not Started
44 | ABC Corp | 1b | ERP | RTR-AHCS | AHCS | Interface | INT029 | AR Feed from FAH to AHCS | Manpreet | Y | FAH Fusion | Oracle AHCS |  |  |  | Interface - Inbound (Using Middleware) |  | Y |  | Very Complex |  |  | Interface - Inbound (Using Middleware) - Very Complex | [8 empty] | Not Started | [7 empty] | Not Started |  |  | Not Started
45 | ABC Corp | 1b | ERP | RTR-AHCS | AHCS | Interface | INT030 | Inventory Feed from FAH to AHCS | Manpreet | Y | FAH Fusion | Oracle AHCS |  |  |  | Interface - Inbound (Using Middleware) |  | Y |  | Complex |  |  | Interface - Inbound (Using Middleware) - Complex | [8 empty] | Not Started | [7 empty] | Not Started |  |  | Not Started
46 | ABC Corp | 1b | ERP | RTR-AHCS | AHCS | Interface | INT031 | CM Feed from FAH to AHCS | Manpreet | Y | FAH Fusion | Oracle AHCS |  |  |  | Interface - Inbound (Using Middleware) |  | Y |  | Complex |  |  | Interface - Inbound (Using Middleware) - Complex | [8 empty] | Not Started | [7 empty] | Not Started |  |  | Not Started
47 | ABC Corp | 1b | ERP | RTR-AHCS | AHCS | Interface | INT032 | Additional Data Models from FAH to AHCS | Manpreet | Y | FAH Fusion | Oracle AHCS |  |  |  | Interface - Inbound (Using Middleware) |  | Y |  | Medium |  |  | Interface - Inbound (Using Middleware) - Medium | [8 empty] | Not Started | [7 empty] | Not Started |  |  | Not Started
48 | ABC Corp | 1b | ERP | RTR-GL | GL | Report | RPT016 | Flag incorrect exchange rates on Journal report | [7 empty] | Report (BI Publisher) |  | Y |  | Medium |  |  | Report (BI Publisher) - Medium | [8 empty] | Not Started | [7 empty] | Not Started |  |  | Not Started |  |  |  |  | Not Applicable
49 | ABC Corp | 1b | ERP | RTR-GL | GL | Report | RPT017 | ABC Corp GL Report # 2 | [7 empty] | Report (BI Publisher) |  | Y |  | Complex |  |  | Report (BI Publisher) - Complex | TBD | [7 empty] | Not Started | [7 empty] | Not Started |  |  | Not Started |  |  |  |  | Not Applicable
50 | ABC Corp | 1b | ERP | RTR-GL | GL | Report | RPT018 | ABC Corp GL Report # 3 | [7 empty] | Report (BI Publisher) |  | Y |  | Medium |  |  | Report (BI Publisher) - Medium | TBD | [7 empty] | Not Started | [7 empty] | Not Started |  |  | Not Started |  |  |  |  | Not Applicable
51 | ABC Corp | 1b | ERP | RTR-GL | GL | Report | RPT019 | ABC Corp GL Report # 4 | [7 empty] | Report (BI Publisher) |  | Y |  | Medium |  |  | Report (BI Publisher) - Medium | TBD | [7 empty] | Not Started | [7 empty] | Not Started |  |  | Not Started |  |  |  |  | Not Applicable
52 | ABC Corp | 1b | ERP | RTR-GL | GL | Report | RPT020 | ABC Corp GL Report # 5 | [7 empty] | Report (BI Publisher) |  | Y |  | Medium |  |  | Report (BI Publisher) - Medium | TBD | [7 empty] | Not Started | [7 empty] | Not Started |  |  | Not Started |  |  |  |  | Not Applicable
53 | ABC Corp | 1b | ERP | RTR-AHCS | AHCS | Report | RPT021 | ABC Corp FAH Report # 1 | Manpreet | [6 empty] | Report (BI Publisher) |  | Y |  | Simple |  |  | Report (BI Publisher) - Simple | [8 empty] | Not Started | [7 empty] | Not Started |  |  | Not Started |  |  |  |  | Not Applicable
54 | ABC Corp | 1b | ERP | RTR-AHCS | AHCS | Report | RPT022 | ABC Corp FAH Report # 2 | Manpreet | [6 empty] | Report (BI Publisher) |  | Y |  | Complex |  |  | Report (BI Publisher) - Complex | [8 empty] | Not Started | [7 empty] | Not Started |  |  | Not Started |  |  |  |  | Not Applicable
55 | ABC Corp | 1b | ERP | RTR-AHCS | AHCS | Report | RPT023 | ABC Corp FAH Report # 3 | Manpreet | [6 empty] | Report (BI Publisher) |  | Y |  | Medium |  |  | Report (BI Publisher) - Medium | [8 empty] | Not Started | [7 empty] | Not Started |  |  | Not Started |  |  |  |  | Not Applicable
56 | ABC Corp | 1b | ERP | RTR-AHCS | AHCS | Report | RPT024 | ABC Corp FAH Report # 4 | Manpreet | [6 empty] | Report (BI Publisher) |  | Y |  | Medium |  |  | Report (BI Publisher) - Medium | [8 empty] | Not Started | [7 empty] | Not Started |  |  | Not Started |  |  |  |  | Not Applicable
57 | ABC Corp | 1b | ERP | RTR-AHCS | AHCS | Report | RPT025 | ABC Corp FAH Report # 5 | Manpreet | [6 empty] | Report (BI Publisher) |  | Y |  | Simple |  |  | Report (BI Publisher) - Simple | [8 empty] | Not Started | [7 empty] | Not Started |  |  | Not Started |  |  |  |  | Not Applicable
58 | ABC Corp | 1b | ERP | RTR-GL | GL | Report | RPT026 | France FEC Report | [5 empty] | Abhijit - Devang - Need to check the standard report availability |  | Report (BI Publisher) |  | Y |  |  |  |  | Report (BI Publisher) - | [5 empty] | 2021-10-01 |  |  | Not Started | [7 empty] | Not Started |  |  | Not Started |  |  |  |  | Not Applicable
59 | ABC Corp | 1b | ERP | RTR-GL | GL | Report | RPT027 | ABC Corp Report Localization Place Holder # 2 | [7 empty] | Report (BI Publisher) |  | Y |  | Medium |  |  | Report (BI Publisher) - Medium | TBD | [7 empty] | Not Started | [7 empty] | Not Started |  |  | Not Started |  |  |  |  | Not Applicable
60 | ABC Corp | 1b | ERP | RTR-GL | GL | Report | RPT028 | ABC Corp Report Localization Place Holder # 3 | [7 empty] | Report (BI Publisher) |  | Y |  | Medium |  |  | Report (BI Publisher) - Medium | TBD | [7 empty] | Not Started | [7 empty] | Not Started |  |  | Not Started |  |  |  |  | Not Applicable
61 | ABC Corp | 1b | ERP | RTR-GL | GL | Report | RPT029 | ABC Corp Report Localization Place Holder # 4 | [7 empty] | Report (BI Publisher) |  | Y |  | Medium |  |  | Report (BI Publisher) - Medium | TBD | [7 empty] | Not Started | [7 empty] | Not Started |  |  | Not Started |  |  |  |  | Not Applicable
62 | ABC Corp | 1b | ERP | RTR-GL | GL | Report | RPT030 | ABC Corp Report Localization Place Holder # 5 | [7 empty] | Report (BI Publisher) |  | Y |  | Simple |  |  | Report (BI Publisher) - Simple | TBD | [7 empty] | Not Started | [7 empty] | Not Started |  |  | Not Started |  |  |  |  | Not Applicable
63 | ABC Corp | 1b | ERP | RTR-GL | GL | Report | RPT031 | ABC Corp Report Localization Place Holder # 6 | [7 empty] | Report (BI Publisher) |  | Y |  | Medium |  |  | Report (BI Publisher) - Medium | TBD | [7 empty] | Not Started | [7 empty] | Not Started |  |  | Not Started |  |  |  |  | Not Applicable
64 | ABC Corp | 1b | ERP | RTR-GL | GL | Report | RPT032 | ABC Corp Report Localization Place Holder # 7 | [7 empty] | Report (BI Publisher) |  | Y |  | Medium |  |  | Report (BI Publisher) - Medium | TBD | [7 empty] | Not Started | [7 empty] | Not Started |  |  | Not Started |  |  |  |  | Not Applicable
65 | ABC Corp | 1b | ERP | RTR-GL | GL | Report | RPT033 | ABC Corp Report Localization Place Holder # 8 | [7 empty] | Report (BI Publisher) |  | Y |  | Complex |  |  | Report (BI Publisher) - Complex | TBD | [7 empty] | Not Started | [7 empty] | Not Started |  |  | Not Started |  |  |  |  | Not Applicable
66 | ABC Corp | 1b | ERP | RTR-GL | GL | Report | RPT034 | ABC Corp Report Localization Place Holder # 9 | [7 empty] | Report (BI Publisher) |  | Y |  | Complex |  |  | Report (BI Publisher) - Complex | TBD | [7 empty] | Not Started | [7 empty] | Not Started |  |  | Not Started |  |  |  |  | Not Applicable
67 | ABC Corp | 1b | ERP | RTR-GL | GL | Report | RPT035 | ABC Corp Report Localization Place Holder # 10 | [7 empty] | Report (BI Publisher) |  | Y |  | Very Complex |  |  | Report (BI Publisher) - Very Complex | TBD | [7 empty] | Not Started | [7 empty] | Not Started |  |  | Not Started |  |  |  |  | Not Applicable
68 | ABC Corp | 1b | ERP | RTR-GL | GL | Report | RPT036 | ABC Corp I/C AR Invoice Presentment Place Holder | [7 empty] | Report (BI Publisher) |  | Y |  | Very Complex |  |  | Report (BI Publisher) - Very Complex | TBD | [7 empty] | Not Started | [7 empty] | Not Started |  |  | Not Started |  |  |  |  | Not Applicable
69 | ABC Corp | 1b | ERP | RTR-GL | GL | Report | RPT037 | ABC Corp I/C AP Invoice Presentment Place Holder | [7 empty] | Report (BI Publisher) |  | Y |  | Complex |  |  | Report (BI Publisher) - Complex | TBD | [7 empty] | Not Started | [7 empty] | Not Started |  |  | Not Started |  |  |  |  | Not Applicable
70 | ABC Corp | 1b | ERP | RTR-AHCS | AHCS | Conversion | CNV005 | Payable Open Invoice, Intercompany, Unvouchered | Manpreet | Y | ABC Corp-FAH legacy | Oracle ERP Cloud |  |  |  | Conversion using FAH |  | Y |  | Very Complex |  |  | Conversion using FAH - Very Complex | [8 empty] | Not Started | [7 empty] | Not Started |  |  | Not Started
71 | ABC Corp | 1b | ERP | RTR-AHCS | AHCS | Conversion | CNV006 | GL (Other) Subledger | Manpreet | Y | ABC Corp-FAH legacy | Oracle ERP Cloud |  |  |  | Conversion using FAH |  | Y |  | Complex |  |  | Conversion using FAH - Complex | [8 empty] | Not Started | [7 empty] | Not Started |  |  | Not Started
72 | ABC Corp | 1b | ERP | RTR-AHCS | AHCS | Conversion | CNV007 | Open AR Invoices, Intercompany, Unvouchered | Manpreet | Y | ABC Corp-FAH legacy | Oracle ERP Cloud |  |  |  | Conversion using FAH |  | Y |  | Complex |  |  | Conversion using FAH - Complex | [8 empty] | Not Started | [7 empty] | Not Started |  |  | Not Started
73 | ABC Corp | 1b | ERP | RTR-AHCS | AHCS | Conversion | CNV008 | Inventory (Stock Balances), Unvouchered | Manpreet | Y | ABC Corp-FAH legacy | Oracle ERP Cloud |  |  |  | Conversion using FAH |  | Y |  | Medium |  |  | Conversion using FAH - Medium | [8 empty] | Not Started | [7 empty] | Not Started |  |  | Not Started
74 | ABC Corp | 1b | ERP | RTR-AHCS | AHCS | Conversion | CNV009 | Bank Balance | Manpreet | Y | ABC Corp-FAH legacy | Oracle ERP Cloud |  |  |  | Conversion using FAH |  | Y |  | Medium |  |  | Conversion using FAH - Medium | [8 empty] | Not Started | [7 empty] | Not Started |  |  | Not Started
75 | ABC Corp | 1b | ERP | RTR-AHCS | AHCS | Report | RPT038 | Unaccounted FAH error report (Common) | Manpreet |  |  | Oracle ERP Cloud |  |  |  | Conversion - Recon Report |  | Y |  | Medium |  |  | Conversion - Recon Report - Medium | [8 empty] | Not Started | [7 empty] | Not Started |  |  | Not Started |  |  |  |  | Not Applicable
76 | ABC Corp | 1b | ERP |  |  | Report | RPT039 | Extracts of double accounted transactions for reversal |  |  |  | Oracle ERP Cloud |  |  |  | Conversion - Recon Report |  | Y |  | Complex |  |  | Conversion - Recon Report - Complex | [8 empty] | Not Started | [7 empty] | Not Started |  |  | Not Started |  |  |  |  | Not Applicable
77 | ABC Corp | 1b | ERP | RTR-GL | GL | Conversion | CNV010 | GL Open Balances (YTD plus Current Fiscal Year period balances) - Reporting Ledgers (Extraction & Conversion Required) |  | Y | PeopleSoft | Oracle ERP Cloud |  |  |  | Conversion (Using ADFDi and FBDI) |  | N |  | Medium |  |  | Conversion (Using ADFDi and FBDI) - Medium | [8 empty] | Not Started |  |  | Sprint 2 |  |  |  |  | Not Started |  |  | Not Started
78 | Common | 1a + 1b | ERP | RTR-GL | GL | Extension | EXT001 | COA Mapping - COA Mapping Service | Gaurav |  |  |  |  | Mapping service invoked in OIC by AHCS integrations with legacy COA and system as input to provide future state COA. This will invoke relevant mapping engine and return futre state COA |  | PaaS Extension |  | N |  | Complex |  |  | PaaS Extension - Complex | Sprint 1 | Omkar | Elizabeth | Satheesh | 2021-06-14 | 2021-07-09 | Approved | Approved | Under GPO Review |  |  | Sprint 2 | Sprint 2 | Dhrumil | 2021-07-12 | 2021-07-30 | Not Started |  |  | Not Started |  |  |  |  | Not Applicable |  |  |  |  | COA Mapping Engine
79 | Common | 1a + 1b | ERP | RTR-GL | GL | Extension | EXT002 | COA Mapping - Mapping Engine | Gaurav |  |  |  |  | This Global COA Mapping engine will be invoked by COA Mapping Service in OIC. This engine will do rule based mapped & return future state COA to Mapping Service |  | PaaS Extension |  | N |  | Very Complex |  |  | PaaS Extension - Very Complex | Sprint 1 | Omkar | Elizabeth | Satheesh | 2021-06-14 | 2021-07-09 | Approved | Approved | Under GPO Review |  |  | Sprint 2 | Sprint 2 | Devang Pandya | 2021-07-12 | 2021-07-30 | Not Started |  |  | Not Started |  |  |  |  | Not Applicable |  |  |  |  | COA Mapping Engine
80 | Common | 1b | ERP | RTR-GL | GL | Extension | EXT003 | COA Mapping - Validation Engine - France Local COA | Gaurav |  |  |  |  | This France COA Mapping engine will be invoked by COA Mapping Service in OIC. This engine will do rule based mapped & return future state COA to Mapping Service |  | PaaS Extension |  | N |  | Very Complex |  |  | PaaS Extension - Very Complex | [11 empty] | Sprint 2 |  |  |  |  | Not Started |  |  | Not Started |  |  |  |  | Not Applicable |  |  |  |  | COA Mapping Engine
81 | Common | 1a + 1b | ERP | RTR-GL | GL | Interface | INT120 | COA Mapping - Mapping Report | Gaurav |  | Oracle DB (PaaS) | sFTP |  | Extract of current state COA mappings in mapping engine |  | Interface - Outbound (Using BI Report) |  | N |  | Complex |  |  | Interface - Outbound (Using BI Report) - Complex | Sprint 1 | Omkar | Elizabeth | Satheesh | 2021-06-14 | 2021-07-09 | Approved |  | Under Process Owner Review |  |  | Sprint 2 | Sprint 2 | Manasi Jain | 2021-07-12 | 2021-08-02 | Not Started |  |  | Not Started |  |  |  |  | Not Applicable |  |  |  |  | COA Mapping - Reporting
82 | Common | 1a + 1b | ERP | RTR-GL | GL | Interface | INT121 | COA Mapping - Oracle COA value import for Validations | Gaurav | N | Oracle ERP Cloud | Oracle DB (PaaS) |  | Integration to import Oracle COA values for target segment validation |  | Interface - Inbound (Using Middleware) |  | N |  | Complex |  |  | Interface - Inbound (Using Middleware) - Complex | Sprint 1 | Omkar | Elizabeth | Satheesh | 2021-06-14 | 2021-07-09 | Approved |  | Under Process Owner Review |  |  | Sprint 2 | Sprint 2 | Mamatha Tata | 2021-07-12 | 2021-08-02 | Not Started |  |  | Not Started |  |  |  |  | Not Applicable |  |  |  |  | COA Mapping Engine
83 | Common | 1a + 1b | ERP | RTR-GL | GL | Extension | EXT004 | COA Mapping - Validation Engine - Global COA | Gaurav |  |  |  |  | This engine will be used to validate target [Oracle values] in loaded COA mappings against Oracle valid COA values |  | PaaS Extension |  | N |  | Complex |  |  | PaaS Extension - Complex | Sprint 1 | Omkar | Elizabeth | Satheesh | 2021-06-14 | 2021-07-09 | Approved |  | Under Process Owner Review |  |  | Sprint 2 | Sprint 2 | Dhrumil | 2021-07-12 | 2021-07-26 | Not Started |  |  | Not Started |  |  |  |  | Not Applicable |  |  |  |  | COA Mapping Engine
84 | Common | 1a + 1b | ERP | RTR-GL | GL | Extension | EXT005 | COA Mapping - UI - Chart structure definition in COA engine [Configuration screen] |  |  |  |  | KDD 23A |  |  | PaaS Extension |  | N |  | Medium |  |  | PaaS Extension - Medium | TBD | [7 empty] | Not Started | [7 empty] | Not Started |  |  | Not Started |  |  |  |  | Not Applicable |  |  |  | Potentially to be de-scoped as part of pending KDD. | COA Maintenance UI - needed due to off-system mapping in Centralized engine
85 | Common | 1a + 1b | ERP | RTR-GL | GL | Extension | EXT006 | COA Mapping - UI - Mapping rule definition for pair of charts. |  |  |  |  | KDD 23A |  |  | PaaS Extension |  | N |  | Complex |  |  | PaaS Extension - Complex | TBD | [7 empty] | Not Started | [7 empty] | Not Started |  |  | Not Started |  |  |  |  | Not Applicable |  |  |  | Potentially to be de-scoped as part of pending KDD. | COA Maintenance UI - needed due to off-system mapping in Centralized engine
86 | Common | 1a + 1b | ERP | RTR-GL | GL | Extension | EXT007 | COA Mapping - UI - Mapping values for a rule [group of segments to group of segments mapping] | Omkar | [6 empty] | PaaS Extension |  | N |  | Complex |  |  | PaaS Extension - Complex | Sprint 2 |  | Elizabeth | Satheesh | 2021-07-12 | 2021-08-06 |  |  | Not Started |  |  | Sprint 3 | Sprint 3 | Manasi Jain | 2021-08-09 | 2021-09-03 | Not Started |  |  | Not Started |  |  |  |  | Not Applicable |  |  |  |  | COA Maintenance UI - always needed
87 | Common | 1a + 1b | ERP | RTR-GL | GL | Extension | EXT008 | COA Mapping - UI - Code combination to code combination mapping for a chart structure pair | Omkar | [6 empty] | PaaS Extension |  | N |  | Medium |  |  | PaaS Extension - Medium | Sprint 2 |  | Elizabeth | Satheesh | 2021-07-12 | 2021-08-06 |  |  | Not Started |  |  | Sprint 3 | Sprint 3 | Manasi Jain | 2021-08-09 | 2021-09-03 | Not Started |  |  | Not Started |  |  |  |  | Not Applicable |  |  |  |  | COA Maintenance UI - always needed
88 | Common | 1a + 1b | ERP | RTR-GL | GL | Extension | EXT009 | COA Mapping - UI - Bulk upload support | Omkar | Y | [5 empty] | PaaS Extension |  | N |  | Complex |  |  | PaaS Extension - Complex | Sprint 2 |  | Elizabeth | Satheesh | 2021-07-12 | 2021-08-06 |  |  | Not Started |  |  | Sprint 3 | Sprint 3 | Manasi Jain | 2021-08-09 | 2021-09-03 | Not Started |  |  | Not Started | [9 empty] | COA Maintenance UI - always needed
89 | Common | 1a + 1b | ERP | RTR-AHCS | AHCS | Extension | EXT010 | AHCS dashboard page - Monitoring AHCS integration flow | Manpreet | [6 empty] | PaaS Extension |  | N |  | Medium |  |  | PaaS Extension - Medium | Sprint 2 | Vishnu | Erica | Satheesh | 2021-07-12 | 2021-08-06 |  |  | Not Started |  |  | Sprint 3 | Sprint 3 | Manasi Jain | 2021-08-09 | 2021-09-03 | Not Started |  |  | Not Started |  |  |  |  | Not Applicable |  |  |  |  | Interface monitoring dashboard – always needed
90 | Common | 1a + 1b | ERP | RTR-AHCS | AHCS | Extension | EXT011 | Monitor Creating Accounting job status (Scheduled) | Manpreet |  |  |  |  | Track the Create Accounting job that is spawned out from the Import Accounting Transactions job in AHCS, as a de-coupled scheduled process and report status to AHCS dashboard page. The tie back process for Completed job with Uploaded file requires additional efforts |  | PaaS Extension |  | N |  | Complex |  |  | PaaS Extension - Complex | Sprint 2 | Vishnu | Erica | Satheesh | 2021-07-12 | 2021-08-06 |  |  | Not Started |  |  | Sprint 3 | Sprint 3 | Mamatha Tata | 2021-08-09 | 2021-09-03 | Not Started |  |  | Not Started |  |  |  |  | Not Applicable |  |  |  |  | Interface monitoring dashboard – always needed
91 | Common | 1a + 1b | ERP | RTR-GL | GL | Extension | EXT012 | COA Mapping - Enable Page / application level security to COA Mapper custom application | Omkar |  |  |  |  | VL : Addressed by Security. AC: Dependency on the completion of the UI application for security implementation |  | PaaS Extension |  | N |  | Complex |  |  | PaaS Extension - Complex | Sprint 2 |  | Elizabeth | Satheesh | 2021-07-12 | 2021-08-06 |  |  | Not Started |  |  | Sprint 4 | Sprint 4 | Devang Pandya | 2021-08-23 | 2021-09-24 | Not Started |  |  | Not Started |  |  |  |  | Not Applicable |  |  |  |  | COA Maintenance UI - always needed
92 | Common | 1a + 1b | ERP | RTR-GL | GL | Extension | EXT013 | COA Mapping - Derive user initiated bulk Old COA to new COA mapping | Omkar | Y |  |  |  | For OffSystems |  | PaaS Extension |  | N |  | Very Complex |  |  | PaaS Extension - Very Complex | Sprint 2 |  | Elizabeth | Satheesh | 2021-07-12 | 2021-08-06 |  |  | Not Started |  |  | Sprint 4 | Sprint 4 | Manasi Jain | 2021-08-23 | 2021-09-24 | Not Started |  |  | Not Started | [9 empty] | COA Maintenance UI - always needed
93 | ABC Corp | 1a | ERP | RTR-AHCS | AHCS | Interface | INT041 | AHCS Data to TeraData - AHCS Reconciliation Balances | Manpreet | Y | Oracle AHCS | TeraData | KDD 8 | Updated the complexity to "Complex" from "Medium" because of the inclusion of AHCS as a Source Data. Data Model of AHCS is complex. - This Component is part of KDD8 | Yes | Interface - Outbound (Using BI Report) |  | N |  | Complex | Medium |  | Interface - Outbound (Using BI Report) - Complex | Sprint 2 | Manosh | Erica | Satheesh | 2021-07-12 | 2021-08-06 |  |  | Not Started |  |  | Sprint 4 | Sprint 4 | Devang Pandya | 2021-09-06 | 2021-09-24 | Not Started |  |  | Not Started
94 | ABC Corp | 1b | ERP | RTR-GL | GL | Interface | INT042 | GL Data to IAP - Balances |  | Y | Oracle ERP Cloud | IAP | KDD 8 | This Component is part of KDD8 - Layout for IAP is same as the TeraData & can be re-used | Yes | Interface - Outbound (Using BI Report) |  | N |  | Medium | Medium |  | Interface - Outbound (Using BI Report) - Medium | [5 empty] | 2021-10-01 |  |  | Not Started | [7 empty] | Not Started |  |  | Not Started
95 | ABC Corp | 1b | ERP | RTR-AHCS | GL | Interface | INT043 | AHCS Data to IAP - AHCS Details |  | Y | Oracle AHCS | IAP | KDD 8 | Updated the complexity to "Complex" from "Medium" because of the information about the ABC Corp Volume is not known currently and it may require a different integration pattern to handle higher volume . Data Model of AHCS is complex. - This Component is part of KDD8 | Yes | Interface - Outbound (Using BI Report) |  | N |  | Complex | Medium |  | Interface - Outbound (Using BI Report) - Complex | [8 empty] | Not Started | [7 empty] | Not Started |  |  | Not Started
96 | ABC Corp | 1b | ERP | RTR-AHCS | GL | Interface | INT044 | AHCS Data to IAP - AHCS Reconciliation Balances |  | Y | Oracle AHCS | IAP | KDD 8 | This Component is part of KDD8 - Layout for IAP is same as the TeraData & can be re-used | Yes | Interface - Outbound (Using BI Report) |  | N |  | Medium | Medium |  | Interface - Outbound (Using BI Report) - Medium | [8 empty] | Not Started | [7 empty] | Not Started |  |  | Not Started
97 | Common | 1a + 1b | ERP | RTR-GL | GL | Extension | EXT014 | COA Mapping - BI / Analytics tool bulk invoke support | Gaurav | Y |  |  |  | Assuming that BI/Analytics systems will be sending a common file format that contains source system & old COA values in that system and the Integration Process will transform this into future state COA values as an output file response |  | PaaS Extension |  | N |  | Very Complex |  |  |  | Sprint 1 | Omkar | Elizabeth | Satheesh | 2021-06-14 | 2021-07-09 | Approved | Approved | Under GPO Review |  |  | Sprint 2 | Sprint 3 | Dhrumil | 2021-07-12 | 2021-08-06 | Not Started |  |  | Not Started | [9 empty] | COA BI Invoke - always needed
99 | ABC Corp | 1a | ERP | RTR-GL | GL | Report | RPT041 | ABC Corp TB with dril-down/link to ABC Corp Subledger Account Analysis Report | Amit |  |  |  |  | Not possible using BI Report. Need to check FRS/Smartview reports |  | Report (BI Publisher) |  | N |  | Complex |  |  |  | Sprint 2 | Andres | Erica | Satheesh |  |  |  |  | Not Started | [7 empty] | Not Started |  |  | Not Started |  |  |  |  | Not Applicable |  |  |  | P0 Need to discuss more with Functional team so as to understand to the planning
100 | ABC Corp | 1a | ERP | RTR-GL | GL | Report | RPT042 | Control Accounts Manual Entry Review Report | [5 empty] | Abhijit/Devang - How to identify the control Accounts |  | Report (BI Publisher) |  | N |  | Medium |  |  |  | Sprint 4 | [7 empty] | Not Started |  |  | Sprint 5 | Sprint 5 |  |  |  | Not Started |  |  | Not Started |  |  |  |  | Not Applicable |  |  |  | P3
101 | ABC Corp | 1a | ERP | RTR-GL | GL | Report | RPT043 | GL Journal report for journals missed reversing | [7 empty] | Report (BI Publisher) |  | N |  | Medium |  |  |  | Sprint 3 | [7 empty] | Not Started |  |  | Sprint 4 | Sprint 5 |  |  |  | Not Started |  |  | Not Started |  |  |  |  | Not Applicable |  |  |  | P1
102 | ABC Corp | 1a | ERP | RTR-GL | GL | Report | RPT044 | Compare GL Balances and GL Journals for Data Corruption | [5 empty] | Abhijit/Devang - What are the criteria to evaluate the Data Corruption |  | Report (BI Publisher) |  | N |  | Medium |  |  |  | Sprint 3 | [7 empty] | Not Started |  |  | Sprint 4 | Sprint 5 |  |  |  | Not Started |  |  | Not Started |  |  |  |  | Not Applicable |  |  |  | P1
103 | ABC Corp | 1a | ERP | RTR-GL | GL | Report | RPT045 | GL/AR/AP Period Status Report | [5 empty] | Need to revisit this report for 1B AP/AR Intercompany |  | Report (BI Publisher) |  | N |  | Medium |  |  |  | Sprint 3 | [7 empty] | Not Started |  |  | Sprint 4 | Sprint 5 |  |  |  | Not Started |  |  | Not Started |  |  |  |  | Not Applicable |  |  |  | P1
104 | ABC Corp | 1a | ERP | RTR-GL | GL | Report | RPT046 | GL Journal Line detail report | Amit | [6 empty] | Report (BI Publisher) |  | N |  | Complex |  |  |  | Sprint 2 | Badar | Erica | Satheesh |  | 2021-10-01 |  |  | Not Started |  |  | Sprint 5 | Sprint 5 |  |  |  | Not Started |  |  | Not Started |  |  |  |  | Not Applicable |  |  |  | P0
105 | ABC Corp | 1a | ERP | RTR-GL | GL | Report | RPT047 | Trial Balance by Entered & Accounted Amounts | [7 empty] | FRS / Smartview |  | N |  | Medium | Simple |  |  | Sprint 2 | Gaurav | Erica | Satheesh |  | 2021-10-01 |  |  | Not Started |  |  | Sprint 5 | Sprint 5 |  |  |  | Not Started |  |  | Not Started |  |  |  |  | Not Applicable |  |  |  | P0
106 | ABC Corp | 1b | ERP | RTR-GL | GL | Report | RPT048 | IC Balance Matrix: IC Balance report by GL balances | [7 empty] | FRS / Smartview |  | N |  | Medium | Simple | [10 empty] | Not Started | [7 empty] | Not Started |  |  | Not Started |  |  |  |  | Not Applicable
107 | ABC Corp | 1b | ERP | RTR-GL | GL | Report | RPT049 | Reval Summary Report - all COA Segments | [7 empty] | Report (BI Publisher) |  | N |  | Complex |  |  |  | Sprint 5 | [7 empty] | Not Started |  |  | Sprint 5 | Sprint 5 |  |  |  | Not Started |  |  | Not Started |  |  |  |  | Not Applicable |  |  |  | P3
108 | ABC Corp | 1b | ERP | RTR-GL | GL | Report | RPT050 | Reval Summary Report - only LE & Account | [7 empty] | Report (BI Publisher) |  | N |  | Complex |  |  |  | Sprint 5 | [7 empty] | Not Started |  |  | Sprint 5 | Sprint 5 |  |  |  | Not Started |  |  | Not Started |  |  |  |  | Not Applicable |  |  |  | P3
109 | ABC Corp | 1a | ERP | RTR-GL | GL | Report | RPT051 | Exchange Rate Export Report | Amit | [6 empty] | Report (BI Publisher) |  | N |  | Medium |  |  |  | Sprint 2 | Yuvaraj | Erica | Satheesh |  |  |  |  | Not Started |  |  | Sprint 3 | Sprint 3 | Dhrumil | 2021-08-09 | 2021-08-13 | Not Started |  |  | Not Started |  |  |  |  | Not Applicable |  |  |  | P1
110 | ABC Corp | 1a | ERP | RTR-GL | GL | Report | RPT052 | BALANCE SHEET TRENDED (GAAP) | [7 empty] | FRS / Smartview |  | N |  | Complex | Medium |  |  | Sprint 3 | [7 empty] | Not Started |  |  | Sprint 5 | Sprint 5 |  |  |  | Not Started |  |  | Not Started |  |  |  |  | Not Applicable |  |  |  | P0
111 | ABC Corp | 1a | ERP | RTR-GL | GL | Report | RPT053 | TRIAL BALANCE BY LEGAL ENTITY (ACCOUNT) | [7 empty] | FRS / Smartview |  | N |  | Medium | Simple |  |  | Sprint 2 | Gaurav | Erica | Satheesh |  |  |  |  | Not Started |  |  | Sprint 5 | Sprint 5 |  |  |  | Not Started |  |  | Not Started |  |  |  |  | Not Applicable |  |  |  | P0
112 | ABC Corp | 1a | ERP | RTR-GL | GL | Report | RPT054 | INCOME STATEMENT TRAILING BY MONTH (GAAP) | [7 empty] | FRS / Smartview |  | N |  | Medium | Simple |  |  | Sprint 3 | [7 empty] | Not Started |  |  | Sprint 5 | Sprint 5 |  |  |  | Not Started |  |  | Not Started |  |  |  |  | Not Applicable |  |  |  | P0
113 | ABC Corp | 1a | ERP | RTR-GL | GL | Report | RPT055 | BALANCE SHEET BY COUNTRY (GAAP) | [7 empty] | FRS / Smartview |  | N |  | Complex | Medium |  |  | Sprint 5 | [7 empty] | Not Started |  |  | Sprint 6 | Sprint 6 |  |  |  | Not Started |  |  | Not Started |  |  |  |  | Not Applicable |  |  |  | P3/P4
114 | ABC Corp | 1a | ERP | RTR-GL | GL | Report | RPT056 | INCOME STATEMENT BY COUNTRY (GAAP) | [7 empty] | FRS / Smartview |  | N |  | Medium | Simple |  |  | Sprint 5 | [7 empty] | Not Started |  |  | Sprint 6 | Sprint 6 |  |  |  | Not Started |  |  | Not Started |  |  |  |  | Not Applicable |  |  |  | P3/P4
115 | ABC Corp | 1a | ERP | RTR-GL | GL | Report | RPT057 | Income Statement Trailing by Quarter (Operating) with % | [7 empty] | FRS / Smartview |  | N |  | Medium | Simple |  |  | Sprint 5 | [7 empty] | Not Started |  |  | Sprint 6 | Sprint 6 |  |  |  | Not Started |  |  | Not Started |  |  |  |  | Not Applicable |  |  |  | P3
116 | ABC Corp | 1a | ERP | RTR-GL | GL | Report | RPT058 | Trial Balance by Branch - Actual | [7 empty] | FRS / Smartview |  | N |  | Medium | Simple |  |  | Sprint 3 | [7 empty] | Not Started |  |  | Sprint 5 | Sprint 5 |  |  |  | Not Started |  |  | Not Started |  |  |  |  | Not Applicable |  |  |  | P0
117 | ABC Corp | 1a | ERP | RTR-GL | GL | Report | RPT059 | Trial Balance by Branch - STAT | [7 empty] | FRS / Smartview |  | N |  | Medium | Simple |  |  | Sprint 3 | [7 empty] | Not Started |  |  | Sprint 5 | Sprint 5 |  |  |  | Not Started |  |  | Not Started |  |  |  |  | Not Applicable |  |  |  | P0
118 | ABC Corp | 1a | ERP | RTR-GL | GL | Report | RPT060 | Trial Balance by Branch Trailing YTD - Actual | [7 empty] | FRS / Smartview |  | N |  | Medium | Simple |  |  | Sprint 4 | [7 empty] | Not Started |  |  | Sprint 5 | Sprint 6 |  |  |  | Not Started |  |  | Not Started |  |  |  |  | Not Applicable |  |  |  | P2
119 | ABC Corp | 1a | ERP | RTR-GL | GL | Report | RPT061 | Trial Balance by Branch Trailing PTD - Actual | [7 empty] | FRS / Smartview |  | N |  | Medium | Simple |  |  | Sprint 4 | [7 empty] | Not Started |  |  | Sprint 5 | Sprint 6 |  |  |  | Not Started |  |  | Not Started |  |  |  |  | Not Applicable |  |  |  | P2
120 | ABC Corp | 1a | ERP | RTR-GL | GL | Report | RPT062 | Trial Balance by Branch Trailing PTD - STAT | [7 empty] | FRS / Smartview |  | N |  | Medium | Simple |  |  | Sprint 4 | [7 empty] | Not Started |  |  | Sprint 5 | Sprint 6 |  |  |  | Not Started |  |  | Not Started |  |  |  |  | Not Applicable |  |  |  | P2
121 | ABC Corp | 1a | ERP | RTR-GL | GL | Report | RPT063 | Income Statement Trailing by Month (Standard Cost Operating) | [7 empty] | FRS / Smartview |  | N |  | Complex | Medium |  |  | Sprint 3 | [7 empty] | Not Started |  |  | Sprint 5 | Sprint 5 |  |  |  | Not Started |  |  | Not Started |  |  |  |  | Not Applicable |  |  |  | P0
122 | ABC Corp | 1b | ERP | RTR-GL | GL | Conversion | CNV011 | GL Open Balances (YTD plus Current Fiscal Year period balances) - Reporting Ledgers (Translation Only) |  | N | N/A | Oracle ERP Cloud |  | No Seprate Conversion is required for Reporting ledger. It's covered as part of Translation post conversion step |  | Conversion (Using ADFDi and FBDI) |  | N |  | Medium | Medium |  | Conversion (Using ADFDi and FBDI) - Medium | [8 empty] | Not Started |  |  | Sprint 2 |  |  |  |  | Not Started |  |  | Not Started |  |  |  |  | Not Applicable
123 | ABC Corp | 1b | ERP | RTR-GL | GL | Conversion | CNV012 | Currency Rates (For Montly translation rate for countries such as FINLAND) | Viji | Y | PeopleSoft | Oracle ERP Cloud |  |  |  | Conversion (Using ADFDi and FBDI) |  | N |  | Medium | Medium |  | Conversion (Using ADFDi and FBDI) - Medium | [8 empty] | Not Started | [7 empty] | Not Started |  |  | Not Started
124 | ABC Corp | 1a | ERP | RTR-AHCS | AHCS | Interface | INT122 | Daily GL journal feed from POC to AHCS | Manpreet | Y | POC | Oracle AHCS | KDD 23B |  |  | Interface - Inbound (Using Middleware) |  |  |  | Complex |  |  | Interface - Inbound (Using Middleware) - Complex | Sprint 1 | Manosh | Erica | Satheesh | 2021-06-14 | 2021-07-09 | Approved | Approved | Under GPO Review |  |  | Sprint 3 | Sprint 3 | Snehal Shirke | 2021-07-12 | 2021-08-11 | Not Started |  |  | Not Started | [10 empty] | 6/30: Next meeting on Friday, expect update then
125 | ABC Corp | 1b | ERP | RTR-AHCS | AHCS | Interface | INT123 | GL Feed from SXE US to AHCS | Manpreet | Y | SXE US | Oracle AHCS | KDD 6B |  |  | Interface - Inbound (Using Middleware) |  |  |  | Complex |  |  | Interface - Inbound (Using Middleware) - Complex | [8 empty] | Not Started | [7 empty] | Not Started |  |  | Not Started
126 | ABC Corp | 1b | ERP | RTR-AHCS | AHCS | Interface | INT124 | GL Feed from Eclipse to AHCS | Manpreet | Y | Eclipse | Oracle AHCS | KDD 6B |  |  | Interface - Inbound (Using Middleware) |  |  |  | Complex |  |  | Interface - Inbound (Using Middleware) - Complex | [8 empty] | Not Started | [7 empty] | Not Started |  |  | Not Started
127 | ABC Corp | 1b | ERP | RTR-AHCS | AHCS | Interface | INT045 | GL Feed from Treasury to AHCS | Manpreet | Y | Treasury | Oracle AHCS | KDD 6B |  |  | Interface - Inbound (Using Middleware) |  |  |  | Complex |  |  | Interface - Inbound (Using Middleware) - Complex | [8 empty] | Not Started | [7 empty] | Not Started |  |  | Not Started
128 | ABC Corp | 1a | ERP | RTR-GL | GL | Interface | INT046 | GL balances summary to Teradata | Amit | Y | Oracle GL | TeraData |  |  |  | Interface - Outbound (Using BI Report) |  |  |  | Complex |  |  | Interface - Outbound (Using BI Report) - Complex | Sprint 2 |  | Erica | Satheesh |  |  |  |  | Not Started |  |  | Sprint 3 | Sprint 3 | Harshit Gangwar
129 | ABC Corp | 1a + 1b | ERP | RTR-GL | GL | Interface | INT047 | Exchange Rates Outbound | Amit | Y | Oracle GL | FCCS/ Oracle EBS / Other AXE systems | KDD 3B1/ 3B2 |  | Yes | Interface - Outbound (Using BI Report) |  | N |  | Medium |  |  | Interface - Outbound (Using BI Report) - Medium | Sprint 2 | Yuvaraj | Erica | Satheesh | [7 empty] | Sprint 3 | Sprint 3 | Dhrumil | 2021-08-16 | 2021-08-27
130 | ABC Corp | 1b | ERP | RTR-AHCS | AHCS | Report | RPT064 | Interface Extract Report | Manpreet | N | [5 empty] | Report (BI Publisher) |  | N |  | Complex |  |  | Report (BI Publisher) - Complex
131 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Report | RPT065 | BALANCE SHEET TRENDED (GAAP) | [5 empty] | EPM-FCCS-032 |  | WebFR or Smartview |  |  |  | Simple
132 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Report | RPT066 | TRIAL BALANCE BY LEGAL ENTITY (ACCOUNT) | [5 empty] | EPM-FCCS-033 |  | WebFR or Smartview |  |  |  | Simple
133 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Report | RPT067 | INCOME STATEMENT TRAILING BY MONTH (GAAP) | [5 empty] | EPM-FCCS-034 |  | WebFR or Smartview |  |  |  | Simple
134 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Report | RPT068 | BALANCE SHEET BY COUNTRY (GAAP) | [5 empty] | EPM-FCCS-035 |  | WebFR or Smartview |  |  |  | Simple
135 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Report | RPT069 | INCOME STATEMENT BY COUNTRY (GAAP) | [5 empty] | EPM-FCCS-036 |  | WebFR or Smartview |  |  |  | Simple
136 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Report | RPT070 | Balance Sheet by Legal Entity - Preliminary Close | [5 empty] | EPM-FCCS-037 |  | WebFR or Smartview |  |  |  | Simple
137 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Report | RPT071 | Income Statement by Legal Entity - Preliminary Close | [5 empty] | EPM-FCCS-038 |  | WebFR or Smartview |  |  |  | Simple
138 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Report | RPT072 | Income Statement History - Preliminary Close | [5 empty] | EPM-FCCS-039 |  | WebFR or Smartview |  |  |  | Simple
139 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Report | RPT073 | Income Statement Trailing by Quarter (Operating) with % | [5 empty] | EPM-FCCS-040 |  | WebFR or Smartview |  |  |  | Simple
140 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Report | RPT074 | Balance Sheet by Ledger (GAAP) Functional Currency | [5 empty] | EPM-FCCS-041 |  | WebFR or Smartview |  |  |  | Simple
141 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Report | RPT075 | Balance Sheet by Reporting Segment | [5 empty] | EPM-FCCS-042 |  | WebFR or Smartview |  |  |  | Simple
142 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Report | RPT076 | Income Statement by Reporting Segment - YTD, QTD, Periodic | [5 empty] | EPM-FCCS-043 |  | WebFR or Smartview |  |  |  | Simple
143 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Report | RPT077 | Trial Balance - Detail & Translation | [5 empty] | EPM-FCCS-046 |  | WebFR or Smartview |  |  |  | Medium
144 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Report | RPT078 | Tax Trial Balance by Legal Entity & Account | [5 empty] | EPM-FCCS-048 |  | WebFR or Smartview |  |  |  | Simple
145 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Report | RPT079 | Income Statement Trailing by Month (Standard Cost Operating) | [5 empty] | EPM-FCCS-049 |  | WebFR or Smartview |  |  |  | Simple
146 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Report | RPT080 | Income Statement Standard Cost History - Preliminary Close | [5 empty] | EPM-FCCS-050 |  | WebFR or Smartview |  |  |  | Simple
147 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Report | RPT081 | Income Statement Standard Cost by Legal Entity - Preliminary Close | [5 empty] | EPM-FCCS-051 |  | WebFR or Smartview |  |  |  | Simple
148 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Report | RPT082 | z9-Adm-trail.htm | [5 empty] | EPM-FCCS-167 |  | WebFR or Smartview |  |  |  | Simple
149 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Report | RPT083 | z9-VarAnUSD-all.htm | [5 empty] | EPM-FCCS-168 |  | WebFR or Smartview |  |  |  | Simple
150 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Report | RPT084 | z9-10000-CAD-YTD.txt | [5 empty] | EPM-FCCS-169 |  | WebFR or Smartview |  |  |  | Simple
151 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Report | RPT085 | z9-10000-FUN-YTD.txt | [5 empty] | EPM-FCCS-170 |  | WebFR or Smartview |  |  |  | Simple
152 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Report | RPT086 | z9-10000-USD-YTD.txt | [5 empty] | EPM-FCCS-171 |  | WebFR or Smartview |  |  |  | Simple
153 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Report | RPT087 | z03-I&E-YTD-Grp.csv | [5 empty] | EPM-FCCS-172 |  | WebFR or Smartview |  |  |  | Simple
154 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Report | RPT088 | z03-I&E-YTD-GrpBr.csv | [5 empty] | EPM-FCCS-173 |  | WebFR or Smartview |  |  |  | Simple
155 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Report | RPT089 | z03-I&E-YTD-GrpReg.csv | [5 empty] | EPM-FCCS-174 |  | WebFR or Smartview |  |  |  | Simple
156 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Report | RPT090 | z11-PY2selected lines.csv | [5 empty] | EPM-FCCS-175 |  | WebFR or Smartview |  |  |  | Simple
157 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Report | RPT091 | z12-PYselected lines.csv | [5 empty] | EPM-FCCS-176 |  | WebFR or Smartview |  |  |  | Simple
158 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Report | RPT092 | z13-CYselected lines.csv | [5 empty] | EPM-FCCS-177 |  | WebFR or Smartview |  |  |  | Simple
159 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Report | RPT093 | z9-Adm-all.htm | [5 empty] | EPM-FCCS-178 |  | WebFR or Smartview |  |  |  | Simple
160 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Report | RPT094 | z9-VarAnCAD.htm | [5 empty] | EPM-FCCS-179 |  | WebFR or Smartview |  |  |  | Simple
161 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Report | RPT095 | z9-VarAnUSD-all.htm | [5 empty] | EPM-FCCS-180 |  | WebFR or Smartview |  |  |  | Simple
162 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Report | RPT096 | z9-VarAnUSDconsol.htm | [5 empty] | EPM-FCCS-181 |  | WebFR or Smartview |  |  |  | Simple
163 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Report | RPT097 | OS_Pull-2020-12.xlsx | [5 empty] | EPM-FCCS-182 |  | WebFR or Smartview |  |  |  | Simple
164 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Report | RPT098 | z6-Branch Header.csv | [5 empty] | EPM-FCCS-183 |  | WebFR or Smartview |  |  |  | Simple
165 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Report | RPT082 | Indirect Cash Flow Statement | [5 empty] | EPM-FCCS-057 |  | WebFR or Smartview |  |  |  | Complex
166 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Report | RPT083 | Cash Flow Worksheet | [5 empty] | EPM-FCCS-060 |  | WebFR or Smartview |  |  |  | Very Complex
167 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Report | RPT084 | Consolidated Cash Flow Report | [5 empty] | EPM-FCCS-064 |  | WebFR or Smartview |  |  |  | Complex
168 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Report | RPT085 | Check report from Data Management to validate initial load of data. | [5 empty] | EPM-FCCS-132 |  | WebFR or Smartview |  |  |  | Medium
169 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Report | RPT086 | Overall validation report to tie GL system to consolidated system. | [5 empty] | EPM-FCCS-133 |  | WebFR or Smartview |  |  |  | Complex
170 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Report | RPT087 | Validation check for prior month, current activity and current month | [5 empty] | EPM-FCCS-137 |  | WebFR or Smartview |  |  |  | Medium
171 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Report | RPT088 | Trend analysis for fluctuations over defined percentages and amounts | [5 empty] | EPM-FCCS-138 |  | WebFR or Smartview |  |  |  | Complex
172 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Report | RPT089 | Intercompany report | [5 empty] | EPM-FCCS-143 |  | WebFR or Smartview |  |  |  | Complex
173 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Report | RPT090 | Report to help validate my CTA calculation | [5 empty] | EPM-FCCS-149 |  | WebFR or Smartview |  |  |  | Complex
174 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT048 | Load FX rates for end of month rate and average rate from Oracle ERP cloud platform |  |  | Oracle GL | FCCS |  | EPM-FCCS-071 |  | Interface - Inbound (Using Middleware) |  |  |  | Complex
175 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT049 | Load data from close and consolidations to Workiva |  |  | FCCS | Workiva |  | EPM-FCCS-072 |  | Interface - Outbound (Using Middleware) |  |  |  | Simple
176 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT050 | Load data from close and consolidations to Enterprise Planning |  |  | FCCS | Enterprise Planning |  | EPM-FCCS-073 |  | Interface - Outbound (Using Middleware) |  |  |  | Complex
177 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT051 | Load data from close and consolidations to TeraData |  |  | FCCS | TeraData |  | EPM-FCCS-074 |  | Interface - Outbound (Using Middleware) |  |  |  | Complex
178 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT052 | Load data from close and consolidations to OneSource Tax Provision |  |  | FCCS | OneSource Tax Provision |  | EPM-FCCS-075 |  | Interface - Outbound (Using Middleware) |  |  |  | Complex
179 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT053 | Load data to Close and Consolidations from PeopleSoft for ABC Corp via flatfiles |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-076 |  | Interface - Inbound (Using Middleware) |  |  |  | Complex
180 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT054 | Load data to Close and Consolidations from P21 for Network Infrastructure & Security - Puerto Rico via flatfiles |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-077 |  | Interface - Inbound (Using Middleware) |  |  |  | Complex
181 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT055 | Load data to Close and Consolidations from Pronto for CSD - APAC via flatfiles |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-078 |  | Interface - Inbound (Using Middleware) |  |  |  | Complex
182 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT056 | Load data to Close and Consolidations from MS - Dynamics for Atlas - APAC via flatfiles |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-079 |  | Interface - Inbound (Using Middleware) |  |  |  | Complex
183 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT057 | Load data to Close and Consolidations from Oracle SCM for CBC - Austin/ Connect via flatfiles |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-080 |  | Interface - Inbound (Using Middleware) |  |  |  | Complex
184 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT058 | Load data to Close and Consolidations from Dax for China - 7248 & 7255 via flatfiles |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-081 |  | Interface - Inbound (Using Middleware) |  |  |  | Complex
185 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT059 | Load data to Close and Consolidations from Eclipse for AED - Atlantic Electric Dist. via flatfiles |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-083 |  | Interface - Inbound (Using Middleware) |  |  |  | Complex
186 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT060 | Load data to Close and Consolidations from Microsoft DAX for Netherlands via flatfiles |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-084 |  | Interface - Inbound (Using Middleware) |  |  |  | Complex
187 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT061 | Load data to Close and Consolidations from AS/400 - Legacy for WIS Europe - Poland via flatfiles |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-085 |  | Interface - Inbound (Using Middleware) |  |  |  | Complex
188 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT062 | Load data to Close and Consolidations from Mocasoft for SPS Aberdeen via flatfiles |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-086 |  | Interface - Inbound (Using Middleware) |  |  |  | Complex
189 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT063 | Load data to Close and Consolidations from Microsoft DAX for ABC Corp UK via flatfiles |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-087 |  | Interface - Inbound (Using Middleware) |  |  |  | Complex
190 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT064 | Load data to Close and Consolidations from AS/400 - Legacy for WIS Europe - Czech via flatfiles |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-088 |  | Interface - Inbound (Using Middleware) |  |  |  | Complex
191 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT065 | Load data to Close and Consolidations from AS/400 - Legacy for WIS UK via flatfiles |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-089 |  | Interface - Inbound (Using Middleware) |  |  |  | Complex
192 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT066 | Load data to Close and Consolidations from AS/400 - Legacy for WIS Europe - France via flatfiles |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-090 |  | Interface - Inbound (Using Middleware) |  |  |  | Complex
193 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT067 | Load data to Close and Consolidations from AS/400 - Legacy for WIS Europe - Germany via flatfiles |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-091 |  | Interface - Inbound (Using Middleware) |  |  |  | Complex
194 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT068 | Load data to Close and Consolidations from Mocasoft for SPS Admin via flatfiles |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-092 |  | Interface - Inbound (Using Middleware) |  |  |  | Complex
195 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT069 | Load data to Close and Consolidations from Mocasoft for SPS Houston via flatfiles |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-093 |  | Interface - Inbound (Using Middleware) |  |  |  | Complex
196 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT070 | Load data to Close and Consolidations from Microsoft DAX for Dubai via flatfiles |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-094 |  | Interface - Inbound (Using Middleware) |  |  |  | Complex
197 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT071 | Load data to Close and Consolidations from DAX for SPS Singapore via flatfiles |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-095 |  | Interface - Inbound (Using Middleware) |  |  |  | Complex
198 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT072 | Load data to Close and Consolidations from AS/400 - Legacy for WIS Singapore via flatfiles |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-096 |  | Interface - Inbound (Using Middleware) |  |  |  | Complex
199 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT073 | Load data to Close and Consolidations from Hyperion/DAX for TVC CAD via flatfiles |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-097 |  | Interface - Inbound (Using Middleware) |  |  |  | Complex
200 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT074 | Load data to Close and Consolidations from QuickBooks for SLS - CAD via flatfiles |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-098 |  | Interface - Inbound (Using Middleware) |  |  |  | Complex
201 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT075 | Load data to Close and Consolidations from AS/400 - Legacy for WIS CAD via flatfiles |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-099 |  | Interface - Inbound (Using Middleware) |  |  |  | Complex
202 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT076 | Load data to Close and Consolidations from QuickBooks for SLS - US via flatfiles |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-100 |  | Interface - Inbound (Using Middleware) |  |  |  | Complex
203 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT077 | Load data to Close and Consolidations from QuickBooks for EcoInsight via flatfiles |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-101 |  | Interface - Inbound (Using Middleware) |  |  |  | Complex
204 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT078 | Load data to Close and Consolidations from Quickbooks for Aelux via flatfiles |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-102 |  | Interface - Inbound (Using Middleware) |  |  |  | Complex
205 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT079 | Load data to Close and Consolidations from Rubicon - Fibertron for CSC - Fibertron via flatfiles |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-103 |  | Interface - Inbound (Using Middleware) |  |  |  | Complex
206 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT080 | Load data to Close and Consolidations from Microsoft DAX for Ireland via flatfiles |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-104 |  | Interface - Inbound (Using Middleware) |  |  |  | Complex
207 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT081 | Load data to Close and Consolidations from AS/400 - Legacy for WIS Europe - Ireland via flatfiles |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-105 |  | Interface - Inbound (Using Middleware) |  |  |  | Complex
208 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT082 | Load data to Close and Consolidations from AS/400 - Legacy for WIS US via flatfiles |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-106 |  | Interface - Inbound (Using Middleware) |  |  |  | Complex
209 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT083 | Load data to Close and Consolidations from AS/400 - Legacy for WIS Malaysia via flatfiles |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-107 |  | Interface - Inbound (Using Middleware) |  |  |  | Complex
210 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT084 | Load data to Close and Consolidations from Mocasoft for SPS Angola via flatfiles |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-108 |  | Interface - Inbound (Using Middleware) |  |  |  | Complex
211 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT085 | Load data to Close and Consolidations from DAX for Thailand via flatfiles |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-109 |  | Interface - Inbound (Using Middleware) |  |  |  | Complex
212 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT086 | Load data to Close and Consolidations from Hyperion / DAX for TVC Mexico Services via flatfiles |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-110 |  | Interface - Inbound (Using Middleware) |  |  |  | Complex
213 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT087 | Load data to Close and Consolidations from Hyperion / DAX for TVC Mexico Distribution via flatfiles |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-111 |  | Interface - Inbound (Using Middleware) |  |  |  | Complex
214 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT088 | Load data to Close and Consolidations from Hyperion / DAX for TVC UK via flatfiles |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-112 |  | Interface - Inbound (Using Middleware) |  |  |  | Complex
215 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT089 | Load data to Close and Consolidations from Hyperion / DAX for TVC Spain via flatfiles |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-113 |  | Interface - Inbound (Using Middleware) |  |  |  | Complex
| ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT090 | Load data to Close and Consolidations from Hyperion/DAX for TVC US via flatfiles |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-114 |  | Interface - Inbound (Using Middleware) |  |  |  | Complex
217 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT091 | Load data to Close and Consolidations from Microsoft DAX for ABC Corp Australia via flatfiles |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-115 |  | Interface - Inbound (Using Middleware) |  |  |  | Complex
218 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT092 | Load data to Close and Consolidations from Microsoft DAX for Hong Kong via flatfiles |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-116 |  | Interface - Inbound (Using Middleware) |  |  |  | Complex
219 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT093 | Load data to Close and Consolidations from AS400 for Conney via flatfiles |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-117 |  | Interface - Inbound (Using Middleware) |  |  |  | Complex
220 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT094 | Load data to Close and Consolidations from Eclipse for Hill Country via flatfiles |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-118 |  | Interface - Inbound (Using Middleware) |  |  |  | Complex
221 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT095 | Load data to Close and Consolidations from Prophet 21 for Hazmasters via flatfiles |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-119 |  | Interface - Inbound (Using Middleware) |  |  |  | Complex
222 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT096 | Load data to Close and Consolidations from WDM - Eclipse for Mexico System via flatfiles |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-120 |  | Interface - Inbound (Using Middleware) |  |  |  | Complex
223 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT097 | Load data to Close and Consolidations from WEAS - Aspel Coi for Mexico System via flatfiles |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-187 |  | Interface - Inbound (Using Middleware) |  |  |  | Complex
224 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT098 | Load data to Close and Consolidations from Mexico - AS400 for Mexico System via flatfiles |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-188 |  | Interface - Inbound (Using Middleware) |  |  |  | Complex
225 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT099 | Load data to Close and Consolidations from Sage 300 for EECOL Properties via flatfiles |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-121 |  | Interface - Inbound (Using Middleware) |  |  |  | Complex
226 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT100 | Load data to Close and Consolidations from regional branches - D3 for EECOL Electric System via flatfiles |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-122 |  | Interface - Inbound (Using Middleware) |  |  |  | Complex
227 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT101 | Load data to Close and Consolidations from Head Office - Sage 300 for EECOL Electric System via flatfiles |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-189 |  | Interface - Inbound (Using Middleware) |  |  |  | Complex
228 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT102 | Load data to Close and Consolidations from Microsoft DAX for EECOL Sudamerica via flatfiles |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-123 |  | Interface - Inbound (Using Middleware) |  |  |  | Complex
229 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT103 | Load data to Close and Consolidations from Microsoft DAX for EECOL Chile Power via flatfiles |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-124 |  | Interface - Inbound (Using Middleware) |  |  |  | Complex
230 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT104 | Load data to Close and Consolidations from Microsoft DAX for EECOL Peru via flatfiles |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-125 |  | Interface - Inbound (Using Middleware) |  |  |  | Complex
231 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT105 | Load data to Close and Consolidations from Microsoft DAX for EECOL Ecuador via flatfiles |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-126 |  | Interface - Inbound (Using Middleware) |  |  |  | Complex
232 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT106 | Load data to Close and Consolidations from Microsoft DAX for EECOL E-Supply via flatfiles |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-127 |  | Interface - Inbound (Using Middleware) |  |  |  | Complex
233 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT107 | Load data to Close and Consolidations from Oracle SCM for HiLine via flatfiles |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-128 |  | Interface - Inbound (Using Middleware) |  |  |  | Complex
234 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT108 | Load data to Close and Consolidations from Rubicon - Liberty for Liberty via flatfiles |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-129 |  | Interface - Inbound (Using Middleware) |  |  |  | Complex
235 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT109 | Load data to Close and Consolidations from Eclipse - Needham for Needham via flatfiles |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-130 |  | Interface - Inbound (Using Middleware) |  |  |  | Complex
236 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT110 | Load data to Close and Consolidations from EDIG for EECOL Holding Sask System via flatfiles |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-185 |  | Interface - Inbound (Using Middleware) |  |  |  | Complex
237 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT111 | Load data to Close and Consolidations from EDIG for EECOL Holding Industrial System via flatfiles |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-186 |  | Interface - Inbound (Using Middleware) |  |  |  | Complex
238 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT112 | Extract from PeopleSoft for ABC Corp |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-076 |  | Interface - Inbound (Using Middleware) |  |  |  | Medium
239 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT113 | Extract from P21 for Network Infrastructure & Security - Puerto Rico |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-077 |  | Interface - Inbound (Using Middleware) |  |  |  | Medium
240 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT114 | Extract from Pronto for CSD - APAC |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-078 |  | Interface - Inbound (Using Middleware) |  |  |  | Medium
241 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT115 | Extract from MS - Dynamics for Atlas - APAC |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-079 |  | Interface - Inbound (Using Middleware) |  |  |  | Medium
242 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT116 | Extract from Oracle SCM for CBC - Austin/ Connect |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-080 |  | Interface - Inbound (Using Middleware) |  |  |  | Medium
243 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT117 | Extract from Dax for China - 7248 & 7255 |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-081 |  | Interface - Inbound (Using Middleware) |  |  |  | Medium
244 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT118 | Extract from Eclipse for AED - Atlantic Electric Dist. |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-083 |  | Interface - Inbound (Using Middleware) |  |  |  | Medium
245 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT119 | Extract from Microsoft DAX for Netherlands |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-084 |  | Interface - Inbound (Using Middleware) |  |  |  | Medium
246 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT120 | Extract from AS/400 - Legacy for WIS Europe - Poland |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-085 |  | Interface - Inbound (Using Middleware) |  |  |  | Medium
247 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT121 | Extract from Mocasoft for SPS Aberdeen |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-086 |  | Interface - Inbound (Using Middleware) |  |  |  | Medium
248 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT122 | Extract from Microsoft DAX for ABC Corp UK |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-087 |  | Interface - Inbound (Using Middleware) |  |  |  | Medium
249 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT123 | Extract from AS/400 - Legacy for WIS Europe - Czech |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-088 |  | Interface - Inbound (Using Middleware) |  |  |  | Medium
250 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT124 | Extract from AS/400 - Legacy for WIS UK |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-089 |  | Interface - Inbound (Using Middleware) |  |  |  | Medium
251 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT125 | Extract from AS/400 - Legacy for WIS Europe - France |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-090 |  | Interface - Inbound (Using Middleware) |  |  |  | Medium
252 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT126 | Extract from AS/400 - Legacy for WIS Europe - Germany |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-091 |  | Interface - Inbound (Using Middleware) |  |  |  | Medium
253 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT127 | Extract from Mocasoft for SPS Admin |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-092 |  | Interface - Inbound (Using Middleware) |  |  |  | Medium
254 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT128 | Extract from Mocasoft for SPS Houston |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-093 |  | Interface - Inbound (Using Middleware) |  |  |  | Medium
255 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT129 | Extract from Microsoft DAX for Dubai |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-094 |  | Interface - Inbound (Using Middleware) |  |  |  | Medium
256 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT130 | Extract from DAX for SPS Singapore |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-095 |  | Interface - Inbound (Using Middleware) |  |  |  | Medium
257 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT131 | Extract from AS/400 - Legacy for WIS Singapore |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-096 |  | Interface - Inbound (Using Middleware) |  |  |  | Medium
258 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT132 | Extract from Hyperion/DAX for TVC CAD |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-097 |  | Interface - Inbound (Using Middleware) |  |  |  | Medium
259 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT133 | Extract from QuickBooks for SLS - CAD |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-098 |  | Interface - Inbound (Using Middleware) |  |  |  | Medium
260 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT134 | Extract from AS/400 - Legacy for WIS CAD |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-099 |  | Interface - Inbound (Using Middleware) |  |  |  | Medium
261 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT135 | Extract from QuickBooks for SLS - US |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-100 |  | Interface - Inbound (Using Middleware) |  |  |  | Medium
262 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT136 | Extract from QuickBooks for EcoInsight |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-101 |  | Interface - Inbound (Using Middleware) |  |  |  | Medium
263 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT137 | Extract from Quickbooks for Aelux |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-102 |  | Interface - Inbound (Using Middleware) |  |  |  | Medium
264 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT138 | Extract from Rubicon - Fibertron for CSC - Fibertron |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-103 |  | Interface - Inbound (Using Middleware) |  |  |  | Medium
265 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT139 | Extract from Microsoft DAX for Ireland |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-104 |  | Interface - Inbound (Using Middleware) |  |  |  | Medium
266 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT140 | Extract from AS/400 - Legacy for WIS Europe - Ireland |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-105 |  | Interface - Inbound (Using Middleware) |  |  |  | Medium
267 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT141 | Extract from AS/400 - Legacy for WIS US |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-106 |  | Interface - Inbound (Using Middleware) |  |  |  | Medium
268 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT142 | Extract from AS/400 - Legacy for WIS Malaysia |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-107 |  | Interface - Inbound (Using Middleware) |  |  |  | Medium
269 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT143 | Extract from Mocasoft for SPS Angola |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-108 |  | Interface - Inbound (Using Middleware) |  |  |  | Medium
270 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT144 | Extract from DAX for Thailand |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-109 |  | Interface - Inbound (Using Middleware) |  |  |  | Medium
271 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT145 | Extract from Hyperion / DAX for TVC Mexico Services |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-110 |  | Interface - Inbound (Using Middleware) |  |  |  | Medium
272 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT146 | Extract from Hyperion / DAX for TVC Mexico Distribution |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-111 |  | Interface - Inbound (Using Middleware) |  |  |  | Medium
273 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT147 | Extract from Hyperion / DAX for TVC UK |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-112 |  | Interface - Inbound (Using Middleware) |  |  |  | Medium
274 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT148 | Extract from Hyperion / DAX for TVC Spain |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-113 |  | Interface - Inbound (Using Middleware) |  |  |  | Medium
275 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT149 | Extract from Hyperion/DAX for TVC US |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-114 |  | Interface - Inbound (Using Middleware) |  |  |  | Medium
276 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT150 | Extract from Microsoft DAX for ABC Corp Australia |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-115 |  | Interface - Inbound (Using Middleware) |  |  |  | Medium
277 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT151 | Extract from Microsoft DAX for Hong Kong |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-116 |  | Interface - Inbound (Using Middleware) |  |  |  | Medium
278 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT152 | Extract from AS400 for Conney |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-117 |  | Interface - Inbound (Using Middleware) |  |  |  | Medium
279 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT153 | Extract from Eclipse for Hill Country |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-118 |  | Interface - Inbound (Using Middleware) |  |  |  | Medium
280 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT154 | Extract from Prophet 21 for Hazmasters |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-119 |  | Interface - Inbound (Using Middleware) |  |  |  | Medium
281 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT155 | Extract from WDM - Eclipse for Mexico System |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-120 |  | Interface - Inbound (Using Middleware) |  |  |  | Medium
282 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT156 | Extract from WEAS - Aspel Coi for Mexico System |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-187 |  | Interface - Inbound (Using Middleware) |  |  |  | Medium
283 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT157 | Extract from Mexico - AS400 for Mexico System |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-188 |  | Interface - Inbound (Using Middleware) |  |  |  | Medium
284 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT158 | Extract from Sage 300 for EECOL Properties |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-121 |  | Interface - Inbound (Using Middleware) |  |  |  | Medium
285 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT159 | Extract from regional branches - D3 for EECOL Electric System |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-122 |  | Interface - Inbound (Using Middleware) |  |  |  | Medium
286 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT160 | Extract from Head Office - Sage 300 for EECOL Electric System |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-189 |  | Interface - Inbound (Using Middleware) |  |  |  | Medium
287 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT161 | Extract from Microsoft DAX for EECOL Sudamerica |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-123 |  | Interface - Inbound (Using Middleware) |  |  |  | Medium
288 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT162 | Extract from Microsoft DAX for EECOL Chile Power |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-124 |  | Interface - Inbound (Using Middleware) |  |  |  | Medium
289 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT163 | Extract from Microsoft DAX for EECOL Peru |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-125 |  | Interface - Inbound (Using Middleware) |  |  |  | Medium
290 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT164 | Extract from Microsoft DAX for EECOL Ecuador |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-126 |  | Interface - Inbound (Using Middleware) |  |  |  | Medium
291 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT165 | Extract from Microsoft DAX for EECOL E-Supply |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-127 |  | Interface - Inbound (Using Middleware) |  |  |  | Medium
292 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT166 | Extract from Oracle SCM for HiLine |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-128 |  | Interface - Inbound (Using Middleware) |  |  |  | Medium
293 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT167 | Extract from Rubicon - Liberty for Liberty |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-129 |  | Interface - Inbound (Using Middleware) |  |  |  | Medium
294 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT168 | Extract from Eclipse - Needham for Needham |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-130 |  | Interface - Inbound (Using Middleware) |  |  |  | Medium
295 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT169 | Extract from EDIG for EECOL Holding Sask System |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-185 |  | Interface - Inbound (Using Middleware) |  |  |  | Medium
296 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Interface | INT170 | Extract from EDIG for EECOL Holding Industrial System |  |  | ABC Corp Offystem | FCCS |  | EPM-FCCS-186 |  | Interface - Inbound (Using Middleware) |  |  |  | Medium
297 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Extension | EXT015 | Manage templates, tasks, and schedules | [5 empty] | EPM-FCCS-029 Extension calc |  | PaaS Extension |  |  |  | Medium
298 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Extension | EXT016 | Adjust EBITDA calculations through data forms for non-recurring entries | [5 empty] | EPM-FCCS-053 Extension form |  | PaaS Extension |  |  |  | Medium
299 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Extension | EXT017 | Internal EBITDA | [5 empty] | EPM-FCCS-054 Extension form |  | PaaS Extension |  |  |  | Medium
300 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Extension | EXT018 | Roll forward data at consolidated level in Close and Consolidations (Main examples include Fixed Assets, Equity, Leases, Intangibles, Goodwill, Debt, Deferred Financing Fees, Pensions, Deferred Income Taxes (Assets and Liabilities)) | [5 empty] | EPM-FCCS-055 Extension form |  | PaaS Extension |  |  |  | Very Complex
301 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Extension | EXT019 | Roll forward data at base level entity in Close and Consolidations (Main examples include Fixed Assets, Equity, Leases, Intangibles, Goodwill, Debt, Deferred Financing Fees, Pensions, Deferred Income Taxes (Assets and Liabilities)) | [5 empty] | EPM-FCCS-184 Extension form |  | PaaS Extension |  |  |  | Complex
302 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Extension | EXT020 | Free Cashflow | [5 empty] | EPM-FCCS-059 Extension form |  | PaaS Extension |  |  |  | Medium
303 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Extension | EXT021 | Auto trigger the calculations & consolidations for the legal entities after the trial balance load | [5 empty] | EPM-FCCS-068 Extension calc |  | PaaS Extension |  |  |  | Complex
304 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Extension | EXT022 | Load YTD balances (Trial balance) from the GL to the Close and Consolidations application | [5 empty] | EPM-FCCS-134 Extension calc |  | PaaS Extension |  |  |  | Medium
305 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Extension | EXT023 | Automated consolidations and translations run after loading data for offsystems | [5 empty] | EPM-FCCS-165 Extension calc |  | PaaS Extension |  |  |  | Complex
306 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Extension | EXT024 | Report EBITDA | [5 empty] | EPM-FCCS-156 Extension form |  | PaaS Extension |  |  |  | Simple
307 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Extension | EXT025 | Report Workdays | [5 empty] | EPM-FCCS-157 Extension form |  | PaaS Extension |  |  |  | Simple
308 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Extension | EXT026 | Report Headcount | [5 empty] | EPM-FCCS-160 Extension form |  | PaaS Extension |  |  |  | Simple
309 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Extension | EXT027 | External EBITDA in the financial statements | [5 empty] | EPM-FCCS-162 Extension form |  | PaaS Extension |  |  |  | Simple
310 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Extension | EXT028 | Adjusted external EBITDA in the financial statements | [5 empty] | EPM-FCCS-163 Extension form |  | PaaS Extension |  |  |  | Simple
311 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Extension | EXT029 | EBITDA by Strategic Business Unit | [5 empty] | EPM-FCCS-164 Extension form |  | PaaS Extension |  |  |  | Medium
312 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Conversion | CNV013 | Closing balances for previous year rolls as opening balances for current year | [5 empty] | EPM-FCCS-011 |  | Conversion will be done in Close and Consolidations |  |  |  | Simple
313 | ABC Corp | 1a | EPM | EPM - CCR | FCCS | Conversion | CNV014 | 2021 monthly Income Statement & Balance Sheet data conversions for go-live | [5 empty] | EPM-FCCS-018 |  | Conversion will be done in Close and Consolidations |  |  |  | Complex
314 | ABC Corp | 1a | EPM | EPM - CCR | ARCS | Interface | INT171 | Auto certify if there is no balance (zero balance) and no activity in the GL account | [5 empty] | EPM-ARCS-011 | [5 empty] | Medium
315 | ABC Corp | 1a | EPM | EPM - CCR | ARCS | Extension | EXT030 | Supporting documentation for any transaction amount over $25k. | [5 empty] | EPM-ARCS-017 | [5 empty] | Simple
316 | ABC Corp | 1a | EPM | EPM - CCR | ARCS | Extension | EXT031 | Tracking only reconciliations to have a mandatory attachment rule before submission | [5 empty] | EPM-ARCS-021 | [5 empty] | Simple
317 | ABC Corp | 1a | EPM | EPM - CCR | ARCS | Extension | EXT032 | Reconciliations with a variance to be submitted with explainations. | [5 empty] | EPM-ARCS-027 | [5 empty] | Simple
318 | ABC Corp | 1a | EPM | EPM - CCR | ARCS | Extension | EXT033 | Auditor to receive notifications once the reconciliations are closed. | [5 empty] | EPM-ARCS-031 | [5 empty] | Complex
319 | ABC Corp | 1a | EPM | EPM - CCR | ARCS | Interface | INT172 | Load data from Oracle Cloud GL to reconcile Functional currency balances | [5 empty] | EPM-ARCS-034 |  | Interface - Inbound (Using Middleware) |  |  |  | Complex
320 | ABC Corp | 1a | EPM | EPM - CCR | ARCS | Interface | INT173 | Load data from Oracle Cloud GL to reconcile Entered currency balances | [5 empty] | EPM-ARCS-034 |  | Interface - Inbound (Using Middleware) |  |  |  | Complex
321 | ABC Corp | 1a | EPM | EPM - CCR | ARCS | Interface | INT174 | Load data from PeopleSoft to reconcile Functional currency balances | [5 empty] | EPM-ARCS-035 |  | Interface - Inbound (Using Middleware) |  |  |  | Complex
322 | ABC Corp | 1a | EPM | EPM - CCR | ARCS | Interface | INT175 | Load data from PeopleSoft to reconcile Entered currency balances | [5 empty] | EPM-ARCS-035 |  | Interface - Inbound (Using Middleware) |  |  |  | Complex
323 | ABC Corp | 1a | EPM | EPM - CCR | ARCS | Interface | INT176 | Load data from Close and Consolidations to reconcile Functional currency balances | [5 empty] | EPM-ARCS-036 |  | Interface - Inbound (Using Middleware) |  |  |  | Complex
324 | ABC Corp | 1a | EPM | EPM - CCR | ARCS | Interface | INT177 | Load data from FX Exchange Rates | [5 empty] | EPM-ARCS-037 |  | Interface - Inbound (Using Middleware) |  |  |  | Complex
325 | ABC Corp | 1a | EPM | EPM - CCR | ARCS | Interface | INT178 | Load balance comparison data from Lease Harbor (flat file) to reconcile my functional currency balances | [5 empty] | EPM-ARCS-037 |  | Interface - Inbound (Using Middleware) |  |  |  | Complex
326 | ABC Corp | 1a | EPM | EPM - CCR | ARCS | Extension | EXT034 | Reconciliations to have the following Risk Rating : Medium : Balance is more than $x Low : Balance is less than $x | [5 empty] | EPM-ARCS-040 | [5 empty] | Medium
327 | ABC Corp | 1a | EPM | EPM - CCR | ARCS | Extension | EXT035 | Ability to do reconciliation based on an Legal Entity-Operating Group-Account- Department- Site-Project combination (unique reconciliations) | [5 empty] | EPM-ARCS-001 | [5 empty] | Complex
354 | ABC Corp | 1A | EPM | EPM - Plan & Budget | EPBCS | Extension | EXT057 | Currency Conversion - Local Currency to USD translation |  |  |  |  | KDD16 | EPM-EPBCS-010 |  | Business Rule |  |  |  | Medium
355 | ABC Corp | 1A | EPM | EPM - Plan & Budget | EPBCS | Extension | EXT117 | EPM Automate - script to trigger data integration process with Daily Sales |  |  |  |  | KDD20 | EPM-EPBCS-072 |  | Business Batch Script |  |  |  | Medium
356 | ABC Corp | 1A | EPM | EPM - Plan & Budget | EPBCS | Extension | EXT058 | EPM Automate - EPM Automation to automate admin activities |  |  |  |  | KDD18 | EPM-EPBCS-004 |  | Business Batch Script |  |  |  | Medium
357 | ABC Corp | 1A | EPM | EPM - Plan & Budget | EPBCS | Extension | EXT059 | Plan/Forecast BS - Ability to input Plan/Forecast values for Balance Sheet at monthly level. |  |  |  |  | KDD16 | EPM-EPBCS-005 |  | WebForm |  |  |  | Simple
358 | ABC Corp | 1A | EPM | EPM - Plan & Budget | EPBCS | Extension | EXT060 | Plan/Forecast P&L - Detailed Income Statement data review on accounts e.g. EBITDA, Gross Margin |  |  |  |  | KDD17 | EPM-EPBCS-006 |  | WebForm |  |  |  | Simple
359 | ABC Corp | 1A | EPM | EPM - Plan & Budget | EPBCS | Extension | EXT062 | Driver Input - Capture Work day, actual billing day as driver |  |  |  |  | KDD17 | EPM-EPBCS-026 |  | WebForm |  |  |  | Simple
360 | ABC Corp | 1A | EPM | EPM - Plan & Budget | EPBCS | Extension | EXT063 | IS by Shipment -Revenue, COS and Billing margin By Shipment type |  |  |  |  | KDD17 | EPM-EPBCS-027 |  | WebForm |  |  |  | Medium
361 | ABC Corp | 1A | EPM | EPM - Plan & Budget | EPBCS | Extension | EXT064 | Global Assumptions Form - Perform Global assumptions at SBU level on Gross Profit accounts |  |  |  |  | KDD19 | EPM- EPBCS-028 |  | WebForm |  |  |  | Complex
362 | ABC Corp | 1A | EPM | EPM - Plan & Budget | EPBCS | Extension | EXT065 | Global Assumptions Form - Perform Global assumptions at SBU level on Operating expense accounts |  |  |  |  | KDD19 | EPM- EPBCS-029 |  | WebForm |  |  |  | Complex
363 | ABC Corp | 1A | EPM | EPM - Plan & Budget | EPBCS | Extension | EXT066 | Global Assumptions - Perform Global assumptions at SBU level on Gross Profit accounts |  |  |  |  | KDD19 | EPM- EPBCS-028 |  | Business Rule |  |  |  | Complex
364 | ABC Corp | 1A | EPM | EPM - Plan & Budget | EPBCS | Extension | EXT067 | Global Assumptions - Perform Global assumptions at SBU level on Operating expense accounts |  |  |  |  | KDD19 | EPM- EPBCS-029 |  | Business Rule |  |  |  | Complex
365 | ABC Corp | 1A | EPM | EPM - Plan & Budget | EPBCS | Extension | EXT068 | Revenue Driver - Capture Revenue driver e.g. Market growth, Price adjustment |  |  |  |  | KDD17 | EPM- EPBCS-030 |  | WebForm |  |  |  | Simple
366 | ABC Corp | 1A | EPM | EPM - Plan & Budget | EPBCS | Extension | EXT069 | Allocations OPEX - Perform Allocation on Operational Expense account at each entity |  |  |  |  | KDD19 | EPM- EPBCS-032 |  | Business Rule |  |  |  | Complex
367 | ABC Corp | 1A | EPM | EPM - Plan & Budget | EPBCS | Extension | EXT070 | COS as % Improvement - Cost of sales planned as % Improvement in Gross Profit $. |  |  |  |  | KDD17 | EPM- EPBCS-036 |  | WebForm |  |  |  | Medium
368 | ABC Corp | 1A | EPM | EPM - Plan & Budget | EPBCS | Extension | EXT071 | People Cost driver - Capture FTE/Headcount as drivers |  |  |  |  | KDD17 | EPM- EPBCS-037 |  | WebForm |  |  |  | Simple
369 | ABC Corp | 1A | EPM | EPM - Plan & Budget | EPBCS | Extension | EXT072 | Corporate Driver - Capture Corporate Driver e.g. HC, In, Outs |  |  |  |  | KDD17 | EPM- EPBCS-038 |  | WebForm |  |  |  | Simple
370 | ABC Corp | 1A | EPM | EPM - Plan & Budget | EPBCS | Extension | EXT073 | Compensation KPI and spend - Capture Compensation and Effciency KPI's |  |  |  |  | KDD17 | EPM- EPBCS-039 |  | Business Rule |  |  |  | Medium
371 | ABC Corp | 1A | EPM | EPM - Plan & Budget | EPBCS | Extension | EXT074 | Expense Planning - Expense Planning based on % of sales and other drivers |  |  |  |  | KDD17 | EPM- EPBCS-040 |  | Business Rule |  |  |  | Simple
372 | ABC Corp | 1A | EPM | EPM - Plan & Budget | EPBCS | Extension | EXT075 | BS Planning - Plan Balance sheet at SBU level |  |  |  |  | KDD17 | EPM-EPBCS-043 |  | Business Rule |  |  |  | Simple
373 | ABC Corp | 1A | EPM | EPM - Plan & Budget | EPBCS | Extension | EXT076 | Calculate Plan/Forecast - Standardized KPI's to evaluate Plan and Forecast |  |  |  |  | KDD17 | EPM-EPBCS-057 |  | Business Rule |  |  |  | Simple
374 | ABC Corp | 1A | EPM | EPM - Plan & Budget | EPBCS | Extension | EXT077 | Report KPI - Report Calculated KPI's based of GL/FCCS to analyze performance on Actuals (in ASO cube) |  |  |  |  | KDD17 | EPM-EPBCS-058 |  | Business Rule |  |  |  | Simple
375 | ABC Corp | 1A | EPM | EPM - Plan & Budget | EPBCS | Extension | EXT078 | Daily Sales Adjustments |  |  |  |  | KDD20 | EPM-EPBCS-074 |  | WebForm |  |  |  | Medium
376 | ABC Corp | 1A | EPM | EPM - Plan & Budget | EPBCS | Extension | EXT079 | Scenario Copy - Data Copy from Seeding Plan to Forecast |  |  |  |  | KDD18 | EPM-EPBCS-075 |  | Business Rule |  |  |  | Simple
377 | ABC Corp | 1A | EPM | EPM - Plan & Budget | EPBCS | Extension | EXT080 | Scenario Copy - Data Copy from Seeding Forecast to Plan |  |  |  |  | KDD18 | EPM-EPBCS-076 |  | Business Rule |  |  |  | Simple
378 | ABC Corp | 1A | EPM | EPM - Plan & Budget | EPBCS | Extension | EXT081 | Version Copy - Data copy between different Versions |  |  |  |  | KDD18 | EPM-EPBCS-077 |  | Business Rule |  |  |  | Simple
379 | ABC Corp | 1A | EPM | EPM - Plan & Budget | EPBCS | Extension | EXT082 | Site Copy - Copy Data from Total Site data to No Site |  |  |  |  | KDD18 | EPM-EPBCS-079 |  | Business Rule |  |  |  | Simple
380 | ABC Corp | 1A | EPM | EPM - Plan & Budget | EPBCS | Interface | INT201 | TB GL to EPBCS Fin - Load Actual Trial Balances data to EPBCS - Financial Cube from Oracle Cloud GL (ERP) |  |  | Oracle ERP Cloud | EPBCS - Financials | KDD18 | EPM-EPBCS-063 |  | Interface |  |  |  | Medium
381 | ABC Corp | 1A | EPM | EPM - Plan & Budget | EPBCS | Interface | INT202 | TB FCCS to EPBCS Fin - Load Actual Trial Balances data to EPBCS - Financial Cube from Oracle Close and Consolidation. |  |  | Oracle EPM - FCCS | EPBCS - Financials | KDD18 | EPM-EPBCS-064 |  | Interface |  |  |  | Simple
382 | ABC Corp | 1A | EPM | EPM - Plan & Budget | EPBCS | Interface | INT203 | Adjustment FCCS to EPBCS Fin - Load Adjustment Balances data to EPBCS - Financial Cube from Oracle Close and Consolidations. |  |  | Oracle EPM - FCCS | EPBCS - Financials | KDD18 | EPM-EPBCS-065 |  | Interface |  |  |  | Simple
383 | ABC Corp | 1A | EPM | EPM - Plan & Budget | EPBCS | Interface | INT204 | Rates FCCS to EPBCS Fin - Load Month End and Month Average Exchange Rates by Currency data to EPBCS - Financial Cube from Oracle Close and Consolidations. |  |  | Oracle EPM - FCCS | EPBCS - Financials | KDD18 | EPM-EPBCS-066 |  | Interface |  |  |  | Simple
384 | ABC Corp | 1A | EPM | EPM - Plan & Budget | EPBCS | Interface | INT205 | Lease Harbour to EPBCS RPT - Load Future rent and operating lease payment projections data to EPBCS- Financial Cube from Lease Harbor. |  |  | Lease Harbor | EPBCS - Reporting | KDD18 | EPM-EPBCS-067 |  | Interface |  |  |  | Medium
385 | ABC Corp | 1A | EPM | EPM - Plan & Budget | EPBCS | Interface | INT206 | TB EPBCS Fin to RPT - Load Actual Trial Balances data to EPBCS - Reporting from EPBCS - Financials Cube. |  |  | EPBCS - Financials | EPBCS - Reporting | KDD18 | EPM-EPBCS-068 |  | Interface |  |  |  | Simple
386 | ABC Corp | 1A | EPM | EPM - Plan & Budget | EPBCS | Interface | INT207 | Budget EPBCS Fin to RPT - Load Budget data by GL Account to EPBCS - Reporting Cube from EPBCS - Financials Cube. |  |  | EPBCS - Financials | EPBCS - Reporting | KDD18 | EPM-EPBCS-069 |  | Interface |  |  |  | Simple
387 | ABC Corp | 1A | EPM | EPM - Plan & Budget | EPBCS | Interface | INT208 | Forecast EPBCS Fin to RPT - Load Forecast data by GL Account to EPBCS- Reporting from EPBCS - Financials Cube. |  |  | EPBCS - Financials | EPBCS - Reporting | KDD18 | EPM-EPBCS-070 |  | Interface |  |  |  | Simple
388 | ABC Corp | 1A | EPM | EPM - Plan & Budget | EPBCS | Interface | INT209 | Budget EPBCS Fin to Teradata - Load level 0 Budget data by GL Account to Teradata from EPBCS - Financials Cube. |  |  | EPBCS - Financials | Teradata | KDD18 | EPM-EPBCS-071 |  | Interface |  |  |  | Simple
389 | ABC Corp | 1A | EPM | EPM - Plan & Budget | EPBCS | Interface | INT210 | Forecast EPBCS Fin to Teradata - Load level 0 Forecast data by GL Account to Teradata from EPBCS - Financials Cube. |  |  | EPBCS - Financials | Teradata | KDD18 | EPM-EPBCS-072 |  | Interface |  |  |  | Simple
390 | ABC Corp | 1A | EPM | EPM - Plan & Budget | EPBCS | Interface | INT211 | Actuals EPBCS Fin to Teradata - Load level 0 Actuals data by GL Account to Teradata from EPBCS - Financials Cube. |  |  | EPBCS - Financials | Teradata | KDD18 | EPM-EPBCS-073 |  | Interface |  |  |  | Simple
391 | ABC Corp | 1A | EPM | EPM - Plan & Budget | EPBCS | Interface | INT212 | Lease Harbour Temp - Standardized data collection templates in Smart View for Lease Harbor data input. |  |  | EPBCS - Financials | Lease Harbor | KDD18 | EPM-EPBCS-033 |  | SmartView Templates |  |  |  | Complex
392 | ABC Corp | 1A | EPM | EPM - Plan & Budget | EPBCS | Extension | EXT083 | Scenario Archived Rule - Copy Scenario data to archive scenario |  |  |  |  | KDD18 | EPM-EPBCS-062 |  | Business Rule |  |  |  | Simple
393 | ABC Corp | 1A | EPM | EPM - Plan & Budget | EPBCS | Extension | EXT084 | Scenario Archived Form - Copy Scenario data to archive scenario |  |  |  |  | KDD18 | EPM-EPBCS-062 |  | Webform | Medium |  |  | Simple
394 | ABC Corp | 1A | EPM | EPM - Plan & Budget | EPBCS | Extension | EXT085 | Selective aggregation Rule - Aggregate data based on selective scenario and period |  |  |  |  | KDD18 | EPM-EPBCS-032 |  | Business Rule |  |  |  | Simple
395 | ABC Corp | 1A | EPM | EPM - Plan & Budget | EPBCS | Extension | EXT086 | Calc all Models - Calculate model once data gets loaded |  |  |  |  | KDD17 | EPM-EPBCS-001 |  | Business Rule |  |  |  | Simple
396 | ABC Corp | 1A | EPM | EPM - Plan & Budget | EPBCS | Extension | EXT087 | Sales Growth% - Calc Sales Growth % based on Prior year for Plan and Forecast |  |  |  |  | KDD17 | EPM-EPBCS-040 |  | Business Rule |  |  |  | Simple
397 | ABC Corp | 1A | EPM | EPM - Plan & Budget | EPBCS | Extension | EXT088 | Data Map - Archive Forecast scenario(BSO to ASO) |  |  |  |  | KDD18 | EPM-EPBCS-068 |  | Data Map |  |  |  | Medium
398 | ABC Corp | 1A | EPM | EPM - Plan & Budget | EPBCS | Extension | EXT089 | Data Map - Actual, Plan, Forecast Scenario(BSO to ASO) |  |  |  |  | KDD18 | EPM-EPBCS-069,070 |  | Data Map |  |  |  | Simple
399 | ABC Corp | 1A | EPM | EPM - Plan & Budget | EPBCS | Extension | EXT090 | Cost of Sales - Calculate Cost of Sales based on Billing Margin inputs |  |  |  |  | KDD17 | EPM-EPBCS-027 |  | Business Rule |  |  |  | Medium
400 | ABC Corp | 1A | EPM | EPM - Plan & Budget | EPBCS | Interface | INT213 | Clear Data - Interface Script to clear selective data before load |  |  |  |  | KDD18 | EPM-EPBCS-069,070(Collect Data) |  | Interface |  |  |  | Simple
401 | ABC Corp | 1A | EPM | EPM - Plan & Budget | EPBCS | Conversion | CNV023 | Load Actuals data |  |  | FCCS | EPBCS - Financials | KDD18 | EPM-EPBCS-068 |  | Data Load |  |  |  | Medium
402 | ABC Corp | 1A | EPM | EPM - Plan & Budget | EPBCS | Conversion | CNV024 | Load Forecast data |  |  | OneStream | EPBCS - Financials | KDD18 | EPM-EPBCS-069 |  | Data Load |  |  |  | Medium
403 | ABC Corp | 1A | EPM | EPM - Plan & Budget | EPBCS | Conversion | CNV025 | Load Plan Data |  |  | OneStream | EPBCS - Financials | KDD18 | EPM-EPBCS-070 |  | Data Load |  |  |  | Medium
404 | ABC Corp | 1A | EPM | EPM - Plan & Budget | EPBCS | Conversion | CNV026 | Setup Data Management job to import historical Daily Sales Report data from EDW |  |  | Teradata EDW | EPBCS - Daily Sales | KDD20 | EPM-EPBCS-095 |  | Data Load |  |  |  | Medium
405 | ABC Corp | 1A | EPM | EPM - Plan & Budget | EPBCS | Extension | EXT091 | Daily Sales Cube will need 5 Business Rules / 25 Member Formulas |  |  |  |  | KDD20 | EPM-EPBCS-095 |  | Business Rule |  |  |  | Simple
406 | ABC Corp | 1A | EPM | EPM - Plan & Budget | EPBCS | Extension | EXT092 | Daily Sales Cube will need 5 Business Rules / 25 Member Formulas |  |  |  |  | KDD20 | EPM-EPBCS-095 |  | Business Rule |  |  |  | Simple
407 | ABC Corp | 1A | EPM | EPM - Plan & Budget | EPBCS | Extension | EXT093 | Daily Sales Cube will need 5 Business Rules / 25 Member Formulas |  |  |  |  | KDD20 | EPM-EPBCS-095 |  | Business Rule |  |  |  | Medium
408 | ABC Corp | 1A | EPM | EPM - Plan & Budget | EPBCS | Extension | EXT094 | Daily Sales Cube will need 5 Business Rules / 25 Member Formulas |  |  |  |  | KDD20 | EPM-EPBCS-095 |  | Business Rule |  |  |  | Medium
409 | ABC Corp | 1A | EPM | EPM - Plan & Budget | EPBCS | Extension | EXT095 | Daily Sales Cube will need 5 Business Rules / 25 Member Formulas |  |  |  |  | KDD20 | EPM-EPBCS-095 |  | Business Rule |  |  |  | Medium
410 | ABC Corp | 1A | EPM | EPM - Plan & Budget | EPBCS | Extension | EXT096 | Actuals_Load_TB_FS - Calculates Periodic value once data gets loaded |  |  |  |  | KDD18 | EPM-EPBCS-063 |  | Business Rule |  |  |  | Simple
411 | ABC Corp | 1A | EPM | EPM - Plan & Budget | EPBCS | Extension | EXT097 | Constant currency IS - Income Statement with Constant Currency Scenario |  |  |  |  | KDD17 | EPM_EPBCS-060 |  | Webform |  |  |  | Complex
412 | ABC Corp | 1A | EPM | EPM - Plan & Budget | EPBCS | Extension | EXT098 | Constant currency BS - Balance Sheet with Constant Currency Scenario |  |  |  |  | KDD17 | EPM-EPBCS-060 |  | Webform |  |  |  | Complex
413 | ABC Corp | 1A | EPM | EPM - Plan & Budget | EPBCS | Extension | EXT099 | Review Exchange Rates - Review rates for various scenarios |  |  |  |  | KDD17 | EPM-EPBCS-046 |  | Webform |  |  |  | Simple
414 | ABC Corp | 1A | EPM | EPM - Plan & Budget | EPBCS | Extension | EXT100 | Allocations OPEX Form - Perform Allocation on Operational Expense account at each entity |  |  |  |  | KDD19 | EPM- EPBCS-032 |  | WebForm | Complex |  |  | Complex
415 | ABC Corp | 1A | EPM | EPM - Plan & Budget | EPBCS | Extension | EXT101 | Compensation KPI Form - Capture Compensation and Effciency KPI's |  |  |  |  | KDD17 | EPM- EPBCS-039 |  | WebForm | Medium |  |  | Simple
416 | ABC Corp | 1A | EPM | EPM - Plan & Budget | EPBCS | Extension | EXT102 | Selective aggregation form - Aggregate data based on selective scenario and period |  |  |  |  | KDD17 | EPM-EPBCS-032 |  | Webform | Medium |  |  | Complex
417 | ABC Corp | 1A | EPM | EPM - Plan & Budget | EPBCS | Extension | EXT103 | Dashboard KPI - Net Sales & Total Gross Profit KPI |  |  |  |  | KDD17 | EPM-EPBCS-007 |  | Webform |  |  |  | Medium
418 | ABC Corp | 1A | EPM | EPM - Plan & Budget | EPBCS | Extension | EXT104 | Dashboard KPI - Margin % & Total field Expenses |  |  |  |  | KDD17 | EPM-EPBCS-007 |  | Webform |  |  |  | Medium
419 | ABC Corp | 1A | EPM | EPM - Plan & Budget | EPBCS | Extension | EXT105 | Dashboard KPI - Expense % of sales & Operating Profit |  |  |  |  | KDD17 | EPM-EPBCS-007 |  | Webform |  |  |  | Medium
420 | ABC Corp | 1A | EPM | EPM - Plan & Budget | EPBCS | Extension | EXT106 | Dashboard KPI - Headcount, IN and Out |  |  |  |  | KDD17 | EPM-EPBCS-038 |  | Webform |  |  |  | Medium
421 | ABC Corp | 1A | EPM | EPM - Plan & Budget | EPBCS | Extension | EXT107 | Dashboard KPI - Market Growth % 2) Pricing Adj % 3) New Cust/Project % |  |  |  |  | KDD17 | EPM-EPBCS-030 |  | Webform |  |  |  | Medium
422 | ABC Corp | 1A | EPM | EPM - Plan & Budget | EPBCS | Extension | EXT108 | Standarized KPI - Billing Margin and Rate |  |  |  |  | KDD17 | EPM-EPBCS-007 |  | Webform |  |  |  | Simple
423 | ABC Corp | 1A | EPM | EPM - Plan & Budget | EPBCS | Extension | EXT109 | Compensation KPI - Fringe Benefits as % of Salaries and 2) Sales / Headcount |  |  |  |  | KDD17 | EPM-EPBCS-039 |  | Webform |  |  |  | Simple
424 | ABC Corp | 1A | EPM | EPM - Plan & Budget | EPBCS | Extension | EXT110 | Dashboard KPI - Standardized KPI for Plan and forecast |  |  |  |  | KDD17 | EPM-EPBCS-057 |  | Webform |  |  |  | Medium
425 | ABC Corp | 1A | EPM | EPM - Plan & Budget | EPBCS | Extension | EXT111 | Dashboard KPI - Report calculated KPI for GL and FCCS performance analysis |  |  |  |  | KDD17 | EPM-EPBCS-058 |  | Webform |  |  |  | Medium
426 | ABC Corp | 1A | EPM | EPM - Plan & Budget | EPBCS | Extension | EXT112 | Daily Sales - review base data received from Teradata EDW |  |  |  |  | KDD20 | EPM-EPBCS-095 |  | Webform |  |  |  | Simple
427 | ABC Corp | 1A | EPM | EPM - Plan & Budget | EPBCS | Extension | EXT113 | Daily Sales - make adjustments to base data to take care of any errors/gaps in dataset |  |  |  |  | KDD20 | EPM-EPBCS-095 |  | Webform |  |  |  | Simple
428 | ABC Corp | 1A | EPM | EPM - Plan & Budget | EPBCS | Extension | EXT114 | Daily Sales - upload off-system entities data |  |  |  |  | KDD20 | EPM-EPBCS-095 |  | Webform |  |  |  | Simple
429 | ABC Corp | 1A | EPM | EPM - Plan & Budget | EPBCS | Extension | EXT115 | Financial Metrics KPI - General finance Metrics KPI to analyse expenses, sales, profit, and cash flow. |  |  |  |  | KDD17 | EPM-EPBCS-007 |  | Webform |  |  |  | Simple
430 | ABC Corp | 1A | EPM | EPM - Plan & Budget | EPBCS | Report | RPT104 | P&L Report - A standardized report based upon the EES P&L report in the EPM_Reports_02JUL21 File. | [5 empty] | EPM-EPBCS-080 |  | Report |  |  |  | Complex
431 | ABC Corp | 1A | EPM | EPM - Plan & Budget | EPBCS | Report | RPT105 | Trended P&L report - A standardized report based upon the Trended P&L report in the EPM_Reports_02JUL21 File. | [5 empty] | EPM-EPBCS-081 |  | Report |  |  |  | Complex
432 | ABC Corp | 1A | EPM | EPM - Plan & Budget | EPBCS | Report | RPT106 | ROIA report - A standardized report based upon the ROIA report in the EPM_Reports_02JUL21 file. | [5 empty] | EPM-EPBCS-082 |  | Report |  |  |  | Complex
433 | ABC Corp | 1A | EPM | EPM - Plan & Budget | EPBCS | Report | RPT107 | Balance Sheet report - A standardized report based upon the provided Balance Sheet report EPM_Reports_02JUL21 file.. | [5 empty] | EPM-EPBCS-083 |  | Report |  |  |  | Complex
434 | ABC Corp | 1A | EPM | EPM - Plan & Budget | EPBCS | Report | RPT108 | Account Review report - A standardized report based upon the Account Review report in the EPM_Reports_02JUL21 file. | [5 empty] | EPM-EPBCS-084 |  | Report |  |  |  | Complex
435 | ABC Corp | 1A | EPM | EPM - Plan & Budget | EPBCS | Report | RPT109 | Balance Sheet report - A standardized report based upon the provided Balance Sheet report Balance Sheet 2021 Plan file provided. | [5 empty] | EPM-EPBCS-085 |  | Report |  |  |  | Simple
436 | ABC Corp | 1A | EPM | EPM - Plan & Budget | EPBCS | Report | RPT110 | Income Statement Variance Analysis (Budget) by Period USD Translated | [5 empty] | EPM-EPBCS-085 |  | Report |  |  |  | Simple
437 | ABC Corp | 1A | EPM | EPM - Plan & Budget | EPBCS | Report | RPT111 | Income Statement History - Preliminary Close | [5 empty] | EPM-EPBCS-086 |  | Report |  |  |  | Simple
438 | ABC Corp | 1A | EPM | EPM - Plan & Budget | EPBCS | Report | RPT112 | Income Statement Variance Analysis (Budget) by Quarter | [5 empty] | EPM-EPBCS-087 |  | Report |  |  |  | Simple
439 | ABC Corp | 1A | EPM | EPM - Plan & Budget | EPBCS | Report | RPT113 | Income Statement Variance Analysis (US Budget) by Quarter | [5 empty] | EPM-EPBCS-088 |  | Report |  |  |  | Simple
440 | ABC Corp | 1A | EPM | EPM - Plan & Budget | EPBCS | Report | RPT114 | Income Statement Variance Analysis (CA Budget) by Quarter | [5 empty] | EPM-EPBCS-089 |  | Report |  |  |  | Simple
441 | ABC Corp | 1A | EPM | EPM - Plan & Budget | EPBCS | Report | RPT115 | Standard Cost Income Statement Variance Analysis (Consolidated Budget) by Period | [5 empty] | EPM-EPBCS-090 |  | Report |  |  |  | Medium
442 | ABC Corp | 1A | EPM | EPM - Plan & Budget | EPBCS | Report | RPT116 | Standard Cost Income Statement Variance Analysis (Canada Budget) by Period | [5 empty] | EPM-EPBCS-091 |  | Report |  |  |  | Simple
443 | ABC Corp | 1A | EPM | EPM - Plan & Budget | EPBCS | Report | RPT117 | Standard Cost Income Statement Variance Analysis (US Budget) by Period | [5 empty] | EPM-EPBCS-092 |  | Report |  |  |  | Simple
444 | ABC Corp | 1A | EPM | EPM - Plan & Budget | EPBCS | Report | RPT118 | Standard Cost History - Preliminary Close | [5 empty] | EPM-EPBCS-093 |  | Report |  |  |  | Simple
445 | ABC Corp | 1A | EPM | EPM - Plan & Budget | EPBCS | Report | RPT119 | OpsFin1-4 | [5 empty] | EPM-EPBCS-094 |  | Report |  |  |  | Medium
446 | ABC Corp | 1A | EPM | EPM - Plan & Budget | EPBCS | Report | RPT120 | Daily Sales Jun21 Current Format | [5 empty] | EPM-EPBCS-095 |  | Report |  |  |  | Medium
447 | ABC Corp | 1A | EPM | EPM - Plan & Budget | EPBCS | Report | RPT121 | Daily Sales CSS Jun21 | [5 empty] | EPM-EPBCS-096 |  | Report |  |  |  | Medium
448 | ABC Corp | 1A | EPM | EPM - Plan & Budget | EPBCS | Report | RPT122 | Page 1 of Daily Sales Analysis 06-21 CSS | [5 empty] | EPM-EPBCS-097 |  | Report |  |  |  | Medium
449 | ABC Corp | 1A | EPM | EPM - Plan & Budget | EPBCS | Report | RPT123 | Page 2 of Daily Sales Analysis 06-21 CSS | [5 empty] | EPM-EPBCS-098 |  | Report |  |  |  | Medium
450 | ABC Corp | 1A | EPM | EPM - Plan & Budget | EPBCS | Report | RPT124 | Cash Flow report - A standardized report based upon the provided Cash Flow 2021 Plan file provided. | [5 empty] | EPM-EPBCS-086 |  | Report |  |  |  | Simple
451 | ABC Corp | 1A | EPM | EPM - Plan & Budget | EPBCS | Interface | INT214 | Inbound data integration from Teradata EDW to EPBCS. A single integration will be built for importing Sales, CoS, Backlog, and Booking and other data points. Data from EDW will be provided in the future state COA model. |  |  | Teradata EDW | EPBCS - Daily Sales | KDD20 | EPM-EPBCS-072 |  | Interface | Complex |  |  | Very Complex
Note on K2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Development on the legacy - boundary application

## AHCS Rep.User Story RICE Ration
Unique ID | L0 | L1 | L2 | User Story | Comments / High-level Approach Notes | Acceptance Criteria 1 | Acceptance Criteria 2 | Acceptance Criteria 3 | Release | AB RICE Name | RICE ID
RTR-AHCS-025 | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As a GL Accountant, I want a report to reconcile AHCS subldger and Oracle Cloud GL so that I can perform period close reconciliations | AHCS to GL Reconciliation Report: Shows AHCS and GL code combination balances side by side for reconciliation | Validate report and compare to legacy subledger to GL reconciliations. | Review AHCS to GL Reconciliation report for variances between legacy, AHCS. Resolve variances as needed. |  | Phase 1A+1B | AHCS to GL Recon Report | RPT-007
RTR-AHCS-026 | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As a GL accountant, I want a report with error details along with error descriptions for all failures (mapping, validations etc.) so that I can review and resolve the errors | AHCS Error Report: Errors from Cloud AHCS after processing data by incoming file name and error description. Error / process summary with source chart of accounts and error description | Validate setups and report with test transactions. Confirm invalid data does not interface / import / post. | Validate incorrect transactions are carved-out of daily interface and not imported to the HUB. Validate the remaining interface transactions that pass validations are import to the HUB. | Review AHCS error report for missing coa segments. Verify that transactions did not import to AHCS until COA missing segments were updated. | Phase 1A+1B | AHCS Error Report | RPT-006
RTR-AHCS-027 | Record to Report | Manage Subledger Accounting | Run Subledger Reports | As a GL Accountant, I want a report that shows exceptions for all AHCS subledgers so that during close I can ensure all transactions are processed from AHCS to GL. | Subledger Period Close Exception Report: This report provides the exceptions in AHCS that are unprocessed, error or invalid transactions. Report should run across all ledgers and across AHCS subledgers. | Validate setups and report with test transactions. Confirm invalid data does not interface / import / post. | Validate incorrect transactions are carved-out of daily interface and not imported to the HUB. Validate the remaining interface transactions that pass validations are import to the HUB. | Review Subledger Period Close Exception Report for error details. Verify that transactions did not import to AHCS until details have been corrected. | Phase 1A+1B | Subledger Period Close Exception Report by Ledger Set | RPT-008

## LOVs
Track | SubTrack | Oracle Module | L0 | L1 | L2 | Release | Design Sprint | Build Sprint | User story disposition | Disposition# | Fit/Gap | Type | SubType | Subtype Status | Priority | User Story Size
RTR | RTR-GL | GL | Close, Consolidate, and Report | Master Data Management | Analyze Financials | Phase 1A+1B | 1 | 0 | 1-Fit-Configuration-Functional | 1 | Fit | Configuration | Functional | Drafted | Must Have | XS
EPM | RTR-AHCS | AHCS | Enterprise Planning, Budgeting, and Reporting | Close | Approve and Post Journal Entries | Phase 1A only | 2 | 1 | 2-Gap-Build-Report | 2 | Gap | Build | Report | Initial Fit/Gap Complete | Should Have | S
COA | COA | EDMCS | Record to Report | Consolidate | Collect Data | Phase 1B only | 3 | 2 | 3-Gap-Build-Interface | 3 | Gap | Build | Interface | Review In Progress | Could Have | M
TECH | TECH | IC |  | Report | Create Subledger Accounting | Future Phase | 4 | 3 | 4-Gap-Build-Conversions | 4 | Gap | Build | Conversions | Acceptance Criteria Documented | Won't Have | L
| AXE-Calendar Change | FCCS |  | Financials | Eliminate Intercompany | Not Required | 5 | 4 | 5-Gap-Build-Extension | 5 | Gap | Build | Extension | Revalidate Fit/Gap |  | XL
| EPM - Plan & Budget | ARCS |  | Manage Subledger Accounting | Maintain Chart of Accounts |  | 6 | 5 | 6-Gap-Work Around-Work Around | 6 | Gap | Work Around | Work Around | Submitted for Approval
| EPM - CCR | EPBCS |  | Manage General Ledger Accounting | Maintain Industry and Company Specific Attributes |  | 7 | 6 | 7-Out of Scope-Out of Scope-Out of Scope | 7 | Out of Scope | Out of Scope | Out of Scope | Approved
| EPM - COA MDM | LEGACY |  | Manage Intercompany Accounting | Maintain Reporting Entities |  | 8 |  | 8-TBD (Temporary)-TBD-TBD | 8 | TBD (Temporary) | TBD | TBD | TBD
| LEGACY | SECURITY |  |  | Maintain Standard Dimensionality |  | 9 |  | 9-Gap (Temporary)-Gap-Gap | 9 | Gap (Temporary) | Gap | Gap
| BI | COA |  |  | Manage Information Interface and Transformation |  | 10 |  | 10-Not Required-Not Required-Not Required | 10 | Not Required | Not Required | Not Required
| SECURITY | BI |  |  | Manage Users and Access Rights |  | 11
[5 empty] | Perform Allocations |  | 12
Perform Balance Sheet Planning
Perform Cash Flow Planning
Perform Currency Revaluations
Perform Equity Accounting
Perform Expense Planning
Perform External Reporting
Perform Financial Management Reporting
Perform Income Statement Planning
Perform Intercompany Netting & Reconciliation
Perform Intercompany Transactions
Perform Management Review
Perform Revenue Planning
Period-End Closing & Reporting
Prepare Financial Statements
Prepare Group Financial Statements
Process Intercompany AR/AP Invoices
Process Intercompany Journal Entries
Process Intercompany Settlements
Process Manual Journal Entries
Process Recurring Journal Entries
Process Reversing Journal Entries
Reconcile Accounts
Run Subledger Reports
Perform AP Period Close
Perform AR Period Close

## SIT2 -Smoke Test (hidden)
Batch I - Dev21 (SIT2) | [6 empty] | Batch II - Dev21 (SIT2) | [6 empty] | Batch III - Dev21 (SIT2)
Subledger | Smoke Test Transaction # | Ledger | Status | Observations | Resolutions |  | Subledger | Smoke Test Transaction # | Ledger | Status | Observations | Resolutions |  | Subledger | Smoke Test Transaction # | Ledger | Status | Observations | Resolutions
APS_TREASURY | TMI20220801210201SMOKE | US USGAAP USD | Success | All Good |  |  | MF AP | ADI124580258 | TW USGAAP TWD | Success
ECLPS | ECLUS_20220801_02533820220801 | US USGAAP USD | Success | All Good |  |  | MF AP | CAI107849432 | US USGAAP USD | Success
SXE | SXEUS_20220801_03300220220801 | US USGAAP USD | Success | All Good |  |  | MF AP | API02083907789 | SG USGAAP SGD | Success
CLOUDPAY | 5064_20220801_141513 | AE USGAAP USD | Success | All Good |  |  | MF AP | BKI139171321 | NL USGAAP EUR | Success
PSFA | 00001052022000000019192DPR | AE USGAAP USD | Success | All Good |  |  | MF AP | AQI3291624183 | HK USGAAP HKD | Success
LEASES | LH-23691-E098N03447K | US USGAAP USD | Success | All Good - additional file got processed in 09/16 date |  |  | MF AR | BKI213426983 | PL USGAAP PLN | Success
LEASES | LH-24588-1116 | US USGAAP USD | Success | All Good - additional file got processed in 09/16 date |  |  | MF AR | SPR103561234_T4 | CL USGAAP USD | Success
MF AP |  |  | Not Started |  |  |  | MF AR | SII106220251_T4 | US USGAAP USD | Success
MF AR |  |  | Not Started |  |  |  | MF AR | CRI1037598964_T4 | US USGAAP USD | Success
MF INV |  |  | Not Started |  |  |  | MF AR | ARI123561476_T4 | US USGAAP USD | Success
[7 empty] | MF INV | FII1113046779KT | US USGAAP USD | Success
[7 empty] | MF INV | IBI1088256939KT | SA USGAAP SAR | Success
[7 empty] | MF INV | ISI1113054059KT | US USGAAP USD | Success
[7 empty] | MF INV | ICI1113252379KT | CL USGAAP USD | Success
[7 empty] | MF INV | CQI029451473KT | US USGAAP USD | Success
[7 empty] | MF INV | IRI192178957KT | BR USGAAP USD | Success
[7 empty] | MF INV | FTI1113056689KT | US USGAAP USD | Success
[7 empty] | MF INV | DAI121003789KT | US USGAAP USD | Success
[7 empty] | MF INV | SPC112352488KT | CN USGAAP CNY | Success
Batch I - Dev22 | [6 empty] | Batch II - Dev22
Subledger | Smoke Test Transaction # | Ledger | Status | Observations | Resolutions | SIT2 Actions | Subledger | Smoke Test Transaction # | Ledger | Status | Observations | Resolutions | SIT2 Actions
APS_TREASURY | TMI20220801210201SMOKETEST | US USGAAP USD | Success |  |  |  | MF AP | ADI124580258 | TW USGAAP TWD | Success
ECLPS | ECLUS_20220801_02533820220801 | US USGAAP USD | Success | TRX created with $0.00 , Merge matching lines was All | Merge Matching Lines set to No in Dev22 | No updates required | MF AP | CAI107849432 | US USGAAP USD | Success
SXE | SXEUS_20220801_03300220220801 | US USGAAP USD | Success | TRX created with $0.00 , Merge matching lines was All | Merge Matching Lines set to No in Dev22 | No updates required | MF AP | API02083907789 | SG USGAAP SGD | Success | The subledger journal entry doesn't balance in the entered currency. Cause: The subledger journal entry doesn't balance in the entered currency and it isn't a cross currency transaction. Action: Verify that the journal entry is generated correctly. |  | No updates required
CLOUDPAY | 5064_20220801_141427 | AE USGAAP USD | Success | JLR condition was wrong in Dev22 | Config Update on Dev22 | No updates required | MF AP | BKI139171321 | NL USGAAP EUR | Success | Invoice Number SR is not populated. Source file don't have the data for this field |  | No updates required
PSFA | 00001052022000000019192DPR | US USGAAP USD | Success |  |  |  | MF AP | AQI3291624183 | HK USGAAP HKD | Success
LEASES | LH-24588-1116 | US USGAAP USD | Success |  |  |  | MF AR | BKI213426983 | PL USGAAP PLN | Success
LEASES | LH-23691-E098N03447K | US USGAAP USD | Success |  |  |  | MF AR | SPR103561234_T4 | CL USGAAP USD | Success | RA Number SR has no value. Source file has no value |  | No updates required
MF AP | LSI02055613786 | FI USGAAP EUR | Success | OP GRP was missing 1111 | Added by GL Team | Need to validate | MF AR | SII106220251_T4 | US USGAAP USD | Success | Product Class SR has no value |  | No updates required
MF AR | LSI102382931_T4 | AT USGAAP EUR | Success | Legacy Location SR value was missing | OIC Code Fix | Code re-migration | MF AR | CRI1037598964_T4 | US USGAAP USD | Success
MF INV | AII108978944KT | PE USGAAP USD | Success | Trading Partner #, Name and RA # values were misisng | OIC Code Fix | Code re-migration | MF AR | ARI123561476_T4 | US USGAAP USD | Success
[7 empty] | MF INV | FII1113046779KT | US USGAAP USD | Success | Intercompany Line generated so total amount became 0.2 |  | No updates required
[7 empty] | MF INV | IBI1088256939KT | SA USGAAP SAR | Success
[7 empty] | MF INV | ISI1113054059KT | US USGAAP USD | Success
[7 empty] | MF INV | ICI1113252379KT | CL USGAAP USD | Success
[7 empty] | MF INV | CQI029451473KT | US USGAAP USD | Success
[7 empty] | MF INV | IRI192178957KT | BR USGAAP USD | Success
[7 empty] | MF INV | FTI1113056689KT | US USGAAP USD | Success
[7 empty] | MF INV | DAI121003789KT | US USGAAP USD | Success
[7 empty] | MF INV | SPC112352488KT | CN USGAAP CNY | Success
[7 empty] | CONCUR | 2935_00201 | CA USGAAP CAD | Success
[7 empty] | CONCUR | 2915_00201 | CA USGAAP CAD | Success
[7 empty] | CONCUR | 2935_069_006_1 | CA USGAAP CAD | Success
[7 empty] | CONCUR | 2935_006_069_2 | CA USGAAP CAD | Success
[7 empty] | CONCUR | 2915_006_069_2 | CA USGAAP CAD | Success
[7 empty] | CONCUR | 2915_069_006_1 | CA USGAAP CAD | Success
[7 empty] | CONCUR | 2935_041_002_1 | US USGAAP USD | Success
[7 empty] | CONCUR | 2935_002_041_2 | US USGAAP USD | Success
[7 empty] | CONCUR | 2915_002_041_2 | US USGAAP USD | Success
[7 empty] | CONCUR | 2915_041_002_1 | US USGAAP USD | Success
Batch I - Dev22 | [6 empty] | Batch II - Dev22

## Legacy Reference (hidden)
Legacy FAH Assessment
File Name | Coverage
1B - Business requirement v1 SII No IC | SII FAH maping with rules
ADI Design V18 | MFAP (ADI) Design Doc for Payments and Void
Anixter FAH Source wise Table structure | Table structure for all sources with Data type
Anixter FAH to PSFT GL Process Flow V2.0 (1) | Flow Diagram
Anixter High Level Finance System Overview V2.0 (1) | Flow Diagram
Anixter High Level Finance System Overview V2.0 (2) | Flow Diagram
Anixter Supporting Referencev0.3 | SR : Balance and Non Balnce by source fro FAH
AP process flow 9.0 | Flow Diagram
API Design V29 | MFAP (API) Design Doc
AQI V19 | MFAP (AQI) Design Doc
AR Adjustments (ARI) v15 | MFAR (ARI) Design doc
AR Process flow V2.0 (1) | Flow Diagram
AXE_Configuration_Document_Common_Setup_v1.1 | BR100 for FAH Common Setup [ GL ]
AXE_Configuration_Document_SLA_Setup_v5.6 | BR100 for FAH SLA Setup Last update on August 2018
AXE_GL_INTERFACE_FUNCTIONAL_DESIGN_USGAAP_V1.1 | GL Interface for FAH MD050 Last Updated: January 15, 20208
AXE_GL_INTERFACE_TECHNICAL_DESIGN_V1.1 | GL Interface for FAH MD070 Last Updated: August 23, 2017
AXE_INVENTORY_INTERFACE_FUNCTIONAL_DESIGN_2.1 | INV Interface for FAH MD050 Last Updated: Aug 26, 2017
AXE_INVENTORY_INTERFACE_TECHNICAL_DESIGN_1.0 | INV Interface for FAH MD070 Last Updated: Aug 26, 2017
AXE_PAYABLES_INTERFACE_FUNCTIONAL_DESIGN v2.2 | (API) Payables FAH MD050 Last Updated: January 15, 20208
AXE_PAYABLES_INTERFACE_TECHNICAL_DESIGN | (API) Payables FAH MD070 Last Updated: June 17, 2021
AXE_QUANTITY_INTERFACE_TECHNICAL_DESIGN_1.2 | QUANTITY Interface for FAH MD070 Last Updated: 11-Apr-2018
AXE_RECEIVABLES_INTERFACE_FUNCTIONAL_DESIGN_v2.2 | GL Receivables Interface for FAH MD050 Last Updated: January 15, 2020
AXE_RECEIVABLES_INTERFACE_TECHNICAL_DESIGN | GL Receivables Interface for FAH MD070 Last Updated: June 17, 2021
BKM Examples | BKM Sample file
Cash (CRI) Business Design v20 (2).docx | CRI Design doc FAH
Cash Process Flow V1.0 | Flow Diagram
CQI Design V28 | CQI Design doc FAH
DIST_LN_BU00201_2021_04 | Sample file
Expenses Reimbursement Flow V1.0 | Flow Diagram
FAH Balance Close out Business Design v10 (4).docx | FAH Inventory Balance Close-Out Tool Business design doc
FAH Custom Job Details | Job details for Reports, Interface and Archival
FAH Master Rules List ver 62 | Interface rules master
FAH vs AHCS effort _Kim's Sheet | Efforts spreadsheet
Fixed Asset Process Flow V1.0 | Flow Diagram
Freight Process Flow V1.0 | Flow Diagram
FTI Design V8 | FTI MD050
General Ledger Process flow V2.0 (1) | Flow Diagram
IBI Design v25 (1) | IBI design
IC Repayment Process v10 (2) | Business design for IC Repayment
Intercompany Intransit (ICI)-Sales v8 | ICI Design details
Intercompany Intransit Backout - AII 8 | Intercompany AII Business design
Inventory - from Sales ISI v37 (1) | Inventory Business design
Inventory_Process_Flow V2.0 | Flow Diagram
IRI Design v28 | Inventory Receipt Interface Business design
Liability Switching v12-1 (1) | Intercompany Liability Switching Business Design
Liability Switching v12-1 (4) | Intercompany Liability Switching Business Design
Manual closing of Accruals | 1 Pager notes for Manual closing accr
OnPrem FAH Assessment (003) | FAH Assessment slides
Sales-Trade and IC Design (SII)v 21 | SALES INTERFACE – TRADE & INTERCOMPANY Business design
Special Customer (SSI) Design v22 | SSI Design doc for business
Special Customer process flowv1.0 | Flow Diagram
XXAXE_OBJECT_INVENTORY | INV Tech details like shell scripts, Prgram, Tables etc.
Accounting Hub Volumetric Analysis | 1.86M Journal Lines / Day
WESCO Oracle Accouting Hub Volumetic analysis | Slide for Hub
Note on B21: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: accounting transformation platform between Mainframe and PeopleSoft 9.1 Reply: Out of scope for FAH Implememtation

## Defects & Enhancements (hidden)
Issue key | Issue id | Status | Summary | Update | Assignee | Due date | Created | Custom field (Defect category)
CTPFS-915 | 74572 | Open | RPT009 - Slow run time | 3.5 mins for 40K records | Ramjee |  | 2021-09-23 12:52 | Build defect
CTPFS-908 | 74297 | Open | FA extract was missing transactions | Missing FA data. Renee working on the code fix. Chris to verify the data. To be tested today | Satheesh Kumar Gooda |  | 2021-09-22 10:57 | Data defect
CTPFS-899 | 74082 | Deferred | INT122 - ERP POC - Validation required for missing mappings for AHCS Transaction Type Derivation |  | Devang Pandya | 2021-10-08 | 2021-09-21 11:57 | Enhancement
CTPFS-898 | 74075 | Fixed | INT122 - ERP_POC-New JE SOURCE 'Projects' | Defect fixed. Tested in DEV20. FUT Defect - Create Accounting - Updating the table as processed (P) and posted, but no data inserted in XLA tables | Vishnu M Menon | 2021-09-28 | 2021-09-21 11:38 | Enhancement
CTPFS-894 | 74031 | Closed | EXT010 - Format issue |  | Ian.Plummer |  | 2021-09-21 09:36 | Build defect
CTPFS-888 | 73925 | Open | RPT006 Count Summary difference column discrepancy | Sum of XLA header and sum of XLA lines | Girish R Acharya | 2021-09-29 | 2021-09-20 12:15 | Build defect
CTPFS-887 | 73913 | Fixed | Not able to increment parameters for a scheduled job | To be closed by Sateesh | Chris Demko | 2021-10-08 | 2021-09-20 11:29 | Enhancement
CTPFS-886 | 73912 | Open | RPT006 -AHCS Error Report Performance Issue |  | Girish R Acharya |  | 2021-09-20 11:14 | Build defect
CTPFS-885 | 73907 | Open | Create Accounting program failed for CA_USGAAP_CAD ledger in SIT1 | Trading Partner Name - Some transactions have more than 30 characters | Aashutosh Kumar Upadhyay |  | 2021-09-20 10:50 | Design defect
CTPFS-883 | 73898 | Fixed | ERP_POC load amount totals different between OIC Dashboard and Subledger Dashboard Views | Duplicates not checked in OIC and are not rejected in OIC. Hence it is visible in OIC and not Accouting Hub. | Chris Demko |  | 2021-09-20 09:28 | Build defect
CTPFS-862 | 73276 | Deferred | RPT006 - Count Summary and Error Summary should be on two separate tabs |  | Girish R Acharya | 2021-10-08 | 2021-09-15 18:50 | Enhancement
CTPFS-851 | 72959 | Fixed | No access to AHCS Dashboards 1&2 in SIT1 |  | Satheesh Kumar Gooda |  | 2021-09-14 11:47 | Build defect
CTPFS-848 | 72944 | Deferred | Journal Batch Name for EBS subledgers is truncating the final two digits |  | Devang Pandya | 2021-10-08 | 2021-09-14 10:36 | Enhancement